## Game Feature List
Fability co | Epic | Feature | Story | Task | System Required | Integration | GDD | Progress | Comments | Owner | Player Promise | Player Need | Success Factor | Definition of Done | Priority | ETA | Actual Time
Player Progression Epic
Player Progression Epic | Player Progression System |  |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
Player Progression Epic |  | [Player Progression] Level Up |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
Player Progression Epic |  |  | [Player Progression] XP gain rules |  |  | Gameplay Eng | Link | 80% | In progress | Game Design |  |  |  | XP from kills/quests/events; level curve; caps. | Must
Player Progression Epic |  |  | [Player Progression] Level-up rewards |  |  | Gameplay Eng | Link | 80% | In progress | Game Design |  |  |  | Unlock abilities; stats; notifications; skill points. | Must
Player Progression Epic |  |  | [Player Progression] Character sheet UI |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Stats breakdown; derived stats; explanations; tooltips. | Must
Player Progression Epic |  |  | [Player Progression] Level-up configuration |  |  | Gameplay Eng | Link | 50% | In progress | Game Design
Player Progression Epic |  | [CC & Management] Character Stats |  |  |  | Gameplay Eng | Link |  |  | Game Design
Player Progression Epic |  |  | [CC & Management] Character Stats Progression |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
Stats Affect Interactions
Player Progression Epic |  | Talent/Skill System |  |  |  | Gameplay Eng | Link |  |  | Game Design
Player Progression Epic |  |  | [Talent] Skills Trees |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Spend points; prerequisites; respec; loadouts. | Should
Player Progression Epic |  |  |  | [Talent] Skill system design |  | Gameplay Eng | Link | 50% | In progress | Game Design
Player Progression Epic |  |  |  | [Talent] Skill system UI |  | Gameplay Eng | Link | 50% | In progress
Player Progression Epic |  |  |  | [Talent] Skill trees implementation |  | Gameplay Eng | Link | 50% | In progress
Player Progression Epic |  | [Player Progression] Achievements/Trophies |  |  |  | Gameplay Eng | Link |  |  | Game Design
Player Progression Epic |  |  | [Player Progression] Achievement system |  |  | Gameplay Eng | Link | 10% | Has basic design | Game Design |  |  |  | Define achievements; tracking; rewards; UI. | Should
Player Progression Epic |  |  | [Player Progression] Meta achievements |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Complete sets; track progress; title/mount rewards. | Could
Player Progression Epic |  |  | [Player Progression] Collections |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Mounts/pets/transmog collections; account binding; UI. | Should
Player Progression Epic |  |  | [Player Progression] Achievements Rewards |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
Player Progression Epic |  | [Player Progression] Factions |  |  |  | Game Design | Link |  | In progress | Game Design
Player Progression Epic |  |  | [Player Progression] Faction Content |  |  | Game Design | Link | 50% | In progress | Game Design
Player Progression Epic |  |  |  | [Player Progression] Faction NPCs |  | Char Art | Link | 50% | In progress | Game Design
Player Progression Epic |  |  |  | [Player Progression] Faction Quests |  | Game Design | Link | 50% | In progress | Game Design
Player Progression Epic |  |  | [Player Progression] Reputation/factions |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Rep gains; ranks; vendor unlocks; hostility; UI. | Should
Player Progression Epic |  | [Player Progression] In-game Tutorial |  |  |  | Gameplay Eng | Link |  | Needs Review | Game Design
Player Progression Epic |  |  | [Player Progression] Tutorial & onboarding |  |  | Gameplay Eng | Link |  | Needs Review | Game Design |  |  |  | Guided intro; tooltips; training area; skip option. | Must
Player Progression Epic |  |  |  | [Player Progression] FTUE Configuration |  | Game Design |  |  | Needs Review | Game Design
Player Progression Epic |  |  |  | [Player Progression] FTUE UI |  | UX/UI |  |  | Needs Review | Game Design
Player Progression Epic |  |  | [Player Progression] Help codex |  |  | Game Design | Link | 0% | Not started | Game Design |  |  |  | In-game encyclopedia; searchable; links from UI. | Should
Player Progression Epic |  |  | [Player Progression] Tooltips |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
Player Progression Epic |  | [Professions] Fishing |  |  |  | Game Design | Link | 50% | In progress | Game Design
Player Progression Epic |  | [Professions] Gathering |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
Player Progression Epic |  |  | [Gathering System] Harvest interactions |  |  | Gameplay Eng | Link | 10% | In progress | Game Design |  |  |  | Mine/chop/skin; tool requirements; cast time; animations. | Should
Player Progression Epic |  |  | [Gathering System] Rare proc drops |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Chance for rare mats; luck modifiers; messaging. | Could
Player Progression Epic |  | [Professions] Crafting System |  |  |  | Gameplay Eng | Link |  | Not started | Game Design
Player Progression Epic |  |  | [Crafting System] Recipe system |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Define recipes; inputs/outputs; skill requirements; quality tiers. | Should
Player Progression Epic |  |  | [Crafting System] Item quality/rolls |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Quality affects stats/value; deterministic or RNG; reroll item. | Could
Player Progression Epic |  |  | [Crafting System] Crafting success/failure (if used) |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Chance-based outcomes; protection; clear UI. | Could
Player Progression Epic |  |  | [Crafting System] Crafting UI |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Search/filter; queue; preview; shows missing mats; craft all. | Should
Player Progression Epic |  |  | [Crafting System] Crafting stations |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Location-based stations; permissions; buffs; tiered stations. | Could
Player Progression Epic |  |  | [Crafting System] Profession progression |  |  | Gameplay Eng | Link | 10% | In progress, very basic | Game Design |  |  |  | XP/levels; unlock recipes; specialization. | Could
Player Progression Epic |  |  | [Crafting System] Specialization trees |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Choose specialization; locked choices; benefits; UI. | Could
Player Progression Epic |  |  | [Crafting System] Player-made item economy hooks |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Bind rules for crafted gear; durability; sinks. | Should
Combat Epic | maybe will go under professions | [Core Combat] Magic |  |  |  | Gameplay Eng | Link |  |  | Game Design
Combat Epic |  |  | [Core Combat] Spellcasting System |  |  | Gameplay Eng | Link | 0% | In progress | Game Design
Combat Epic |  |  | [Core Combat] Magic Weapons |  |  | Gameplay Eng | Link | 0% | In progress | Game Design
Player Progression Epic |  | Character Creation & Management |  |  |  |  | Link |  | In progress | Game Design
Player Progression Epic |  |  | [CC & Management] Character Management |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
Player Progression Epic |  |  |  | [CC & Management] Multiple characters per account |  | Gameplay Eng | Link | 0% | Not started | Game Design
Player Progression Epic |  |  |  | [CC & Management] Character rename |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Rename with policy; uniqueness; rename cooldown; logs. | Should
Player Progression Epic |  |  |  | [CC & Management] Character transfer (server/shard) |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Paid/free transfer; preserve inventory/mail; cooldown; restrictions. | Could
Player Progression Epic |  | [CC & Management] Appearance customization |  |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Face/body/hair/skin; colors; preview; randomize; save presets. | Should
Player Progression Epic |  |  | [CC & Management] Race/species selection |  |  | Gameplay Eng | Link | 20% | In progress We have races/species in work from the art side, not integrated into the CC yet | Game Design |  |  |  | Selectable races/species with starting stats/visuals; validates. | Must
Player Progression Epic |  |  | [CC & Management] Appearance presets/randomizer |  |  | Gameplay Eng |  | 0% | Not started
Player Progression Epic |  | [CC & Management] Garment System |  |  |  | Gameplay Eng | Link |  |  | Game Design
Player Progression Epic |  |  | [CC & Management] Garment Presets |  |  | Gameplay Eng | Link | 0% | Not started | Char Art
Player Progression Epic |  |  | [CC & Management] Garment Customization |  |  | Gameplay Eng | Link | 0% | Not started | Char Art
Player Progression Epic |  | [CC & Management] CC & Garment UI |  |  |  | Gameplay Eng | Link |  |  | UX/UI Lead
Player Progression Epic |  |  | [CC & Management] CC & Garment Menus |  |  | Gameplay Eng | Link | 50% | We have something we'll probably completely rework | UX/UI Lead
Player Progression Epic |  |  | [CC & Management] CC & Garment UI Access |  |  | Gameplay Eng | Link | 50% | We have something we'll probably completely rework | UX/UI Lead
World Systems Epic
World Systems | World Systems
World Systems |  | Corruption |  |  |  |  | Link |  | In progress | Game Design
World Systems |  |  | [Corruption] Corruption Implementation |  |  | Gameplay Eng | Link |  | In progress | Game Design
World Systems |  |  |  | [Corruption] Corruption VFX |  | Gameplay Eng | Link | 50% | In progress | Game Design
World Systems |  |  |  | [Corruption] Different types support |  | Gameplay Eng | Link | 10% | In progress | Game Design
Corrupted environment
World Systems |  |  |  | [Corruption] Corruption SFX |  | Gameplay Eng | Link | 90% | In Progress | Game Design
World Systems |  |  |  | [Corruption] Different levels of corruption |  | Gameplay Eng | Link | 0% | Not started | Game Design
World Systems |  |  |  | [World & Zones] Black Hole R&D |  | Gameplay Eng | Link | 10% | On pause | TechArt
World Systems |  |  | [Corruption] Restoration |  |  | Gameplay Eng | Link | 13.33% | In Progress | Game Design
World Systems |  |  |  | [Corruption] Restoration Abilities |  | Gameplay Eng | Link | 20% | In Progress | Game Design
World Systems |  |  |  | [Corruption] Restoration Weapons/Tools |  | Gameplay Eng | Link | 10% | In Progress | Game Design
World Systems |  |  |  | [Corruption] Restoration Quests |  | Gameplay Eng | Link | 10% | In Progress | Game Design
World Systems |  | Movement System |  |  |  | Gameplay Eng | Link |  | In Progress | Game Design
World Systems |  |  | [Movement System] Basic character movements |  |  | Gameplay Eng | Link | 70% | In progress | Game Design
World Systems |  |  |  | Move/turn/strafe/jump/double jump/move midair |  | Gameplay Eng | Link | 70% | In progress | Game Design
World Systems |  |  | [Movement System] Sprinting/stamina |  |  | Gameplay Eng | Link | 30% | In progress | Game Design |  |  |  | Sprint toggle/hold; stamina drain/regen; UI feedback. | Should
World Systems |  |  |  | Speedup Archways Animations |  | Gameplay Eng | Link | 90% | In progress | Game Design
World Systems |  |  | [Movement System] Swimming/breath |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Water volumes; swim movement; breath meter; drowning. | Could
World Systems |  |  |  | Water detection |  | Gameplay Eng | Link | 10% | In progress | Game Design
Swimming water effects
Drowning/damage in the water
World Systems |  |  | [Movement System] Traversal Mechanics |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Climbable surfaces; vault; fall damage interactions. | Could
World Systems |  |  |  | Gliding |  | Gameplay Eng | Link | 80% | In progress | Game Design
World Systems |  |  |  | Grappling Hooks |  | Gameplay Eng | Link | 80% | In progress | Game Design
World Systems |  |  |  | Ziplines |  | Gameplay Eng | Link | 80% | In progress | Game Design
World Systems |  |  |  | Launch pads |  | Gameplay Eng | Link | 80% | In progress | Game Design
Cannons
|  |  |  | Climbing |  | Gameplay Eng | Link | 0% | Not started | Game Design
World Systems |  |  | [Movement System] Mounts/vehicles |  |  | Gameplay Eng | Link |  | In progress We have a prototype, needs review and proper design | Game Design |  |  |  | Mount summon/dismiss; speed tiers; restrictions; cosmetics. | Should
|  |  |  | Various vehicles types |  | Gameplay Eng | Link | 10% | Mounts R&D | Game Design
World Systems |  |  | [Movement System] Teleport items/spells |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Cast time; restrictions; fail handling. (hearthstone, but back to User Space) | Must
World Systems |  | Navigation |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
World Systems |  |  | [World & Zones] World map UI |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Zoom/pan; filters; player marker; quest markers; fog-of-war. | Must
World Systems |  |  | [World & Zones] Minimap / compass |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Optional minimap/compass; markers; rotation modes. | Should
Height detection
World Systems |  |  | [World & Zones] Fog-of-war reveal |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Reveal on exploration; persists per character; reset rules. | Could
World Systems |  |  | [World & Zones] Ports/boats/transport network |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Schedules; boarding; travel scenes; reliability. | Could
World Systems |  |  | [World & Zones] Fast travel / waypoints |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Unlock points; cost/cooldowns; safe checks. | Should
World Systems |  |  | [World & Zones] Collision & navmesh |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Accurate collision; navmesh per zone; regeneration pipeline. | Must
World Systems |  |  | [World & Zones] Fall damage |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Thresholds; mitigations; death handling; UI feedback. | Must
World Systems |  | Instancing |  |  |  |  | Link |  |  | Level Design
World Systems |  |  | [World & Zones] Instancing |  |  | Server Team | Link |  |  | Server Team
World Systems |  |  | [World & Zones] Dungeon instances |  |  | Server Team | Link | 0% | Research | Server Team |  |  |  | Entry/exit; checkpoints; wipes; lockouts; scaling. | Should
World Systems |  |  | [World & Zones] Zone/region loading |  |  | Server Team | Link | 0% | Research | Server Team |  |  |  | Load zones seamlessly or via transitions; handles disconnects. | Must
World Systems |  |  | [World & Zones] Instance servers |  |  | Server Team | Link | 0% | Not started | Server Team |  |  |  | Spin up instance servers; matchmaking integration; teardown. | Must
World Systems |  |  | [World & Zones] Shard/realm architecture |  |  | Server Team | Link | 0% | Not started | Server Team |  |  |  | Realms/shards; load balancing; transfers; queueing. | Must
World Systems |  | Day/night cycle |  |  |  | Gameplay Eng | Link | 20% | In progress - techart exploration | Game Design |  |  |  | Time progression; lighting; NPC schedules; server time. | Could
World Systems |  | Dynamic weather |  |  |  | Gameplay Eng | Link | 20% | In progress - techart exploration | Game Design |  |  |  | Weather states; transitions; gameplay hooks optional. | Could
World Systems | [5 empty] | Gameplay Eng | Link |  |  | Game Design
World Systems |  |  | [World & Zones] Interactable objects |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Use/pickup/inspect; permissions; cooldowns; sync. | Must
|  |  | Destructibles |  |  | Gameplay Eng
World Systems |  |  | [World & Zones] Resource nodes |  |  | Game Design | Link | 50% | In progress | Game Design |  |  |  | Spawn tables; depletion; respawn; competition rules. | Should
World Systems |  |  | [World & Zones] Chests/lootables |  |  | Level Design | Link | 50% | In progress | Game Design |  |  |  | Spawn rules; lock/key; personal vs shared; anti-farm. | Should
Combat Epic
Combat Epic | Combat Epic
Combat Epic |  | [Core Combat] Combat Framework |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
Combat Epic |  |  | [Core Combat] Combat state machine |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | In/out of combat; regen rules; mount restrictions; logout timer. | Must
Combat Epic |  |  | [Core Combat] Combat encounter reset conditions |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Reset on leash/timeouts; clears debuffs; prevents cheese. | Must
Combat Epic |  |  | [Core Combat] Death & respawn |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Death screen; corpse; respawn points; penalties. | Must
Combat Epic |  |  |  | [Core Combat] Downed state |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Optional downed/bleedout; ally revive; PvP rules. | Could
Combat Epic |  |  |  | [Core Combat] Revive / resurrection |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Self/ally revive; consumables; restrictions; timers. | Should
Combat Epic |  |  |  | [Core Combat] Combat resurrection limits |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Limit battle res per encounter; tracking; UI. | Could
Combat Epic |  | [Core Combat] Combat Effect Systems |  |  |  | Gameplay Eng | Link |  |  | Game Design
Combat Epic |  |  | [Core Combat] Buff/debuff framework |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Timed effects; stacking rules; dispels; persistence rules. | Must
Combat Epic |  |  | [Core Combat] Rested/bonus XP |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Accumulation rules; display; consumption. | Could
Combat Epic |  |  | [Core Combat] Player Status Effects |  |  | Gameplay Eng | Link | 30% | In progress | Game Design
Combat Epic |  |  |  | Water/fire, water/electricity etc |  | Gameplay Eng | Link | 30% | In progress | Game Design
Combat Epic |  | [Core Combat] Combat Targeting & Validation |  |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
Combat Epic |  |  | [Core Combat] Friendly targeting rules |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Heal/assist selection; smart targeting; party priority. | Should
Combat Epic |  |  | [Core Combat] Targeting system |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Tab target/soft target/action target; line-of-sight; range. | Must
Combat Epic |  | [Core Combat] Combat Hit & Damage Processing |  |  |  | Gameplay Eng | Link |  |  | Game Design
Combat Epic |  |  | [Core Combat] Hit resolution |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Server-authoritative hit checks; latency compensation; anti-cheat. | Must
Combat Epic |  |  | [Core Combat] Damage/healing pipeline |  |  | Gameplay Eng | Link | 50% | In progress as a part of combat system | Game Design |  |  |  | Mitigation; crit; resist; shields; overheal; logs. | Must
Combat Epic |  |  | [Core Combat] Diminishing returns framework |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | DR categories; reset timers; UI tooltip for immunity. | Could
Combat Epic |  |  | [Core Combat] Cooldown reduction stacking rules |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | CDR caps; multiplicative/additive; UI shows effective CD. | Should
Combat Epic |  | [Core Combat] Combat Interactions |  |  |  | Gameplay Eng | Link |  |  | Game Design
Combat Epic |  |  | [Core Combat] Combo/proc system |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Conditional triggers; internal cooldowns; UI proc notification. | Should
Combat Epic |  |  | [Core Combat] Dual Wielding |  |  | Gameplay Eng | Link | 50% | In progress
Combat Epic |  | [Core Combat] Ranged Combat
Ranged - Firearms
Ranged - Two-handed weapons
Ranged - Ammo
Combat Epic |  | [Core Combat] AI Combat Behavior |  |  |  | Gameplay Eng | Link |  |  | Game Design
Combat Epic |  |  | [Core Combat] Threat/aggro system |  |  | Gameplay Eng | Link | 50% | In progress as a part of combat system | Game Design |  |  |  | NPC threat tables; taunts; drop rules; leashing. | Should
Combat Epic |  |  | [Core Combat] NPC combat AI |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Decision trees/BT; ability use; pathing; kiting protection. | Must
Combat Epic |  |  | [Core Combat] Elite/boss AI mechanics |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Telegraphs; phases; enrage; target swaps. | Should
Combat Epic |  |  | [Core Combat] Mob spawning & population |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Spawn points; density; scaling; despawn; roaming. | Must
Combat Epic |  |  | [Core Combat] Named/rare spawns |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Timers; announcements; loot rules; anti-camp. | Should
Combat Epic |  |  | [Core Combat] Line-of-sight & cover checks |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | LOS uses server raycasts; prevents shooting through walls. | Must
Combat Epic |  | [Core Combat] PvP Combat System |  |  |  | Gameplay Eng | Link |  | Not started | Game Design
Combat Epic |  |  | [Core Combat] Battleground arenas |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Matchmaking; teams; scoring; maps; rewards. | Could
Combat Epic |  |  | [Core Combat] World PvP objectives |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Capture points; resource control; buffs; timers. | Could
Combat Epic |  |  | [Core Combat] MMR / ranking ladder |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Rating calculation; seasons; decay; UI. | Could
Combat Epic |  |  | [Core Combat] Anti-wintrading detection |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Detect collusion; suspicious patterns; enforcement. | Should
Combat Epic |  |  | [Core Combat] Spectator mode |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | View matches; delay; privacy; anti-stream-snipe. | Could
Combat Epic |  |  | [Core Combat] PvP gear normalization |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Stat templates; scaling; separate PvP stats. | Could
Combat Epic |  |  | [Core Combat] Queue types (solo/duo/premade) |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Different queues; matchmaking constraints; UI. | Could
Combat Epic |  |  | [Core Combat] PvP toxicity controls |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Match chat restrictions; report in match; auto penalties. | Should
Combat Epic |  | [Core Combat] Combat UX & Telemetry |  |  |  | Gameplay Eng | Link |  | Not started | Game Design
Combat Epic |  |  | [Core Combat] Floating combat text |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Damage/heal numbers; filters; crit styling; toggle. | Must
Combat Epic |  |  | [Core Combat] Combat log |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Detailed log; filtering; export; support for addons if allowed. | Should
Post-match checks on cheats
Combat Epic |  | [Combat Abilities] Ability Core |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
Combat Epic |  |  | [Combat Abilities] Ability data definitions |  |  | Gameplay Eng | Link | 10% | In progress as a part of combat system | Game Design |  |  |  | Cooldown/cast time/cost/range; tags; scaling; ranks. | Must
Combat Epic |  |  | [Combat Abilities] Global cooldown rules |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Optional GCD; exceptions; UI indicators. | Should
Combat Epic |  |  | [Combat Abilities] Resource systems (mana/energy/rage) |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Resources regenerate/spend; regen modifiers; UI bars. | Must
Combat Epic |  |  | [Combat Abilities] Ability queueing / buffering |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Queue next ability within window; cancel rules; latency friendly. | Should
Combat Epic |  | [Combat Abilities] Casting Mechanics |  |  |  | Gameplay Eng | Link | 10% | In progress | Game Design
Combat Epic |  |  | [Combat Abilities] Channeling abilities |  |  | Gameplay Eng | Link | 10% | In progress | Game Design |  |  |  | Interrupt rules; movement rules; tick timing. | Should
Combat Epic |  |  | [Combat Abilities] Interrupts & crowd control |  |  | Gameplay Eng | Link | 10% | In progress | Game Design |  |  |  | Stun/root/silence/fear; DR rules; break on damage. | Should
Combat Epic |  |  | [Combat Abilities] Cast bar & interrupt feedback |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Cast bar shows progress; interrupt message; sound cue. | Must
Combat Epic |  | [Combat Abilities] Area & Effect Handling |  |  |  | Gameplay Eng | Link |  | Not started | Game Design
Combat Epic |  |  | [Combat Abilities] Area-of-effect |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Circles/cones/lines; ground-targeting; friendly fire rules. | Must
Combat Epic |  |  | [Combat Abilities] Status effects visuals |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Buff/debuff icons; durations; stack count; tooltip. | Must
Combat UI & HUD
US & Minigames to be broken down
US & Minigames | User Space |  |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
US & Minigames |  | [User Space] Server Support |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
US & Minigames |  |  | [User Space] Player housing instance |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Purchase/unlock; enter/exit; persistence; permissions. | Could
US & Minigames |  |  | [User Space] Visitor permissions |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Invite friends/guild/public listing; ban list. | Could
US & Minigames |  |  | [User Space] Mobile front doors |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Place your front door (portal) anywhere. | Should
US & Minigames |  | [User Space] Decoration |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
|  |  | Buildings/parts of buildings placement/design | rooms, windows, etc
US & Minigames |  |  | [User Space] Decoration placement |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Place/move/rotate/scale; grid/snapping; collision; limits. | Could
US & Minigames |  |  | [User Space] Crafting stations in housing |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Place stations; buffs; restrictions; economy impacts. | Could
US & Minigames |  |  | [User Space] Housing storage |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Extra storage; access rules; anti-dupe. | Could
US & Minigames |  |  | [User Space] Blueprints/presets |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Save room layouts; share; import/export. | Could
US & Minigames |  |  | [User Space] World/activities distribution |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
US & Minigames |  |  | [User Space] Lootable themed decorations per zone |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
US & Minigames | Minigames |  |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
US & Minigames |  | [Minigames] Single-player minigames |  |  |  | Gameplay Eng | Link | 10% | In progress | Game Design
US & Minigames |  | [Minigames] Multiplayer minigames |  |  |  | Gameplay Eng | Link | 10% | In progress | Game Design
Items & Inventory System Epic | [6 empty] | Link |  |  | Game Design
Items & Inventory Epic | Items & Inventory System Epic
Items & Inventory Epic |  | Item Core System |  |  |  | Gameplay Eng | Link |  |  | Game Design
Items & Inventory Epic |  |  | [Item System]
Items & Inventory Epic |  |  |  | [Item System] Initial Item Lists by type
Items & Inventory Epic |  |  | [Item System] Item Data & Rules |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
Items & Inventory Epic |  |  |  | [Item System] Item definition schema |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Stats; rarity; binding; stacks; durability; unique limits. | Must
Items & Inventory Epic |  |  |  | [Item System] Item level / power scoring |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Compute ilvl; gates content; display in UI. | Should
Items & Inventory Epic |  |  |  | [Item System] Item binding rules |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Bind on pickup/equip/use; trade restrictions; UI labels. | Must
Items & Inventory Epic |  |  |  | [Item System] Durability & repair |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Durability loss; repair cost; repair NPC; break rules. | Could
Items & Inventory Epic |  |  | [Item System] Item Lifecycle & Protection |  |  | Gameplay Eng | Link |  | Not started | Game Design
Items & Inventory Epic |  |  |  | [Item System] Destroy item confirmation |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Prompt for rare/bound; type-to-confirm option. | Should
Items & Inventory Epic |  |  |  | [Item System] Item locking / favorites |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Lock items to prevent delete/sell; favorite marking. | Should
Items & Inventory Epic |  |  |  | [Item System] Loot protection |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Duplicate protection for certain rewards; soulbound rules. | Could
Items & Inventory Epic |  |  |  | [Item System] Loot lock & corpse ownership |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Prevent looting by others; timeouts; group access. | Should
Items & Inventory Epic |  |  | [Item System] Cosmetic & Appearance as Items |  |  | Gameplay Eng | Link |  | Not started | Game Design
Items & Inventory Epic |  |  |  | [Item System] Cosmetic transmog/glamour |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Apply appearances independent of stats; unlock collection. | Should
Items & Inventory Epic |  |  |  | [Item System] Dye system |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Recolor gear/skins; channels; preview; saved palettes. | Could
Items & Inventory Epic |  |  |  | [Item System] Appearance collection tracking |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Unlock appearances on obtain; UI collection; duplicates handling. | Should
Player Progression Epic |  |  |  | [CC & Management] Titles & vanity |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Earned/equipped titles; vanity slots; preview. | Could
Player Progression Epic |  |  |  | [CC & Management] Emotes & gestures |  | Gameplay Eng | Link | 0% | We have something we need to review | Game Design |  |  |  | Emote list; unlocks; chat integration; animations. | Should
World Systems |  |  | [World & Zones] In-game maps |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
Items & Inventory Epic |  | Inventory System |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
Items & Inventory Epic |  |  | [Inventory] Player-Carried Storage |  |  | Gameplay Eng | Link |  | In progress | Game Design
Items & Inventory Epic |  |  | [Inventory] Bag/backpack system |  |  | Gameplay Eng | Link | 50% | In progress | Game Design |  |  |  | Slot-based; stacking; sorting; auto-loot; overflow handling. | Must
Items & Inventory Epic |  |  | [Inventory] Auto-sort rules |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Sort by type/rarity/ilvl; custom categories. | Should
Items & Inventory Epic |  |  | [Inventory] Split stacks & stack merging |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Split stack UI; partial moves; merge behavior. | Must
Items & Inventory Epic |  |  | [Inventory] Junk tagging & vendor sell-all |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Mark junk; sell all junk; confirm; blacklist. | Should
Items & Inventory Epic |  |  | [Inventory] Long-Term Storage |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
Items & Inventory Epic |  |  | [Inventory] Bank/storage system |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Extra storage; tabs; search; sorting; permissions. | Should
Items & Inventory Epic |  |  | [Inventory] Account-wide stash |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Shared across characters; restrictions; currency. | Should
Items & Inventory Epic |  |  | [Inventory] Mail attachments as overflow |  |  | Gameplay Eng | Link | 10% | In progress | Game Design |  |  |  | Send items/currency via mail; anti-abuse; return on expiry. | Should
Items & Inventory Epic |  |  | [Inventory] Search in bank/stash |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Search by name/tag; filters; highlight. | Should
Items & Inventory Epic |  |  | [Inventory] Item models
Items & Inventory Epic |  |  | [Inventory] Item icons
Items & Inventory Epic |  |  | [Inventory] Buy/Sell (Vendor transfer)
Items & Inventory Epic |  |  | [Inventory] Loot transfer/item drops
Items & Inventory Epic |  |  | [Inventory] Item editor and tools
Items & Inventory Epic |  |  | [Inventory] Inventory UI |  |  | Gameplay Eng | Link |  | In progress | Game Design
Items & Inventory Epic |  | Equipment System |  |  |  | Gameplay Eng | Link |  | In progress | Game Design
Items & Inventory Epic |  |  | [Equipment] Equipment UI |  |  | Gameplay Eng | Link |  | In progress | UX/UI Lead
Items & Inventory Epic |  |  | [Equipment] Equipment slots |  |  | Gameplay Eng | Link | 50% | In progress | UX/UI Lead |  |  |  | Equip/unequip; validation; visual swaps; two-hand rules. | Must
Items & Inventory Epic |  |  | [Equipment] Item comparison tooltips |  |  | Gameplay Eng | Link | 0% | Not started | UX/UI Lead |  |  |  | Compare to equipped; stat deltas; advanced tooltip toggle. | Should
Items & Inventory Epic |  |  | [Equipment] Enchanting/augment slots |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Attach augments; remove rules; caps; UI. | Could
Items & Inventory Epic |  |  | [Equipment] Upgrade system |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Upgrade ilvl with materials/currency; caps; UI preview. | Could
Items & Inventory Epic |  |  | [Equipment] Item reforging/rerolling |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Change secondary stats; costs; RNG; limits. | Could
Items & Inventory Epic |  |  | [Equipment] Set bonuses |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Track sets; activate bonuses; UI indicators. | Should
Items & Inventory Epic |  |  | [Gathering System] Gathering Equipment |  |  | Gameplay Eng | Link |  |  | Game Design
Items & Inventory Epic |  |  | Equipment] Armour and Kit list
Items & Inventory Epic |  |  | [Gathering System] Tool durability/quality |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Tools affect yield; durability; repairs; sinks. | Could
Player Progression Epic |  | Pets |  |  |  | Gameplay Eng | Link |  |  | Game Design
Player Progression Epic |  |  | [Combat] Combat companions
Player Progression Epic |  |  | [CC & Management] Pet/companion system |  |  | Gameplay Eng | Link | 50% | In progress, needs review | Game Design |  |  |  | Summon pets; cosmetic/combat; commands; persistence. | Could
Player Progression Epic |  |  | [CC & Management] Pets Customization |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
Player Progression Epic |  |  |  | [CC & Management] Pets Naming |  | Gameplay Eng | Link | 0% | Not started | Game Design
Player Progression Epic |  |  |  | [CC & Management] Pets Clothes/Accessories |  | Gameplay Eng | Link | 0% | Not started | Game Design
Player Progression Epic |  | Forge System |  |  |  | Char & Techart | Link | 0% | In research | Game Design, Char Art
Player Progression Epic |  |  | [Equipment] Forge Crafting system
Player Progression Epic |  |  | [Equipment] Forge Item list
Player Progression Epic |  |  | [Equipment] Forge models and icons
Items & Inventory Epic |  | Loot Distribution Systems |  |  |  | Gameplay Eng | Link |  | Not started | Game Design
Items & Inventory Epic |  |  | [Loot Distribution] Loot Drop Generation |  |  | Gameplay Eng | Link |  | Not started | Game Design
Items & Inventory Epic |  |  | [Loot Distribution] Loot tables & drops |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Per-NPC loot tables; weighted rolls; guarantees; pity timers. | Must
Items & Inventory Epic |  |  | [Loot Distribution] Personal vs shared loot |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Loot mode selection; group rules; loot lockouts. | Should
Items & Inventory Epic |  |  | [Loot Distribution] Group Loot Distribution |  |  | Gameplay Eng | Link |  | Not started | Game Design
Items & Inventory Epic |  |  | [Loot Distribution] Need/greed roll |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Group roll UI; timeouts; master looter optional. | Should
Player Economy
Player Economy | In-game economy |  |  |  |  | Gameplay/Backend | Link |  | In progress, very basic | Game Design
Player Economy |  | Currency System
Player Economy |  |  | Sources and drains
Player Economy |  |  | Crafting Economy
Player Economy |  |  | Profession economies / boosts
Player Economy |  |  | Reward Economy / Loot Value
Player Economy |  |  | [Trading] Multiple currencies |  | Monetization | Gameplay/Backend | Link | 10% | In progress | Game Design |  |  |  | Gold + premium + tokens; wallet UI; caps; sinks. | Must
Player Economy |  |  | [Trading] Currency flows |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design
Player Economy |  |  | [Trading] Currency transactions ledger |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Server-side ledger; audit trails; rollback support. | Must
Player Economy |  | Trading system |  |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design
Player Economy |  |  | [Trading] Direct player trade |  | Monetization | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Trade window; confirm; prevents scams; distance; locks. | Should
Player Economy |  |  | COD (cash on delivery) |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Optional COD; safe transaction; escrow; cancel rules. | Could
Player Economy |  |  | [Trading] Trade restrictions |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Level/region limits; bind rules; rate limits; anti-RMT flags. | Must
Player Economy |  |  | [Trading] Search filters (ilvl, stats) |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Advanced filters; saved searches; controller friendly. | Should
Player Economy |  |  | [Trading] Tax & fee tuning |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Configurable fees; sinks; tooltips show net proceeds. | Should
Player Economy |  |  | [Trading] Buyback tab |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Buyback recently sold items; timer; UI. | Should
Player Economy |  |  | [Trading] In-game store UI |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Browse items; featured; categories; preview; wishlist. | Could
Player Economy |  |  | [Trading] NPC vendors |  |  | Gameplay/Backend | Link | 50% | In progress | Game Design |  |  |  | Buy/sell; limited stock; reputation discounts; restock timers. | Must
Player Economy |  |  | [Trading] Repair & services vendors |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Repair, respec, travel fees; UI. | Should
Player Economy |  |  | [Trading] Token/vendor catch-up gear |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Earn tokens; purchase gear; caps; season rollover rules. | Could
Player Economy |  |  | [Trading] Suspicious trade detection |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Heuristics for laundering; alerts; thresholds; review queue. | Should
Player Economy |  |  | [Trading] Listing limits & anti-snipe |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Limit listings; anti-bot; purchase confirmation for high value. | Should
Player Economy |  | Auction house / market board |  |  | Monetization | Gameplay/Backend | Link | 20% | Paused | Game Design |  |  |  | List/buy/sell; taxes; duration; search/sort; history. | Should
Player Economy |  |  | [Trading Market] Auction building
Player Economy |  |  | [Trading] Market price history |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Display last N sales; volume; API rate limits. | Could
Player Economy |  |  | [Trading] Market tools (retrieval, reversal)
Player Economy |  |  | [Trading] Offline sales delivery |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Sales settle offline; proceeds via mail; cancel listing. | Should
Quest System Epic
Quests Epic | Quest System |  |  |  |  | Gameplay Engineering | Link |  | In progress | Game Design
Quests Epic |  | [Quest System] Quests Backend/Tooling |  |  |  | Gameplay Engineering | Link |  | In progress | Game Design
Quests Epic |  |  | [Quest System] Quest definitions & scripting |  |  | Gameplay Engineering | Link |  | In progress | Game Design |  |  |  | Define quests with steps/conditions/rewards; scripting hooks. | Must
Quests Epic |  |  | [Quest System] Quest acceptance/turn-in |  |  | Gameplay Engineering | Link |  | In progress | Game Design |  |  |  | NPC/auto acceptance; checks prereqs; reward selection. | Must
Quests Epic |  |  | [Quest System] Quest log |  |  | Gameplay Engineering | Link |  | In progress | Game Design |  |  |  | List/track/abandon; sorting; categories; limits. | Must
Quests Epic |  |  | [Quest System] Objective tracking |  |  | Gameplay Engineering | Link |  | In progress | Game Design |  |  |  | Kill/collect/explore/talk/use; partial credit; reset rules. | Must
Quests Epic |  |  | [Quest System] Location-based objectives |  |  | Gameplay Engineering | Link |  | In progress | Game Design |  |  |  | Trigger volumes; map pin; completion criteria. | Must
Quests Epic |  |  | [Quest System] Branching choices |  |  | Gameplay Engineering | Link |  | In progress | Game Design |  |  |  | Mutually exclusive branches; flags; consequences; replay rules. | Should
Quests Epic |  |  | [Quest System] Dialogue system |  |  | Gameplay Engineering | Link |  | In progress | Game Design |  |  |  | Branching dialogue; localization; VO triggers; skip/cinematics. | Should
Quests Epic |  |  | [Quest System] Cinematics / cutscenes |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design |  |  |  | In-engine/Video; skip vote in groups; replay. | Could
Quests Epic |  |  | [Quest System] Quest markers & breadcrumbs |  |  | Gameplay Engineering | Link |  | In progress | Game Design |  |  |  | HUD markers; world indicators; distance; toggle. | Should
Quests Epic |  |  | [Quest System] Quest exploit prevention |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design |  |  |  | Detect repeat abuse; reset logic; server-side validation. | Must
Quests Epic |  |  | [Quest System] Quest item delivery |  |  | Gameplay Engineering | Link |  | In progress | Game Design |  |  |  | Auto-grant quest items; reclaim if deleted; prevent softlocks. | Should
Quests Epic |  |  | Quest Editor
Quests Epic |  |  | [Quest System] Reward framework |  |  | Gameplay Engineering | Link |  | In progress | Game Design |  |  |  | XP/currency/items/rep; choice rewards; mail overflow. | Must
Quests Epic |  | [Quest System] Quests as Events |  |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design
Quests Epic |  |  | [Quest System] Repeatable quests |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design |  |  |  | Daily/weekly timers; reset schedule; caps. | Should
Quests Epic |  |  | [Quest System] Bounties/contract board |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design |  |  |  | Procedural quest offering; expiration; difficulty tiers. | Could
Quests Epic |  |  | [Quest System] World events as quests |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design |  |  |  | Dynamic objectives with time limit; public participation; scaling. | Should
Quests Epic |  | [Quest System] Quest Multiplayer |  |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design
Quests Epic |  |  | [Quest System] Shared/group quest progress |  |  | Gameplay Engineering | Link |  | In progress, needs review with code and design | Game Design |  |  |  | Rules for party contribution; credit radius; loot sharing. | Should
Quests Epic |  |  | [Quest System] Quest sharing |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design |  |  |  | Share quest to party; eligibility checks; cooldown. | Could
Quests Epic |  | [Quest System] Quest Types |  |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design
Quests Epic |  |  | [Quest System] Escort AI missions |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design |  |  |  | Escort NPC path; fail conditions; scaling. | Could
Quests Epic |  |  | [Quest System] Timed objectives |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design |  |  |  | Countdown timers; failure state; UI urgency cues. | Should
Gather Resources
Collect Unique Item
Interact with Objects
Kill Enemies
Kill & Collect
Investigate / Track
Explore Area
Cleanse Area of corruption
Challenge / Minigame
Puzzle
Riddle / Dialogue
Quests Epic |  | [Quest System] Quest Narrative |  |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design
Quests Epic |  |  | [Quest System] Lore codex unlocks |  |  | Gameplay Engineering | Link | 0% | Not started | Game Design |  |  |  | Unlock lore entries from exploration/quests; UI browse/search. | Could
Quests Epic |  |  | Quest Localization
Social & Multiplayer Systems Epic | [6 empty] | Link
Social & Multiplayer Systems |  | [Social Systems] Player Chat |  |  |  | Backend Eng | Link |  | In progress | Game Design
Social & Multiplayer Systems |  |  | [Social Systems] General chat channels |  |  | Backend Eng | Link | 50% | In progress | Game Design |  |  |  | Global/zone/local/party/guild/whisper; moderation hooks. | Must
Social & Multiplayer Systems |  |  | [Social Systems] Chat UI & history |  |  | Backend Eng | Link | 50% | In progress | Game Design |  |  |  | Scrollable chat; tabs; filters; timestamps; copy/paste. | Must
Social & Multiplayer Systems |  |  | [Social Systems] Profanity filter |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Locale-aware filter; user toggle; strict mode for minors. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Spam throttling |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Rate limits; mutes; anti-flood; link limits. | Must
Social & Multiplayer Systems |  |  | [Social Systems] Emojis/stickers |  |  | Backend Eng | Link | 10% | In progress | Game Design |  |  |  | Emoji support; custom stickers; entitlement gating. | Could
Social & Multiplayer Systems |  |  | [Social Systems] Block/mute players |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Block whispers/invites; mute chat; persistence. | Must
Social & Multiplayer Systems |  |  | [Social Systems] Voice chat integration |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | In-game voice or platform; push-to-talk; mute; reporting. | Could
Social & Multiplayer Systems |  |  | [Social Systems] Player reporting |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Report chat/name/behavior; attach evidence; routing. | Must
Social & Multiplayer Systems |  |  | [Social Systems] Slash commands framework |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Commands (/w,/invite,/ignore,/roll); autocompletion; help. | Must
Social & Multiplayer Systems |  |  | [Social Systems] Chat link items/achievements |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Clickable links to items/quests; safe rendering; spoof prevention. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Chat Moderation |  |  | Backend Eng | Link | 0% | Not started | Game Design
Social & Multiplayer Systems |  |  |  | [Social Systems] Chat moderation automation |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Keyword triggers; auto-mute thresholds; escalation. | Could
Social & Multiplayer Systems |  |  |  | [Social Systems] Language tags / auto-translate (optional) |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Detect language; tag; optional translate; privacy notice. | Could
Social & Multiplayer Systems |  |  |  | [Social Systems] Chat moderation tools |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Mute, shadowmute, channel bans; audit trail. | Must
Social & Multiplayer Systems |  |  |  | [Social Systems] Chat logs retrieval tooling |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Secure access for moderators; retention rules. | Must
Combat Epic |  |  | Tagging/credit rules |  |  | Gameplay Eng | Link | 0% | ? | Game Design |  |  |  | First hit vs contribution; shared credit; anti-ninja. | Must
Social & Multiplayer Systems |  | [Social Systems] Friends |  |  |  | Backend Eng | Link | 0% | Not started | Game Design
Social & Multiplayer Systems |  |  | [Social Systems] Friends list |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Add/remove; requests; blocks; notes; presence. | Must
Social & Multiplayer Systems |  |  | [Social Systems] Presence/status |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Online/away/busy; current zone/activity; privacy settings. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Friend notes/nicknames |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Local nicknames/notes; private; sync optional. | Could
Social & Multiplayer Systems |  |  | [Social Systems] Friend suggestions |  |  | Backend Eng | Link | 0% | Not started | Game Design |  |  |  | Suggest from mutual guild/party; privacy-respecting. | Could
Social & Multiplayer Systems |  | [Social Systems] Multiplayer - Co-op |  |  |  | Gameplay/Backend | Link |  | In progress | Game Design
Social & Multiplayer Systems |  |  | [Social Systems] Party formation |  |  | Gameplay/Backend | Link |  | In progress | Game Design |  |  |  | Invite/accept; role slots; leader; kick; loot rules. | Must
Social & Multiplayer Systems |  |  | [Social Systems] Matchmaking / LFG |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Queue for dungeons/raids; role selection; MMR optional. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Cross-server grouping |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Invite across servers; instancing; chat routing. | Could
Social & Multiplayer Systems |  |  | [Social Systems] Co-op Ready check |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Ready prompt; timeout; kick logic for queues. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Dungeon finder deserter penalty |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Leaving early adds debuff/timeout; exemptions for kicks. | Could
Social & Multiplayer Systems |  |  | [Social Systems] Role enforcement & composition rules |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Tank/healer/DPS validation; flexible rules; warnings. We may not require this. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Instance vote kick |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Vote kick with reasons; cooldowns; abuse prevention. | Could
Social & Multiplayer Systems |  |  | [Social Systems] Player inspect |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Inspect gear/build; privacy toggle; compare. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Player profile card |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Name, titles, achievements, guild; report/block buttons. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Matchmaking service |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Queue management; skill/role matching; timeouts; penalties. | Should
Social & Multiplayer Systems |  | [Social Systems] Multiplayer - Raids |  |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design
Social & Multiplayer Systems |  |  | [Social Systems] Raid group sizes |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Flexible/fixed sizes; role requirements; scaling. | Could
Social & Multiplayer Systems |  |  | [Social Systems] Raid lockouts & saves |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Weekly lockouts; save states; partial clears; resets. | Could
Social & Multiplayer Systems |  |  | [Social Systems] Dungeon/raid loot distribution |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Personal loot; token systems; currencies; pity timers. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Mythic+/keystone system (if used) |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Scaling difficulty; affixes; timed runs; leaderboards. | Could
Social & Multiplayer Systems |  |  | [Social Systems] Raid finder difficulty (if used) |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Automated raid matching; simplified mechanics; lockouts. | Could
Combat Epic |  | [Core Combat] Dueling |  |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Invite/accept; safe boundaries; rewards none; anti-grief. | Should
Social & Multiplayer Systems |  | Guild System |  |  |  | Gameplay/Backend | Link |  |  | Game Design
Social & Multiplayer Systems |  |  | [Guilds] Guild Identity & Structure |  |  | Gameplay/Backend | Link |  | In progress | Game Design
Social & Multiplayer Systems |  |  |  | [Guilds] Guild creation |  | Gameplay/Backend | Link | 10% | In progress | Game Design |  |  |  | Name/tag validation; cost; leadership assignment. | Should
Social & Multiplayer Systems |  |  |  | [Guilds] Guild ranks & permissions |  | Gameplay/Backend | Link | 10% | In progress | Game Design |  |  |  | Configurable roles; bank permissions; invite/kick; logs. | Should
Social & Multiplayer Systems |  |  |  | [Guilds] Guild emblem/branding |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Create emblem/colors; displays on banners/tabards. | Could
Social & Multiplayer Systems |  |  | [Guilds] Guild Communication |  |  | Gameplay/Backend | Link |  | In progress | Game Design
Social & Multiplayer Systems |  |  |  | [Guilds] Guild chat & MOTD |  | Gameplay/Backend | Link | 10% | In progress | Game Design |  |  |  | Dedicated chat; announcements; pinned messages. | Should
Social & Multiplayer Systems |  |  | [Guilds] Guild Membership Visibility |  |  | Gameplay/Backend | Link |  | Not started | Game Design
Social & Multiplayer Systems |  |  |  | [Guilds] Guild roster & profiles |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Member list; last online; notes; applications. | Should
Social & Multiplayer Systems |  |  |  | [Guilds] Guild recruitment board |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Post recruitment; applications; auto-accept rules. | Could
Social & Multiplayer Systems |  |  | [Guilds] Guild Administrative Tools |  |  | Gameplay/Backend | Link |  | Not started | Game Design
Social & Multiplayer Systems |  |  |  | [Guilds] Guild moderation tools |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Remove offenders; audit logs; reporting; name policy. | Should
Social & Multiplayer Systems |  |  |  | [Guilds] Guild activity logs |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Logs for invites/kicks/bank transactions; export. | Should
Social & Multiplayer Systems |  |  |  | [Guilds] Guild ranks & permissions controls |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Configurable roles; bank permissions; invite/kick; logs. | Should
Social & Multiplayer Systems |  |  | [Guilds] Guild Meta Systems |  |  | Gameplay/Backend | Link |  | Not started | Game Design
Social & Multiplayer Systems |  |  |  | [Guilds] Guild progression/perks |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Guild XP; unlock bonuses; caps; UI. | Could
Social & Multiplayer Systems |  |  |  | [Guilds] Guild perks management UI |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Select perks; show costs; cooldowns; permissions. | Could
Social & Multiplayer Systems |  |  | [Guilds] Guild Shared Resources |  |  | Gameplay/Backend | Link |  | Not started | Game Design
Social & Multiplayer Systems |  |  |  | [Guilds] Guild bank |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Shared storage; tabs; permissions; logs; withdrawal limits. | Should
Social & Multiplayer Systems |  |  | [Guilds] Guild Events |  |  | Gameplay/Backend | Link |  |  | Game Design
Social & Multiplayer Systems |  |  |  | [Guilds] Guild calendar/events |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Schedule raids; RSVPs; reminders; timezones. | Could
Social & Multiplayer Systems |  |  |  | [Guilds] Guild competitions |  | Gameplay/Backend | Link | 0% | Not started | Game Design
Social & Multiplayer Systems |  |  | [Guilds] Guild Physical Presence |  |  | Gameplay/Backend | Link |  | Not started | Game Design
Social & Multiplayer Systems |  |  |  | [Guilds] Guild housing/instances |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Access rules; Bans/kicks; Customisation | Must
Social & Multiplayer Systems |  | [Social Systems] In-game Mail |  |  |  | Gameplay/Backend | Link |  | In progress | Game Design
Social & Multiplayer Systems |  |  | [Social Systems] In-game mail send/receive |  |  | Gameplay/Backend | Link | 10% | In progress | Game Design |  |  |  | Send mail to players; delivery delay; inbox UI; unread indicators. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Mail attachments |  |  | Gameplay/Backend | Link | 10% | In progress | Game Design |  |  |  | Attach items/currency; limits; return on expiry; anti-dupe checks. | Should
Social & Multiplayer Systems |  |  | [Social Systems] Mail enhancements
Social & Multiplayer Systems |  |  | [Social Systems] mail box models
Social & Multiplayer Systems |  |  | [Social Systems] Mail expiry & cleanup |  |  | Gameplay/Backend | Link | 10% | In progress | Game Design |  |  |  | Messages expire; warnings; auto-return attachments; logs. | Should
Social & Multiplayer Systems |  | [Social Systems] Notifications |  |  |  | Gameplay/Backend | Link |  | Not started | Game Design
Social notifications
Social & Multiplayer Systems |  |  | [Social Systems] Red dot system |  |  | Gameplay/Backend | Link | 0% | Not started | Game Design |  |  |  | Friend online, invite, guild events; settings. | Should
UX, UI & Player Experience
UX, UI & Player Experience | Game Interfaces | [5 empty] | Link |  | Needs review/overhaul | UX/UI Lead
UX, UI & Player Experience |  | [Game Interfaces] HUD & In-Game Interface |  |  |  |  | Link |  | Needs review/overhaul | UX/UI Lead
UX, UI & Player Experience |  |  | [Game Interfaces] Health/resource bars |  |  |  | Link |  | Needs review/overhaul | UX/UI Lead |  |  |  | Player/target frames; buffs/debuffs; cast bars. | Must
UX, UI & Player Experience |  |  | [Game Interfaces] Action bars & hotkeys |  |  |  | Link |  | Needs review/overhaul | UX/UI Lead |  |  |  | Multiple bars; paging; keybind display; cooldown swipe. | Must
UX, UI & Player Experience |  |  | [Game Interfaces] Damage direction indicators |  |  |  | Link |  | Needs review/overhaul | UX/UI Lead |  |  |  | Indicators for incoming hits; toggle; accessibility. | Could
UX, UI & Player Experience |  |  | [Game Interfaces] Buff/debuff management UI |  |  |  | Link |  | Needs review/overhaul | UX/UI Lead |  |  |  | Separate sections; whitelist; enlarge important debuffs. | Should
UX, UI & Player Experience |  |  | [Game Interfaces] Quest tracker widget |  |  |  | Link |  | Needs review/overhaul | UX/UI Lead |  |  |  | Track active objectives; collapse; click-to-navigate. | Must
UX, UI & Player Experience |  |  | [Game Interfaces] Group UI frames |  |  |  | Link |  | Needs review/overhaul | UX/UI Lead |  |  |  | Party/raid frames; role icons; ready checks; sorting. | Should
UX, UI & Player Experience |  | [Game Interfaces] UI Framework & UX Standards |  |  |  |  | Link |  | Needs review/overhaul | UX/UI Lead
UX, UI & Player Experience |  |  | [Game Interfaces] Notifications/toasts |  |  |  | Link |  | Needs review/overhaul | UX/UI Lead |  |  |  | Loot, XP, achievements; rate limiting; accessibility. | Should
UX, UI & Player Experience |  |  | [Game Interfaces] Settings menu |  |  |  | Link |  | Needs review/overhaul | UX/UI Lead |  |  |  | Graphics/audio/controls/gameplay; apply/revert; presets. | Must
UX, UI & Player Experience |  |  | [Game Interfaces] UI scaling |  |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Scale UI; safe areas; font size; per-platform. | Should
UX, UI & Player Experience |  |  | [Game Interfaces] Search within menus |  |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Search options/collections; highlight results. | Could
UX, UI & Player Experience |  |  | [Game Interfaces] Rich tooltips |  |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Compare, show sources, show requirements; controller friendly. | Must
UX, UI & Player Experience |  |  | [Game Interfaces] Localization-ready UI |  |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | No hard-coded text; supports RTL; font fallback; truncation. | Must
UX, UI & Player Experience |  |  | [Game Interfaces] UI mod/addon support (if allowed) |  |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | API sandbox; permissions; versioning; anti-cheat constraints. | Not yet!
UX, UI & Player Experience |  |  | [Game Interfaces] Notification center |  |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | History of messages/rewards; clears; filters. | Could
UX, UI & Player Experience |  |  | [Game Interfaces] Keybind UI & conflict resolver |  |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Shows conflicts; reset to default; import/export binds. | Must
UX, UI & Player Experience |  |  | [Game Interfaces] Error handling & messaging |  |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Human-readable errors; retry prompts; offline handling. | Must
UX, UI & Player Experience |  | Controls |  |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
UX, UI & Player Experience |  |  | [Controls] General game settings |  |  | Gameplay Eng | Link | 0% | Not started | Game Design
UX, UI & Player Experience |  |  |  | [Controls] Rebindable controls |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Full keybinds; per-device profiles; conflict resolution. | Must
UX, UI & Player Experience |  |  |  | [Controls] Gamepad support |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | UI navigation; aim assist options; prompts; vibration. | Should
UX, UI & Player Experience |  |  |  | [Controls] Controller glyph switching |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Auto-detect input; display correct glyph set. | Should
UX, UI & Player Experience |  |  |  | [Controls] Toggle/hold options |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Hold-to-sprint, hold-to-aim, etc. configurable. | Should
UX, UI & Player Experience |  |  |  | [Controls] 3rd/1st person camera |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Orbit/zoom; collision; FOV; shoulder swap; sensitivity. | Must
UX, UI & Player Experience |  |  |  | [Controls] Loadout switching |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Save/restore gear+skills+UI; restrictions in combat. | Should
UX, UI & Player Experience |  |  |  | [Controls] Loadout presets |  | Gameplay Eng | Link | 0% | Not started | Game Design
UX, UI & Player Experience |  | UX Optimizations |  |  |  |  | Link |  | Not started | UX/UI Lead
UX, UI & Player Experience |  |  | [UX] Modern UI/UX Expectations |  |  |  | Link |  | Not started | UX/UI Lead
UX, UI & Player Experience |  |  |  | [UX] Search everywhere |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Search inventory, bank, auction, codex, settings. | Should
UX, UI & Player Experience |  |  |  | [UX] Ping/marker system |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | World pings; group visible markers; expiration. | Could
UX, UI & Player Experience |  |  |  | [UX] Photo mode |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Free cam; filters; hide UI; poses. | Could
UX, UI & Player Experience |  |  |  | [UX] Reconnect & session resume |  |  | Link |  | In progress | UX/UI Lead |  |  |  | Reconnect to same instance; preserve party; grace timers. | Must
UX, UI & Player Experience |  |  |  | [UX] AFK detection |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | AFK timers; kick from queues; status display. | Should
UX, UI & Player Experience |  |  |  | [UX] Combat readability options |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Reduce clutter; highlight enemy casts; outline allies. | Should
UX, UI & Player Experience |  |  |  | [UX] Tooltip explanation mode |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Explain stats/formulas; beginner mode; toggles. | Could
UX, UI & Player Experience |  |  |  | [UX] Account-wide unlocks |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Mounts/pets/cosmetics shared; rule exceptions. | Should
UX, UI & Player Experience |  |  |  | [UX] Returner experience |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Welcome back rewards; recap; suggestions. | Could
UX, UI & Player Experience |  |  |  | [UX] Community safety onboarding |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | First-time prompts; reporting tutorial; safe comms. | Should
UX, UI & Player Experience |  | Accessibility |  |  |  |  | Link |  |  | UX/UI Lead
UX, UI & Player Experience |  |  | [Accessibility] Visual Accessibility |  |  |  | Link |  |  | UX/UI Lead
UX, UI & Player Experience |  |  |  | [Accessibility] Colorblind modes |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Filter presets; test patterns; applies to UI and telegraphs. | Should
UX, UI & Player Experience |  |  |  | [Accessibility] Reduce motion |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Disable camera shake/motion blur; simplified VFX option. | Should
UX, UI & Player Experience |  |  |  | [Accessibility] High-contrast UI mode |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Contrast theme; outlines; readability. | Could
UX, UI & Player Experience |  |  |  | [Accessibility] Screen reader hints |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | UI labels for screen readers where supported; navigation cues. | Could
UX, UI & Player Experience |  |  | [Accessibility] Audio & Communication Accessibility |  |  |  | Link |  |  | UX/UI Lead
UX, UI & Player Experience |  |  |  | [Accessibility] Subtitles & captions |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Subtitles for dialogue; speaker labels; size options. | Should
UX, UI & Player Experience |  |  |  | [Accessibility] Audio cues alternatives |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Visual indicators for important sounds; UI pings. | Could
UX, UI & Player Experience |  |  |  | [Accessibility] Speech-to-text (STT) for voice |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Optional captions for voice; privacy notices. | Could
UX, UI & Player Experience |  |  |  | [Accessibility] Text-to-speech (TTS) for chat |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Optional TTS; profanity safe; volume/rate controls. | Could
UX, UI & Player Experience |  |  | [Accessibility] Input & Control Accessibility |  |  |  | Link |  |  | UX/UI Lead
UX, UI & Player Experience |  |  |  | [Accessibility] Remappable UI navigation |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Full remap; controller/KB; one-handed presets optional. | Should
UX, UI & Player Experience |  |  |  | [Accessibility] Toggle rapid actions |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Auto-repeat for held inputs; accessibility options. | Could
UX, UI & Player Experience |  |  |  | [Accessibility] Input smoothing options |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Adjust dead zones, sensitivity curves; presets. | Should
UX, UI & Player Experience |  |  | [Accessibility] Learning & Guidance Accessibility |  |  |  | Link |  |  | UX/UI Lead
UX, UI & Player Experience |  |  |  | [Accessibility] Tutorial replay & hints |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Replay tutorial; contextual hints; can disable. | Should
UX, UI & Player Experience |  | Presentation & Immersion |  |  |  |  | Link |  |  | UX/UI Lead
UX, UI & Player Experience |  |  | [Presentation] Visual Presentation |  |  |  | Link |  |  | UX/UI Lead
UX, UI & Player Experience |  |  |  | [Presentation] Telegraph / readability VFX |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Clear telegraphs; scalable; performance tiers. | Should
UX, UI & Player Experience |  |  |  | [Presentation] Ability animation system |  |  | Link | 10% | In progress | UX/UI Lead |  |  |  | Sync animation to ability timings; cancel windows; blend. | Must
UX, UI & Player Experience |  |  |  | [Presentation] Emote animation library |  |  | Link | 0% | Not started | UX/UI Lead |  |  |  | Emote playback; loop; cancel; network sync. | Must
UX, UI & Player Experience |  |  | [Presentation] Audio Presentation |  |  |  | Link |  |  | Audio Lead
UX, UI & Player Experience |  |  |  | [Presentation] 3D positional audio |  |  | Link | 0% | Not started | Audio Lead |  |  |  | Spatial audio; occlusion; distance falloff; mix. (PS5 support in future) | Must
UX, UI & Player Experience |  |  |  | [Presentation] Adaptive music |  |  | Link | 0% | Not started | Audio Lead |  |  |  | Dynamic music by zone/combat; transitions. | Could
UX, UI & Player Experience |  |  |  | [Presentation] UI SFX |  |  | Link | 20% | In progress | Audio Lead
UX, UI & Player Experience |  |  |  | [Presentation] Other SFX |  |  | Link | 20% | In progress | Audio Lead
UX, UI & Player Experience |  |  |  | [Presentation] Ambience Music |  |  | Link | 20% | In progress | Audio Lead
UX, UI & Player Experience |  |  |  | [Presentation] User Space music |  |  | Link | 0% | Not started | Audio Lead
UX, UI & Player Experience |  |  |  | [Presentation] Zone Music |  |  | Link | 10% | In progress | Audio Lead
UX, UI & Player Experience |  |  | [Presentation] VFX |  |  |  | Link |  | In progress | VFX Lead
UX, UI & Player Experience |  |  |  | Multiple VFX examples |  |  | Link | 20% | In progress | VFX Lead
Platform Epic
Platform | Platform |  |  |  |  | Web/Backend Team | Link | 40% | To be reviewed | Platform/EP
Platform |  | [Platform] Account Creation/Deletion |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform |  |  | [Platform] Account creation / registration |  |  | Web/Backend Team | Link | 90% | Done or partially done. I don't think we're storing profiles atm | Platform/EP |  |  |  | User can create account; validates email/username/password; handles errors; stores profile. | Must
Platform |  |  | [Platform] Display name policy & rename |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Unique rules; profanity filter; rename tokens; history. | Should
Platform |  |  | [Platform] Ban/suspension state handling |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Account state blocks login appropriately; shows reason codes. | Must
Platform |  |  | [Platform] Character delete |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Delete with confirmation; cooldown; prevents deleting last char if needed. | Must
Platform |  |  | [Platform] Name validation |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Uniqueness rules; reserved words; profanity; unicode handling. | Must
Platform |  | [Platform] Account Authentification |  |  |  | Web/Backend Team | Link | 75% |  | Platform/EP |  |  |  | Verification email sent; account gated until verified; resend + rate limits. | Must
Platform |  |  | [Platform] Email verification |  |  | Web/Backend Team | Link | 100% | Done or partially done | Platform/EP
Platform |  |  | [Platform] Login / authentication |  |  | Web/Backend Team | Link | 100% | Partially done. We have basic login system | Platform/EP |  |  |  | Secure login; session tokens; remember-me; logout all devices. | Must
Platform |  |  | [Platform] Password reset |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Self-serve reset via email/SMS; token expiry; audit event. | Must
Platform |  |  | [Platform] Multi-factor authentication (MFA) |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Optional/required MFA; recovery codes; device trust. | Should
Platform |  |  | [Platform] Sign-in Methods |  |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  |  | [Platform] Sign-in with email |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  |  | [Platform] Sign-in with Google |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  |  | [Platform] Sign-in with Discord |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  | [Platform] Account recovery workflow |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Support-assisted recovery; ownership proof; lockout handling. | Should
Platform |  |  | [Platform] Account linking (Steam/PSN/Xbox/Epic/CH) |  |  | Web/Backend Team | Link | 0% | Paused - decided not to link Steam. Needs additional discussion | Platform/EP |  |  |  | Link/unlink external identities; conflict resolution. | Should
Platform |  |  | License/ownership check |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Validate game license and DLC/expansions entitlements. | Must
Platform |  |  | Cross-progression entitlements |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Entitlements reconcile across platforms; prevents dupes. | Should
Platform |  | [Platform] Account Privacy Settings & Legal |  |  |  | Web/Backend Team | Link | 0% |  | Platform/EP
Platform |  |  | [Platform] Consent management |  | Legal | Web/Backend Team | Link | 0% | Not started though we have a confirmed version of ToU | Platform/EP |  |  |  | Track and store consent for ToS/Privacy/marketing; versioned. | Must
Platform |  |  | [Platform] Data export (GDPR/CCPA) |  | Legal | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | User can request export; generates bundle; authenticated delivery. | Should
Platform |  |  | [Platform] Account deletion / erasure |  | Legal | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | User can request deletion; cool-off; deletes/anonymizes per policy. | Should
Platform |  |  | [Platform] Age gating / parental controls |  | Legal | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Age check; chat restrictions; spending limits; COPPA flows. | Should
Platform |  |  |  | Age gating restriction flow for the game |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  |  | Age gating process for 3rd party game partners |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  | [Platform] [Player Dashboard] Player Account Features |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform |  |  | [Player Dashboard] Account Info Display |  |  | Web/Backend Team | Link | 80% |  | Platform/EP
Platform |  |  |  | Nickname |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  |  | Default profile picture |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  |  | Account avatar upload |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  |  | Account level |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  |  | Log out |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  | [Player Dashboard] Player Achievements |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  | [Player Dashboard] CH currency wallet |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  | [Player Dashboard] Account Settings |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  | [Player Dashboard] Support & FAQ |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  | [Platform] [Player Dashboard] Game Dashboard |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform |  |  | [Player Dashboard] Partner Games Display |  |  | Web/Backend Team | Link | 27.5% |  | Platform/EP
Platform |  |  |  | All games |  | Web/Backend Team | Link | 10% | In progress | Platform/EP
Platform |  |  |  | Unlocked games |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  |  | Quests required to unlock |  | Web/Backend Team | Link | 50% | In progress | Platform/EP
Platform |  |  |  | Steam key redemption |  | Web/Backend Team | Link | 50% | In progress | Platform/EP
Platform |  |  | [Player Dashboard] Partner Assets (items) display |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform |  |  |  | Inventory section |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  | [Player Dashboard] Available Quests Tracking |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  | [Player Dashboard] Launcher Download |  |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  | [Player Dashboard] Community Hub |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  | [Player Dashboard] Featured Games section |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  | [Platform] [Player Dashboard] Friends |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform |  |  | [Player Dashboard] Friend List Management |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  | [Player Dashboard] Chat |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  | [Platform] [Player Dashboard] Search & Notifications |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform |  |  | [Player Dashboard] Search |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  | [Player Dashboard] Web notifications/red dots |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  | [Platform] [Player Dashboard] Marketplace |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform |  |  | [Player Dashboard] P2P Marketplace |  |  | Web/Backend Team | Link | 0% | Not started, needs discussion | Platform/EP
Platform |  | [Platform] [Developer Dashboard] Developer Account |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform |  |  | [Developer Dashboard] Account creation/sign in |  |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  | [Developer Dashboard] Company Info Form |  |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform |  |  | [Developer Dashboard] Manage account |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  | [Platform] [Developer Dashboard] Game Dashboard |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform |  |  | [Developer Dashboard] Games management |  |  | Web/Backend Team | Link | 80% | In progress | Platform/EP
Platform |  |  | [Developer Dashboard] Keys management |  |  | Web/Backend Team | Link | 80% | In progress | Platform/EP
Platform |  |  | [Developer Dashboard] Analytics |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  | [Platform] [Developer Dashboard] Settings & Support |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform |  |  | [Developer Dashboard] contact support & FAQ |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  | [Platform] Quest Tracking |  |  |  | Web/Backend Team | Link |  |  | Platform/EP |  |  |  | Designers create quests; Translation/Localisation links; Dialogue/Narrative links. | Should
Platform |  |  | [Platform] Quest Input System |  |  | Web/Backend Team | Link | 50% | In progress | Platform/EP
Platform |  |  | [Platform] Partner Quest Integration |  |  | Web/Backend Team | Link | 50% | In progress | Platform/EP
Platform |  | [Platform] Platform Certification |  |  |  | EP/Platform Lead | Link |  | Not started | Platform/EP |  |  |  | PS/Xbox/Nintendo TRCs; submission checklists. Steam also needs this if we decide to go there | Must
Platform |  |  | [Platform] Platform certification requirements |  |  | EP/Platform Lead | Link | 0% | Not started | Platform/EP
Platform |  | [Platform] Payment Processing |  |  |  | EP/Platform Lead | Link |  | Not started | Platform/EP
Platform |  |  | [Platform] Payment System Integration |  |  | EP/Platform Lead | Link | 0% | Not started | Platform/EP
Platform |  | [Platform] Online Services & Backend |  |  |  | Web/Backend Team | Link |  |  | Platform/EP |  |  |  | Transactional emails; throttling; deliverability. | Should
Platform |  |  | [Platform] Session concurrency limits |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Limit simultaneous logins; kick/notify; anti-abuse. | Should
Platform |  |  | [Platform] Email/SMS service integration |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  | [Platform] Patch/manifest CDN |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Serve patches; delta patching; region caches; integrity. | Must
Platform |  |  | [Platform] Account-wide settings service |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Store settings server-side; sync; conflict resolution. | Should
Platform |  |  | [Platform] Notification/push service |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Send push for events (optional); opt-in; region compliance. | Could
Platform |  |  | [Platform] Regional routing / shard selection |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | User chooses region/shard; can transfer with rules. | Should
Platform |  | [Platform] Launcher & Distribution |  |  |  | Web/Backend Team | Link |  | Not started | Platform/EP |  |  |  | Self-update; verify files; repair; disk space checks. | Must
Platform |  |  | [Platform] Patch/update system |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform |  |  | [Platform] Launcher integration |  |  | Web/Backend Team | Link | 100% | In progress | Platform/EP |  |  |  | News, login, patch; SSO; crash log upload. | Should
Platform |  |  | [Platform] Crossplay toggle |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | User setting; matchmaking rules; compliance. | Could
Platform |  |  | [Platform] Cross-save |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Upload/download save; conflict resolution; offline behavior. | Should
Platform |  |  | [Platform] Screenshot/video capture hooks |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Share on platform; privacy; parental settings. | Could
Platform |  |  | [Platform] Offline mode behavior |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | If offline allowed: restrict features; queue actions; messaging. | Could
Platform |  |  | [Platform] Hardware detection & defaults |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Detect hardware; set recommended settings; benchmark optional. | Should
Platform |  |  | [Platform] Input method auto-switching |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Instant switch between KB/mouse and controller; UI updates. | Should
Platform |  |  | [Platform] Multiple language packs |  |  | Web/Backend Team | Link | 0% | We have something on localization, needs check | Platform/EP |  |  |  | Download language packs; switch without reinstall; UI. | Could
Platform |  |  | [Platform] Cross-session settings sync |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Settings stored server-side; per-platform overrides. | Should
Platform |  | [Platform] Desktop App (?) |  |  |  |  | Link | 0%
Platform |  | [Platform] Mobile App (?) |  |  |  |  | Link | 0%

## Feature Versions
Feature Name | V0 | V1 | V2 | V3 | V4 | V5 | V6 | V7
| Not Started | R&D | Prototype | MVP | Launch | Optimize | Expand | Scale
| The feature is in the backlog, no one has started working on any aspect of it yet | Research the idea, validate need, explore solutions, and define the recommended approach | Basic implementation created to prove the concept is viable and test core assumptions | Minimum functional version delivering core value with limited scope and acceptable temporary quality | Complete and polished version ready for public release or production use | Improvements based on testing or real usage, focused on quality, balance, fixes, and efficiency | Additional scope, content, features, or depth added beyond the initial release | System improvements enabling larger usage, faster iteration, long-term growth, and maintainability
Level Up | - | - | - | Player gains XP from gameplay actions and levels up. Basic UI/VFX. Placeholder progression balance | Final XP rules, sources, pacing, rewards, and polished level-up presentation | Bug fixing, performance improvements, and XP/reward balancing based on playtests or release data | - | -
Character Stats | The feature is in the backlog, no one has started working on any aspect of it yet | Define stats definition and behavior, do competitor research, prepare documentation | Implement and playtest basic stats | Implement all desired stats and test out their connection with other sustems in the game (economy, quests, combat etc) | Final stats functionality and balance across all game systems | Bug fixing, performance improvements, and stats balancing based on playtests or release data | Adding new stats, UI improvements, tooltips, presets | Character stats/progression system improvements and tool for designers to work with it
Talent/Skill System | The feature is in the backlog, no one has started working on any aspect of it yet | Define talents and skill paths, talent points getting and distribution rules, prepare documentation | One skill path implemented with placeholder UI; skill points gain and distribution implemented | All desired skill paths designed ad implementation started. Connection and affect to other gameplay system in testing | All desired skill paths are implemented in the release quality. Final UI and efefcts. Balance and progression configration is final | Bug fixing, performance improvements, and skills balancing based on playtests or release data | Adding new skill paths, expanding the existing ones, further balance tweaks, UI/UX improvements | Overall skill system optimization and improvement in line with live operations strategy
Achievements/Trophies | The feature is in the backlog, no one has started working on any aspect of it yet | Achievements conditions and rewards defined, scope confirmed, documentation prepared | Basic achievements functionality implemented (player performs an action - player gets the achievement) | Basic UI and effects implemented. UX tested, if achievements are more than cosmetic - connection with other systems tested | All achievements are implemented with final UX/UI and effects. Achievement getting conditions are tested. Achievements are tracked at the Platform layer | Bug fixes and optimizations | New achievements addition, achievements rarity, special achievements based on community demand | Achievement system improvements across game, web and mobile layers
Factions | The feature is in the backlog, no one has started working on any aspect of it yet | Factions defined, each faction reputation gain rules are set and designed, faction content and narrative ready, documentation finished | Faction content in production (areas, NPCs, symbols etc), demo faction quests implemented, basic reputation gain fuctionality implemented | All factions visible in game with placeholder dialogues in quests and WIP content. Factions reputation progression finalized and tested with other game systems | Faction content final and implemented, factions reputation progression balanced, all needed quest lines are implemented and tested | Bug fixes and improvements, dialogue/localization tweaks, UX/UI improvements | More faction quests, reputation tree expanded/deepened, new factions, seasonal faction content | Reputation system expanded or applied to other systems in the game that use similar mechanics
In-game Tutorial | The feature is in the backlog, no one has started working on any aspect of it yet | First-time player experience goals defined, player journey described. All systems, features and content participating in FTUE defined, the scope confirmed. Tutotial pop-ups/tooltips described/written. Tutorial segment is included as a part of documentation template for all new features | Basic in-game tutorial implemented, feedback for player implemented, temporary tutorial area exists | Tutorial rules finalized and implemented, design/level design close to final. Player progression through tutorial is in testing. Help codex basic fuctionality is implemented, tooltips across the game implemented | Full tutorial segment is implemented in final quality with all needed UX/UI passes. Tutorial progression is balanced, XP gain set. The player gets access to all needed systems, the progression is not blocked. Each feature the player encounters for the first time has hints. Help codex is full and easily accessible | Bugfix and tweaks bacsed on playtesting/user feedback | Each new feature contains tutorial/tooltips and added to the help codex | Tutorial systems are used during the LiveOps stage for events
Fishing | The feature is in the backlog, no one has started working on any aspect of it yet | Professions progression and skill points rules are defined and escribed in the documentation. The list of launch-needed professions is finalized | Basic fishing implemented with placeholder UI, animations and content | Fishing skill path implemented with progression rules in place; fishing is a part of trading and in-game economy. Basic aquarium functionality added. Placeholder UI | Fishing minigame and skill progression are final. UX/UI, content and effects are final. Enough content to support the progression. Economy/trading balance finalized. Fishing spot placement in the world is done. US aquarium finalized. Tutorial in place | Bug fixes and improvements based on user feedback | More content (fish types, fishing areas, rods, customization) based on global content expansions and events | Multiplayer fishing systems and competitions
Gathering | The feature is in the backlog, no one has started working on any aspect of it yet |  | Gathering mechanic implemented, items are added to the inventory; placeholder animations and effects | Gathering skill path implemented with progression rules in place with placeholder UI. Gathering is a part of trading and in-game economy | Gathering profession is fully implemented with final animations, content and configuration. Gathering nodes placement is finalized. Gathered resources balance is final. Gathering skill path UI is final | Bug fixes and improvements based on user feedback | More content (gathering spots, resource types etc) based on global content expansions and events | -
Crafting System | The feature is in the backlog, no one has started working on any aspect of it yet |  | Basic crafting is implemented (items can be combined to get a new item) with placeholder effects and animations | Crafting stations implemented. Crafting skill path implemented with progression rules in place with placeholder UI. Crafting is a part of trading and in-game economy | Crafting profession is fully implemented with final animations, content and configuration. Crafted resources balance is final. Crafting skill path UI is final | Bug fixes and improvements based on user feedback | More content (new crafted items etc) based on global content expansions and events | Crafting nechanic is used as the base for new systems (like Forge), for more UGC content and events
Magic | The feature is in the backlog, no one has started working on any aspect of it yet | Magic defined, main goals and rules of the mechanic set. Competitor research done. Documentation complete | Basic spell casting implemented with placeholder animations and effects. Placeholder magic configuration | Sufficient number of magic types is implemented and supported by animations and effects. Magic is tested as a part of combat/professions system. Magic profession skill path is implemented with placeholder UI | All types of magic are implemented and balanced, with final animations and effects in place. Skill path UI is final | Bug fixes, optimizations and balance tweaks | New magic types, magic-based puzzles, magic weapons/scrolls | Multiplayer magic usage
Character Management | The feature is in the backlog, no one has started working on any aspect of it yet | Number of characters per server, char transfer rules, naming rules etc are defined and run through best pratices, competitor research done, documentation completed. Anti-cheat system designed | The game supports at least one character per server that can be renamed, deleted or transffered. Placeholder UI | All decided functionality implemented with temporary UI. UX is close to final. Basic anti-cheat protection implemented | Number of characters, transfer and naming rules etc are fully implemented, with final UX/UI and effects. Anti-cheat system is in place | Bug fixes and optimizations | - | -
Appearance customization | The feature is in the backlog, no one has started working on any aspect of it yet | The limitations of appearance customization defined, with the minimum scope of content needed. Starting appearance defined. Rules of how players can change their appearance in the future explored and set | Basic appearance customization implemented with basic appearance parts to be changed. Placeholder UX/UI, limited customization options | All customization slots implemented with placeholder UI and limited options. Points of appearance customization in the game are implemented. Appearance items are included in the in-game economy with placeholder balance | Final UI and roaster of options. Final economy balance and configuration for tradable appearance items. Appearance presets | Bug fixes and optimizations | More appearance customization options, appearance randomizer | Appearance customization system expanded with more character's parts to alter. Deeper customization. Using the technology to add pets customization
Garment System | The feature is in the backlog, no one has started working on any aspect of it yet | The limitations of garment choice and garment slots defined, with the minimum scope of content needed. Starting garments defined. Rules of how players can change their garments in the future explored and set | Basic garment system implemented with a limited number of slots to be changed. Placeholder UX/UI, limited customization options | All garment slots are changable with placeholder UI. More customization options added. Garment items are included into the game economy with placeholder balance. UX flow of changing the garments in-game (how do I change the garments - inventory, Barbersmith etc) implemented | Final UI and roaster of options. Final economy balance and configuration for tradable garment items. Garment presets | Bug fixes and optimizations | More garment options, garment sets randomizer, partner and seasonal/event garments | Improve clothing pipelines, performance, compatibility, and tooling to support large wardrobes and long-term live content growth. Support UGC garments
Corruption | The feature is in the backlog, no one has started working on any aspect of it yet | Corruption types, cleansing mechanic and role in the world designed, documentation completed | Techart R&D completed with one type of corruption implemented. Corruption texture implemented. Corruption cleansing implemented. Corruptions visuals defined | 1-2 types of corruption fully supported with placeholder VFX. Corruption quests added. Corruption cleansing skill path added with placeholder UI and balance. One corrupted enemy supported. Corruption server/client behavior supported | 3-4 corruption types are added and placed around the world in accordance with player progression. Corruption cleansing skill path has final congfiguration with final UI and supported by quests. Final corruption weapon, enemies, animations and VFX in place | Bug fixes and optimizations | New corruption types, new weapons, new corrupted areas and enemies. Black hole as a part of corrupted area. Corruption-based events
Movement System | The feature is in the backlog, no one has started working on any aspect of it yet | Define movement style, controls, responsiveness targets, and technical approach | Basic character locomotion with simple input and camera movement | Core movement functional with stable controls and essential traversal actions | Final movement set polished, responsive, and ready for full gameplay use | Improve feel, fix bugs, tune responsiveness, and refine animations/performance | Add advanced traversal options or new movement mechanics | Improve networking, performance, and support for many players or platforms
Navigation | The feature is in the backlog, no one has started working on any aspect of it yet | Define navigation model, world traversal rules, and pathfinding requirements | Basic pathfinding and movement across simple environments | Core navigation functional for standard maps and gameplay scenarios | Reliable navigation across full game content with finalized rules, final map and compass UX/UI | Improve path quality, fix stuck cases, and tune performance | Add advanced navigation features or support for new environment types | Support larger worlds, more agents, and faster content generation workflows
Instancing | The feature is in the backlog, no one has started working on any aspect of it yet | Define instancing goals, player flow, server model, and technical requirements. Documentation finished | Basic creation and joining of isolated test instances | Core instancing functional for key gameplay content and party access | Stable instancing with matchmaking, rules, and production readiness | Improve load times, stability, recovery, and resource efficiency | Add new instance types, rulesets, or player experiences | Support high concurrency, automation, and efficient server capacity growth
Day/night cycle | The feature is in the backlog, no one has started working on any aspect of it yet | Day/night cycle rules defined, documentation ready | Techart R&D completed to figure out technical limitations. Demo cycle set | Day/night change functional and configurable with placeholder visuals | Final configuration and visuals implemented | Bug fixes and optimizations | Special day/night conditions added | Improve synchronization, performance, tooling, and support for large worlds, zones, and live content systems
Dynamic weather | The feature is in the backlog, no one has started working on any aspect of it yet | Dynamic weather limitations and rules defined with every season/weather type specifics set and change rules/restrictions | Techart R&D completed to figure out technical limitations. Demo weather set with switch between two states | 1-2 weather types functional and configurable with placeholder visuals | All weather types and seasons implemented with cycle rules configured | Bug fixes and optimizations | New weather types and seasons added, special conditions for new zones and events | Support large worlds, zone-specific weather, synchronization, live events, and efficient content control
Combat unified | The feature is in the backlog, no one has started working on any aspect of it yet | Define combat vision, pacing, depth, skill ceiling, target audience | Basic melee combo / attack chain Basic shooting/projectile One enemy AI that attacks/chases Damage numbers / HP loss Placeholder animations/VFX PvP prototyped Test arena only | Core melee + ranged both functional Several enemy archetypes Basic abilities / cooldowns Hit reactions / dodge / interrupt basics Core stats affecting combat PvE encounters playable PvP arena playable | Final weapon/class kits Good responsiveness / animation quality Full enemy combat behavior set Balanced TTK / progression UI clarity / FX readability Stable multiplayer sync Combo systems Status effects | Balance classes/builds Fix frustrating AI Improve hit feel Reduce ability spam/ clunkiness Meta adjustments | New weapon archetypes New enemy mechanics Advanced builds | Large raids with many entities Server authority improvements Ability scripting tools Combat telemetry dashboards Faster content creation pipeline
User Space | The feature is in the backlog, no one has started working on any aspect of it yet | Competitor research and user space functionality defined; technical research on the system support | Basic user space instance functionality with furniture placement; placeholder objects, VFX and UI | Users can create and decorate their user space (added quest to get a user space); refined UX/UI and camera position; connection between user spaces explored | User space obtain, decorate and visit final functionality; a roaster of user space items; user space crafting stations; stable server support; conencted user spaces | Bugfix and stabilization | More user spaces items and trophies added; user space expansion (room -> several rooms -> house -> garden etc) | Reuse housing systems, permissions, and content pipelines to support guild houses and future shared spaces
Minigames | The feature is in the backlog, no one has started working on any aspect of it yet | Define the minigames mechanics we need, single-player/multiplayer and plan out minigames accessibility through the game. Prepare all needed documentation | 1-2 minigames core implemented on temporary assets | 1-2 minigames are fully functional with final assets and content. Server/client support and syncronization | All required minigames are implemented with final assets and content. Stable server/client support, progress save, multiplayer etc | Bugfix and stabilization | New minigames added, seasonal content and rewards | Expanding minigames mechanics into fully functional features/events
Items & Inventory General Feature | The feature is in the backlog, no one has started working on any aspect of it yet | Combines R&D stages of item core, inventory, equipment and loot systems | Basic item creation, storage, equip, and drop loop works | Players can obtain, store, equip, and use items in core gameplay | Stable, polished, scalable item ecosystem ready for live players | QoL, balance, exploits, performance, UX improvement | Crafting hooks, rarity depth, loadouts, advanced loot rules, new item types | Shared backend/tools supporting large content volume and future systems
Item Core System | The feature is in the backlog, no one has started working on any aspect of it yet | Define item architecture, data model, types, rarity, ownership, and technical foundations | Basic item definitions created and recognized by the game | Core item properties, usage rules, stacking, and persistence functional | Finalized item framework supporting all planned item categories and gameplay systems | Fix issues, improve data workflows, and tune item logic/performance | Add new item categories, advanced properties, and deeper system integrations | Data-driven architecture and tooling supporting large item libraries and future systems
Inventory System | The feature is in the backlog, no one has started working on any aspect of it yet | Define inventory rules, capacity, UX flows, storage logic, and technical requirements | Basic item storage with add, remove, and move actions | Core inventory management functional with slots, stacking, and persistence | Final inventory UX, sorting, rules, and stable gameplay integration ready for release | Improve usability, fix bugs, and optimize performance/load times | Add filters, presets, extra storage types, and advanced management features | Support high item counts, shared storage, and efficient backend/content operations
Equipment System | The feature is in the backlog, no one has started working on any aspect of it yet | Define equipment slots, stat impact, restrictions, and progression goals | Basic equip/unequip actions with simple slot support | Core equipment slots, stat application, and visual updates functional | Final equipment rules, polished UX, full item support, and stable gameplay integration | Balance gear progression, fix issues, and improve usability/performance | Add loadouts, set bonuses, cosmetic slots, and advanced gear systems | Support many item types, reusable slot systems, and efficient content growth pipelines
Loot Distribution Systems | The feature is in the backlog, no one has started working on any aspect of it yet | Define loot sources, ownership rules, fairness model, and reward goals | Basic item drops from enemies or containers | Core loot drops and player acquisition rules functional for gameplay loops | Final loot tables, party rules, rarity balance, and polished reward presentation | Tune drop rates, fix exploits, and improve reward pacing | Add smart loot, group modes, event loot, and advanced reward systems | Support large content libraries, automated loot pipelines, and high concurrency gameplay
Player Economy | The feature is in the backlog, no one has started working on any aspect of it yet | Define player economy pillars, currency sources and sinks, main currency flows and rules. Perform competitor research and prepare documentation | Basic currencies, earning/spending flows, vendor transactions, and simple player trading tested to validate core value loops | Core economy functional with currencies, rewards, sinks, item pricing, vendors, and basic player exchange supporting regular gameplay progression | Final economy functionality with antii-cheat protection, server validation etc. Platform transactions are a part of the economy. LiveOps economy is included into overall balance. Tracking and BI in place | Bug fixes and improvements, UX/UI optimizations, balance tweaks | New currency sources/sinks, new currency types, LiveOps economy expansion | Advanced tools, analytics, automation, and balancing systems supporting large player populations, live operations, multiple markets, and long-term economic stability
Trading System | The feature is in the backlog, no one has started working on any aspect of it yet | Define player-to-player and player-to-NPC trading rules, restrictions, pricing, and security needs | Basic item or currency exchange with players and NPC vendors functional | Core player trade and NPC buy/sell flows working reliably with item and currency transfer | Final trading UX, pricing rules, restrictions, safeguards, and stable gameplay integration ready for release | Improve usability, balance prices, prevent exploits, and refine speed/stability | Add gifting, barter, COD mail, reputation vendors, or advanced trading features | Support high trade volume, many vendors, cross-server systems, automation tools, and long-term live operations
Currency System | The feature is in the backlog, no one has started working on any aspect of it yet | Define currencies, sources, sinks, progression role, and balancing goals | Basic earning and spending of core currency functional | Core currencies integrated with rewards, vendors, and progression loops | Final currency balance, sinks, UI clarity, and stable economy integration ready for release | Tune inflation, rewards, sinks, and fix economy issues | Add premium, seasonal, faction, or specialized currencies | Advanced balancing tools, analytics, and support for multiple currencies across live operations
Auction House | The feature is in the backlog, no one has started working on any aspect of it yet | Define marketplace goals, pricing model, taxes, and anti-abuse requirements | Basic item listing, browsing, and purchasing functional | Core marketplace flow with listings, purchases, expiration, and simple search/filter tools | Final marketplace UX, taxes/fees, safeguards, and stable production readiness | Improve search, pricing clarity, performance, and abuse prevention | Add bidding, advanced filters, history, smart pricing, or regional markets | Support high listing volume, cross-server markets, automation tools, and long-term economy management
Pets | The feature is in the backlog, no one has started working on any aspect of it yet | Pets functionality defined and described; division between functional and cosmetic pets set; pets obtain flow defined | Player can get a cosmetic pet and equip/summon it; placeholder model/animations/effects | Player can get one cosmetic and one functional pet. Pet functionality works as intended with stats/ combat/ economy/ game interactions affect tested | Roaster of cosmetic and functional pets with final content is ready. Final economy/combat balance and defined pets sources | Bug fixes, optimizations and improvements | New pet types, themed and partner pets, new pet functionality introduced | Pet customization & garments shared pets, pet upgrade and development
Forge System | V0: The feature is in the backlog, no one has started working on any aspect of it yet
Quest System | The feature is in the backlog, no one has started working on any aspect of it yet | Define quest structure, content goals, progression role, tooling needs, and technical approach | Basic quest creation, acceptance, objective tracking, completion, and reward flow functional | Core quest types, progression integration, rewards, and essential UI fully playable | Final quest content framework, polished UX, reliable scripting, and stable gameplay integration ready for release | Improve pacing, fix bugs, refine rewards, readability, and content flow based on testing | Add advanced quest types, branching paths, dynamic events, chains, and richer narrative systems | Support large content volumes, designer-friendly tools, localization pipelines, live updates, and long-term content operations
Player Chat | The feature is in the backlog, no one has started working on any aspect of it yet | Prepare GDD and TDD on chat functionality, techology and limits | Basic chat with placeholder UX/UI with send-receive functionality | Send-receive functions, slash commands, more concurrent players support. Personal/party chat | Final UX/UI, emoji/colored text support, expanded functionality: block/report, add to friends, LFG. Profanity filters and chat moderation tools | Bug fixes and optimization | Voice chat support, more commands added | Chat technology used as the basis for guild functionality and friends. Overall chat system stability and load improvements and optimizations
Friends | The feature is in the backlog, no one has started working on any aspect of it yet | Prepare GDD and TDD on friends functionality, techology and limits | Basic Friend list with add/remove functionality, placeholder UI | Players can add, remove and block friends, open chat with them, check friends profiles, party. Adding to friends is available from different places of the game | Polished functionality and UX/UI implemented. Server support and syncronization across game and platform | Bug fixes and stability improvements | New friend features (gifts, etc), seasonal events for friends | Support large social graphs, cross-platform/cross-server connections, high concurrency, and efficient tools for managing long-term social features
Multiplayer (Co-op, raids and dueling) | The feature is in the backlog, no one has started working on any aspect of it yet | Define multiplayer architecture, modes, and rules | Basic co-op + simple duel + dummy raid instance | Functional co-op, duels, and basic raid loop | Polished multiplayer modes with full rulesets | Balance, latency fixes, UX improvements | New raid types, ranked duels, modifiers | Large-scale encounters, server optimization, tooling
Guild System | The feature is in the backlog, no one has started working on any aspect of it yet | Define guild goals and functionality, prepare all needed documentation and best practices/competitor research | Basic create and join guild functionality with placeholder UI | Players can create, join, leave the guild, see the list of members, chat. Guild menu exists and players can check guild info. Placeholder UI | Fully functional guilds with menus, guild halls, shared bank and chats. Server stability | Bug fixes, server stability and syncronization improvements, UX/UI optimizations | Guild wars/events, guild halls expansions, guild cosmetics | Larger guilds support and overall system improvements
In-game Mail | V0: The feature is in the backlog, no one has started working on any aspect of it yet
Notifications | V0: The feature is in the backlog, no one has started working on any aspect of it yet
HUD & In-Game Interface | V0: The feature is in the backlog, no one has started working on any aspect of it yet
UI Framework & UX Standards | V0: The feature is in the backlog, no one has started working on any aspect of it yet
Controls | V0: The feature is in the backlog, no one has started working on any aspect of it yet
UX Optimizations | V0: The feature is in the backlog, no one has started working on any aspect of it yet
Accessibility | V0: The feature is in the backlog, no one has started working on any aspect of it yet
Presentation & Immersion | V0: The feature is in the backlog, no one has started working on any aspect of it yet
Platform Features
[Platform] Account Creation/Deletion | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] Account Authentification | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] Account Privacy Settings & Legal | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] [Player Dashboard] Player Account Features | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] [Player Dashboard] Game Dashboard | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] [Player Dashboard] Friends | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] [Player Dashboard] Search & Notifications | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] [Player Dashboard] Marketplace | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] [Developer Dashboard] Developer Account | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] [Developer Dashboard] Game Dashboard | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] [Developer Dashboard] Settings & Support | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] Quest Tracking | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] Platform Certification | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] Payment Processing | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] Online Services & Backend | V0: The feature is in the backlog, no one has started working on any aspect of it yet
[Platform] Launcher & Distribution | V0: The feature is in the backlog, no one has started working on any aspect of it yet

## TDD
Tag | Epic | Feature | Story | Task | System Required | Integration | TDD | Progress | Comments | Owner | Player Promise | Priority | ETA | Actual Time
Player Progression Epic | Player Progression
Player Progression Epic |  | [Player Progression] Level Up |  |  |  |  | Link
Player Progression Epic |  | [Player Progression] Achievements |  |  |  |  | Link
Player Progression Epic |  | [Player Progression] Factions |  |  |  |  | Link
Player Progression Epic |  | [Player Progression] In-game Tutorial |  |  |  |  | Link
Player Progression Epic |  | [Professions] Fishing |  |  |  |  | Link
Player Progression Epic |  | [Professions] Gathering |  |  |  |  | Link
Player Progression Epic |  | [Professions] Crafting System |  |  |  |  | Link
Player Progression Epic |  | Character Creation & Management |  |  |  |  | Link
Player Progression Epic |  | [CC & Management] Garment System |  |  |  |  | Link
Player Progression Epic |  | [CC & Management] Character Stats |  |  |  |  | Link
Player Progression Epic |  | [CC & Management] Pets |  |  |  |  | Link
Player Progression Epic |  | [CC & Management] CC & Garment UI |  |  |  |  | Link
Player Progression Epic |  | Talent/Skill System |  |  |  |  | Link
World Systems | World Systems | [5 empty] | Link
World Systems |  | Corruption |  |  |  |  | Link
World Systems |  | Movement System |  |  |  |  | Link
World Systems |  | Navigation |  |  |  |  | Link
World Systems |  | Instancing |  |  |  |  | Link
World Systems |  | Day/night cycle |  |  |  |  | Link
World Systems |  | Dynamic weather |  |  |  |  | Link
World Systems |  | World Resources |  |  |  |  | Link
Combat | Combat | [5 empty] | Link
Combat |  | [Core Combat] Combat Framework |  |  |  |  | Link
Combat |  | [Core Combat] Combat Effect Systems |  |  |  |  | Link
Combat |  | [Core Combat] Combat Targeting & Validation |  |  |  |  | Link
Combat |  | [Core Combat] Combat Hit & Damage Processing |  |  |  |  | Link
Combat |  | [Core Combat] Combat Interactions |  |  |  |  | Link
Combat |  | [Core Combat] Ranged Combat |  |  |  |  | Link
Combat |  | [Core Combat] Magic |  |  |  |  | Link
Combat |  | [Core Combat] AI Combat Behavior |  |  |  |  | Link
Combat |  | [Core Combat] PvP Combat System |  |  |  |  | Link
Combat |  | [Core Combat] Combat UX & Telemetry |  |  |  |  | Link
Combat |  | [Combat Abilities] Ability Core |  |  |  |  | Link
Combat |  | [Combat Abilities] Casting Mechanics |  |  |  |  | Link
Combat |  | [Combat Abilities] Area & Effect Handling |  |  |  |  | Link
US & Minigames | User Space & Minigames | [5 empty] | Link
US & Minigames |  | [User Space] Server Support |  |  |  |  | Link
US & Minigames |  | [User Space] Decoration |  |  |  |  | Link
US & Minigames |  | [Minigames] Single-player minigames |  |  |  |  | Link
US & Minigames |  | [Minigames] Multiplayer minigames |  |  |  |  | Link
Items & Inventory | Items & Inventory | [5 empty] | Link
Items & Inventory |  | Item Core System |  |  |  |  | Link
Items & Inventory |  | Inventory System |  |  |  |  | Link
Items & Inventory |  | Equipment System |  |  |  |  | Link
Items & Inventory |  | Loot Distribution Systems |  |  |  |  | Link
Items & Inventory |  | Trading System |  |  |  |  | Link
Quest System | Quest System | [5 empty] | Link
Quest System |  | [Quest System] Quests Backend/Tooling |  |  |  |  | Link
Quest System |  | [Quest System] Quests as Events |  |  |  |  | Link
Quest System |  | [Quest System] Quest Multiplayer |  |  |  |  | Link
Quest System |  | [Quest System] Quest Rewards |  |  |  |  | Link
Quest System |  | [Quest System] Quest Types |  |  |  |  | Link
Quest System |  | [Quest System] Quest Narrative |  |  |  |  | Link
Multiplayer Systems | Multiplayer Systems | [5 empty] | Link
Multiplayer Systems |  | Chat |  |  |  |  | Link
Multiplayer Systems |  | Friends |  |  |  |  | Link
Multiplayer Systems |  | Party (co-op) |  |  |  |  | Link
Multiplayer Systems |  | Multiplayer - raids |  |  |  |  | Link
Multiplayer Systems |  | In-game mail |  |  |  |  | Link
Multiplayer Systems |  | Notifications |  |  |  |  | Link
Multiplayer Systems |  | Guild System |  |  |  |  | Link
UX/UI | UX/UI | [5 empty] | Link
UX/UI |  | [Game Interfaces] HUD & In-Game Interface |  |  |  |  | Link
UX/UI |  | [Game Interfaces] UI Framework & UX Standards |  |  |  |  | Link
UX/UI |  | Controls |  |  |  |  | Link
UX/UI |  | UX Optimizations |  |  |  |  | Link
UX/UI |  | Accessibility |  |  |  |  | Link
UX/UI |  | Presentation & Immersion |  |  |  |  | Link
Platform | Platform | [5 empty] | Link
Platform |  | [Platform] Account Creation/Deletion |  |  |  |  | Link
Platform |  | [Platform] Account Authentification |  |  |  |  | Link
Platform |  | [Platform] Account Privacy Settings & Legal |  |  |  |  | Link
Platform |  | [Platform] [Player Dashboard] Player Account Features |  |  |  |  | Link
Platform |  | [Platform] [Player Dashboard] Game Dashboard |  |  |  |  | Link
Platform |  | [Platform] [Player Dashboard] Friends |  |  |  |  | Link
Platform |  | [Platform] [Player Dashboard] Search & Notifications |  |  |  |  | Link
Platform |  | [Platform] [Player Dashboard] Marketplace |  |  |  |  | Link
Platform |  | [Platform] [Developer Dashboard] Developer Account |  |  |  |  | Link
Platform |  | [Platform] [Developer Dashboard] Game Dashboard |  |  |  |  | Link
Platform |  | [Platform] [Developer Dashboard] Settings & Support |  |  |  |  | Link
Platform |  | [Platform] Quest Tracking |  |  |  |  | Link
Platform |  | [Platform] Platform Certification |  |  |  |  | Link
Platform |  | [Platform] Payment Processing |  |  |  |  | Link
Platform |  | [Platform] Online Services & Backend |  |  |  |  | Link
Platform |  | [Platform] Launcher & Distribution |  |  |  |  | Link
Platform |  | [Platform] Desktop App (?) |  |  |  |  | Link
Platform |  | [Platform] Mobile App (?) |  |  |  |  | Link
Online Services & Backend | Online Services & Backend |  |  |  |  | Network Eng | Link |  |  | Backend/Server Team
Online Services & Backend |  | [Online Services & Backend] Multiplayer Backend & Simulation Systems |  |  |  | Network Eng | Link |  |  | Backend/Server Team
Online Services & Backend |  |  | [Online Services & Backend] Authoritative server simulation |  |  | Network Eng | Link |  |  | Backend/Server Team |  | Must
Online Services & Backend |  |  | [Online Services & Backend] Character persistence |  |  | Network Eng | Link |  |  | Backend/Server Team |  | Must
Online Services & Backend |  |  | [Online Services & Backend] Inventory persistence |  |  | Network Eng | Link |  |  | Backend/Server Team |  | Must
Online Services & Backend |  |  | [Online Services & Backend] Economy ledger |  |  | Network Eng | Link |  |  | Backend/Server Team |  | Must
Online Services & Backend |  |  | [Online Services & Backend] API versioning & schema migrations |  |  | Network Eng | Link |  |  | Backend/Server Team |  | Must
Player Support System | Player Support System | [5 empty] | Link |  | Not started | CS Lead
Player Support System |  | [CS] Player Support Tools |  |  |  |  | Link |  | Not started | CS Lead
Player Support System |  |  | [CS] In-game help & ticketing |  |  |  | Link | 0% | Not started | CS Lead |  | Should
Player Support System |  |  | [CS] Knowledge base integration |  |  |  | Link | 0% | Not started | CS Lead |  | Could
Player Support System |  |  | [CS] Report triage queue |  |  |  | Link | 0% | Not started | CS Lead |  | Should
Player Support System |  |  | [CS] Harassment protection |  |  |  | Link | 0% | Not started | CS Lead |  | Should
Player Support System |  |  | [CS] Appeals workflow |  |  |  | Link | 0% | Not started | CS Lead |  | Should
Player Support System |  |  | [CS] Name change enforcement |  |  |  | Link | 0% | Not started | CS Lead |  | Should
Analytics System | Analytics System | [5 empty] | Link |  | Not started | Analytics Lead/EP
Analytics System |  | [Analytics] Gameplay & Product Analytics |  |  |  |  | Link |  | Not started | Analytics Lead/EP
Analytics System |  |  | [Analytics] Core gameplay events |  |  |  | Link | 0% | Not started | Analytics Lead/EP |  | Must
Analytics System |  |  | [Analytics] Onboarding funnel |  |  |  | Link | 0% | Not started | Analytics Lead/EP |  | Should
Analytics System |  |  | [Analytics] Economy monitoring |  |  |  | Link | 0% | Not started | Analytics Lead/EP |  | Should
Analytics System |  |  | [Analytics] Feature flag analytics |  |  |  | Link | 0% | Not started | Analytics Lead/EP |  | Could
Analytics System |  | [Analytics] Performance & Technical Telemetry |  |  |  |  | Link |  | Not started | Analytics Lead/EP
Analytics System |  |  | [Analytics] Client/server perf telemetry |  |  |  | Link | 0% | Not started | Analytics Lead/EP |  | Must
Analytics System |  |  | [Analytics] Telemetry privacy controls |  |  |  | Link | 0% | Not started | Analytics Lead/EP |  | Must
Analytics System |  | [Analytics] Business Intelligence |  |  |  |  | Link |  | Not started | Analytics Lead/EP
Analytics System |  |  | [Analytics] KPI dashboards |  |  |  | Link | 0% | Not started | Analytics Lead/EP |  | Must
Analytics System |  |  | [Analytics] Data warehouse & governance |  |  |  | Link | 0% | Not started | Analytics Lead/EP |  | Must
Analytics System |  | [Analytics] Alerts System |  |  |  |  | Link |  | Not started | Analytics Lead/EP
Analytics System |  |  | [Analytics] Anomaly detection alerts |  |  |  | Link | 0% | Not started | Analytics Lead/EP |  | Must
Performance & Reliability | Performance & Reliability | [5 empty] | Link |  |  | Backend Team
Performance & Reliability |  | [Performance] Client Performance |  |  |  |  | Link |  |  | Backend Team
Performance & Reliability |  |  | [Performance] Graphics scalability |  |  |  | Link |  |  | Backend Team |  | Must
Performance & Reliability |  |  | [Performance] Memory management |  |  |  | Link |  |  | Backend Team |  | Must
Performance & Reliability |  |  | [Performance] Asset optimization pipeline |  |  |  | Link |  |  | Backend Team |  | Must
Performance & Reliability |  |  | [Performance] Tick rate & scaling |  |  |  | Link |  |  | Backend Team |  | Must
Performance & Reliability |  | [Performance] Network & Simulation Performance |  |  |  |  | Link |  |  | Backend Team
Performance & Reliability |  |  | [Performance] Latency management |  |  |  | Link |  |  | Backend Team |  | Must
Performance & Reliability |  |  | [Performance] Network latency indicators |  |  |  | Link |  |  | Backend Team |  | Should
Performance & Reliability |  | [Performance] Infrastructure Scalability |  |  |  |  | Link |  |  | Backend Team
Performance & Reliability |  |  | [Performance] Data consistency checks |  |  |  | Link | 0% | Not started | Backend Team |  | Must
Performance & Reliability |  |  | [Performance] Autoscaling policies |  |  |  | Link | 0% | Not started | Backend Team |  | Must
Performance & Reliability |  | [Performance] Reliability & Resilience |  |  |  |  | Link |  |  | Backend Team
Performance & Reliability |  |  | [Performance] Backups & disaster recovery |  |  |  | Link | 0% | Not started | Backend Team |  | Must
Performance & Reliability |  |  | [Performance] Incident response runbooks |  |  |  | Link | 0% | Not started | Backend Team |  | Should
Performance & Reliability |  |  | [Performance] Chaos testing / fault injection |  |  |  | Link | 0% | Not started | Backend Team |  | Could
Performance & Reliability |  | [Performance] Service Quality Monitoring |  |  |  |  | Link |  |  | Backend Team
Performance & Reliability |  |  | [Performance] SLOs/SLAs tracking |  |  |  | Link | 0% | Not started | Backend Team |  | Should
QA & Release Engineering | QA & Release Engineering | [5 empty] | Link |  | Not started | QA Lead/Backend Team
QA & Release Engineering |  | [QA & Release Engineering] QA Tools |  |  |  |  | Link |  | Not started | QA Lead
QA & Release Engineering |  |  | [QA & Release Engineering] Automated tests |  |  |  | Link | 0% | Not started | QA Lead |  | Should
QA & Release Engineering |  |  | [QA & Release Engineering] Feature flags |  |  |  | Link | 0% | Not started | QA Lead |  | Must
QA & Release Engineering |  |  | [QA & Release Engineering] Test environments |  |  |  | Link | 0% | Not started | QA Lead |  | Must
QA & Release Engineering |  |  | [QA & Release Engineering] Crash reporting |  |  |  | Link | 0% | Not started | QA Lead |  | Must
QA & Release Engineering |  |  | [QA & Release Engineering] Replay/record system for bugs |  |  |  | Link | 0% | Not started | QA Lead |  | Could
QA & Release Engineering |  |  | [QA & Release Engineering] Load testing |  |  |  | Link | 0% | Not started | QA Lead |  | Must
QA & Release Engineering |  | [QA & Release Engineering] Release Tools |  |  |  |  | Link |  |  | Backend Team
QA & Release Engineering |  |  | [QA & Release Engineering] CI/CD pipeline |  |  |  | Link |  |  | Backend Team |  | Must
QA & Release Engineering |  |  | [QA & Release Engineering] Automated rollback |  |  |  | Link | 0% | Not started | Backend Team |  | Should
QA & Release Engineering |  |  | [QA & Release Engineering] Client signing / anti-tamper build steps |  |  |  | Link |  |  | Backend Team |  | Must
QA & Release Engineering |  |  | [QA & Release Engineering] Stable daily builds provision |  |  |  | Link |  |  | Backend Team
DevOps & Tools | DevOps & Tools |  |  |  |  | DevOps | Link |  | Not started | DevOps
DevOps & Tools |  | [DevOps] Content Creation Tools |  |  |  | DevOps | Link |  | Not started | DevOps
DevOps & Tools |  |  | [DevOps] Content editor tooling |  |  | DevOps | Link | 0% | Not started | DevOps |  | Must
DevOps & Tools |  |  | [DevOps] World building tools |  |  | DevOps | Link | 0% | Not started | DevOps |  | Must
DevOps & Tools |  | [DevOps] Globalization Pipeline |  |  |  | DevOps | Link |  | Not started | DevOps
DevOps & Tools |  |  | [DevOps] Localization pipeline |  |  | DevOps | Link | 0% | Not started | DevOps |  | Must
DevOps & Tools |  |  | [DevOps] Localization QA tooling |  |  | DevOps | Link | 0% | Not started | DevOps |  | Should
DevOps & Tools |  | [DevOps] Data & Observability Platform |  |  |  | DevOps | Link |  | Not started | DevOps
DevOps & Tools |  |  | [DevOps] Log aggregation |  |  | DevOps | Link | 0% | Not started | DevOps |  | Must
DevOps & Tools |  |  | [DevOps] Telemetry schema registry |  |  | DevOps | Link | 0% | Not started | DevOps |  | Must
DevOps & Tools |  | [DevOps] Build & Content Validation |  |  |  | DevOps | Link |  | Not started | DevOps
DevOps & Tools |  |  | [DevOps] Asset validation pipeline |  |  | DevOps | Link | 0% | Not started | DevOps |  | Must
DevOps & Tools

## Platform Feature List (hidden)
Tag | Epic | Feature | Story | Task | System Required | Integration | GDD | Progress | Comments | Owner | Player Promise | Player Need | Success Factor | Definition of Done | Priority | ETA | Actual Time
Platform, Security & Compliance
Platform, Security & Compliance | Platform |  |  |  |  | Web/Backend Team | Link | 40% | To be reviewed | Platform/EP
Platform, Security & Compliance |  | [Platform] Account Creation/Deletion |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform, Security & Compliance |  |  | [Platform] Account creation / registration |  |  | Web/Backend Team | Link | 90% | Done or partially done. I don't think we're storing profiles atm | Platform/EP |  |  |  | User can create account; validates email/username/password; handles errors; stores profile. | Must
Platform, Security & Compliance |  |  | [Platform] Display name policy & rename |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Unique rules; profanity filter; rename tokens; history. | Should
Platform, Security & Compliance |  |  | [Platform] Ban/suspension state handling |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Account state blocks login appropriately; shows reason codes. | Must
Platform, Security & Compliance |  |  | [Platform] Character delete |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Delete with confirmation; cooldown; prevents deleting last char if needed. | Must
Platform, Security & Compliance |  |  | [Platform] Name validation |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Uniqueness rules; reserved words; profanity; unicode handling. | Must
Platform, Security & Compliance |  | [Platform] Account Authentification |  |  |  | Web/Backend Team | Link | 75% |  | Platform/EP |  |  |  | Verification email sent; account gated until verified; resend + rate limits. | Must
Platform, Security & Compliance |  |  | [Platform] Email verification |  |  | Web/Backend Team | Link | 100% | Done or partially done | Platform/EP
Platform, Security & Compliance |  |  | [Platform] Login / authentication |  |  | Web/Backend Team | Link | 100% | Partially done. We have basic login system | Platform/EP |  |  |  | Secure login; session tokens; remember-me; logout all devices. | Must
Platform, Security & Compliance |  |  | [Platform] Password reset |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Self-serve reset via email/SMS; token expiry; audit event. | Must
Platform, Security & Compliance |  |  | [Platform] Multi-factor authentication (MFA) |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Optional/required MFA; recovery codes; device trust. | Should
Platform, Security & Compliance |  |  | [Platform] Sign-in Methods |  |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  |  | [Platform] Sign-in with email |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  |  | [Platform] Sign-in with Google |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  |  | [Platform] Sign-in with Discord |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  | [Platform] Account recovery workflow |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Support-assisted recovery; ownership proof; lockout handling. | Should
Platform, Security & Compliance |  |  | [Platform] Account linking (Steam/PSN/Xbox/Epic/CH) |  |  | Web/Backend Team | Link | 0% | Paused - decided not to link Steam. Needs additional discussion | Platform/EP |  |  |  | Link/unlink external identities; conflict resolution. | Should
Platform, Security & Compliance |  |  | License/ownership check |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Validate game license and DLC/expansions entitlements. | Must
Platform, Security & Compliance |  |  | Cross-progression entitlements |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Entitlements reconcile across platforms; prevents dupes. | Should
Platform, Security & Compliance |  | [Platform] Account Privacy Settings & Legal |  |  |  | Web/Backend Team | Link | 0% |  | Platform/EP
Platform, Security & Compliance |  |  | [Platform] Consent management |  | Legal | Web/Backend Team | Link | 0% | Not started though we have a confirmed version of ToU | Platform/EP |  |  |  | Track and store consent for ToS/Privacy/marketing; versioned. | Must
Platform, Security & Compliance |  |  | [Platform] Data export (GDPR/CCPA) |  | Legal | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | User can request export; generates bundle; authenticated delivery. | Should
Platform, Security & Compliance |  |  | [Platform] Account deletion / erasure |  | Legal | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | User can request deletion; cool-off; deletes/anonymizes per policy. | Should
Platform, Security & Compliance |  |  | [Platform] Age gating / parental controls |  | Legal | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Age check; chat restrictions; spending limits; COPPA flows. | Should
Platform, Security & Compliance |  |  |  | Age gating restriction flow for the game |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  |  | Age gating process for 3rd party game partners |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  | [Platform] [Player Dashboard] Player Account Features |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Account Info Display |  |  | Web/Backend Team | Link | 80% |  | Platform/EP
Platform, Security & Compliance |  |  |  | Nickname |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  |  | Default profile picture |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  |  | Account avatar upload |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  |  | Account level |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  |  | Log out |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Player Achievements |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] CH currency wallet |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Account Settings |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Support & FAQ |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  | [Platform] [Player Dashboard] Game Dashboard |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Partner Games Display |  |  | Web/Backend Team | Link | 27.5% |  | Platform/EP
Platform, Security & Compliance |  |  |  | All games |  | Web/Backend Team | Link | 10% | In progress | Platform/EP
Platform, Security & Compliance |  |  |  | Unlocked games |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  |  | Quests required to unlock |  | Web/Backend Team | Link | 50% | In progress | Platform/EP
Platform, Security & Compliance |  |  |  | Steam key redemption |  | Web/Backend Team | Link | 50% | In progress | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Partner Assets (items) display |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform, Security & Compliance |  |  |  | Inventory section |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Available Quests Tracking |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Launcher Download |  |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Community Hub |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Featured Games section |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  | [Platform] [Player Dashboard] Friends |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Friend List Management |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Chat |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  | [Platform] [Player Dashboard] Search & Notifications |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Search |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] Web notifications/red dots |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  | [Platform] [Player Dashboard] Marketplace |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform, Security & Compliance |  |  | [Player Dashboard] P2P Marketplace |  |  | Web/Backend Team | Link | 0% | Not started, needs discussion | Platform/EP
Platform, Security & Compliance |  | [Platform] [Developer Dashboard] Developer Account |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform, Security & Compliance |  |  | [Developer Dashboard] Account creation/sign in |  |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  | [Developer Dashboard] Company Info Form |  |  | Web/Backend Team | Link | 100% | Done | Platform/EP
Platform, Security & Compliance |  |  | [Developer Dashboard] Manage account |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  | [Platform] [Developer Dashboard] Game Dashboard |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform, Security & Compliance |  |  | [Developer Dashboard] Games management |  |  | Web/Backend Team | Link | 80% | In progress | Platform/EP
Platform, Security & Compliance |  |  | [Developer Dashboard] Keys management |  |  | Web/Backend Team | Link | 80% | In progress | Platform/EP
Platform, Security & Compliance |  |  | [Developer Dashboard] Analytics |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  | [Platform] [Developer Dashboard] Settings & Support |  |  |  | Web/Backend Team | Link |  |  | Platform/EP
Platform, Security & Compliance |  |  | [Developer Dashboard] contact support & FAQ |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  | [Platform] Quest Tracking |  |  |  | Web/Backend Team | Link |  |  | Platform/EP |  |  |  | Designers create quests; Translation/Localisation links; Dialogue/Narrative links. | Should
Platform, Security & Compliance |  |  | [Platform] Quest Input System |  |  | Web/Backend Team | Link | 50% | In progress | Platform/EP
Platform, Security & Compliance |  |  | [Platform] Partner Quest Integration |  |  | Web/Backend Team | Link | 50% | In progress | Platform/EP
Platform, Security & Compliance |  | [Platform] Platform Certification |  |  |  | EP/Platform Lead | Link |  | Not started | Platform/EP |  |  |  | PS/Xbox/Nintendo TRCs; submission checklists. Steam also needs this if we decide to go there | Must
Platform, Security & Compliance |  |  | [Platform] Platform certification requirements |  |  | EP/Platform Lead | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  | [Platform] Payment Processing |  |  |  | EP/Platform Lead | Link |  | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Platform] Payment System Integration |  |  | EP/Platform Lead | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  | [Platform] Online Services & Backend |  |  |  | Web/Backend Team | Link |  |  | Platform/EP |  |  |  | Transactional emails; throttling; deliverability. | Should
Platform, Security & Compliance |  |  | [Platform] Session concurrency limits |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Limit simultaneous logins; kick/notify; anti-abuse. | Should
Platform, Security & Compliance |  |  | [Platform] Email/SMS service integration |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Platform] Patch/manifest CDN |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Serve patches; delta patching; region caches; integrity. | Must
Platform, Security & Compliance |  |  | [Platform] Account-wide settings service |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Store settings server-side; sync; conflict resolution. | Should
Platform, Security & Compliance |  |  | [Platform] Notification/push service |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Send push for events (optional); opt-in; region compliance. | Could
Platform, Security & Compliance |  |  | [Platform] Regional routing / shard selection |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | User chooses region/shard; can transfer with rules. | Should
Platform, Security & Compliance |  | [Platform] Launcher & Distribution |  |  |  | Web/Backend Team | Link |  | Not started | Platform/EP |  |  |  | Self-update; verify files; repair; disk space checks. | Must
Platform, Security & Compliance |  |  | [Platform] Patch/update system |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP
Platform, Security & Compliance |  |  | [Platform] Launcher integration |  |  | Web/Backend Team | Link | 100% | In progress | Platform/EP |  |  |  | News, login, patch; SSO; crash log upload. | Should
Platform, Security & Compliance |  |  | [Platform] Crossplay toggle |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | User setting; matchmaking rules; compliance. | Could
Platform, Security & Compliance |  |  | [Platform] Cross-save |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Upload/download save; conflict resolution; offline behavior. | Should
Platform, Security & Compliance |  |  | [Platform] Screenshot/video capture hooks |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Share on platform; privacy; parental settings. | Could
Platform, Security & Compliance |  |  | [Platform] Offline mode behavior |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | If offline allowed: restrict features; queue actions; messaging. | Could
Platform, Security & Compliance |  |  | [Platform] Hardware detection & defaults |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Detect hardware; set recommended settings; benchmark optional. | Should
Platform, Security & Compliance |  |  | [Platform] Input method auto-switching |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Instant switch between KB/mouse and controller; UI updates. | Should
Platform, Security & Compliance |  |  | [Platform] Multiple language packs |  |  | Web/Backend Team | Link | 0% | We have something on localization, needs check | Platform/EP |  |  |  | Download language packs; switch without reinstall; UI. | Could
Platform, Security & Compliance |  |  | [Platform] Cross-session settings sync |  |  | Web/Backend Team | Link | 0% | Not started | Platform/EP |  |  |  | Settings stored server-side; per-platform overrides. | Should
Platform, Security & Compliance |  | [Platform] Desktop App (?) |  |  |  |  | Link | 0%
Platform, Security & Compliance |  | [Platform] Mobile App (?) |  |  |  |  | Link | 0%
Platform, Security & Compliance | Compliance |  |  |  |  | Web/Backend Team | Link |  |  | EP/Legal
Platform, Security & Compliance |  | [Compliance] Mandatory Legal Docs & Procedures |  |  |  | Web/Backend Team | Link |  |  | EP/Legal
Platform, Security & Compliance |  |  | [Compliance] Terms of Service / EULA acceptance |  | Legal | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | Must accept before play; versioning; re-consent. | Must
Platform, Security & Compliance |  |  | [Compliance] Privacy policy presentation |  | Legal | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | Accessible in-game; locale; versioning. | Must
Platform, Security & Compliance |  |  | [Compliance] Cookie/consent for web components |  | Legal | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | If web views used; region rules. | Should
Platform, Security & Compliance |  |  | [Compliance] Loot box odds disclosure |  | Finance | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | Display odds where required; logs; audits. | Could
Platform, Security & Compliance |  |  | [Compliance] Data retention & deletion policy |  |  | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | Retention windows; deletion jobs; backup handling. | Must
Platform, Security & Compliance |  |  | [Compliance] Vulnerability disclosure process |  |  | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | Security contact; bug bounty policy optional. | Should
Platform, Security & Compliance |  |  | [Compliance] Accessibility compliance checks |  |  | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | WCAG-inspired checks for UI; console TRCs; docs. | Should
Platform, Security & Compliance |  |  | [Compliance] Regional content ratings |  | Legal | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | ESRB/PEGI/USK; descriptors; age gating. | Should
Platform, Security & Compliance | Security & Abuse Prevention |  |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Platform, Security & Compliance |  | [Security] Access & Capacity Protection |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Platform, Security & Compliance |  |  | [Security] Login queue |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Queue when servers full; ETA; priority lanes; disconnect handling. | Should
Platform, Security & Compliance |  |  | [Security] Rate limiting & abuse protection |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Global per-IP/account rate limits; WAF; alerts. | Must
Platform, Security & Compliance |  |  | [Security] DDoS mitigation |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Traffic scrubbing; rate limits; failover. | Must
Platform, Security & Compliance |  | [Security] Anti-Cheat |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Platform, Security & Compliance |  |  | [Security] Anti-tamper / integrity checks |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Detect modified clients; secure bootstraps; update enforcement. | Should
Platform, Security & Compliance |  |  | [Security] Server-side cheat detection |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Speed/teleport; impossible actions; DPS anomalies; flags. | Must
Platform, Security & Compliance |  |  | [Security] Client-side anti-cheat (if used) |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Kernel/user mode as appropriate; privacy notices; compatibility. | Should
Platform, Security & Compliance |  | [Security] Communication & Data Security |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Platform, Security & Compliance |  |  | [Security] Encryption in transit |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | TLS everywhere; cert pinning optional; secure websockets. | Must
Platform, Security & Compliance |  |  | [Security] Secrets management |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | No secrets in client; rotate keys; least privilege. | Must
Platform, Security & Compliance |  | [Security] Economic & Transaction Protection |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Platform, Security & Compliance |  |  | [Security] Fraud & chargeback handling |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Detect suspicious purchases; velocity limits; chargeback workflows. | Should
Platform, Security & Compliance |  |  | [Security] RMT mitigation |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Trade caps; detection; escrow; enforcement tooling. | Should
Platform, Security & Compliance |  | [Security] Behavioral Abuse Prevention |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Platform, Security & Compliance |  |  | [Security] Botting mitigation |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Behavioral detection; captcha in web; in-game friction; bans. | Should
Platform, Security & Compliance |  |  | [Security] Account takeover prevention |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Suspicious login alerts; device fingerprint; step-up auth. | Should
Platform, Security & Compliance |  | [Security] Compliance & Data Protection |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Platform, Security & Compliance |  |  | [Security] Secure logging & PII redaction |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Redact PII in logs; access controls; audit. | Must

## Content List
Tag | Epic | Feature | Content Task | Art Team | System Required | Integration | GDD | Progress | Comments | Owner | Definition of Done | Priority | ETA | Actual Time
Player Progression Epic | Player Progression
Player Progression Epic |  | [Player Progression] Level Up |  |  |  |  | Link
|  |  | Level Up UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Level Up VFX | VFX |  |  |  |  | Scale Healing VFX | Lead VFX Artist
Player Progression Epic |  | [Player Progression] Achievements |  |  |  |  | Link
|  |  | Achievements UI VFX | VFX |  |  |  |  | Extra SS effects | Lead VFX Artist
|  |  | Achievements UI | UX/UI, Concept | [5 empty] | Lead UX/UI Artist
|  |  | Achievements Icons | Concept | [5 empty] | Art Director
Player Progression Epic |  | [Player Progression] Factions |  |  |  |  | Link
|  |  | Factions NPCs | Concept, Character, Animations, TechArt | [5 empty] | Lead Character Artist
|  |  | Faction player clothing | Character, Concept, TechArt, Animations | [5 empty] | Lead Character Artist
|  |  | Faction dialogue UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Factions Banners/Symbols | Concept, Environment | [5 empty] | Lead Env Artist
Player Progression Epic |  | [Player Progression] In-game Tutorial |  |  |  |  | Link
|  |  | Tutorial Archive UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Tutorial VFX (arrows) | VFX |  |  |  |  | Mesh + VFX | Lead VFX Artist
|  |  | Tutorial UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
Player Progression Epic |  | [Professions] Fishing |  |  |  |  | Link
|  |  | Fishing Animations | Animations, TechArt | [5 empty] | Lead Anim Artist
|  |  | Fishing Rod Model | Concept, Character | [5 empty] | Lead Env Artist
|  |  | Fish Models + inventory | Concept, Character | [5 empty] | Lead Character Artist
|  |  | Fishing Sign Model/icon | Concept, Environment | [5 empty] | Lead Env Artist
|  |  | Fishing UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Aquarium Model | Concept, Environment, VFX, TechArt | [5 empty] | Lead Env Artist
|  |  | Fishing shop | Concept, Environment | [5 empty] | Lead Env Artist
|  |  | Fishing profession UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Fishing VFX | VFX |  |  |  |  | Water material + additional VFX | Lead VFX Artist
Player Progression Epic |  | [Professions] Gear
|  |  | Torches, magic crystals, shields and other non-weapon equippables | Character, TechArt, VFX | [5 empty] | Lead Character Artist
Player Progression Epic |  | [Professions] Gathering |  |  |  |  | Link
|  |  | Gathering Animations | Animations, TechArt, VFX | [5 empty] | Lead Anim Artist
|  |  | Gathering UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Gathering VFX | VFX |  |  |  |  | Design and concept art | Lead VFX Artist
|  |  | Gathering profession UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Gathering inventory items | Concept | [5 empty] | Art Director
|  |  | Gathering Tools Models | Concept, Character | [5 empty] | Lead Character Artist
Player Progression Epic |  | [Professions] Crafting System |  |  |  |  | Link
|  |  | Crafting Animations | Animations, VFX, TechArt | [5 empty] | Lead Anim Artist
|  |  | Crafting UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Crafting VFX | VFX |  |  |  |  | Props proposition and concepts | Lead VFX Artist
|  |  | Crafting profession UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Crafting material icons | Concept | [5 empty] | Art Director
|  |  | Crafting Tools Models | Concept, Character | [5 empty] | Lead Character Artist
Player Progression Epic |  | Character Creation & Management |  |  |  |  | Link
|  |  | Base face models | Animations, Character, TechArt | [5 empty] | Lead Character Artist
|  |  | Base body models with variations (gender/proportions) | Animations, Character, TechArt | [5 empty] | Lead Character Artist
|  |  | Appearance Elements Sets (eyes, hair, lips etc) | Animations, Character, TechArt | [5 empty] | Lead Character Artist
|  |  | Character UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Races variations | Animations, Character, TechArt | [5 empty] | Lead Character Artist
Player Progression Epic |  | [CC & Management] Garment System |  |  |  |  | Link
|  |  | Basic garment options | Character, TechArt | [5 empty] | Lead Character Artist
|  |  | Garment variations for slots | Character, TechArt | [5 empty] | Lead Character Artist
|  |  | Skins | Character, TechArt | [5 empty] | Lead Character Artist
|  |  | Armour models | Concept, Character, TechArt | [5 empty] | Lead Character Artist
|  |  | Armour UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Armour slot crystals | Concept, UX/UI, VFX | [5 empty] | Lead Character Artist
|  |  | Partner skins | Concept, Character, TechArt | [5 empty] | Lead Character Artist
Player Progression Epic |  | [CC & Management] Character Stats |  |  |  |  | Link
|  |  | Skill Tree UI icons | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Stats UI Icons + interface | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
Player Progression Epic |  | [CC & Management] Pets |  |  |  |  | Link
|  |  | Pets Models | Concept, Character, TechArt | [5 empty] | Lead Character Artist
|  |  | Pets Animations | Concept, Animations, TechArt | [5 empty] | Lead Anim Artist
|  |  | Partner Pets | Concept, Character | [5 empty] | Lead Character Artist
|  |  | Pets VFX (trails, summon) | Concept, Animations, TechArt, VFX |  |  |  |  | Characters guidelines | Lead VFX Artist
|  |  | Pets Appearance Customization Options | Concept, Character, TechArt | [5 empty] | Lead Character Artist
|  |  | Pets Garments (collars?) | Concept, Character, TechArt | [5 empty] | Lead Character Artist
Player Progression Epic |  | [CC & Management] CC & Garment UI |  |  |  |  | Link
|  |  | CC & Garment Menus | Concept, UX/UI |  |  |  |  | Devs implement. | Lead Tech Artist
|  |  | CC & Garment Presets | UX/UI, Character, TechArt |  |  |  |  | Tech validation from Char. Art | Lead Tech Artist
|  |  | CC & Garment Randomizer | UX/UI, Character, TechArt |  |  |  |  | Ready to use, DA, Maya scipt | Lead Tech Artist
Player Progression Epic |  | Talent/Skill System |  |  |  |  | Link
|  |  | Talent System UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Talent Upgrade VFX | VFX |  |  |  |  | Design and Chars (?) | Lead VFX Artist
World Systems | World Systems | [5 empty] | Link
World Systems |  | World Ambience
|  |  | Ambient area VFX | VFX |  |  |  |  | Env. | Lead VFX Artist
World Systems |  | Corruption |  |  |  |  | Link
|  |  | Different corruption types support (TechArt) | Concept, TechArt, VFX |  |  |  |  | Mechanics and material visual, VFX support following phase | Lead Tech Artist
|  |  | Corruption cleansing mechanic | TechArt, VFX |  |  |  |  | Ready, optimization pass 1 done | Lead Tech Artist
|  |  | Corruption weapon | Concept, Character, TechArt, VFX | [5 empty] | Lead Character Artist
|  |  | Corrupted enemies | Concept, Animations, Character, TechArt, VFX | [5 empty] | Lead Character Artist
|  |  | Corrupted models | Concept, Character, TechArt, VFX, Environment |  |  |  |  | Volumetric and Painting ready to be implemented, Designers and Env to feedback possible upgrade in shape and underneath material | Lead Tech Artist
|  |  | Corruption VFX | Concept, Character, TechArt, VFX |  |  |  |  | Co-dev with TA | Lead VFX Artist
World Systems |  | Movement System |  |  |  |  | Link
|  |  | Basic Movement Animations (walk, run, sprint, jump) | Animations | [5 empty] | Lead Anim Artist
|  |  | Gliding Animations | Animations | [5 empty] | Lead Anim Artist
|  |  | Gliding Device | Concept, Character, VFX | [5 empty] | Lead Character Artist
|  |  | Grappling Animations | Animations | [5 empty] | Lead Anim Artist
|  |  | Grappling Hook Device | Concept, Character, VFX | [5 empty] | Lead Character Artist
|  |  | Ziplines Animations | Animations | [5 empty] | Lead Anim Artist
|  |  | Grappling Hook Points | Concept, VFX | [5 empty] | Lead VFX Artist
|  |  | Zipline device | Concept, Character | [5 empty] | Lead Character Artist
|  |  | Vaulting animations | Animations | [5 empty] | Lead Anim Artist
|  |  | Avoidance anims | Animations | [5 empty] | Lead Anim Artist
|  |  | Launch anims | Animations | [5 empty] | Lead Anim Artist
|  |  | Dodge anims | Animations | [5 empty] | Lead Anim Artist
|  |  | Slide, Crouch, land, strafe | Animations | [5 empty] | Lead Anim Artist
|  |  | Movement VFX | VFX |  |  |  |  | Trails + further concepts | Lead VFX Artist
|  |  | Ziplines Model | Environment | [5 empty] | Lead Env Artist
World Systems |  | Navigation |  |  |  |  | Link
|  |  | World Map UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Minimap UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Compass UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Portals | Concept, VFX, Environment |  |  |  |  | Upgrade present with no performance heavy solutions | Lead VFX Artist
|  |  | Archway race VFX | VFX, Environment | [5 empty] | Lead Env Artist
|  |  | Teleportation scrolls/VFX | Concept, TechArt, VFX |  |  |  |  | Scalable | Lead VFX Artist
World Systems |  | Day/night cycle |  |  |  |  | Link
|  |  | Dynamic day/night cycle | Environment, TechArt, VFX | [5 empty] | Lead Env Artist
|  |  | Town lighting (when dark) | Environment | [5 empty] | Lead Env Artist
|  |  | Dynamic lighting | Environment, TechArt, VFX | [5 empty] | Lead Env Artist
World Systems |  | Dynamic weather |  |  |  |  | Link
|  |  | Cloud system | Environment, TechArt | [5 empty] | Lead Env Artist
|  |  | Define the weather cycle and needs | Environment, TechArt, VFX | [5 empty] | Lead Env Artist
World Systems |  | World Resources |  |  |  |  | Link
|  |  | Collectible resources models | Concept, Environment, VFX | [5 empty] | Lead Env Artist
|  |  | Destructible resources models & VFX | Concept, Environment, VFX, TechArt |  |  |  |  | Explored and planned, start with barrels/crate, expand | Lead VFX Artist
|  |  | Chests | Concept, Animations, Environment, VFX | [5 empty] | Lead Env Artist
World Systems |  | Initial Island Layout |  |  |  |  | Link |  |  |  | Digit Isle 1 9 initial zones, 2D map design, layout
|  |  | Initial Island Blockouts | Concept, Environment | [5 empty] | Lead Env Artist
|  |  | Initial island Biomes Definition | Concept, Environment | [5 empty] | Art Director
|  |  | Initial Island Zones Scope and Sizes | Environment | [5 empty] | Lead Env Artist
World Systems |  | Points of interest (POIs) |  |  |  |  | Link |  |  |  | POI definitions; discovery; map markers; tooltips.
|  |  | List all zones and POIs | Environment | [5 empty] | Lead Env Artist
|  |  | Dungeons layout and set dressing | Environment | [5 empty] | Lead Env Artist
|  |  | Concept all zones and POIs | Concept, Environment | [5 empty] | Art Director
|  |  | POIs set dressing | Environment | [5 empty] | Lead Env Artist
|  |  | Props | Environment | [5 empty] | Lead Env Artist
|  |  | Vegetation | Environment | [5 empty] | Lead Env Artist
|  |  | Environmental VFX | Environment, VFX |  |  |  |  | List | Lead VFX Artist
World Systems |  | Curved Horizon R&D |  |  |  |  | Link
|  |  | Decide if we proceed with this idea and how | Concept, Environment, TechArt | [5 empty] | Lead Env Artist
Combat | Combat | [5 empty] | Link
Combat |  | [Core Combat] Combat Framework | Combat Animations (player, AI) Combat VFX Weapons models (melee, ranged, magic) Combat UI Combat abilities animations & VFX | Animations |  |  | Link |  |  | Lead Anim Artist
Combat |  | [Core Combat] Combat Effect Systems |  | Animations, VFX |  |  | Link |  | Melee w/o weapons | Lead VFX Artist
Combat |  | [Core Combat] Combat Hit & Damage Processing |  | Animations, VFX, UX/UI |  |  | Link |  |  | Lead Anim Artist
Combat |  | [Core Combat] Combat Interactions |  | Animations, VFX, UX/UI |  |  | Link |  |  | Lead Anim Artist
Combat |  | [Core Combat] Ranged Combat |  | Animations, VFX, UX/UI |  |  | Link |  |  | Lead Anim Artist
Combat |  | [Core Combat] Magic |  | Animations, VFX, UX/UI |  |  | Link |  | Weapon + Magic spells, coord with Combat Dept | Lead VFX Artist
Combat |  | [Core Combat] AI Combat Behavior |  | Animations |  |  | Link |  |  | Lead Anim Artist
Combat |  | [Combat Abilities] Skill Tree Abilities for melee weapons |  | Animations |  |  | Link |  |  | Lead Anim Artist
Combat |  | [Combat Abilities] Casting Mechanics |  | Animations, VFX, UX/UI |  |  | Link |  |  | Lead Anim Artist
Combat |  | [Combat Abilities] Area & Effect Handling |  | Animations, VFX, UX/UI |  |  | Link |  |  | Lead Anim Artist
PVP Combat
|  |  | PvP Arena Layout & Set dressing | Concept, Environment | [5 empty] | Lead Env Artist
[Enemies] Content
|  |  | Enemies types 3D support (define with design) | Concept, Animations, Character, TechArt, VFX | [5 empty] | Lead Character Artist
|  |  | Enemies animations & VFX per type | Concept, Animations, VFX | [5 empty] | Art Director
|  |  | Bosses & mini-bosses artwork (models, animations, VFX) | Concept, Animations, Character, TechArt, VFX | [5 empty] | Art Director
|  |  | Corrupted enemies | Concept, Animations, Character, TechArt, VFX | [5 empty] | Lead Character Artist
US & Minigames | User Space & Minigames | [5 empty] | Link
US & Minigames |  | [User Space] Decoration |  |  |  |  | Link
|  |  | Decoration/furniture sets | Concept, Environment | [5 empty] | Lead Env Artist
|  |  | External balcony doors | Concept, Environment | [5 empty] | Lead Env Artist
|  |  | Partner US objects/trophies | Concept, Environment | [5 empty] | Lead Env Artist
|  |  | Furniture inventory items | Concept, Environment
|  |  | Object addition VFX | VFX |  |  |  |  | Scalable VFX | Lead VFX Artist
|  |  | Interactive US objects & animations/UI | Concept, UX/UI, Animations | [5 empty] | Lead UX/UI Artist
US & Minigames |  | [Minigames] Single-player minigames |  |  |  |  | Link
|  |  | Lockpicking UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Arcade cabinet for US (review existing one) | Environment, Concept | [5 empty] | Lead Env Artist
US & Minigames |  | [Minigames] Multiplayer minigames |  |  |  |  | Link
|  |  | Speed archway in Downtime (review models, VFX) | Concept, Environment, VFX |  |  |  |  | Design, art concept and upgrade (logic ready) | Lead VFX Artist
Items & Inventory | Items & Inventory | [5 empty] | Link
Items & Inventory |  | Item Core System |  |  |  |  | Link
|  |  | Static items (collectibles, crafting items, quest items) | Concept, Environment, VFX | [5 empty] | Lead Env Artist
|  |  | Interactive items (destructibles) | Concept, Environment, TechArt, VFX | [5 empty] | Lead Env Artist
Items & Inventory |  | Inventory System |  |  |  |  | Link
|  |  | Inventory UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
Items & Inventory |  | Equipment System |  |  |  |  | Link
|  |  | Equipment UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
Items & Inventory |  | Trading System |  |  |  |  | Link
|  |  | Trading UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Vendors NPC | Concept, Animations, Character | [5 empty] | Lead Character Artist
|  |  | Vendors Animations | Animations | [5 empty] | Lead Anim Artist
|  |  | Shops Buildings & Props | Concept, Environment | [5 empty] | Lead Env Artist
Quest System | Quest System | [5 empty] | Link
Quest System |  | [Quest System] Quest UI |  | Concept, UX/UI |  |  | Link
|  | Quest Tracking (exclamation marks, search area etc) |  | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  | Quest Special NPCs models |  | Concept, Animations, Character, VFX | [5 empty] | Lead Character Artist
Multiplayer Systems | Multiplayer Systems | [5 empty] | Link
Multiplayer Systems |  | Chat |  |  |  |  | Link
|  |  | Chat UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
Multiplayer Systems |  | Friends |  |  |  |  | Link
|  |  | Friends UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
Multiplayer Systems |  | Party (co-op) |  |  |  |  | Link
|  |  | Party UI/HUD | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
Multiplayer Systems |  | In-game mail |  |  |  |  | Link
|  |  | Mail UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
Multiplayer Systems |  | Notifications |  |  |  |  | Link
|  |  | Notifications UI | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
Multiplayer Systems |  | Guild System |  |  |  |  | Link
|  |  | Guild UI & chat | Concept, UX/UI | [5 empty] | Lead UX/UI Artist
|  |  | Guild TV + portals | Concept, Environment, VFX |  |  |  |  | Engineering support and co-dev | Lead VFX Artist
|  |  | Guild Space (guild house/user space) | Concept, Environment | [5 empty] | Lead Env Artist
UX/UI | UX/UI | [5 empty] | Link
UX/UI |  | [Game Interfaces] HUD & In-Game Interface | The current UX/UI throughout the game needs review and decision if we change the style/flows or proceed with the current ones. Each feature needs supporting interfaces | Concept, VFX, UX/UI |  |  | Link |  |  | Lead UX/UI Artist
UX/UI |  | [Game Interfaces] UI Framework & UX Standards |  | UX/UI |  |  | Link |  |  | Lead UX/UI Artist
UX/UI |  | Controls |  | UX/UI |  |  | Link |  |  | Lead UX/UI Artist
UX/UI |  | UX Optimizations |  | UX/UI |  |  | Link |  |  | Lead UX/UI Artist
UX/UI |  | Accessibility |  | UX/UI |  |  | Link |  |  | Lead UX/UI Artist
UX/UI |  | Presentation & Immersion |  | UX/UI |  |  | Link |  |  | Lead UX/UI Artist

## Live Service Features
Tag | Epic | Feature | Story | Task | System Required | Integration | GDD | Progress | Comments | Owner | Player Promise | Player Need | Success Factor | Definition of Done | Priority | ETA | Actual Time
LiveOps | LiveOps System |  |  |  |  | Gameplay Eng | Link |  |  | EP/LiveOps Team
LiveOps |  | [LiveOps] Events |  |  |  | Gameplay Eng | Link |  |  | EP/LiveOps Team
LiveOps |  |  | [LiveOps] Public events |  |  | Gameplay Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Spawn triggers; participation; scaling; reward distribution. | Should
LiveOps |  |  | [LiveOps] Seasonal events |  |  | Gameplay Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Timed live events; themed rewards; calendar scheduling. | Could
LiveOps |  |  | [LiveOps] World bosses |  |  | Gameplay Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Schedule/spawn rules; scaling; loot lockouts. | Could
LiveOps |  | [LiveOps] Seasonal Content |  |  |  | Gameplay Eng | Link |  |  | EP/LiveOps Team
LiveOps |  |  | [LiveOps] Season rollover & rewards |  |  | Gameplay Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | End-of-season rewards; rank snapshots; soft reset rules. | Could
LiveOps |  |  | [LiveOps] Battle pass / season track |  |  | Gameplay Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | XP track; rewards; premium track; catch-up; UI. | Could
LiveOps |  |  | [Core Combat] PvP rewards & seasons |  |  | Gameplay Eng | Link | 0% | Not started | Game Design |  |  |  | Seasonal resets; cosmetics; currency; anti-farm caps. | Could
LiveOps |  | [LiveOps] Retention Activities |  |  |  | Gameplay Eng | Link |  |  | EP/LiveOps Team
LiveOps |  |  | [LiveOps] Daily/weekly objectives |  |  | Gameplay Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Rotating objectives; reset schedule; streaks; UI. | Should
LiveOps |  |  | [LiveOps] Catch-up mechanics |  |  | Gameplay Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Boosts for new/returning; cap removals; UI messaging. | Should
LiveOps |  | [LiveOps] Live Service Reliability |  |  |  | Network Eng | Link |  | Not started | EP/LiveOps Team
LiveOps |  |  | [LiveOps] Telemetry pipeline |  |  | Network Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Event ingestion; batching; privacy flags; schema versioning. | Must
LiveOps |  |  | [LiveOps] Service health checks |  |  | Network Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Heartbeat endpoints; SLO monitoring; dashboards. | Must
LiveOps |  |  | [LiveOps] Graceful degradation |  |  | Network Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | If service down (e.g., store), game continues with limits. | Should
LiveOps |  | [LiveOps] Live Patching |  |  |  |  | Link |  | Not started | EP/LiveOps Team
LiveOps |  |  | [LiveOps] Server-side config / tuning |  |  | Network Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Hotfix values without client patch; versioned configs. | Must
LiveOps |  |  | [LiveOps] Content patch pipeline |  |  | Fullstack Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Build, validate, publish; rollback; partial rollout. | Must
LiveOps |  |  | [LiveOps] Event scheduling system |  |  | Fullstack Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Schedule start/end; timezones; rewards; announcements. | Should
LiveOps |  |  | [LiveOps] In-game announcements |  |  | Fullstack Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | MOTD, banners, popups; targeting; localization. | Should
LiveOps |  |  | [LiveOps] Experiment framework |  |  | Fullstack Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Randomized assignment; metrics; kill switches; ethics. | Could
LiveOps |  |  | [LiveOps] Server restart/maintenance mode |  |  | Network Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Broadcast; safe shutdown; kick timers; maintenance page. | Must
LiveOps |  |  | [LiveOps] Localization hotfixes |  |  |  | Link |  | Not started | EP/LiveOps Team |  |  |  | Update text assets without full patch; cache busting. | Should
LiveOps |  |  | [LiveOps] Rollback / restore tooling |  |  |  | Link |  | Not started | EP/LiveOps Team |  |  |  | Restore character/inventory from backups; transaction replays. | Should
LiveOps |  | [LiveOps] LiveOps Tools |  |  |  | Fullstack Eng | Link |  |  | EP/LiveOps Team
LiveOps |  |  | [LiveOps] GM tools (admin) |  |  | Fullstack Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Teleport, spawn, inspect, ban/mute; audit logs. | Should
LiveOps |  |  | [LiveOps] Ban waves & enforcement tooling |  |  | Fullstack Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Bulk actions; evidence; appeal flags; audit. | Should
LiveOps |  |  | [LiveOps] Server-side reward grants |  |  | Fullstack Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Grant compensation; targeted cohorts; logs; idempotent. | Should
LiveOps |  |  | [LiveOps] Customer messaging for incidents |  |  | Fullstack Eng | Link |  | Not started | EP/LiveOps Team |  |  |  | Status page integration; in-game banner; localized. | Should
LiveOps |  |  | [LiveOps] Feature configuration UI |  |  |  | Link |  | Not started | EP/LiveOps Team |  |  |  | Non-dev tuning UI; permissioned; change tracking. | Should
LiveOps |  |  | [LiveOps] Content permissions & approvals |  |  |  | Link |  | Not started | EP/LiveOps Team |  |  |  | Role-based approvals; publish gates; audit logs. | Should
Monetization | Player Monetization | [5 empty] | Link |  |  | EP/Monetization Lead
Monetization |  | [Monetization] Purchases |  |  |  |  | Link |  |  | EP/Monetization Lead
Monetization |  |  | [Monetization] Purchase flow |  | Platform | Backend Eng | Link | 0% | Not started | EP/Monetization Lead |  |  |  | Platform payment; confirmations; error handling; receipts. | Could
Monetization |  |  | [Monetization] Entitlement delivery |  |  | Backend Eng | Link | 0% | Not started | EP/Monetization Lead |  |  |  | Grant items/currency; idempotent; offline delivery; logs. | Could
Monetization |  |  | [Monetization] Refund processing |  |  | Backend Eng | Link | 0% | Not started | EP/Monetization Lead |  |  |  | Revoke entitlements where possible; currency sinks; logs. | Could
Monetization |  |  | [Monetization] Spending limits & transparency |  | Legal, Finance | Backend Eng | Link | 0% | Not started | EP/Monetization Lead |  |  |  | Purchase confirmations; spending history; parental controls. | Should
Monetization |  |  | [Monetization] Premium currency wallet |  |  | Backend Eng | Link | 0% | Not started | EP/Monetization Lead |  |  |  | Purchase/spend; display rates; region pricing. | Could
Monetization |  |  | [Monetization] Regional pricing & taxes |  | Finance | Backend Eng | Link | 0% | Not started | EP/Monetization Lead |  |  |  | Price tiers by region; VAT; platform rules. | Could
Monetization |  |  | [Monetization] Gift purchases |  |  | Backend Eng | Link | 0% | Not started | EP/Monetization Lead |  |  |  | Gift items to others; fraud controls; delivery confirmation. | Could
Monetization |  | [Monetization] Monetization Types |  |  |  |  | Link |  | Not started | EP/Monetization Lead
Monetization |  |  | [Monetization] Subscription benefits |  |  |  | Link | 0% | Not started | EP/Monetization Lead |  |  |  | Monthly perks; renewal; grace period; messaging. | Could
Monetization |  |  | [Monetization] Loot boxes / random packs (if used) |  |  |  | Link | 0% | Not started | EP/Monetization Lead |  |  |  | Odds disclosure; pity timers; regulation compliance; age gate. | Could
Monetization |  |  | [Monetization] Cosmetic preview & dressing room |  |  |  | Link | 0% | Not started | EP/Monetization Lead |  |  |  | Try on skins; preview in different lighting; share. | Could
Monetization |  | [Monetization] Partner Monetization |  |  |  |  | Link | 0% | Not started | EP/Monetization Lead
Monetization |  |  | [Monetization] Subsidized Game Purchase |  |  |  | Link | 0% | Not started | EP/Monetization Lead
Monetization |  |  | [Monetization] Partner Assets Purchase |  |  |  | Link | 0% | Not started | EP/Monetization Lead
Compliance | Compliance |  |  |  |  | Web/Backend Team | Link |  |  | EP/Legal
Compliance |  | [Compliance] Mandatory Legal Docs & Procedures |  |  |  | Web/Backend Team | Link |  |  | EP/Legal
Compliance |  |  | [Compliance] Terms of Service / EULA acceptance |  | Legal | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | Must accept before play; versioning; re-consent. | Must
Compliance |  |  | [Compliance] Privacy policy presentation |  | Legal | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | Accessible in-game; locale; versioning. | Must
Compliance |  |  | [Compliance] Cookie/consent for web components |  | Legal | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | If web views used; region rules. | Should
Compliance |  |  | [Compliance] Loot box odds disclosure |  | Finance | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | Display odds where required; logs; audits. | Could
Compliance |  |  | [Compliance] Data retention & deletion policy |  |  | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | Retention windows; deletion jobs; backup handling. | Must
Compliance |  |  | [Compliance] Vulnerability disclosure process |  |  | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | Security contact; bug bounty policy optional. | Should
Compliance |  |  | [Compliance] Accessibility compliance checks |  |  | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | WCAG-inspired checks for UI; console TRCs; docs. | Should
Compliance |  |  | [Compliance] Regional content ratings |  | Legal | Web/Backend Team | Link | 0% | Not started | EP/Legal |  |  |  | ESRB/PEGI/USK; descriptors; age gating. | Should
Security | Security & Abuse Prevention |  |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Security |  | [Security] Access & Capacity Protection |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Security |  |  | [Security] Login queue |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Queue when servers full; ETA; priority lanes; disconnect handling. | Should
Security |  |  | [Security] Rate limiting & abuse protection |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Global per-IP/account rate limits; WAF; alerts. | Must
Security |  |  | [Security] DDoS mitigation |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Traffic scrubbing; rate limits; failover. | Must
Security |  | [Security] Anti-Cheat |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Security |  |  | [Security] Anti-tamper / integrity checks |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Detect modified clients; secure bootstraps; update enforcement. | Should
Security |  |  | [Security] Server-side cheat detection |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Speed/teleport; impossible actions; DPS anomalies; flags. | Must
Security |  |  | [Security] Client-side anti-cheat (if used) |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Kernel/user mode as appropriate; privacy notices; compatibility. | Should
Security |  | [Security] Communication & Data Security |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Security |  |  | [Security] Encryption in transit |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | TLS everywhere; cert pinning optional; secure websockets. | Must
Security |  |  | [Security] Secrets management |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | No secrets in client; rotate keys; least privilege. | Must
Security |  | [Security] Economic & Transaction Protection |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Security |  |  | [Security] Fraud & chargeback handling |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Detect suspicious purchases; velocity limits; chargeback workflows. | Should
Security |  |  | [Security] RMT mitigation |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Trade caps; detection; escrow; enforcement tooling. | Should
Security |  | [Security] Behavioral Abuse Prevention |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Security |  |  | [Security] Botting mitigation |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Behavioral detection; captcha in web; in-game friction; bans. | Should
Security |  |  | [Security] Account takeover prevention |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Suspicious login alerts; device fingerprint; step-up auth. | Should
Security |  | [Security] Compliance & Data Protection |  |  |  | Web/Backend Team | Link |  | Not started | Backend Team
Security |  |  | [Security] Secure logging & PII redaction |  |  | Web/Backend Team | Link | 0% | Not started | Backend Team |  |  |  | Redact PII in logs; access controls; audit. | Must

## Legend (hidden)
Legend
Priority
Must | Core for a functional, shippable MMO experience (for most designs).
Should | Strongly recommended for a modern MMO; may be deferred post-launch with care.
Could | Nice-to-have; often post-launch or genre-specific.
Out of Scope | Explicitly not planned (helps filter).
Level
L2 | Subsystem-level capability (e.g., 'Quest system').
L3 | Granular features/requirements within the subsystem.
Type
Gameplay | Player-facing rules and content.
Tech | Engine/network/backend and performance.
UX | UI/controls/usability.
Ops | Live operations, CS, tooling.
Security | Anti-cheat, fraud prevention, data integrity.
Compliance | Privacy, legal, platform requirements.
LiveOps | Events, tuning, config, delivery.
Monetization | Store/subscription/battle pass etc.
Analytics | Telemetry and dashboards.
Safety | Reporting, chat safety, harassment controls.
Accessibility | Inclusive design options.
Presentation | Audio/VFX/animation systems (as requirements).

## Dashboard (hidden)
Dashboard — Feature counts by Area and Priority
(Counts are precomputed; if you edit the Feature List, re-run counts or use a pivot table.)
Area | Must | Should | Could | Total
Account & Identity | 7 | 10 | 0 | 17
Character System | 7 | 5 | 4 | 16
Movement & Controls | 3 | 6 | 2 | 11
World & Zones | 6 | 7 | 4 | 17
Questing & Narrative | 7 | 8 | 5 | 20
Combat & Abilities | 13 | 13 | 4 | 30
Items & Inventory | 6 | 16 | 6 | 28
Crafting & Gathering | 1 | 5 | 9 | 15
Economy & Trading | 4 | 9 | 1 | 14
Social & Community | 8 | 10 | 10 | 28
Guilds & Organizations | 0 | 7 | 5 | 12
PvE Content | 3 | 5 | 7 | 15
PvP Systems | 0 | 3 | 8 | 11
Progression & Meta | 3 | 6 | 3 | 12
Housing & Player Spaces | 0 | 0 | 8 | 8
UI/UX | 10 | 6 | 4 | 20
Accessibility | 0 | 6 | 6 | 12
Presentation | 1 | 3 | 1 | 5
Online Services & Backend | 12 | 5 | 1 | 18
Security & Anti-Cheat | 5 | 6 | 0 | 11
Live Ops & Content Delivery | 3 | 8 | 1 | 12
Monetization & Commerce | 0 | 1 | 10 | 11
Support & Moderation | 2 | 5 | 1 | 8
Analytics & Telemetry | 4 | 4 | 1 | 9
QA & Release Engineering | 6 | 2 | 1 | 9
Compliance & Legal | 4 | 4 | 1 | 9
Platform & Distribution | 1 | 5 | 4 | 10
Performance & Reliability | 8 | 3 | 1 | 12
Developer Tools & Pipeline | 6 | 4 | 0 | 10
Modern UX Expectations | 1 | 6 | 4 | 11
Grand Total | 131 | 178 | 112 | 421