CTO Hiring Plan (Cam)
Action List and Calendar

Prepared for: Executive Leadership
Date: 27 Jan 2026 (UK)
Weeks start Monday

Action List

1) Cam status

Pulse check with Cam: Done

He is in a good space, very interested, OK with base in the 200s, and much more interested in equity.

No comp details were discussed with him. Vardi and Ari handle salary, benefits, and equity specifics.

2) Finish the interview loop (week of Mon 2 Feb 2026)

Cam finishes interviews that week with department heads.

Schedule the following week with Vardi.

Once the interview round is complete:

Fill in the scorecard.

Make sure everyone is included and heard.

Collect feedback.

Surface and address any staff pain points.

3) Pre-factor the comp package (Ari away week of Mon 2 Feb 2026) Internal

Align internally on salary range and how far you want to go.

Agree the benefits package.

Agree equity structure and positioning (founder-level operator framing).

Goal: go into the London meetup on week three already clear on the intended package.

4) London close-out meetup (week of Mon 16 Feb 2026)

Cam comes down to London for dinner, drinks, and a full meetup with leadership present.

Book a hotel overnight (clear signal we are serious).

5) Close the offer (next day or day after the London meetup)

Vardi and Ari deliver the offer and run the comp conversation.

Close salary, benefits, and equity within 24 to 48 hours after the meetup.

Move straight into onboarding and platform setup once closed.

6) Onboarding (post-offer close)

CTO onboarding deep dive:

Staff profiles already built.

Tech org and key people (Rainer, Mustafa).

Web front end.

Backend architecture.

Headcount plan.

Platform: access, repos, environments, build and release pipeline, tooling, and day-one operating rhythm.

Market demographic: who the game is for (target audience definition and why).

7) Operational setup (Lorenza and Mustafa) once offer is out and start date is set

Build out his profile (internal and public-ready bio pack if needed).

Set up all access and accounts (tooling, repos, comms, cloud, docs).

Provision his machine and confirm day-one readiness.

Confirm start-day schedule, introductions, and required pre-reads.

8) Comms

Public announcement: Cam joins as CTO (background and intro).

Studio announcement and quick introduction, either a short video or a town hall.

Calendar Grid (Weeks starting Monday)

| Workstream | Week of Mon 26 Jan 2026 | Week of Mon 2 Feb 2026 | Week of Mon 9 Feb 2026 | Week of Mon 16 Feb 2026 | Week of Mon 23 Feb 2026 |
| --- | --- | --- | --- | --- | --- |
| Hiring status | Pulse check with Cam: Done |  |  |  |  |
| Finish the interview loop |  | Dept head interviews (Cam) | Vardi interview(s) Scorecard + feedback Surface and address any staff pain points |  |  |
| Comp pre-factor (Ari away w/c 2 Feb) |  | Capture comp inputs and constraints (salary range, benefits, equity guardrails) | Internal alignment on intended package (ready for London) |  |  |
| London close-out meetup |  |  | Book hotel; lock dinner/drinks; confirm attendees and agenda | Cam in London: dinner, drinks, full meetup |  |
| Close offer |  |  | Draft final offer docs and approval path | Deliver offer; close within 24 to 48 hours after meetup |  |
| CTO onboarding deep dive |  |  |  | Kick off post-close: staff profiles; tech org and key people; web front end; backend; headcount; platform setup; market demographic | Continue onboarding execution and first-week operating cadence |
| Operational setup (Lorenza + Mustafa) |  |  | Prep checklist and owners | Trigger after offer and start date: profile; access; machine; start-day plan | Complete provisioning; verify access; day-one readiness |
| Comms |  |  | Draft announcement materials in parallel with acceptance |  | Publish announcement and do studio intro once start date is locked |

Note: Dates are anchored to Tue 27 Jan 2026. If interview timing shifts, adjust weeks accordingly.