## Project Plan
Ref | Priority | Artifact Name | Description | Legal Basis / Driver | Deadline / Trigger | Owner | Status Change | Status | ETA | ARTIFACTS | Link to Artifacts | Dependencies | Notes | References | Lorenza's Notes | ACTIONS
| P1 | PRIORITY 1: LEGALLY REQUIRED BEFORE FIRST HIRE
1.1 | P1 | Employment Contract (Section 1 Statement) | Written statement of employment particulars. Must include all mandatory items per s.1 ERA 1996 as amended. Must incorporate SSP day-one changes, paternity/parental leave day-one rights, flexible working reference, IP assignment clause, moral rights waiver (CDPA 1988 s.87), restrictive covenants, and reference ERA 2025. | Employment Rights Act 1996 s.1; Employment Rights Act 2025 | Before first employee starts | HR Lead + Legal | updated | DONE |  | Legally compliant FTE Contract | https://docs.google.com/document/d/1XCWALv3G2Ct1idEibBgs3m_2N1pOKsbq/edit | Legal review of current template; SSP clause rewrite | The existing Appendix Two template requires 11 mandatory corrections identified in the revised guide. Build from scratch recommended. | https://www.legislation.gov.uk/ukpga/1996/18/section/1 | - Pension may not be sufficient----> It should be specified that NEST is our Provider. | Create a clause to add Nest as pension provider in the contract.
1.2 | P1 | Offer Letter Template | Conditional offer letter including salary, start date, conditions (references, right to work), pension reference, Section 1 statement timing, acceptance deadline. | Best practice; supports contractual clarity | Before first employee starts | HR Lead | updated | Done |  | Offer Letter | here: https://docs.google.com/document/d/1CTaE93VqWhhlAlZlOOrj4UbY3IPGNErp/edit?usp=drive_link&ouid=111631440583371827928&rtpof=true&sd=true | Contract template (1.1) must be finalised first | Existing Appendix One needs corrections per revised guide.
1.3 | P1 | Employee Privacy Notice (UK GDPR) | Mandatory privacy notice for all employees. Must detail: categories of personal data collected, lawful bases, retention periods, recipients, data subject rights, cross-border transfers (to US parent NBI LLC), DPO contact if appointed. | UK GDPR Articles 13-14; Data Protection Act 2018 | Before first employee starts | Legal / DPO | updated | In Review | 14/04/2026 | GDPR Letter to check with Dino update: letter ready to be sent with employment contract update 1: Glen having the policy reviewed. | here: https://drive.google.com/file/d/1PwL8hJR9n3zPpMPQhif1vqBcPxQSHQB4/view?usp=drive_link | Cross-border data transfer agreement (2.6) must be planned in parallel | Required to be provided to every employee. Non-compliance is an ICO enforcement risk.
1.4 | P1 | Right to Work Checks Procedure | Step-by-step procedure for verifying right to work. Must cover: manual checks, online checks (share codes/eVisa), Employer Checking Service, record-keeping requirements, anti-discrimination safeguards (must check everyone equally). State civil penalty: up to £45,000 first breach / £60,000 repeat breach. *** for UK citizens do the IDVT method | Immigration, Asylum and Nationality Act 2006; Home Office Employer Right to Work Checklist | Before first employee starts | HR Lead | WIP | In Review | 15/04/2026 | Summary document and workflow tutorial | Lorenza Menna | None | Criminal offence to knowingly employ an illegal worker. Also a sponsor licence compliance requirement. |  | - Flow chart for Right to work check
1.5 | P1 | Health and Safety Policy | Written H&S policy mandatory for 5+ employees. Must include: general statement of intent, organisation and arrangements, risk assessment procedures, DSE assessments for remote/hybrid workers, fire safety, first aid, lone working, accident/incident reporting. | Health and Safety at Work etc. Act 1974; Management of Health and Safety at Work Regulations 1999; Health and Safety (Display Screen Equipment) Regulations 1992 | Before 5th employee starts (best practice: before first hire) | Operations Lead | follow up with Glen | Not started | 16/04/2026 | H&S policy | Glen Pryer to upload the document here: https://drive.google.com/drive/u/0/folders/14vYrPChhwqt9TK2EbxMOcLXMfVbhXdxm | Risk assessments must be completed for each workplace/role | A gaming studio has specific DSE risks. Remote workers require individual DSE assessments.
1.6 | P1 | Pension Auto-Enrolment Communication Letter | Template letter to each employee within 6 weeks of assessment explaining pension rights, scheme details, contribution rates, opt-out rights. | Pensions Act 2008; The Pensions Regulator guidance | Within 6 weeks of first eligible employee's start date | Payroll / HR Lead | follow up with Glen | Not started A template could be usefull |  | - Pension Scheme - Pension Letter for employee to know they are autoenrolled + Pension Scheme - Policy (Handbook) + Letter for people if they want to remove themselves from Pension Scheme - ONBOARDING Workflow to check the 6 weeks deadline | Lorenza Menna to start onboarding workflow | Pension scheme must be chosen and set up first | Can be templated and populated per employee. | NEST Pension scheme 5%- 3%. TO check with Nest if: - they autoenroll people - they have any template we can share with employees | - NEST Pension Scheme 5% employer + 3 %employee - autoenroll people at the beginning - to check if Nest autoenrolls people - no postponement - find template on NEST - link between NEST and PAYE - link with HiBob too | - access NEST to check if contributions are propoerly set and if Nest is autoenrolling
1.7 | P1 | EL Insurance Certificate Display | Obtain Employers' Liability Insurance (£5m minimum). Display certificate physically or electronically where employees can access it. | Employers' Liability (Compulsory Insurance) Act 1969 | Before first employee starts | Finance / Operations | updated | Done |  | - EL Insurance Certificate Display | here: https://drive.google.com/file/d/1bkCVdij9nYXPoHj31va8FlV6mg1mxu0X/view?usp=drive_link | Insurance broker/provider selection | Fine of £2,500 per day without cover. Home Office requires sight of this for sponsor licence.
| P2 | PRIORITY 2: REQUIRED WITHIN FIRST MONTHS / BEFORE SCALING
2.1 | P2 | Employee Handbook / Staff Handbook | Comprehensive handbook containing all workplace policies. See sub-items 2.1a-2.1q below. | Various statutes; ACAS Code of Practice; best practice | Within first 3 months of first hire | HR Lead + Legal | Glen to review it | Not started |  | Handbook (50 pages max) | - Lorenza Menna 1. SHORT VERSION: https://docs.google.com/document/d/1-mPTnXfYyHtZV5K8Q2S30yNlB4lCmxPd/edit 2. LONG VERSION: https://docs.google.com/document/d/1N78tUcIctM6UnSXC-5zTqlh4zg7w155T/edit - Glen Pryer to review it tomorrow at 4.30 | Contract template (1.1) must be finalised first | Single document or modular policy set. Must be reviewed annually.
2.1a | P2 | -- Disciplinary Policy and Procedure | Aligned with ACAS Code of Practice on Disciplinary and Grievance Procedures. Must cover investigation, hearing, appeal stages, right to be accompanied. | ACAS Code of Practice; ERA 1996 s.98 | Part of handbook | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook |  | Tribunals can increase awards by 25% for failure to follow ACAS Code.
2.1b | P2 | -- Grievance Policy and Procedure | Aligned with ACAS Code. Must cover informal resolution, formal grievance, investigation, hearing, appeal. | ACAS Code of Practice; ERA 1996 | Part of handbook | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook
2.1c | P2 | -- Sickness Absence Policy | Updated for SSP changes from 6 April 2026: no waiting days, no LEL, 80%-of-AWE rate. Cover self-certification (7 days), fit notes, return to work interviews, long-term absence management. | ERA 2025; SSP Regulations | Part of handbook. URGENT: must reflect 6 April 2026 changes. | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook | SSP clause in contract (1.1) | Remove any reference to 3-day waiting period or earnings threshold.
2.1d | P2 | -- Holiday and Leave Policy | Statutory minimum 5.6 weeks (28 days for 5-day week). Carry-over rules (including statutory right to carry over up to 20 days for sick workers for 18 months). Sickness during holiday conversion. Holiday accrual for irregular hours workers (12.07% method from April 2024). | Working Time Regulations 1998 (as amended) | Part of handbook | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook
2.1e | P2 | -- Family Leave Policies | Maternity, Paternity (day-one right from 6 April 2026), Adoption, Shared Parental, Unpaid Parental Leave (day-one right from 6 April 2026), Parental Bereavement, Neonatal Care Leave (from April 2025), Bereaved Partner's Paternity Leave (from 6 April 2026). | ERA 1996; ERA 2025; Maternity and Parental Leave etc. Regulations 1999; Bereaved Partner's Paternity Leave Regulations 2026 | Part of handbook. URGENT: day-one rights from 6 April 2026. | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook |  | Must remove old qualifying period references for paternity and unpaid parental leave.
2.1f | P2 | -- Flexible Working Policy | Day-one right to request since 6 April 2024. 2 requests per year. Employer must decide within 2 months. Must consult before refusing. ERA 2025 will further require structured reasoning if refusing. | ERA 1996 s.80F-80I (as amended); ERA 2025 | Part of handbook | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook
2.1g | P2 | -- Anti-Harassment and Bullying Policy | Must cover all protected characteristics (Equality Act 2010). Include sexual harassment specifically. Reference the preventative duty (reasonable steps from Oct 2024; all reasonable steps from Oct 2026). Include third-party harassment. Clear reporting routes. | Equality Act 2010; Worker Protection (Amendment of Equality Act 2010) Act 2023; ERA 2025 | Part of handbook | HR Lead + Legal |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook | Sexual Harassment Risk Assessment (2.8) | Compensation can be uplifted by 25% if employer cannot demonstrate preventative steps.
2.1h | P2 | -- Equal Opportunities Policy | Cover all protected characteristics under Equality Act 2010. Apply to recruitment, promotion, training, pay, and termination. | Equality Act 2010 | Part of handbook | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook
2.1i | P2 | -- Whistleblowing Policy | Public Interest Disclosure Act 1998 protections. Explain qualifying disclosures, how to raise concerns, protection from detriment. From April 2026, sexual harassment disclosures are qualifying disclosures. | PIDA 1998; ERA 2025 | Part of handbook | HR Lead + Legal |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook
2.1j | P2 | -- Data Protection Policy | UK GDPR and DPA 2018 compliance. Cover data handling, subject access requests, breach reporting, acceptable use of employee data. | UK GDPR; DPA 2018 | Part of handbook | Legal / DPO |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook | Privacy notice (1.3)
2.1k | P2 | -- IT Acceptable Use and Social Media Policy | Cover use of company systems, personal devices, social media, email monitoring. Include reference to UK GDPR for monitoring. | Best practice; supports disciplinary framework | Part of handbook | IT Lead / HR |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook
2.1l | P2 | -- Expenses Policy | Cover what is reimbursable, approval process, receipts, HMRC-approved mileage rates. | Best practice; supports payroll and tax compliance | Part of handbook | Finance / HR |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook
2.1m | P2 | -- Probationary Period Policy | Define probation length, review process, extension mechanism, confirmation/termination. Note: from January 2027, UFD qualifying period drops to 6 months. Probation must be designed with this in mind. | Contractual; informed by ERA 2025 UFD changes | Part of handbook | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook | Contract template (1.1) | There is no statutory concept of probation. It is a contractual mechanism. ACAS Code compliance applies throughout.
2.1n | P2 | -- Redundancy Policy | Cover consultation obligations (20+ redundancies: collective consultation with 45-day minimum period). Protective award now up to 180 days' pay from April 2026. From 2027, organisation-wide threshold may apply. | Trade Union and Labour Relations (Consolidation) Act 1992; ERA 2025 | Part of handbook | HR Lead + Legal |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook
2.1o | P2 | -- Working Time and 48-Hour Week Policy | Explain 48-hour average week limit, opt-out mechanism, rest breaks (20 min per 6 hours), daily rest (11 hours), weekly rest (24 hours). Address crunch periods specifically for gaming studio context. | Working Time Regulations 1998 | Part of handbook | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook |  | Gaming industry is notorious for crunch. Policy must proactively manage this risk.
2.1p | P2 | -- Alcohol and Drugs Policy | Testing, support, disciplinary implications. | Best practice; H&S obligations | Part of handbook | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook
2.1q | P2 | -- Training and Development Policy | Mandatory and optional training, time off for study, payment during training. | ERA 1996 s.1 (mandatory particular); best practice | Part of handbook | HR Lead |  | Not started |  |  | Lorenza to check if we have this section int he Lean version of the handboook
2.2 | P2 | IP Assignment Agreement | Standalone deed or contract clause assigning all IP created during employment (code, artwork, game design, sound, trade secrets) to the company. Must include: moral rights waiver under CDPA 1988 s.87, future IP, work-for-hire provisions, obligations on termination. | Copyright, Designs and Patents Act 1988; Patents Act 1977; common law | Before first creative/technical hire starts | Legal |  | Not started |  |  |  | Contract template (1.1) | CRITICAL for a gaming studio. Without this, default UK law may not vest all IP in the employer.
2.3 | P2 | Confidentiality / NDA (Standalone) | Project-level NDA for contractors, partners, and specific projects beyond the general contractual confidentiality clause. | Common law; contractual | As needed per project | Legal |  | Not started |  |  |  | Contract template (1.1) has a general clause | Current contract has a confidentiality clause but may need strengthening for project-level use.
2.4 | P2 | Post-Termination Restrictive Covenants | Non-compete, non-solicitation, non-dealing clauses tailored to gaming industry roles. Must be reasonable in scope, duration, and geography to be enforceable. | Common law; must be reasonable to be enforceable | Build into contract template (1.1) | Legal |  | Not started |  |  | Lorenza to put link to the contract | Contract template (1.1) | Review in light of fire-and-rehire restrictions from October 2026.
2.5 | P2 | DPIA Template | Data Protection Impact Assessment template for high-risk processing activities (e.g. employee monitoring, CCTV, biometric data). | UK GDPR Article 35 | Before any high-risk processing begins | Legal / DPO |  | Not started |  | Link to a document + Handbook + Contract
2.6 | P2 | Cross-Border Data Transfer Agreement | UK International Data Transfer Agreement (IDTA) or UK Addendum to EU Standard Contractual Clauses. Required for any transfer of employee personal data to NBI LLC (US parent). | UK GDPR Chapter V; ICO guidance | Before any data is shared with US parent | Legal / DPO |  | Not started |  | Statement to put in the handbook. |  | Privacy notice (1.3) must reference transfers | ICO has published templates. Must be completed and signed before transfers begin.
2.7 | P2 | Record Retention Policy | Comprehensive policy covering: payroll/wage records (6 years), PAYE records (3 years), SSP records (3 years), maternity records (3 years), working time records (duration of employment + 2 years), pension records (6 years), recruitment records (6 months post-decision minimum), dismissal records (minimum 6 months to match new tribunal time limit from October 2026), accident reports (3 years), right to work records (2 years after termination). | Various: Taxes Management Act 1970; WTR 1998; RIDDOR 2013; UK GDPR; ERA 2025 | Within first 3 months | HR Lead / Legal |  | Not started |  | - Statement in the handbook - Trackers/ document where we summarize where each excel spreadhseet/Hibob is |  |  | Must be updated when tribunal time limits extend to 6 months in October 2026.
2.8 | P2 | Sexual Harassment Risk Assessment | Documented risk assessment identifying risks of sexual harassment in the workplace (including from third parties such as clients, players, online interactions). Must assess risks and document preventative steps. | Worker Protection (Amendment of Equality Act 2010) Act 2023; ERA 2025 (October 2026: 'all reasonable steps') | Before October 2026 (best practice: immediately) | HR Lead |  | Not started |  | - Assessment Document internal confidential |  | Anti-harassment policy (2.1g) | Without this, employer cannot demonstrate compliance with the preventative duty. 25% compensation uplift risk.
| P3 | PRIORITY 3: REQUIRED FOR SPONSOR LICENCE APPLICATION
3.1 | P3 | Sponsor Licence HR Compliance Pack | Documented systems for: tracking attendance, visa expiry monitoring, passport/visa copy storage, Home Office reporting procedures. Must satisfy Home Office audit requirements. | Immigration Rules; Sponsor Guidance Part 1 (version 03/26) | Before sponsor licence application | HR Lead |  | Not started |  |  |  | HRIS platform selection (4.8) | Weak HR systems are the biggest reason for licence rejection.
3.2 | P3 | Sponsored Worker File Template | Standardised personnel file structure per sponsored worker: CoS details, visa copy, passport copy, right to work check record, attendance records, salary details, role description matching SOC code. | Sponsor Guidance Part 2 (version 03/26) | Before first CoS assignment | HR Lead |  | Not started |  |  |  | Sponsor licence granted
3.3 | P3 | Absence Reporting Procedure (Sponsored Workers) | Procedure for reporting unauthorised absences of 10+ consecutive working days to the Home Office via SMS. | Sponsor Guidance; Immigration Rules | Before first CoS assignment | HR Lead |  | Not started |  |  |  | Sponsor licence granted | Failure to report can result in licence downgrade or revocation.
3.4 | P3 | Salary and Role Change Reporting Procedure | Procedure for notifying the Home Office of changes to sponsored workers' salary, role, job title, or working location. | Sponsor Guidance; Immigration Rules | Before first CoS assignment | HR Lead |  | Not started |  |  |  | Sponsor licence granted
| P4 | PRIORITY 4: OPERATIONAL AND BEST-PRACTICE DOCUMENTS
4.1 | P4 | Job Description Templates | Standardised templates for all roles. Must include SOC 2020 occupation codes (for sponsor licence use) and salary benchmarking. | Best practice; supports sponsor licence compliance and equal pay | Before first recruitment round | HR Lead |  | Not started
4.2 | P4 | Interview Scoring Matrix | Structured scoring template for fair, consistent candidate evaluation. Aligned with Equality Act 2010 requirements. | Best practice; Equality Act 2010 | Before first recruitment round | HR Lead |  | Not started
4.3 | P4 | Onboarding Checklist | Comprehensive checklist: contract signing, right to work check, pension enrolment, IT setup, policy acknowledgements, training, DSE assessment, emergency contacts. | Best practice; consolidates legal requirements | Before first employee starts | HR Lead / Operations |  | Not started |  |  |  | Contract (1.1), RTW procedure (1.4), pension letter (1.6), H&S policy (1.5)
4.4 | P4 | Probation Review Template | Structured template for probation reviews: objectives, performance criteria, development areas, confirmation/extension/termination decision. | Best practice; supports UFD defence from January 2027 | Before first probation review | HR Lead |  | Not started |  |  |  | Probation policy (2.1m) | Critical for managing early-stage performance given 6-month UFD from January 2027.
4.5 | P4 | Performance Review Template | Annual/bi-annual performance review template. | Best practice | Within first year | HR Lead |  | Not started
4.6 | P4 | Exit Interview Template | Standardised questions for departing employees. | Best practice | Before first leaver | HR Lead |  | Not started
4.7 | P4 | Leaver Checklist | Final pay, pension cessation, return of property, revocation of IT access, IP confirmation, Home Office notification (if sponsored worker), reference policy. | Best practice; sponsor licence compliance | Before first leaver | HR / Operations |  | Not started
4.8 | P4 | HRIS Platform Selection and Implementation | Requirements spec for system integrating: personnel records, payroll, pension, recruitment, absence management, document storage, visa/sponsor tracking. | Best practice; supports multiple compliance requirements | Within first 3 months | Operations / HR |  | Not started |  |  |  |  | Payroll provider and pension provider must be selected first.
4.9 | P4 | Bribery Act Compliance Policy | Adequate procedures to prevent bribery under Bribery Act 2010 s.7. Cover gifts, hospitality, facilitation payments, third-party due diligence. | Bribery Act 2010 | Within first 6 months | Legal / Finance |  | Not started |  | To check with Dino/Aris/LILI |  |  | Defence of 'adequate procedures' requires documented policy.
4.10 | P4 | Modern Slavery Statement (OPTIONAL) | Statement of steps taken to prevent modern slavery in business and supply chains. Required if turnover exceeds £36m; good practice regardless. | Modern Slavery Act 2015 | When turnover threshold met (or voluntarily earlier) | Legal / Operations |  | Not started |  | To check with Dino/Aris/LILI |  |  | Only legally required if turnover exceeds £36 million. Not applicable at current scale.
4.12 | P4 | EMI Share Scheme Documentation (OPTIONAL) | Enterprise Management Incentives scheme: option agreement, scheme rules, HMRC notification, board resolutions, company valuation. Highly tax-efficient for UK tech startups. | Income Tax (Earnings and Pensions) Act 2003; HMRC EMI guidance | When ready to offer equity incentives | Legal / Finance |  | Not started |  | To check with Dino/Aris/LILI |  | Company valuation required | Hiring competitiveness tool, not a legal requirement. Build when ready to offer equity incentives.
4.13 | P4 | DSE Assessment Template | Display Screen Equipment assessment form for each employee (office and remote). Must cover workstation setup, screen position, chair, lighting, breaks. | Health and Safety (Display Screen Equipment) Regulations 1992 | Before each employee starts working at a screen | Operations / HR |  | Not started |  |  |  | H&S Policy (1.5) | Particularly important for a studio where all staff use screens.
4.14 | P4 | Trade Union Rights Communication Template | Template all-staff communication informing workers of their right to join a trade union and the protections that apply to union membership and activities. | ERA 2025 (from October 2026) | Before October 2026 | HR Lead |  | Not started |  |  |  |  | New mandatory duty from October 2026.
| P5 | PRIORITY 5: COMPANIES HOUSE AND CORPORATE GOVERNANCE
5.1 | P5 | Companies House Filing Calendar | Schedule for: confirmation statement (annual), annual accounts, PSC register maintenance, filing of any changes to directors/registered office/share capital. | Companies Act 2006 | Ongoing from incorporation | Finance / Legal |  | Done |  |  |  |  | Late filing penalties apply.
5.2 | P5 | PSC Register | Register of People with Significant Control. Must be kept up to date and filed with Companies House. | Companies Act 2006 Part 21A | From incorporation | Legal / Company Secretary |  | Done
5.3 | P5 | Director Identity Verification | Required under Economic Crime and Corporate Transparency Act 2023. Directors must verify their identity with Companies House. | ECCTA 2023 | When required by Companies House (phased implementation 2025/2026) | Directors / Legal |  | Done |  |  |  |  | Check Companies House for current implementation status.
5.4 | P5 | Corporation Tax Registration | Register with HMRC for Corporation Tax within 3 months of starting business activity. | Corporation Tax Act 2009 | Within 3 months of starting activity | Finance |  | Done
5.5 | P5 | VAT Registration Assessment | Assess whether turnover exceeds the £90,000 threshold (from April 2024). Register if required. Consider voluntary registration for input tax recovery. | Value Added Tax Act 1994 | Monitor ongoing; register when threshold reached | Finance |  | Done |  |  |  |  | Gaming studio may benefit from voluntary registration for input VAT recovery on equipment/services.
5.6 | P5 | R&D Tax Relief Assessment (OPTIONAL) | Assess eligibility for R&D tax relief (SME scheme or RDEC). Game development typically qualifies. Can be worth 10-33% of qualifying R&D expenditure. | Corporation Tax Act 2009 Part 13; Finance Act 2024 | First Corporation Tax return | Finance / Tax Advisor |  | in progress |  | to check with Aris |  |  | Tax optimisation, not a compliance requirement. Pursue with tax advisor at first CT return.

## Red Team Findings
# | Finding | Severity | Where It Affects | Action Required | Added to Plan?
1 | Bereaved Partner's Paternity Leave (new from 6 April 2026) not mentioned in original guide or in Section 6 timeline | HIGH | Section 6; Family Leave Policies | Add to ERA 2025 timeline (Section 6.1) and to Family Leave Policies artifact (2.1e) | YES
2 | Sexual harassment risk assessment not listed as standalone artifact | HIGH | Artifacts list; H&S | Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'. | YES
3 | Trade union communication obligation (October 2026) not mentioned | MEDIUM | Section 6; Artifacts list | Add to ERA 2025 timeline (Section 6.2) and create template artifact (4.14) | YES
4 | Record retention policy not listed as artifact. Payroll record retention stated as '3 years' but wage records require 6 years. | HIGH | Section 4.13; Artifacts list | Add Record Retention Policy as artifact (2.7). Correct 6-year obligation for payroll/wage records. | YES
7 | Working Time Regulations 48-hour week / crunch culture risk not addressed | MEDIUM | Section 5; Handbook | Add Working Time and 48-Hour Week Policy to handbook (2.1o). Address crunch periods specifically. | YES
8 | Right to work civil penalty amounts not stated (£45k first / £60k repeat) | MEDIUM | Section 5; RTW procedure | Add penalty figures to RTW Checks Procedure (1.4) | YES
9 | IP assignment: moral rights waiver (CDPA 1988 s.87) not specified | HIGH | Artifacts list; Contract | Add moral rights waiver requirement to IP Assignment Agreement spec (2.2) and contract (1.1) | YES
10 | DSE Assessment not listed as standalone artifact template | MEDIUM | H&S Policy; Artifacts list | Add DSE Assessment Template as artifact (4.13) | YES
11 | Equality (Race and Disability) Bill on legislative horizon for ethnicity/disability pay gap reporting (250+ employees). Not mentioned. | LOW | Awareness only at current size | Note for future. Not actionable until enacted. Monitor progress. | NO (future)
12 | 6-year record retention for payroll/wage records vs. 3 years stated in guide | HIGH | Section 4.13 | Correct Section 4.13 from 'at least 3 years' to 'at least 3 years (PAYE) / 6 years (payroll and wage records)'. | YES
13 | R&D tax relief not mentioned. Gaming studios commonly qualify and the cash benefit is significant. | MEDIUM | Corporate governance | Add R&D Tax Relief Assessment as artifact (5.6) | YES

## Compliance Timeline
Date | Change / Deadline | Category | Impact on CH | Artifact(s) Affected
Before first hire | Employers' Liability Insurance obtained and displayed | Insurance | Mandatory. £2,500/day fine without. | 1.7
Before first hire | Employment contract template finalised (with all 11 corrections) | Contract | Mandatory Section 1 statement from day one. | 1.1
Before first hire | Right to work check procedure in place | Immigration | Up to £60,000 per illegal worker (repeat breach). | 1.4
Before first hire | Employee privacy notice drafted | Data Protection | UK GDPR requirement. ICO enforcement risk. | 1.3
Before first hire | HMRC employer registration completed | Payroll | Must register before first payday. | Section 4
Before first hire | Pension scheme selected and set up | Pensions | Auto-enrolment duties begin with first eligible employee. | 1.6
1 April 2026 | NMW/NLW rates increase (£12.71 for 21+) | Pay | All salaries must meet new minimums. | Contract, payroll
6 April 2026 | SSP: waiting period removed, LEL removed, 80%-of-AWE rate | Statutory Pay | Contracts and policies must be updated. Payroll systems must handle new calculation. | 1.1, 2.1c
6 April 2026 | Paternity leave becomes day-one right | Family Leave | Remove qualifying period from policies. | 1.1, 2.1e
6 April 2026 | Unpaid parental leave becomes day-one right | Family Leave | Remove qualifying period from policies. | 1.1, 2.1e
6 April 2026 | Bereaved Partner's Paternity Leave introduced | Family Leave | New entitlement. Add to family leave policies. | 2.1e
6 April 2026 | Collective redundancy protective award doubled to 180 days | Redundancy | Increased financial risk of getting consultation wrong. | 2.1n
6 April 2026 | Sexual harassment becomes qualifying whistleblowing disclosure | Whistleblowing | Update whistleblowing policy. | 2.1i
6 April 2026 | Fair Work Agency established | Enforcement | New enforcement body for NMW, holiday pay, SSP. | Awareness
6 April 2026 | Trade union recognition simplified; electronic balloting | Trade Unions | Lower threshold for union recognition. | Awareness
6 April 2026 | Voluntary payrolling of BIK available (mandatory from April 2027) | Payroll / Tax | Optional to test systems. Mandatory from April 2027. | Section 4.12
8 April 2026 | Immigration fee increases (~6-7%) | Immigration | Higher costs for sponsor licence and visa applications. | Section 3
October 2026 | Fire and rehire becomes automatically unfair | Contracts | Review variation clauses in contract template. | 1.1, 2.4
October 2026 | Sexual harassment duty tightened to 'all reasonable steps' | Harassment | Risk assessment must be documented. All reasonable steps demonstrated. | 2.1g, 2.8
October 2026 | Third-party harassment liability reintroduced | Harassment | Assess risks from clients, players, online interactions. | 2.1g, 2.8
October 2026 | Tribunal time limits extended to 6 months | Litigation | Longer window for claims. Update record retention. | 2.7
October 2026 | Employer must inform workers of right to join a union | Trade Unions | Mandatory all-staff communication. | 4.14
January 2027 | Unfair dismissal qualifying period drops to 6 months | Dismissal | Anyone hired from ~July 2026 gains UFD protection Jan 2027. Probation design critical. | 1.1, 2.1m, 4.4
January 2027 | Unfair dismissal compensation cap removed | Dismissal | Unlimited compensatory awards. Getting dismissals wrong is now more expensive. | 2.1a, 2.1m
April 2027 | Mandatory payrolling of benefits in kind | Payroll / Tax | P11D no longer available for most benefits. Payroll systems must handle BIK reporting via RTI. | Section 4.12
2027 | Zero-hours contract guaranteed hours right | Contracts | If using ZHC workers, must offer guaranteed hours after reference period. | Awareness
2027 | Mandatory equality action plans (250+ employers) | Reporting | Only applies if CH reaches 250 employees. | Future

## HR Policies
| Key Provisions | Exceptions and Exemptions | Enforcement | LINKS
Working Time Regulations | Maximum Weekly Hours: Workers cannot work more than an average of 48 hours per week (usually calculated over a 17-week reference period), unless they have signed a voluntary opt-out agreement. | Opt-Out: Adult workers (18+) can choose to opt out of the 48-hour maximum, but this must be in writing. | Workers can bring claims to an employment tribunal if employers breach these regulations, such as failing to allow rest breaks or exceeding the 48-hour limit without an opt-out. | link
| Rest Breaks: Workers are entitled to a 20-minute rest break if they work more than 6 hours per day. | Excluded Sectors: Specific rules apply to sectors like transport, sea work, and air transport.
| Daily Rest: Workers are entitled to 11 consecutive hours of rest between working days. | "Autonomous Workers": Those with control over their own working time (e.g., managers) may be exempt from working hour limits.
Weekly Rest: Workers are entitled to an uninterrupted rest period of 24 hours every 7 days, or 48 hours every 14 days.
Annual Leave: Workers are entitled to a minimum of 5.6 weeks (28 days for a 5-day week) paid annual leave.
Night Work: Limits apply to night workers, typically averaging no more than 8 hours in 24, with mandatory free health assessments
Equality Act 2010 | Protected Characteristics Defined The nine characteristics protected under the Act include: - Age - Disability (physical or mental impairment with a substantial, long-term impact on daily life). - Gender Reassignment - Marriage and Civil Partnership (applies specifically in employment). - Pregnancy and Maternity - Race (includes colour, nationality, ethnic or national origins). - Religion or Belief - Sex - Sexual Orientation |  |  | link 1
link 2