## _STATS
Project | Item count
Production Strategy & Implementation | 151
HR | 133
Studio Operations | 244
UK Company Setup | 102
Studio Business | 249
Closed/Killed | 5
Game | 1194
AI | 138
TOTAL | 2216

## MASTER
parent_path | title | description | status | priority | health_state | work_type | assignees | due_date | dependencies | practice_area | type | layer | confidence | source | notes
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | JIRA Implementation & Rollout | Configure and roll out JIRA across the studio with Agilefall workflows | In progress | High | Green |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 1
Couch Heroes / HR / Hiring Pipeline - Process | Decide whether to use True Recruitment Assessment Tool (with Lorenza) | Evaluate tool for hiring process - we don't believe that Tru's recruitment assessment tool is meaningful for Couch Heroes | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 2
Couch Heroes / HR / Coaching Programme | Department Leads Development | Training modules, role clarity, and stretch assignments for leads | In progress | Medium | Green |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 3
Couch Heroes / HR / Coaching Programme | Short written reflections after key meetings | Institutionalise learning | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 4
Couch Heroes / HR / Coaching Programme | Two observed live interactions per month with written feedback (ongoing) | Structured observation programme | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 5
Couch Heroes / HR / Coaching Programme | Field practice during real meetings with debriefs (ongoing) | Ongoing live coaching | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 6
Couch Heroes / HR / Coaching Programme | Build playbooks with step-by-step patterns | Practical coaching tool | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 7
Couch Heroes / HR / Coaching Programme | Define role charters, scope, and KPIs aligned to product goals | Role clarity for each lead | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 8
Couch Heroes / HR / Coaching Programme | Deliver micro-training modules: planning quality, estimation, stakeholder updates, risk language | Capability building for leads | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 9
Couch Heroes / HR / Coaching Programme | Executive Coaching Programme | Structured coaching: conflict playbook, live observations, reflections Q2 (2026-04-26): Moved from EP Hiring to HR → Coaching Programme. The coaching is separate work from hiring Graham (who has already accepted, ~May 18 start). | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 10
Couch Heroes / HR / Coaching Programme | Identify key strengths and weaknesses across C-level and department head staff to establish areas of work | Communication is spotty and erratic. Key elements of clarity are missing around core details such as: • roles and remits • clarity between roles • consistency of decision making • most critically, clarity on vision and overall direction of the game, which needs to be addressed the department has had no existing forum that was just for them. They were not in a place to challenge and support each other in a healthy way. Establishing the leads meeting has been met positively across department leads. They adapted to the hiring process quickly. They are fairly open about what's working well and what's not. The current sense of ownership is still a little tentative and will take time to establish but is already growing. So far they're a great group of people to work with. | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 11
Couch Heroes / HR / Coaching Programme | Assign stretch work: cross-team dependency burn-down, release readiness packs | Development through stretch assignments | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 12
Couch Heroes / HR / Hiring Pipeline - DONE | Lead Animator Hiring | Evaluate current candidate and prepare interview materials. David Luong is decision-maker Q3 (2026-04-26): Same role as Alon. Marked Done. | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 13
Couch Heroes / Studio Operations / Org Design & Structure | QA Structure & UX Research | Define QA org, headcount, and UX research approach | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 14
Couch Heroes / HR / Hiring Pipeline - Process | Write Anthony Marques JD and leveling guide | Role definition and leveling | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 15
Couch Heroes / HR / 1:1s - Weekly Programme | Weekly coaching: Department Leads + bi-weekly 1:1s | Recurring weekly coaching and bi-weekly one-to-ones with leads | In progress | Medium | Green |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 16
Couch Heroes / HR / Hiring Pipeline - Process | Fix hiring plan to add UI/UX staffing and reset Anthony Marques's role | Headcount gap identified in Valeria 1:1 - this was missed in the head cap plan and is an alert that needs to be brought back up to Aris and added | Not started | Critical ACT |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 17
Couch Heroes / HR / Hiring Pipeline - Process | Define the critical needed headcount for next steps | Priority roles for studio growth - department heads have come together to provide feedback. Headcount has been assembled and it is currently in review with the leadership of Couch Heroes for approval | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 18
Couch Heroes / HR / Hiring Pipeline - Process | Build out the initial staffing process for Couch Heroes | Define end-to-end hiring workflow - the end-to-end hiring process from selecting staff down through onboarding has been completed in Miro and needs to be put into a report and we need to define a dissemination process, whether it's on Confluence or somewhere else | Drafted | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 19
Couch Heroes / HR / Hiring Pipeline - Process | Link the MIRO board for recruitment workflow / RACI matrix | Connect recruitment process documentation | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 20
Couch Heroes / HR / Hiring Pipeline - Process | Hiring Process & Infrastructure | Build end-to-end hiring workflow and address headcount gaps | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 21
Couch Heroes / HR / Hiring Pipeline - Engineering | Realign Mustafa to new role, define new role scope | Part of CTO transition planning - Mustafa has very comfortably aligned to Principal Engineer this transition has so far gone smoothly | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 22
Couch Heroes / HR / Hiring Pipeline - Engineering | Help close the CTO role | Support offer and negotiation - Cam has a family situation that requires him to go to Australia and be there for an extended period of time. We have offered to Cam, as a studio, to work in an advisor capacity for the time being, with boots on the ground, helping him execute with the team and working with his guidance we are currently waiting on his response to that. Q1: Cam dead. Cancelled. | Cancelled | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 23
Couch Heroes / HR / Hiring Pipeline - Engineering | Participate in CTO interviews | Advisory role in interview panel | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 24
Couch Heroes / HR / Hiring Pipeline - Engineering | Build CTO interview structure and process | End-to-end interview design | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 25
Couch Heroes / HR / Hiring Pipeline - DONE | Build question set for Lead Animator interviews | Interview preparation - this was done and I attended the lead animator interview, asking questions directly Q4 (2026-04-26): Done. ACTION: locate the questions actually used (no separate doc on disk), document them, attach during WorkSage upload. | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 26
Couch Heroes / HR / Hiring Pipeline - Engineering | Identify key CTO candidates | Build target candidate list - our first candidate was Cam Dunn and he is the best out of the candidates they've delivered. There are complications that we're working through but confidence is high that this will continue to a full CTO roll Q1: Cam was the candidate. Cancelled. Need fresh candidate identification. | Cancelled | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 27
Couch Heroes / HR / Hiring Pipeline - Engineering | Find an executive recruiter for CTO role | Source specialist exec recruiter - this is Charlie at True | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 28
Couch Heroes / HR / 1:1s - Weekly Programme | Weekly coaching: Dino 1:1 | Recurring weekly 1:1 coaching sessions with Dino | In progress | High | Green |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 29
Couch Heroes / Studio Operations / Org Design & Structure | Org Design Presentation & Strategy | Finalise 3-model org design presentation for exec team and address red team findings | In progress | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 30
Couch Heroes / HR / Hiring Pipeline - Production & Design | Template for interview questions for EP | Standardised question set | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 31
Couch Heroes / Studio Operations / Org Design & Structure | Clarify ownership & decision making between designers and artists | Build a clear decision making flow and accountability to remove conflicts and uncertainty | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 32
Couch Heroes / HR / Pay & Performance | Give feedback on promotions presentation | Attachment: {"originalUrl":"https:\/\/couchheroes.slack.com\/archives\/C08L3QGJ0AE\/p1772630282819889","attachment":{},"displayAsUrl":false} | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 33
Couch Heroes / UK Company Setup / UK Transition Operational | Gather contractor / employee ID and info | Attachment: {"originalUrl":"https:\/\/docs.google.com\/spreadsheets\/d\/1J0-lJg8RrN7xkh0x1JVxtAYLQAi3WF33Td3pFQ-Ccvc\/edit?gid=0#gid=0","attachment":{},"displayAsUrl":false} | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 34
Couch Heroes / UK Company Setup / UK Transition Operational | Review FTE contract | Attachment: {"originalUrl":"https:\/\/drive.google.com\/drive\/folders\/14vYrPChhwqt9TK2EbxMOcLXMfVbhXdxm","attachment":{},"displayAsUrl":false} | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 35
Couch Heroes / UK Company Setup / UK Transition Operational | Handbook review and iteration | Attachment: {"originalUrl":"https:\/\/drive.google.com\/drive\/folders\/14vYrPChhwqt9TK2EbxMOcLXMfVbhXdxm","attachment":{},"displayAsUrl":false} | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 36
Couch Heroes / Studio Business / BD | Player target Segments |  | Not started | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 37
Couch Heroes / Studio Business / BD | Go To Market Strategy |  | Not started | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 38
Couch Heroes / Studio Business / BD | Build a solid website | There is an existing website. It's pretty terrible. They're replacing it with a new one. It's taken roughly three months to build using full-stack engineers. It'll be a step-up iteration. We need to plan the next iteration to get it viable for the studio. | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 39
Couch Heroes / Closed/Killed / Gamescom (Cancelled) | Scope features with the leads | After the walkthrough is set, define the achievable scope for each feature we need to deliver and estimate it | Cancelled | Medium |  |  | Valeria |  |  | Game Studio Operations |  |  |  | CSV row 40 | Killed (Gamescom)
Couch Heroes / Closed/Killed / Gamescom (Cancelled) | Prepare Investor/Partner Narrative | With Vardis Confirm that the walkthrough creates the right impression for partners and investors | Cancelled | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 41 | Killed (Gamescom)
Couch Heroes / Closed/Killed / Gamescom (Cancelled) | Audit Platform readiness | With <@U07K2JSAP9V> Review the current stage of the platform and the connection between the web app and the game and decide on changes/additions | Cancelled | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 42 | Killed (Gamescom)
Couch Heroes / Closed/Killed / Gamescom (Cancelled) | Define the game experience we want to achieve | • Define features and mechanics players use • Define the sequence that feels fun to play • Define how the partner content is blended into this sequence to feel natural | Cancelled | Medium |  |  | Robin |  |  | Game Studio Operations |  |  |  | CSV row 43 | Killed (Gamescom)
Couch Heroes / Closed/Killed / Gamescom (Cancelled) | Shape the player walkthrough | • Set the walkthrough time per person • Outline the narrative arc to follow and places to visit • Assess the features we want to showcase and stages for each of them | Cancelled | Medium |  |  | Valeria |  |  | Game Studio Operations |  |  |  | CSV row 44 | Killed (Gamescom)
Couch Heroes / Game / Game Vision & Design | Game Vision & Design |  | In progress | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 45
Couch Heroes / AI / Usage Policy & Governance | AI Policy: verify final presentation item | develop a clear AI policy to safeguard CH AI usage and IP | Not started | High | Red |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 46
Couch Heroes / HR / Hiring Pipeline - Production & Design | create lead level designer JD | Build a job description for lead level designer and use the template, then get it approved so we can use that template boilerplate as the future structure for all job descriptions | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 47
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Dino | See Dino Notes for one-on-ones | In progress | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 48
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Lorenza | See Lorenza notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 49
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Vardis | See Vardis notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 50
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Aris | See artist notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 51
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Mustafa | See Mustafa notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 52
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Robin | See Robin notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 53
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with David | See David notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 54
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Valeria | See Valeria notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 55
Couch Heroes / HR / Pay & Performance | Identify staff and salary bands for targeted new roles added in the hiring process | Take selected roles added in the hiring plan and establish salaries for the UK based on median salary in non-hub locations | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 56
Couch Heroes / HR / Pay & Performance | Build and gain commitment on Pay and performance process for future delivery | Process flow out all the steps and owners of the pay and performance review. The studio is identifying owners on specific areas and steps to go through. Create a Confluence-style article and Visio flow that supports us. | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 57
Couch Heroes / HR / Pay & Performance | Support Dept heads and Leads through delivery | 4 challenge deliveries thus far all have been worked through | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 58
Couch Heroes / HR / Hiring Pipeline - Engineering | CTO Hiring | Executive search for Chief Technology Officer Q1 (2026-04-26): Cam, Neil, Nia ALL DEAD. Restarting search. Question set staged at Clients/Couch Heroes/CTO_Interview_Questions_Couch_Heroes.docx. Scorecard at CTO_Scorecard.xlsx. Recruiting brief at CTO_Recruiting_Brief_v6.pdf. Need to refresh and resource new candidates. | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 60
Couch Heroes / HR / Hiring Pipeline - Production & Design | Build scorecard for EP interviews | Structured evaluation criteria | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 61
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Make the implementation plan more human-readable | Current plan is too technical for leads | In progress | High | Red |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 62
Couch Heroes / HR / Hiring Pipeline - Production & Design | Get bids for external UX research | Vendor evaluation for outsourced UX | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 63
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Define exit criteria per gate | What must be true to pass each gate | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 64
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Draft rationale and full gate structure | Concept > Pre-Prod > Prod Start > Mid Prod > Late Prod > Alpha > Beta > Launch > First Release | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 65
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Build training sessions, quick-start guides, and recordings | Enablement materials for all staff | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 66
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Pilot in two teams for one cadence, capture improvements | Controlled test before full rollout | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 67
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Handle change communications | Studio-wide comms plan for the shift | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 68
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Roll out with department leads and sub-leads, get commits | Change management and buy-in | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 69
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define feature-based team structure (replacing department-based) | Structural shift from dept to feature teams | Planning | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 70
Couch Heroes / HR / Hiring Pipeline - QA | Meet with Hannah: cover QA plan, headcount needs, internal vs external split | Foundational QA planning session | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 71
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define target ways of working: cadence, estimation, DoR/DoD, scope control | Target state documentation | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 72
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Production audit: review current backlogs, pipelines, rituals | Baseline assessment of current state | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 73
Couch Heroes / HR / Hiring Pipeline - QA | Review Hannah Pickard for combined QA / UX Research role | Evaluate candidate fit for dual role | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 74
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Build out the Agilefall plan with Valeria | Core methodology design document | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 75
Couch Heroes / HR / Hiring Pipeline - Production & Design | Send UX agency details | Share agency info with team | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 76
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Integrate production backlog into gate system | Align existing work to gate structure | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 77
Couch Heroes / HR / Hiring Pipeline - QA | Set up one with Hannah | Set up a one-on-one with Hannah to support her as she is the solo QA. We will need to start doing builds and rapid iteration testing so we need to not only understand where she is, what she's already done, but establish what she needs in support of the edit workload coming her way | Not started | High | [5 empty] | Game Studio Operations |  |  |  | CSV row 78
Couch Heroes / Studio Operations / IT & Systems | Review and assess primary tool set, specifically test rail and purchase tool set | On top of test rail, look at AI implementations that could support and scale QA in a way that mitigates large team | Not started | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 79
Couch Heroes / HR / Hiring Pipeline - QA | Align with Hannah on overall team size at phases of development | Structure team and hiring process for expected needs going into heavier velocity production | Not started | High | [5 empty] | Game Studio Operations |  |  |  | CSV row 80
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Gate System Design & Rollout | Define milestone gates from Concept through First Release with exit criteria and review process | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 81
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Agilefall Methodology Rollout | Design and roll out Agilefall production methodology studio-wide | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 82
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Get commits and go live | Final sign-off from leads | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 83
Couch Heroes / Studio Operations / Org Design & Structure | Finalise org design presentation (3 models: A/B/C) | Three alternatives for executive leadership review | In progress | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 84
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Walk through with leads on February 18th | Presentation and Q&A with all department leads Q9 (2026-04-26): Postponed. Target ~2 weeks after offsite (mid-May), conditional on roadmap + process flow agreement first. | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 85
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Build Miro board implementation flow | Visual flow for how JIRA will be used | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 86
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Build Excel project plan for implementation | Detailed rollout timeline and dependencies | Drafted | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 87
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Build out master system board (with Valeria) | Central board setup and configuration | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 88
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Define Jira rules and workflow configuration (with Valeria) | Rules for statuses, fields, transitions | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 89
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Studio walkthrough and commitment | Present to studio and get sign-off | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 90
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Create risk and dependency register with owners and SLAs | Foundational risk tracking tied to gates | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 91
Couch Heroes / HR / Hiring Pipeline - Production & Design | Build/confirm interview brief for EP role | Equivalent to the one built for Cam's role | Done | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 92
Couch Heroes / HR / Pay & Performance | Performance Review Process | Complete current cycle actions and build infrastructure for next cycle | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 93
Couch Heroes / HR / Hiring Pipeline - Production & Design | Set up interview panel with Leads | Identify panel members and schedule | Done | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 94
Couch Heroes / HR / Hiring Pipeline - Process | Executive Producer Hiring | CRITICAL FIRST HIRE: Set up full interview process for EP role | In progress | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 95
Couch Heroes / UK Company Setup / UK Transition Operational | Discuss next steps and risks (EOR, visa, etc.) | Risk assessment with Lorenza once unblocked | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 96
Couch Heroes / UK Company Setup / UK Transition Operational | Review Lorenza's finalised transition checklist | Checklist review once unblocked | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 97
Couch Heroes / UK Company Setup / UK Transition Operational | UK Transition Planning | Build out a complete and comprehensive plan on moving staff under an LLC in the UK establish the following categories: • Staff and staff regulation • Financing • Operational needs according to Home Office rules • Who handles tax? • Who handles budget? • Communications to staff on transition • Timing - schedule ◦ Legal Checklist ◦ Payroll check ◦ Communication checklist ◦ Certificate of Sponsorship Detail and Checklist | In progress | Medium | Yellow |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 98
Couch Heroes / HR / Pay & Performance | Follow back up with Raynor to confirm everything is copacetic | Check alignment on salary and bonus equity | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 99
Couch Heroes / HR / Pay & Performance | Structure salary bands for pay review | Compensation bands by level and role - celery pans globally were researched and identified and delivered and ingested into the existing staff files | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 100
Couch Heroes / HR / Pay & Performance | Decide on Dino's performance review (on hold until Aris) | BLOCKED: waiting on Aris decision Q7 (2026-04-26): Performance review was already DELIVERED. Exit timeline (1mo transition + 2mo garden leave) is TENTATIVE - see Dino exit story for tracking. | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 101
Couch Heroes / HR / Pay & Performance | Train leads on PIP handling and delivery | Capability building for difficult conversations | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 102
Couch Heroes / HR / Pay & Performance | Put coaching and performance check processes in place before next cycle | Prevent inaccurate ratings next round | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 103
Couch Heroes / HR / Pay & Performance | Book meeting with Aris about Valeria | Schedule once Aris is available | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 104
Couch Heroes / HR / Pay & Performance | Give Lorenza feedback on Valeria performance review template | Review the linked document and provide feedback | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 105
Couch Heroes / HR / Pay & Performance | Pay & Performance Governance | Build compensation governance framework for ongoing use | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 106
Couch Heroes / Production Strategy & Implementation / Roadmap & Cadence Rollout | Roadmap & Cadence Rollout | Establish roadmap-based production rhythm and rituals | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 107
Couch Heroes / HR / Salary Review Delivery (CLOSED) | Share salary file with Heads of Departments | Distribute to HoDs so delivery conversations can start | Done | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 108
Couch Heroes / HR / Salary Review Delivery (CLOSED) | Fix the formula on the salary file | Formula issue blocking final version | Done | Medium |  |  | Lorenza |  |  | Game Studio Operations |  |  |  | CSV row 109
Couch Heroes / HR / Salary Review Delivery (CLOSED) | Send the final salary file worldwide | WIP, needs to go out ASAP | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 110
Couch Heroes / HR / Pay & Performance | Salary Review Delivery | URGENT: Complete and distribute salary file, enable delivery conversations across studio | Done | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 111
Couch Heroes / Studio Operations / Org Design & Structure | Studio review, approval, and commitment | Studio-wide sign-off on framework | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 112
Couch Heroes / Studio Operations / Org Design & Structure | Build a RACI matrix | Clear ownership and accountability mapping | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 113
Couch Heroes / Studio Operations / Org Design & Structure | Build position and level grades per role | Leveling framework for all positions | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 114
Couch Heroes / Studio Operations / Org Design & Structure | Roles & Responsibilities Framework | Build leveling framework, RACI matrix, and get studio commitment | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 115
Couch Heroes / HR / Hiring Pipeline - DONE | Talk with David about Lead Animator (current candidate may not be best choice) | Get David's input on direction - this was done. He preferred his top candidate | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 116
Couch Heroes / Production Strategy & Implementation / Roadmap & Cadence Rollout | Configure goals and OKR tracking | Set up tracking infrastructure | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 117
Couch Heroes / Production Strategy & Implementation / Roadmap & Cadence Rollout | Align leadership on cadence: 2-day quarterly planning, 2-week sprints, weekly health checks | Get leadership buy-in on rhythm | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 118
Couch Heroes / HR / Hiring Pipeline - DONE | Hire Lead Animator | We hired Alon who is working partial weeks until he finishes his contract with Rick Kindled over the next few months. Legal constraints and risks were assessed. Contracts were put in place. Dino reviewed. Lorenza set up all of the logistics. Alon is started. | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 119
Couch Heroes / Production Strategy & Implementation / Roadmap & Cadence Rollout | Move to roadmap-based production with feature-based teams | Shift from dept-based to feature-based delivery | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 120
Couch Heroes / HR / Coaching Programme | Coaching Programme |  | Not started | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 121
Couch Heroes / UK Company Setup / Project Plan | PRIORITY 1: LEGALLY REQUIRED BEFORE FIRST HIRE | {'Priority': 'P1', 'Artifact Name': 'PRIORITY 1: LEGALLY REQUIRED BEFORE FIRST HIRE'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref
Couch Heroes / UK Company Setup / Project Plan | 1.1 Employment Contract (Section 1 Statement) | {'Ref': '1.1', 'Priority': 'P1', 'Artifact Name': 'Employment Contract (Section 1 Statement)', 'Description': 'Written statement of employment particulars. Must include all mandatory items per s.1 ERA 1996 as amended. Must incorporate SSP day-one changes, paternity/parental leave day-one rights, flexible working reference, IP assignment clause, moral rights waiver (CDPA 1988 s.87), restrictive covenants, and reference ERA 2025.', 'Legal Basis / Driver': 'Employment Rights Act 1996 s.1; Employment Rights Act 2025', 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'HR Lead + Legal', 'Status Change': 'updated', 'Status': 'DONE', 'ARTIFACTS': 'Legally compliant FTE Contract', 'Link to Artifacts': 'https://docs.google.com/document/d/1XCWALv3G2Ct1idEibBgs3m_2N1pOKsbq/edit', 'Dependencies': 'Legal review of current template; SSP clause rewrite', 'Notes': 'The existing Appendix Two template requires 11 mandatory corrections identified in the revised guide. Build from scratch reco | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.1
Couch Heroes / UK Company Setup / Project Plan | 1.2 Offer Letter Template | {'Ref': '1.2', 'Priority': 'P1', 'Artifact Name': 'Offer Letter Template', 'Description': 'Conditional offer letter including salary, start date, conditions (references, right to work), pension reference, Section 1 statement timing, acceptance deadline.', 'Legal Basis / Driver': 'Best practice; supports contractual clarity', 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'HR Lead', 'Status Change': 'updated', 'Status': 'Done', 'ARTIFACTS': 'Offer Letter ', 'Link to Artifacts': 'here: https://docs.google.com/document/d/1CTaE93VqWhhlAlZlOOrj4UbY3IPGNErp/edit?usp=drive_link&ouid=111631440583371827928&rtpof=true&sd=true ', 'Dependencies': 'Contract template (1.1) must be finalised first', 'Notes': 'Existing Appendix One needs corrections per revised guide.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.2
Couch Heroes / UK Company Setup / Project Plan | 1.3 Employee Privacy Notice (UK GDPR) | {'Ref': '1.3', 'Priority': 'P1', 'Artifact Name': 'Employee Privacy Notice (UK GDPR)', 'Description': 'Mandatory privacy notice for all employees. Must detail: categories of personal data collected, lawful bases, retention periods, recipients, data subject rights, cross-border transfers (to US parent NBI LLC), DPO contact if appointed.', 'Legal Basis / Driver': 'UK GDPR Articles 13-14; Data Protection Act 2018', 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'Legal / DPO', 'Status Change': 'updated', 'Status': 'In Review', 'ETA': '14/04/2026', 'ARTIFACTS': 'GDPR Letter to check with Dino\n\nupdate: letter ready to be sent with employment contract\n\nupdate 1: Glen having the policy reviewed. ', 'Link to Artifacts': 'here: https://drive.google.com/file/d/1PwL8hJR9n3zPpMPQhif1vqBcPxQSHQB4/view?usp=drive_link ', 'Dependencies': 'Cross-border data transfer agreement (2.6) must be planned in parallel', 'Notes': 'Required to be provided to every employee. Non-compliance is an | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.3
Couch Heroes / UK Company Setup / Project Plan | 1.4 Right to Work Checks Procedure | {'Ref': '1.4', 'Priority': 'P1', 'Artifact Name': 'Right to Work Checks Procedure', 'Description': 'Step-by-step procedure for verifying right to work. Must cover: manual checks, online checks (share codes/eVisa), Employer Checking Service, record-keeping requirements, anti-discrimination safeguards (must check everyone equally). State civil penalty: up to £45,000 first breach / £60,000 repeat breach. *** for UK citizens do the IDVT method ', 'Legal Basis / Driver': 'Immigration, Asylum and Nationality Act 2006; Home Office Employer Right to Work Checklist', 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'HR Lead', 'Status Change': 'WIP', 'Status': 'In Review', 'ETA': '15/04/2026', 'ARTIFACTS': 'Summary document and workflow tutorial', 'Link to Artifacts': 'Lorenza Menna', 'Dependencies': 'None', 'Notes': 'Criminal offence to knowingly employ an illegal worker. Also a sponsor licence compliance requirement.', "Lorenza's Notes": '- Flow chart for Right to work check '} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.4
Couch Heroes / UK Company Setup / Project Plan | 1.5 Health and Safety Policy | {'Ref': '1.5', 'Priority': 'P1', 'Artifact Name': 'Health and Safety Policy', 'Description': 'Written H&S policy mandatory for 5+ employees. Must include: general statement of intent, organisation and arrangements, risk assessment procedures, DSE assessments for remote/hybrid workers, fire safety, first aid, lone working, accident/incident reporting.', 'Legal Basis / Driver': 'Health and Safety at Work etc. Act 1974; Management of Health and Safety at Work Regulations 1999; Health and Safety (Display Screen Equipment) Regulations 1992', 'Deadline / Trigger': 'Before 5th employee starts (best practice: before first hire)', 'Owner': 'Operations Lead', 'Status Change': 'follow up with Glen', 'Status': 'Not started', 'ETA': '16/04/2026', 'ARTIFACTS': 'H&S policy ', 'Link to Artifacts': 'Glen Pryer to upload the document here: https://drive.google.com/drive/u/0/folders/14vYrPChhwqt9TK2EbxMOcLXMfVbhXdxm', 'Dependencies': 'Risk assessments must be completed for each workplace/role', 'Notes': | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.5
Couch Heroes / UK Company Setup / Project Plan | 1.6 Pension Auto-Enrolment Communication Letter | {'Ref': '1.6', 'Priority': 'P1', 'Artifact Name': 'Pension Auto-Enrolment Communication Letter', 'Description': 'Template letter to each employee within 6 weeks of assessment explaining pension rights, scheme details, contribution rates, opt-out rights.', 'Legal Basis / Driver': 'Pensions Act 2008; The Pensions Regulator guidance', 'Deadline / Trigger': "Within 6 weeks of first eligible employee's start date", 'Owner': 'Payroll / HR Lead', 'Status Change': 'follow up with Glen', 'Status': 'Not started\n\nA template could be usefull', 'ARTIFACTS': '- Pension Scheme\n- Pension Letter for employee to know they are autoenrolled + Pension Scheme\n- Policy (Handbook) + Letter for people if they want to remove themselves from Pension Scheme\n\n\n- ONBOARDING Workflow to check the 6 weeks deadline', 'Link to Artifacts': 'Lorenza Menna to start onboarding workflow', 'Dependencies': 'Pension scheme must be chosen and set up first', 'Notes': 'Can be templated and populated per employee.', 'Refere | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.6
Couch Heroes / UK Company Setup / Project Plan | 1.7 EL Insurance Certificate Display | {'Ref': '1.7', 'Priority': 'P1', 'Artifact Name': 'EL Insurance Certificate Display', 'Description': "Obtain Employers' Liability Insurance (£5m minimum). Display certificate physically or electronically where employees can access it.", 'Legal Basis / Driver': "Employers' Liability (Compulsory Insurance) Act 1969", 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'Finance / Operations', 'Status Change': 'updated', 'Status': 'Done', 'ARTIFACTS': '- EL Insurance Certificate Display', 'Link to Artifacts': 'here: https://drive.google.com/file/d/1bkCVdij9nYXPoHj31va8FlV6mg1mxu0X/view?usp=drive_link ', 'Dependencies': 'Insurance broker/provider selection', 'Notes': 'Fine of £2,500 per day without cover. Home Office requires sight of this for sponsor licence.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.7
Couch Heroes / UK Company Setup / Project Plan | PRIORITY 2: REQUIRED WITHIN FIRST MONTHS / BEFORE SCALING | {'Priority': 'P2', 'Artifact Name': 'PRIORITY 2: REQUIRED WITHIN FIRST MONTHS / BEFORE SCALING'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref
Couch Heroes / UK Company Setup / Project Plan | 2.1 Employee Handbook / Staff Handbook | {'Ref': '2.1', 'Priority': 'P2', 'Artifact Name': 'Employee Handbook / Staff Handbook', 'Description': 'Comprehensive handbook containing all workplace policies. See sub-items 2.1a-2.1q below.', 'Legal Basis / Driver': 'Various statutes; ACAS Code of Practice; best practice', 'Deadline / Trigger': 'Within first 3 months of first hire', 'Owner': 'HR Lead + Legal', 'Status Change': 'Glen to review it', 'Status': 'Not started', 'ARTIFACTS': 'Handbook (50 pages max) ', 'Link to Artifacts': '- Lorenza Menna \n\n1. SHORT VERSION: https://docs.google.com/document/d/1-mPTnXfYyHtZV5K8Q2S30yNlB4lCmxPd/edit\n2. LONG VERSION: https://docs.google.com/document/d/1N78tUcIctM6UnSXC-5zTqlh4zg7w155T/edit\n\n- Glen Pryer to review it tomorrow at 4.30 ', 'Dependencies': 'Contract template (1.1) must be finalised first', 'Notes': 'Single document or modular policy set. Must be reviewed annually.'} | In Review | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1
Couch Heroes / UK Company Setup / Project Plan | 2.1a -- Disciplinary Policy and Procedure | {'Ref': '2.1a', 'Priority': 'P2', 'Artifact Name': '-- Disciplinary Policy and Procedure', 'Description': 'Aligned with ACAS Code of Practice on Disciplinary and Grievance Procedures. Must cover investigation, hearing, appeal stages, right to be accompanied.', 'Legal Basis / Driver': 'ACAS Code of Practice; ERA 1996 s.98', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Notes': 'Tribunals can increase awards by 25% for failure to follow ACAS Code.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1a
Couch Heroes / UK Company Setup / Project Plan | 2.1b -- Grievance Policy and Procedure | {'Ref': '2.1b', 'Priority': 'P2', 'Artifact Name': '-- Grievance Policy and Procedure', 'Description': 'Aligned with ACAS Code. Must cover informal resolution, formal grievance, investigation, hearing, appeal.', 'Legal Basis / Driver': 'ACAS Code of Practice; ERA 1996', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1b
Couch Heroes / UK Company Setup / Project Plan | 2.1c -- Sickness Absence Policy | {'Ref': '2.1c', 'Priority': 'P2', 'Artifact Name': '-- Sickness Absence Policy', 'Description': 'Updated for SSP changes from 6 April 2026: no waiting days, no LEL, 80%-of-AWE rate. Cover self-certification (7 days), fit notes, return to work interviews, long-term absence management.', 'Legal Basis / Driver': 'ERA 2025; SSP Regulations', 'Deadline / Trigger': 'Part of handbook. URGENT: must reflect 6 April 2026 changes.', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Dependencies': 'SSP clause in contract (1.1)', 'Notes': 'Remove any reference to 3-day waiting period or earnings threshold.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1c
Couch Heroes / UK Company Setup / Project Plan | 2.1d -- Holiday and Leave Policy | {'Ref': '2.1d', 'Priority': 'P2', 'Artifact Name': '-- Holiday and Leave Policy', 'Description': 'Statutory minimum 5.6 weeks (28 days for 5-day week). Carry-over rules (including statutory right to carry over up to 20 days for sick workers for 18 months). Sickness during holiday conversion. Holiday accrual for irregular hours workers (12.07% method from April 2024).', 'Legal Basis / Driver': 'Working Time Regulations 1998 (as amended)', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1d
Couch Heroes / UK Company Setup / Project Plan | 2.1e -- Family Leave Policies | {'Ref': '2.1e', 'Priority': 'P2', 'Artifact Name': '-- Family Leave Policies', 'Description': "Maternity, Paternity (day-one right from 6 April 2026), Adoption, Shared Parental, Unpaid Parental Leave (day-one right from 6 April 2026), Parental Bereavement, Neonatal Care Leave (from April 2025), Bereaved Partner's Paternity Leave (from 6 April 2026).", 'Legal Basis / Driver': "ERA 1996; ERA 2025; Maternity and Parental Leave etc. Regulations 1999; Bereaved Partner's Paternity Leave Regulations 2026", 'Deadline / Trigger': 'Part of handbook. URGENT: day-one rights from 6 April 2026.', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Notes': 'Must remove old qualifying period references for paternity and unpaid parental leave.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1e
Couch Heroes / UK Company Setup / Project Plan | 2.1f -- Flexible Working Policy | {'Ref': '2.1f', 'Priority': 'P2', 'Artifact Name': '-- Flexible Working Policy', 'Description': 'Day-one right to request since 6 April 2024. 2 requests per year. Employer must decide within 2 months. Must consult before refusing. ERA 2025 will further require structured reasoning if refusing.', 'Legal Basis / Driver': 'ERA 1996 s.80F-80I (as amended); ERA 2025', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1f
Couch Heroes / UK Company Setup / Project Plan | 2.1g -- Anti-Harassment and Bullying Policy | {'Ref': '2.1g', 'Priority': 'P2', 'Artifact Name': '-- Anti-Harassment and Bullying Policy', 'Description': 'Must cover all protected characteristics (Equality Act 2010). Include sexual harassment specifically. Reference the preventative duty (reasonable steps from Oct 2024; all reasonable steps from Oct 2026). Include third-party harassment. Clear reporting routes.', 'Legal Basis / Driver': 'Equality Act 2010; Worker Protection (Amendment of Equality Act 2010) Act 2023; ERA 2025', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead + Legal', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Dependencies': 'Sexual Harassment Risk Assessment (2.8)', 'Notes': 'Compensation can be uplifted by 25% if employer cannot demonstrate preventative steps.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1g
Couch Heroes / UK Company Setup / Project Plan | 2.1h -- Equal Opportunities Policy | {'Ref': '2.1h', 'Priority': 'P2', 'Artifact Name': '-- Equal Opportunities Policy', 'Description': 'Cover all protected characteristics under Equality Act 2010. Apply to recruitment, promotion, training, pay, and termination.', 'Legal Basis / Driver': 'Equality Act 2010', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1h
Couch Heroes / UK Company Setup / Project Plan | 2.1i -- Whistleblowing Policy | {'Ref': '2.1i', 'Priority': 'P2', 'Artifact Name': '-- Whistleblowing Policy', 'Description': 'Public Interest Disclosure Act 1998 protections. Explain qualifying disclosures, how to raise concerns, protection from detriment. From April 2026, sexual harassment disclosures are qualifying disclosures.', 'Legal Basis / Driver': 'PIDA 1998; ERA 2025', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead + Legal', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1i
Couch Heroes / UK Company Setup / Project Plan | 2.1j -- Data Protection Policy | {'Ref': '2.1j', 'Priority': 'P2', 'Artifact Name': '-- Data Protection Policy', 'Description': 'UK GDPR and DPA 2018 compliance. Cover data handling, subject access requests, breach reporting, acceptable use of employee data.', 'Legal Basis / Driver': 'UK GDPR; DPA 2018', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'Legal / DPO', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Dependencies': 'Privacy notice (1.3)'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1j
Couch Heroes / UK Company Setup / Project Plan | 2.1k -- IT Acceptable Use and Social Media Policy | {'Ref': '2.1k', 'Priority': 'P2', 'Artifact Name': '-- IT Acceptable Use and Social Media Policy', 'Description': 'Cover use of company systems, personal devices, social media, email monitoring. Include reference to UK GDPR for monitoring.', 'Legal Basis / Driver': 'Best practice; supports disciplinary framework', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'IT Lead / HR', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1k
Couch Heroes / UK Company Setup / Project Plan | 2.1l -- Expenses Policy | {'Ref': '2.1l', 'Priority': 'P2', 'Artifact Name': '-- Expenses Policy', 'Description': 'Cover what is reimbursable, approval process, receipts, HMRC-approved mileage rates.', 'Legal Basis / Driver': 'Best practice; supports payroll and tax compliance', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'Finance / HR', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1l
Couch Heroes / UK Company Setup / Project Plan | 2.1m -- Probationary Period Policy | {'Ref': '2.1m', 'Priority': 'P2', 'Artifact Name': '-- Probationary Period Policy', 'Description': 'Define probation length, review process, extension mechanism, confirmation/termination. Note: from January 2027, UFD qualifying period drops to 6 months. Probation must be designed with this in mind.', 'Legal Basis / Driver': 'Contractual; informed by ERA 2025 UFD changes', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Dependencies': 'Contract template (1.1)', 'Notes': 'There is no statutory concept of probation. It is a contractual mechanism. ACAS Code compliance applies throughout.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1m
Couch Heroes / UK Company Setup / Project Plan | 2.1n -- Redundancy Policy | {'Ref': '2.1n', 'Priority': 'P2', 'Artifact Name': '-- Redundancy Policy', 'Description': "Cover consultation obligations (20+ redundancies: collective consultation with 45-day minimum period). Protective award now up to 180 days' pay from April 2026. From 2027, organisation-wide threshold may apply.", 'Legal Basis / Driver': 'Trade Union and Labour Relations (Consolidation) Act 1992; ERA 2025', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead + Legal', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1n
Couch Heroes / UK Company Setup / Project Plan | 2.1o -- Working Time and 48-Hour Week Policy | {'Ref': '2.1o', 'Priority': 'P2', 'Artifact Name': '-- Working Time and 48-Hour Week Policy', 'Description': 'Explain 48-hour average week limit, opt-out mechanism, rest breaks (20 min per 6 hours), daily rest (11 hours), weekly rest (24 hours). Address crunch periods specifically for gaming studio context.', 'Legal Basis / Driver': 'Working Time Regulations 1998', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Notes': 'Gaming industry is notorious for crunch. Policy must proactively manage this risk.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1o
Couch Heroes / UK Company Setup / Project Plan | 2.1p -- Alcohol and Drugs Policy | {'Ref': '2.1p', 'Priority': 'P2', 'Artifact Name': '-- Alcohol and Drugs Policy', 'Description': 'Testing, support, disciplinary implications.', 'Legal Basis / Driver': 'Best practice; H&S obligations', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1p
Couch Heroes / UK Company Setup / Project Plan | 2.1q -- Training and Development Policy | {'Ref': '2.1q', 'Priority': 'P2', 'Artifact Name': '-- Training and Development Policy', 'Description': 'Mandatory and optional training, time off for study, payment during training.', 'Legal Basis / Driver': 'ERA 1996 s.1 (mandatory particular); best practice', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1q
Couch Heroes / UK Company Setup / Project Plan | 2.2 IP Assignment Agreement | {'Ref': '2.2', 'Priority': 'P2', 'Artifact Name': 'IP Assignment Agreement', 'Description': 'Standalone deed or contract clause assigning all IP created during employment (code, artwork, game design, sound, trade secrets) to the company. Must include: moral rights waiver under CDPA 1988 s.87, future IP, work-for-hire provisions, obligations on termination.', 'Legal Basis / Driver': 'Copyright, Designs and Patents Act 1988; Patents Act 1977; common law', 'Deadline / Trigger': 'Before first creative/technical hire starts', 'Owner': 'Legal', 'Status': 'Not started', 'Dependencies': 'Contract template (1.1)', 'Notes': 'CRITICAL for a gaming studio. Without this, default UK law may not vest all IP in the employer.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.2
Couch Heroes / UK Company Setup / Project Plan | 2.3 Confidentiality / NDA (Standalone) | {'Ref': '2.3', 'Priority': 'P2', 'Artifact Name': 'Confidentiality / NDA (Standalone)', 'Description': 'Project-level NDA for contractors, partners, and specific projects beyond the general contractual confidentiality clause.', 'Legal Basis / Driver': 'Common law; contractual', 'Deadline / Trigger': 'As needed per project', 'Owner': 'Legal', 'Status': 'Not started', 'Dependencies': 'Contract template (1.1) has a general clause', 'Notes': 'Current contract has a confidentiality clause but may need strengthening for project-level use.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.3
Couch Heroes / UK Company Setup / Project Plan | 2.4 Post-Termination Restrictive Covenants | {'Ref': '2.4', 'Priority': 'P2', 'Artifact Name': 'Post-Termination Restrictive Covenants', 'Description': 'Non-compete, non-solicitation, non-dealing clauses tailored to gaming industry roles. Must be reasonable in scope, duration, and geography to be enforceable.', 'Legal Basis / Driver': 'Common law; must be reasonable to be enforceable', 'Deadline / Trigger': 'Build into contract template (1.1)', 'Owner': 'Legal', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to put link to the contract', 'Dependencies': 'Contract template (1.1)', 'Notes': 'Review in light of fire-and-rehire restrictions from October 2026.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.4
Couch Heroes / UK Company Setup / Project Plan | 2.5 DPIA Template | {'Ref': '2.5', 'Priority': 'P2', 'Artifact Name': 'DPIA Template', 'Description': 'Data Protection Impact Assessment template for high-risk processing activities (e.g. employee monitoring, CCTV, biometric data).', 'Legal Basis / Driver': 'UK GDPR Article 35', 'Deadline / Trigger': 'Before any high-risk processing begins', 'Owner': 'Legal / DPO', 'Status': 'Not started', 'ARTIFACTS': 'Link to a document + Handbook + Contract'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.5
Couch Heroes / UK Company Setup / Project Plan | 2.6 Cross-Border Data Transfer Agreement | {'Ref': '2.6', 'Priority': 'P2', 'Artifact Name': 'Cross-Border Data Transfer Agreement', 'Description': 'UK International Data Transfer Agreement (IDTA) or UK Addendum to EU Standard Contractual Clauses. Required for any transfer of employee personal data to NBI LLC (US parent).', 'Legal Basis / Driver': 'UK GDPR Chapter V; ICO guidance', 'Deadline / Trigger': 'Before any data is shared with US parent', 'Owner': 'Legal / DPO', 'Status': 'Not started', 'ARTIFACTS': 'Statement to put in the handbook.', 'Dependencies': 'Privacy notice (1.3) must reference transfers', 'Notes': 'ICO has published templates. Must be completed and signed before transfers begin.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.6
Couch Heroes / UK Company Setup / Project Plan | 2.7 Record Retention Policy | {'Ref': '2.7', 'Priority': 'P2', 'Artifact Name': 'Record Retention Policy', 'Description': 'Comprehensive policy covering: payroll/wage records (6 years), PAYE records (3 years), SSP records (3 years), maternity records (3 years), working time records (duration of employment + 2 years), pension records (6 years), recruitment records (6 months post-decision minimum), dismissal records (minimum 6 months to match new tribunal time limit from October 2026), accident reports (3 years), right to work records (2 years after termination).', 'Legal Basis / Driver': 'Various: Taxes Management Act 1970; WTR 1998; RIDDOR 2013; UK GDPR; ERA 2025', 'Deadline / Trigger': 'Within first 3 months', 'Owner': 'HR Lead / Legal', 'Status': 'Not started', 'ARTIFACTS': '- Statement in the handbook \n- Trackers/ document where we summarize where each excel spreadhseet/Hibob is', 'Notes': 'Must be updated when tribunal time limits extend to 6 months in October 2026.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.7
Couch Heroes / UK Company Setup / Project Plan | 2.8 Sexual Harassment Risk Assessment | {'Ref': '2.8', 'Priority': 'P2', 'Artifact Name': 'Sexual Harassment Risk Assessment', 'Description': 'Documented risk assessment identifying risks of sexual harassment in the workplace (including from third parties such as clients, players, online interactions). Must assess risks and document preventative steps.', 'Legal Basis / Driver': "Worker Protection (Amendment of Equality Act 2010) Act 2023; ERA 2025 (October 2026: 'all reasonable steps')", 'Deadline / Trigger': 'Before October 2026 (best practice: immediately)', 'Owner': 'HR Lead', 'Status': 'Not started', 'ARTIFACTS': '- Assessment Document internal confidential ', 'Dependencies': 'Anti-harassment policy (2.1g)', 'Notes': 'Without this, employer cannot demonstrate compliance with the preventative duty. 25% compensation uplift risk.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.8
Couch Heroes / UK Company Setup / Project Plan | PRIORITY 3: REQUIRED FOR SPONSOR LICENCE APPLICATION | {'Priority': 'P3', 'Artifact Name': 'PRIORITY 3: REQUIRED FOR SPONSOR LICENCE APPLICATION'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref
Couch Heroes / UK Company Setup / Project Plan | 3.1 Sponsor Licence HR Compliance Pack | {'Ref': '3.1', 'Priority': 'P3', 'Artifact Name': 'Sponsor Licence HR Compliance Pack', 'Description': 'Documented systems for: tracking attendance, visa expiry monitoring, passport/visa copy storage, Home Office reporting procedures. Must satisfy Home Office audit requirements.', 'Legal Basis / Driver': 'Immigration Rules; Sponsor Guidance Part 1 (version 03/26)', 'Deadline / Trigger': 'Before sponsor licence application', 'Owner': 'HR Lead', 'Status': 'Not started', 'Dependencies': 'HRIS platform selection (4.8)', 'Notes': 'Weak HR systems are the biggest reason for licence rejection.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 3.1
Couch Heroes / UK Company Setup / Project Plan | 3.2 Sponsored Worker File Template | {'Ref': '3.2', 'Priority': 'P3', 'Artifact Name': 'Sponsored Worker File Template', 'Description': 'Standardised personnel file structure per sponsored worker: CoS details, visa copy, passport copy, right to work check record, attendance records, salary details, role description matching SOC code.', 'Legal Basis / Driver': 'Sponsor Guidance Part 2 (version 03/26)', 'Deadline / Trigger': 'Before first CoS assignment', 'Owner': 'HR Lead', 'Status': 'Not started', 'Dependencies': 'Sponsor licence granted'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 3.2
Couch Heroes / UK Company Setup / Project Plan | 3.3 Absence Reporting Procedure (Sponsored Workers) | {'Ref': '3.3', 'Priority': 'P3', 'Artifact Name': 'Absence Reporting Procedure (Sponsored Workers)', 'Description': 'Procedure for reporting unauthorised absences of 10+ consecutive working days to the Home Office via SMS.', 'Legal Basis / Driver': 'Sponsor Guidance; Immigration Rules', 'Deadline / Trigger': 'Before first CoS assignment', 'Owner': 'HR Lead', 'Status': 'Not started', 'Dependencies': 'Sponsor licence granted', 'Notes': 'Failure to report can result in licence downgrade or revocation.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 3.3
Couch Heroes / UK Company Setup / Project Plan | 3.4 Salary and Role Change Reporting Procedure | {'Ref': '3.4', 'Priority': 'P3', 'Artifact Name': 'Salary and Role Change Reporting Procedure', 'Description': "Procedure for notifying the Home Office of changes to sponsored workers' salary, role, job title, or working location.", 'Legal Basis / Driver': 'Sponsor Guidance; Immigration Rules', 'Deadline / Trigger': 'Before first CoS assignment', 'Owner': 'HR Lead', 'Status': 'Not started', 'Dependencies': 'Sponsor licence granted'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 3.4
Couch Heroes / UK Company Setup / Project Plan | PRIORITY 4: OPERATIONAL AND BEST-PRACTICE DOCUMENTS | {'Priority': 'P4', 'Artifact Name': 'PRIORITY 4: OPERATIONAL AND BEST-PRACTICE DOCUMENTS'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref
Couch Heroes / UK Company Setup / Project Plan | 4.1 Job Description Templates | {'Ref': '4.1', 'Priority': 'P4', 'Artifact Name': 'Job Description Templates', 'Description': 'Standardised templates for all roles. Must include SOC 2020 occupation codes (for sponsor licence use) and salary benchmarking.', 'Legal Basis / Driver': 'Best practice; supports sponsor licence compliance and equal pay', 'Deadline / Trigger': 'Before first recruitment round', 'Owner': 'HR Lead', 'Status': 'Not started'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.1
Couch Heroes / UK Company Setup / Project Plan | 4.2 Interview Scoring Matrix | {'Ref': '4.2', 'Priority': 'P4', 'Artifact Name': 'Interview Scoring Matrix', 'Description': 'Structured scoring template for fair, consistent candidate evaluation. Aligned with Equality Act 2010 requirements.', 'Legal Basis / Driver': 'Best practice; Equality Act 2010', 'Deadline / Trigger': 'Before first recruitment round', 'Owner': 'HR Lead', 'Status': 'Not started'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.2
Couch Heroes / UK Company Setup / Project Plan | 4.3 Onboarding Checklist | {'Ref': '4.3', 'Priority': 'P4', 'Artifact Name': 'Onboarding Checklist', 'Description': 'Comprehensive checklist: contract signing, right to work check, pension enrolment, IT setup, policy acknowledgements, training, DSE assessment, emergency contacts.', 'Legal Basis / Driver': 'Best practice; consolidates legal requirements', 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'HR Lead / Operations', 'Status': 'Not started', 'Dependencies': 'Contract (1.1), RTW procedure (1.4), pension letter (1.6), H&S policy (1.5)'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.3
Couch Heroes / UK Company Setup / Project Plan | 4.4 Probation Review Template | {'Ref': '4.4', 'Priority': 'P4', 'Artifact Name': 'Probation Review Template', 'Description': 'Structured template for probation reviews: objectives, performance criteria, development areas, confirmation/extension/termination decision.', 'Legal Basis / Driver': 'Best practice; supports UFD defence from January 2027', 'Deadline / Trigger': 'Before first probation review', 'Owner': 'HR Lead', 'Status': 'Not started', 'Dependencies': 'Probation policy (2.1m)', 'Notes': 'Critical for managing early-stage performance given 6-month UFD from January 2027.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.4
Couch Heroes / UK Company Setup / Project Plan | 4.5 Performance Review Template | {'Ref': '4.5', 'Priority': 'P4', 'Artifact Name': 'Performance Review Template', 'Description': 'Annual/bi-annual performance review template.', 'Legal Basis / Driver': 'Best practice', 'Deadline / Trigger': 'Within first year', 'Owner': 'HR Lead', 'Status': 'Not started'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.5
Couch Heroes / UK Company Setup / Project Plan | 4.6 Exit Interview Template | {'Ref': '4.6', 'Priority': 'P4', 'Artifact Name': 'Exit Interview Template', 'Description': 'Standardised questions for departing employees.', 'Legal Basis / Driver': 'Best practice', 'Deadline / Trigger': 'Before first leaver', 'Owner': 'HR Lead', 'Status': 'Not started'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.6
Couch Heroes / UK Company Setup / Project Plan | 4.7 Leaver Checklist | {'Ref': '4.7', 'Priority': 'P4', 'Artifact Name': 'Leaver Checklist', 'Description': 'Final pay, pension cessation, return of property, revocation of IT access, IP confirmation, Home Office notification (if sponsored worker), reference policy.', 'Legal Basis / Driver': 'Best practice; sponsor licence compliance', 'Deadline / Trigger': 'Before first leaver', 'Owner': 'HR / Operations', 'Status': 'Not started'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.7
Couch Heroes / UK Company Setup / Project Plan | 4.8 HRIS Platform Selection and Implementation | {'Ref': '4.8', 'Priority': 'P4', 'Artifact Name': 'HRIS Platform Selection and Implementation', 'Description': 'Requirements spec for system integrating: personnel records, payroll, pension, recruitment, absence management, document storage, visa/sponsor tracking.', 'Legal Basis / Driver': 'Best practice; supports multiple compliance requirements', 'Deadline / Trigger': 'Within first 3 months', 'Owner': 'Operations / HR', 'Status': 'Not started', 'Notes': 'Payroll provider and pension provider must be selected first.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.8
Couch Heroes / UK Company Setup / Project Plan | 4.9 Bribery Act Compliance Policy | {'Ref': '4.9', 'Priority': 'P4', 'Artifact Name': 'Bribery Act Compliance Policy', 'Description': 'Adequate procedures to prevent bribery under Bribery Act 2010 s.7. Cover gifts, hospitality, facilitation payments, third-party due diligence.', 'Legal Basis / Driver': 'Bribery Act 2010', 'Deadline / Trigger': 'Within first 6 months', 'Owner': 'Legal / Finance', 'Status': 'Not started', 'ARTIFACTS': 'To check with Dino/Aris/LILI', 'Notes': "Defence of 'adequate procedures' requires documented policy."} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.9
Couch Heroes / UK Company Setup / Project Plan | 4.10 Modern Slavery Statement (OPTIONAL) | {'Ref': '4.10', 'Priority': 'P4', 'Artifact Name': 'Modern Slavery Statement (OPTIONAL)', 'Description': 'Statement of steps taken to prevent modern slavery in business and supply chains. Required if turnover exceeds £36m; good practice regardless.', 'Legal Basis / Driver': 'Modern Slavery Act 2015', 'Deadline / Trigger': 'When turnover threshold met (or voluntarily earlier)', 'Owner': 'Legal / Operations', 'Status': 'Not started', 'ARTIFACTS': 'To check with Dino/Aris/LILI', 'Notes': 'Only legally required if turnover exceeds £36 million. Not applicable at current scale.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.10
Couch Heroes / UK Company Setup / Project Plan | 4.12 EMI Share Scheme Documentation (OPTIONAL) | {'Ref': '4.12', 'Priority': 'P4', 'Artifact Name': 'EMI Share Scheme Documentation (OPTIONAL)', 'Description': 'Enterprise Management Incentives scheme: option agreement, scheme rules, HMRC notification, board resolutions, company valuation. Highly tax-efficient for UK tech startups.', 'Legal Basis / Driver': 'Income Tax (Earnings and Pensions) Act 2003; HMRC EMI guidance', 'Deadline / Trigger': 'When ready to offer equity incentives', 'Owner': 'Legal / Finance', 'Status': 'Not started', 'ARTIFACTS': 'To check with Dino/Aris/LILI', 'Dependencies': 'Company valuation required', 'Notes': 'Hiring competitiveness tool, not a legal requirement. Build when ready to offer equity incentives.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.12
Couch Heroes / UK Company Setup / Project Plan | 4.13 DSE Assessment Template | {'Ref': '4.13', 'Priority': 'P4', 'Artifact Name': 'DSE Assessment Template', 'Description': 'Display Screen Equipment assessment form for each employee (office and remote). Must cover workstation setup, screen position, chair, lighting, breaks.', 'Legal Basis / Driver': 'Health and Safety (Display Screen Equipment) Regulations 1992', 'Deadline / Trigger': 'Before each employee starts working at a screen', 'Owner': 'Operations / HR', 'Status': 'Not started', 'Dependencies': 'H&S Policy (1.5)', 'Notes': 'Particularly important for a studio where all staff use screens.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.13
Couch Heroes / UK Company Setup / Project Plan | 4.14 Trade Union Rights Communication Template | {'Ref': '4.14', 'Priority': 'P4', 'Artifact Name': 'Trade Union Rights Communication Template', 'Description': 'Template all-staff communication informing workers of their right to join a trade union and the protections that apply to union membership and activities.', 'Legal Basis / Driver': 'ERA 2025 (from October 2026)', 'Deadline / Trigger': 'Before October 2026', 'Owner': 'HR Lead', 'Status': 'Not started', 'Notes': 'New mandatory duty from October 2026.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.14
Couch Heroes / UK Company Setup / Project Plan | PRIORITY 5: COMPANIES HOUSE AND CORPORATE GOVERNANCE | {'Priority': 'P5', 'Artifact Name': 'PRIORITY 5: COMPANIES HOUSE AND CORPORATE GOVERNANCE'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref
Couch Heroes / UK Company Setup / Project Plan | 5.1 Companies House Filing Calendar | {'Ref': '5.1', 'Priority': 'P5', 'Artifact Name': 'Companies House Filing Calendar', 'Description': 'Schedule for: confirmation statement (annual), annual accounts, PSC register maintenance, filing of any changes to directors/registered office/share capital.', 'Legal Basis / Driver': 'Companies Act 2006', 'Deadline / Trigger': 'Ongoing from incorporation', 'Owner': 'Finance / Legal', 'Status': 'Done', 'Notes': 'Late filing penalties apply.'} | Done | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.1
Couch Heroes / UK Company Setup / Project Plan | 5.2 PSC Register | {'Ref': '5.2', 'Priority': 'P5', 'Artifact Name': 'PSC Register', 'Description': 'Register of People with Significant Control. Must be kept up to date and filed with Companies House.', 'Legal Basis / Driver': 'Companies Act 2006 Part 21A', 'Deadline / Trigger': 'From incorporation', 'Owner': 'Legal / Company Secretary', 'Status': 'Done'} | Done | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.2
Couch Heroes / UK Company Setup / Project Plan | 5.3 Director Identity Verification | {'Ref': '5.3', 'Priority': 'P5', 'Artifact Name': 'Director Identity Verification', 'Description': 'Required under Economic Crime and Corporate Transparency Act 2023. Directors must verify their identity with Companies House.', 'Legal Basis / Driver': 'ECCTA 2023', 'Deadline / Trigger': 'When required by Companies House (phased implementation 2025/2026)', 'Owner': 'Directors / Legal', 'Status': 'Done', 'Notes': 'Check Companies House for current implementation status.'} | Done | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.3
Couch Heroes / UK Company Setup / Project Plan | 5.4 Corporation Tax Registration | {'Ref': '5.4', 'Priority': 'P5', 'Artifact Name': 'Corporation Tax Registration', 'Description': 'Register with HMRC for Corporation Tax within 3 months of starting business activity.', 'Legal Basis / Driver': 'Corporation Tax Act 2009', 'Deadline / Trigger': 'Within 3 months of starting activity', 'Owner': 'Finance', 'Status': 'Done'} | Done | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.4
Couch Heroes / UK Company Setup / Project Plan | 5.5 VAT Registration Assessment | {'Ref': '5.5', 'Priority': 'P5', 'Artifact Name': 'VAT Registration Assessment', 'Description': 'Assess whether turnover exceeds the £90,000 threshold (from April 2024). Register if required. Consider voluntary registration for input tax recovery.', 'Legal Basis / Driver': 'Value Added Tax Act 1994', 'Deadline / Trigger': 'Monitor ongoing; register when threshold reached', 'Owner': 'Finance', 'Status': 'Done', 'Notes': 'Gaming studio may benefit from voluntary registration for input VAT recovery on equipment/services.'} | Done | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.5
Couch Heroes / UK Company Setup / Project Plan | 5.6 R&D Tax Relief Assessment (OPTIONAL) | {'Ref': '5.6', 'Priority': 'P5', 'Artifact Name': 'R&D Tax Relief Assessment (OPTIONAL)', 'Description': 'Assess eligibility for R&D tax relief (SME scheme or RDEC). Game development typically qualifies. Can be worth 10-33% of qualifying R&D expenditure.', 'Legal Basis / Driver': 'Corporation Tax Act 2009 Part 13; Finance Act 2024', 'Deadline / Trigger': 'First Corporation Tax return', 'Owner': 'Finance / Tax Advisor', 'Status': 'in progress', 'ARTIFACTS': 'to check with Aris', 'Notes': 'Tax optimisation, not a compliance requirement. Pursue with tax advisor at first CT return.'} | In progress | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.6
Couch Heroes / UK Company Setup / Red Team Findings | Section 6; Artifacts list | {'2': '3', 'Sexual harassment risk assessment not listed as standalone artifact': 'Trade union communication obligation (October 2026) not mentioned', 'HIGH': 'MEDIUM', 'Artifacts list; H&S': 'Section 6; Artifacts list', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add to ERA 2025 timeline (Section 6.2) and create template artifact (4.14)', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Section 4.13; Artifacts list | {'2': '4', 'Sexual harassment risk assessment not listed as standalone artifact': "Record retention policy not listed as artifact. Payroll record retention stated as '3 years' but wage records require 6 years.", 'HIGH': 'HIGH', 'Artifacts list; H&S': 'Section 4.13; Artifacts list', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add Record Retention Policy as artifact (2.7). Correct 6-year obligation for payroll/wage records.', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Section 5; Handbook | {'2': '7', 'Sexual harassment risk assessment not listed as standalone artifact': 'Working Time Regulations 48-hour week / crunch culture risk not addressed', 'HIGH': 'MEDIUM', 'Artifacts list; H&S': 'Section 5; Handbook', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add Working Time and 48-Hour Week Policy to handbook (2.1o). Address crunch periods specifically.', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Section 5; RTW procedure | {'2': '8', 'Sexual harassment risk assessment not listed as standalone artifact': 'Right to work civil penalty amounts not stated (£45k first / £60k repeat)', 'HIGH': 'MEDIUM', 'Artifacts list; H&S': 'Section 5; RTW procedure', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add penalty figures to RTW Checks Procedure (1.4)', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Artifacts list; Contract | {'2': '9', 'Sexual harassment risk assessment not listed as standalone artifact': 'IP assignment: moral rights waiver (CDPA 1988 s.87) not specified', 'HIGH': 'HIGH', 'Artifacts list; H&S': 'Artifacts list; Contract', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add moral rights waiver requirement to IP Assignment Agreement spec (2.2) and contract (1.1)', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | H&S Policy; Artifacts list | {'2': '10', 'Sexual harassment risk assessment not listed as standalone artifact': 'DSE Assessment not listed as standalone artifact template', 'HIGH': 'MEDIUM', 'Artifacts list; H&S': 'H&S Policy; Artifacts list', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add DSE Assessment Template as artifact (4.13)', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Awareness only at current size | {'2': '11', 'Sexual harassment risk assessment not listed as standalone artifact': 'Equality (Race and Disability) Bill on legislative horizon for ethnicity/disability pay gap reporting (250+ employees). Not mentioned.', 'HIGH': 'LOW', 'Artifacts list; H&S': 'Awareness only at current size', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Note for future. Not actionable until enacted. Monitor progress.', 'YES': 'NO (future)'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Section 4.13 | {'2': '12', 'Sexual harassment risk assessment not listed as standalone artifact': '6-year record retention for payroll/wage records vs. 3 years stated in guide', 'HIGH': 'HIGH', 'Artifacts list; H&S': 'Section 4.13', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": "Correct Section 4.13 from 'at least 3 years' to 'at least 3 years (PAYE) / 6 years (payroll and wage records)'.", 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Corporate governance | {'2': '13', 'Sexual harassment risk assessment not listed as standalone artifact': 'R&D tax relief not mentioned. Gaming studios commonly qualify and the cash benefit is significant.', 'HIGH': 'MEDIUM', 'Artifacts list; H&S': 'Corporate governance', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add R&D Tax Relief Assessment as artifact (5.6)', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.7 | {'Date': 'Before first hire', 'Change / Deadline': "Employers' Liability Insurance obtained and displayed", 'Category': 'Insurance', 'Impact on CH': 'Mandatory. £2,500/day fine without.', 'Artifact(s) Affected': '1.7'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1 | {'Date': 'Before first hire', 'Change / Deadline': 'Employment contract template finalised (with all 11 corrections)', 'Category': 'Contract', 'Impact on CH': 'Mandatory Section 1 statement from day one.', 'Artifact(s) Affected': '1.1'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.4 | {'Date': 'Before first hire', 'Change / Deadline': 'Right to work check procedure in place', 'Category': 'Immigration', 'Impact on CH': 'Up to £60,000 per illegal worker (repeat breach).', 'Artifact(s) Affected': '1.4'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.3 | {'Date': 'Before first hire', 'Change / Deadline': 'Employee privacy notice drafted', 'Category': 'Data Protection', 'Impact on CH': 'UK GDPR requirement. ICO enforcement risk.', 'Artifact(s) Affected': '1.3'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Section 4 | {'Date': 'Before first hire', 'Change / Deadline': 'HMRC employer registration completed', 'Category': 'Payroll', 'Impact on CH': 'Must register before first payday.', 'Artifact(s) Affected': 'Section 4'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.6 | {'Date': 'Before first hire', 'Change / Deadline': 'Pension scheme selected and set up', 'Category': 'Pensions', 'Impact on CH': 'Auto-enrolment duties begin with first eligible employee.', 'Artifact(s) Affected': '1.6'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Contract, payroll | {'Date': '1 April 2026', 'Change / Deadline': 'NMW/NLW rates increase (£12.71 for 21+)', 'Category': 'Pay', 'Impact on CH': 'All salaries must meet new minimums.', 'Artifact(s) Affected': 'Contract, payroll'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1, 2.1c | {'Date': '6 April 2026', 'Change / Deadline': 'SSP: waiting period removed, LEL removed, 80%-of-AWE rate', 'Category': 'Statutory Pay', 'Impact on CH': 'Contracts and policies must be updated. Payroll systems must handle new calculation.', 'Artifact(s) Affected': '1.1, 2.1c'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1, 2.1e | {'Date': '6 April 2026', 'Change / Deadline': 'Paternity leave becomes day-one right', 'Category': 'Family Leave', 'Impact on CH': 'Remove qualifying period from policies.', 'Artifact(s) Affected': '1.1, 2.1e'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1, 2.1e | {'Date': '6 April 2026', 'Change / Deadline': 'Unpaid parental leave becomes day-one right', 'Category': 'Family Leave', 'Impact on CH': 'Remove qualifying period from policies.', 'Artifact(s) Affected': '1.1, 2.1e'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1e | {'Date': '6 April 2026', 'Change / Deadline': "Bereaved Partner's Paternity Leave introduced", 'Category': 'Family Leave', 'Impact on CH': 'New entitlement. Add to family leave policies.', 'Artifact(s) Affected': '2.1e'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1n | {'Date': '6 April 2026', 'Change / Deadline': 'Collective redundancy protective award doubled to 180 days', 'Category': 'Redundancy', 'Impact on CH': 'Increased financial risk of getting consultation wrong.', 'Artifact(s) Affected': '2.1n'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1i | {'Date': '6 April 2026', 'Change / Deadline': 'Sexual harassment becomes qualifying whistleblowing disclosure', 'Category': 'Whistleblowing', 'Impact on CH': 'Update whistleblowing policy.', 'Artifact(s) Affected': '2.1i'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Awareness | {'Date': '6 April 2026', 'Change / Deadline': 'Fair Work Agency established', 'Category': 'Enforcement', 'Impact on CH': 'New enforcement body for NMW, holiday pay, SSP.', 'Artifact(s) Affected': 'Awareness'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Awareness | {'Date': '6 April 2026', 'Change / Deadline': 'Trade union recognition simplified; electronic balloting', 'Category': 'Trade Unions', 'Impact on CH': 'Lower threshold for union recognition.', 'Artifact(s) Affected': 'Awareness'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Section 4.12 | {'Date': '6 April 2026', 'Change / Deadline': 'Voluntary payrolling of BIK available (mandatory from April 2027)', 'Category': 'Payroll / Tax', 'Impact on CH': 'Optional to test systems. Mandatory from April 2027.', 'Artifact(s) Affected': 'Section 4.12'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Section 3 | {'Date': '8 April 2026', 'Change / Deadline': 'Immigration fee increases (~6-7%)', 'Category': 'Immigration', 'Impact on CH': 'Higher costs for sponsor licence and visa applications.', 'Artifact(s) Affected': 'Section 3'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1, 2.4 | {'Date': 'October 2026', 'Change / Deadline': 'Fire and rehire becomes automatically unfair', 'Category': 'Contracts', 'Impact on CH': 'Review variation clauses in contract template.', 'Artifact(s) Affected': '1.1, 2.4'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1g, 2.8 | {'Date': 'October 2026', 'Change / Deadline': "Sexual harassment duty tightened to 'all reasonable steps'", 'Category': 'Harassment', 'Impact on CH': 'Risk assessment must be documented. All reasonable steps demonstrated.', 'Artifact(s) Affected': '2.1g, 2.8'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1g, 2.8 | {'Date': 'October 2026', 'Change / Deadline': 'Third-party harassment liability reintroduced', 'Category': 'Harassment', 'Impact on CH': 'Assess risks from clients, players, online interactions.', 'Artifact(s) Affected': '2.1g, 2.8'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.7 | {'Date': 'October 2026', 'Change / Deadline': 'Tribunal time limits extended to 6 months', 'Category': 'Litigation', 'Impact on CH': 'Longer window for claims. Update record retention.', 'Artifact(s) Affected': '2.7'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 4.14 | {'Date': 'October 2026', 'Change / Deadline': 'Employer must inform workers of right to join a union', 'Category': 'Trade Unions', 'Impact on CH': 'Mandatory all-staff communication.', 'Artifact(s) Affected': '4.14'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1, 2.1m, 4.4 | {'Date': 'January 2027', 'Change / Deadline': 'Unfair dismissal qualifying period drops to 6 months', 'Category': 'Dismissal', 'Impact on CH': 'Anyone hired from ~July 2026 gains UFD protection Jan 2027. Probation design critical.', 'Artifact(s) Affected': '1.1, 2.1m, 4.4'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1a, 2.1m | {'Date': 'January 2027', 'Change / Deadline': 'Unfair dismissal compensation cap removed', 'Category': 'Dismissal', 'Impact on CH': 'Unlimited compensatory awards. Getting dismissals wrong is now more expensive.', 'Artifact(s) Affected': '2.1a, 2.1m'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Section 4.12 | {'Date': 'April 2027', 'Change / Deadline': 'Mandatory payrolling of benefits in kind', 'Category': 'Payroll / Tax', 'Impact on CH': 'P11D no longer available for most benefits. Payroll systems must handle BIK reporting via RTI.', 'Artifact(s) Affected': 'Section 4.12'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Awareness | {'Date': '2027', 'Change / Deadline': 'Zero-hours contract guaranteed hours right', 'Category': 'Contracts', 'Impact on CH': 'If using ZHC workers, must offer guaranteed hours after reference period.', 'Artifact(s) Affected': 'Awareness'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Future | {'Date': '2027', 'Change / Deadline': 'Mandatory equality action plans (250+ employers)', 'Category': 'Reporting', 'Impact on CH': 'Only applies if CH reaches 250 employees.', 'Artifact(s) Affected': 'Future'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / HR / Hiring Pipeline - Art | Hire: TECHNICAL ANIMATOR (HIRED) | {'Role': 'TECHNICAL ANIMATOR (HIRED)', 'Annual Salary (000s)': 44160, 'Benchmark Salary': 60949.99999999999, 'Original Currency': 38400, 'Start Month': 2} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: CTO | {'Role': 'CTO', 'Annual Salary (000s)': 230000, 'Original Currency': 200000, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: EXECUTIVE PRODUCER | {'Role': 'EXECUTIVE PRODUCER', 'Annual Salary (000s)': 172500, 'Original Currency': 150000, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: LEVEL DESIGN LEAD | {'Role': 'LEVEL DESIGN LEAD', 'Annual Salary (000s)': 71300, 'Original Currency': 62000, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: SR CHARACTER MODELER | {'Role': 'SR CHARACTER MODELER', 'Annual Salary (000s)': 57499.99999999999, 'Original Currency': 50000, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: JIRA ADMIN CONTRACTOR | {'Role': 'JIRA ADMIN CONTRACTOR', 'Annual Salary (000s)': 57499.99999999999, 'Original Currency': 50000, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: HR OPERATIONS | {'Role': 'HR OPERATIONS', 'Annual Salary (000s)': 50024.99999999999, 'Original Currency': 43500, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: LEAD ANIMATOR (HIRED) | {'Role': 'LEAD ANIMATOR (HIRED)', 'Annual Salary (000s)': 114960, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: LEAD FULL STACK DEVELOPER | {'Role': 'LEAD FULL STACK DEVELOPER', 'Annual Salary (000s)': 92000, 'Original Currency': 80000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: LEAD GAMEPLAY DEVELOPER | {'Role': 'LEAD GAMEPLAY DEVELOPER', 'Annual Salary (000s)': 92000, 'Original Currency': 80000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: SNR NETWORK ENGINEER | {'Role': 'SNR NETWORK ENGINEER', 'Annual Salary (000s)': 70150, 'Original Currency': 61000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: HEAD OF FINANCE | {'Role': 'HEAD OF FINANCE', 'Annual Salary (000s)': 97749.99999999999, 'Original Currency': 85000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: GAME DESIGN LEAD | {'Role': 'GAME DESIGN LEAD', 'Annual Salary (000s)': 70150, 'Original Currency': 61000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: ART PRODUCER | {'Role': 'ART PRODUCER', 'Annual Salary (000s)': 54624.99999999999, 'Original Currency': 47500, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - QA | Hire: MID QA TESTER (CONTRACT) | {'Role': 'MID QA TESTER (CONTRACT)', 'Annual Salary (000s)': 33350, 'Original Currency': 29000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: UI/UX LEAD (NEW) | {'Role': 'UI/UX LEAD (NEW)', 'Start Month': 5} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: IT LEAD | {'Role': 'IT LEAD', 'Annual Salary (000s)': 69000, 'Original Currency': 60000, 'Start Month': 6} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: TOOLS ENGINEER | {'Role': 'TOOLS ENGINEER', 'Annual Salary (000s)': 67850, 'Original Currency': 59000, 'Start Month': 8} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: TECH PRODUCER | {'Role': 'TECH PRODUCER', 'Annual Salary (000s)': 53474.99999999999, 'Original Currency': 46500, 'Start Month': 9} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: SNR TECHNICAL ARTIST | {'Role': 'SNR TECHNICAL ARTIST', 'Annual Salary (000s)': 66700, 'Original Currency': 58000, 'Start Month': 9} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: SENIOR LEVEL DESIGNER | {'Role': 'SENIOR LEVEL DESIGNER', 'Annual Salary (000s)': 54624.99999999999, 'Original Currency': 47500, 'Start Month': 9} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: SNR ENVIRO ARTIST | {'Role': 'SNR ENVIRO ARTIST', 'Annual Salary (000s)': 80500, 'Original Currency': 70000, 'Start Month': 9} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - QA | Hire: MID QA TESTER | {'Role': 'MID QA TESTER', 'Annual Salary (000s)': 33350, 'Original Currency': 29000, 'Start Month': 9} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: SR VFX ARTIST | {'Role': 'SR VFX ARTIST', 'Annual Salary (000s)': 61524.99999999999, 'Original Currency': 53500, 'Start Month': 10} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: MID GENERAL DESIGNER | {'Role': 'MID GENERAL DESIGNER', 'Annual Salary (000s)': 40250, 'Original Currency': 35000, 'Start Month': 10} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Audio | Hire: AUDIO MENTOR (3-MONTH CONTRACT) | {'Role': 'AUDIO MENTOR (3-MONTH CONTRACT)', 'Annual Salary (000s)': 69000, 'Original Currency': 60000, 'Start Month': 10} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: ASSOC PRODUCER | {'Role': 'ASSOC PRODUCER', 'Annual Salary (000s)': 31050, 'Original Currency': 27000, 'Start Month': 11} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: SNR LIGHTING ARTIST | {'Role': 'SNR LIGHTING ARTIST', 'Annual Salary (000s)': 57499.99999999999, 'Original Currency': 50000, 'Start Month': 12} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: LEAD CONCEPT ARTIST | {'Role': 'LEAD CONCEPT ARTIST', 'Annual Salary (000s)': 71300, 'Original Currency': 62000, 'Start Month': 11} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Audio | Hire: AUDIO LEAD | {'Role': 'AUDIO LEAD', 'Annual Salary (000s)': 69000, 'Original Currency': 60000, 'Start Month': 10} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Headcount Totals | {'Role': 'Headcount Totals'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: COGS Headcount | {'Role': 'COGS Headcount', 'Cost Type': 'COGS'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: S&M Headcount | {'Role': 'S&M Headcount', 'Cost Type': 'S&M'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: R&D Headcount | {'Role': 'R&D Headcount', 'Cost Type': 'R&D'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: G&A Headcount | {'Role': 'G&A Headcount', 'Cost Type': 'G&A'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Total Headcount | {'Role': 'Total Headcount'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Salary Totals | {'Role': 'Salary Totals'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic Salary Subtotals | {'Role': 'Basic Salary Subtotals'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic COGS Salaries | {'Role': 'Basic COGS Salaries', 'Cost Type': 'COGS'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic S&M Salaries | {'Role': 'Basic S&M Salaries', 'Cost Type': 'S&M'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic R&D Salaries | {'Role': 'Basic R&D Salaries', 'Cost Type': 'R&D'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic G&A Salaries | {'Role': 'Basic G&A Salaries', 'Cost Type': 'G&A'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic Salary Subtotal | {'Role': 'Basic Salary Subtotal'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded Salary Subtotals | {'Role': 'Loaded Salary Subtotals'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: (Incl. benefits, employer taxes, + annual raises) | {'Role': '(Incl. benefits, employer taxes, + annual raises)'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded COGS Salaries | {'Role': 'Loaded COGS Salaries', 'Cost Type': 'COGS'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded S&M Salaries | {'Role': 'Loaded S&M Salaries', 'Cost Type': 'S&M'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded R&D Salaries | {'Role': 'Loaded R&D Salaries', 'Cost Type': 'R&D'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded G&A Salaries | {'Role': 'Loaded G&A Salaries', 'Cost Type': 'G&A'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Total Salaries (Loaded) | {'Role': 'Total Salaries (Loaded)'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Recruiting Fees | {'Role': 'Recruiting Fees'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded Salaries + Recruiting | {'Role': 'Loaded Salaries + Recruiting'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Salary Assumptions | {'Role': 'Salary Assumptions'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Payroll Load (Benefits & Taxes) | {'Role': 'Payroll Load (Benefits & Taxes)', 'Annual Salary (000s)': 0.15, 'Start Month': 0.15, 'Cost Type': 0.15} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Annual Salary Increase % | {'Role': 'Annual Salary Increase %', 'Start Month': 0.03, 'Cost Type': 0.03} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Recruiting Fee % | {'Role': 'Recruiting Fee %', 'Annual Salary (000s)': 0.2, 'Start Month': 0.2, 'Cost Type': 0.2} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: Recruiting Start Month | {'Role': 'Recruiting Start Month', 'Annual Salary (000s)': 13} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / Game / Game Features / Player Progression System | Player Progression System | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Level Up | [Player Progression] Level Up | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Level Up | [Player Progression] XP gain rules | DoD: XP from kills/quests/events; level curve; caps. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Level Up | [Player Progression] Level-up rewards | DoD: Unlock abilities; stats; notifications; skill points. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Level Up | [Player Progression] Character sheet UI | DoD: Stats breakdown; derived stats; explanations; tooltips. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Level Up | [Player Progression] Level-up configuration | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [CC & Management] Character Stats | [CC & Management] Character Stats | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Player Progression System / [CC & Management] Character Stats | [CC & Management] Character Stats Progression | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [CC & Management] Character Stats | Stats Affect Interactions |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System | Talent/Skill System | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System | [Talent] Skills Trees | DoD: Spend points; prerequisites; respec; loadouts. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System / [Talent] Skills Trees | [Talent] Skill system design | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System / [Talent] Skills Trees | [Talent] Skill system UI | Comments: In progress ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System / [Talent] Skills Trees | [Talent] Skill trees implementation | Comments: In progress ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Achievements/Trophies | [Player Progression] Achievements/Trophies | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Achievements/Trophies | [Player Progression] Achievement system | DoD: Define achievements; tracking; rewards; UI. ¦ Comments: Has basic design ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Achievements/Trophies | [Player Progression] Meta achievements | DoD: Complete sets; track progress; title/mount rewards. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Achievements/Trophies | [Player Progression] Collections | DoD: Mounts/pets/transmog collections; account binding; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Achievements/Trophies | [Player Progression] Achievements Rewards | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Factions | [Player Progression] Factions | Comments: In progress ¦ Owner: Game Design ¦ Integration: Game Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Factions | [Player Progression] Faction Content | Comments: In progress ¦ Owner: Game Design ¦ Integration: Game Design | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Factions / [Player Progression] Faction Content | [Player Progression] Faction NPCs | Comments: In progress ¦ Owner: Game Design ¦ Integration: Char Art | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Factions / [Player Progression] Faction Content | [Player Progression] Faction Quests | Comments: In progress ¦ Owner: Game Design ¦ Integration: Game Design | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Factions | [Player Progression] Reputation/factions | DoD: Rep gains; ranks; vendor unlocks; hostility; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial | [Player Progression] In-game Tutorial | Comments: Needs Review ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial | [Player Progression] Tutorial & onboarding | DoD: Guided intro; tooltips; training area; skip option. ¦ Comments: Needs Review ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial / [Player Progression] Tutorial & onboarding | [Player Progression] FTUE Configuration | Comments: Needs Review ¦ Owner: Game Design ¦ Integration: Game Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial / [Player Progression] Tutorial & onboarding | [Player Progression] FTUE UI | Comments: Needs Review ¦ Owner: Game Design ¦ Integration: UX/UI | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial | [Player Progression] Help codex | DoD: In-game encyclopedia; searchable; links from UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Game Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial | [Player Progression] Tooltips | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Fishing | [Professions] Fishing | Comments: In progress ¦ Owner: Game Design ¦ Integration: Game Design | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Gathering | [Professions] Gathering | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Gathering | [Gathering System] Harvest interactions | DoD: Mine/chop/skin; tool requirements; cast time; animations. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Gathering | [Gathering System] Rare proc drops | DoD: Chance for rare mats; luck modifiers; messaging. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Professions] Crafting System | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Recipe system | DoD: Define recipes; inputs/outputs; skill requirements; quality tiers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Item quality/rolls | DoD: Quality affects stats/value; deterministic or RNG; reroll item. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Crafting success/failure (if used) | DoD: Chance-based outcomes; protection; clear UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Crafting UI | DoD: Search/filter; queue; preview; shows missing mats; craft all. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Crafting stations | DoD: Location-based stations; permissions; buffs; tiered stations. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Profession progression | DoD: XP/levels; unlock recipes; specialization. ¦ Comments: In progress, very basic ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Specialization trees | DoD: Choose specialization; locked choices; benefits; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Player-made item economy hooks | DoD: Bind rules for crafted gear; durability; sinks. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [Core Combat] Magic | [Core Combat] Magic | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [Core Combat] Magic | [Core Combat] Spellcasting System | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [Core Combat] Magic | [Core Combat] Magic Weapons | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management | Character Creation & Management | Comments: In progress ¦ Owner: Game Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management | [CC & Management] Character Management | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management / [CC & Management] Character Management | [CC & Management] Multiple characters per account | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management / [CC & Management] Character Management | [CC & Management] Character rename | DoD: Rename with policy; uniqueness; rename cooldown; logs. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management / [CC & Management] Character Management | [CC & Management] Character transfer (server/shard) | DoD: Paid/free transfer; preserve inventory/mail; cooldown; restrictions. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Appearance customization | [CC & Management] Appearance customization | DoD: Face/body/hair/skin; colors; preview; randomize; save presets. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Appearance customization | [CC & Management] Race/species selection | DoD: Selectable races/species with starting stats/visuals; validates. ¦ Comments: In progress We have races/species in work from the art side, not integrated into the CC yet ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Appearance customization | [CC & Management] Appearance presets/randomizer | Comments: Not started ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Garment System | [CC & Management] Garment System | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Garment System | [CC & Management] Garment Presets | Comments: Not started ¦ Owner: Char Art ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Garment System | [CC & Management] Garment Customization | Comments: Not started ¦ Owner: Char Art ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] CC & Garment UI | [CC & Management] CC & Garment UI | Owner: UX/UI Lead ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] CC & Garment UI | [CC & Management] CC & Garment Menus | Comments: We have something we'll probably completely rework ¦ Owner: UX/UI Lead ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] CC & Garment UI | [CC & Management] CC & Garment UI Access | Comments: We have something we'll probably completely rework ¦ Owner: UX/UI Lead ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems | World Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / World Systems / Corruption | Corruption | Comments: In progress ¦ Owner: Game Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption | [Corruption] Corruption Implementation | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | [Corruption] Corruption VFX | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | [Corruption] Different types support | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | Corrupted environment |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | [Corruption] Corruption SFX | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | [Corruption] Different levels of corruption | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | [World & Zones] Black Hole R&D | Comments: On pause ¦ Owner: TechArt ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Corruption | [Corruption] Restoration | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Restoration | [Corruption] Restoration Abilities | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Restoration | [Corruption] Restoration Weapons/Tools | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Restoration | [Corruption] Restoration Quests | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System | Movement System | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Basic character movements | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Basic character movements | Move/turn/strafe/jump/double jump/move midair | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Sprinting/stamina | DoD: Sprint toggle/hold; stamina drain/regen; UI feedback. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Sprinting/stamina | Speedup Archways Animations | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Swimming/breath | DoD: Water volumes; swim movement; breath meter; drowning. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Swimming/breath | Water detection | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Swimming/breath | Swimming water effects |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Swimming/breath | Drowning/damage in the water |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Traversal Mechanics | DoD: Climbable surfaces; vault; fall damage interactions. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Gliding | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Grappling Hooks | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Ziplines | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Launch pads | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Cannons |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Climbing | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Mounts/vehicles | DoD: Mount summon/dismiss; speed tiers; restrictions; cosmetics. ¦ Comments: In progress We have a prototype, needs review and proper design ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Mounts/vehicles | Various vehicles types | Comments: Mounts R&D ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Teleport items/spells | DoD: Cast time; restrictions; fail handling. (hearthstone, but back to User Space) ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Navigation | Navigation | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] World map UI | DoD: Zoom/pan; filters; player marker; quest markers; fog-of-war. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Minimap / compass | DoD: Optional minimap/compass; markers; rotation modes. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Navigation | Height detection |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Fog-of-war reveal | DoD: Reveal on exploration; persists per character; reset rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Ports/boats/transport network | DoD: Schedules; boarding; travel scenes; reliability. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Fast travel / waypoints | DoD: Unlock points; cost/cooldowns; safe checks. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Collision & navmesh | DoD: Accurate collision; navmesh per zone; regeneration pipeline. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Fall damage | DoD: Thresholds; mitigations; death handling; UI feedback. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Instancing | Instancing | Owner: Level Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Instancing | [World & Zones] Instancing | Owner: Server Team ¦ Integration: Server Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Instancing | [World & Zones] Dungeon instances | DoD: Entry/exit; checkpoints; wipes; lockouts; scaling. ¦ Comments: Research ¦ Owner: Server Team ¦ Integration: Server Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Instancing | [World & Zones] Zone/region loading | DoD: Load zones seamlessly or via transitions; handles disconnects. ¦ Comments: Research ¦ Owner: Server Team ¦ Integration: Server Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Instancing | [World & Zones] Instance servers | DoD: Spin up instance servers; matchmaking integration; teardown. ¦ Comments: Not started ¦ Owner: Server Team ¦ Integration: Server Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Instancing | [World & Zones] Shard/realm architecture | DoD: Realms/shards; load balancing; transfers; queueing. ¦ Comments: Not started ¦ Owner: Server Team ¦ Integration: Server Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Day/night cycle | Day/night cycle | DoD: Time progression; lighting; NPC schedules; server time. ¦ Comments: In progress - techart exploration ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Dynamic weather | Dynamic weather | DoD: Weather states; transitions; gameplay hooks optional. ¦ Comments: In progress - techart exploration ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Dynamic weather | [World & Zones] Interactable objects | DoD: Use/pickup/inspect; permissions; cooldowns; sync. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Dynamic weather | Destructibles | Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Dynamic weather | [World & Zones] Resource nodes | DoD: Spawn tables; depletion; respawn; competition rules. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Game Design | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Dynamic weather | [World & Zones] Chests/lootables | DoD: Spawn rules; lock/key; personal vs shared; anti-farm. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Level Design | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic | Combat Epic |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework | [Core Combat] Combat Framework | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework | [Core Combat] Combat state machine | DoD: In/out of combat; regen rules; mount restrictions; logout timer. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework | [Core Combat] Combat encounter reset conditions | DoD: Reset on leash/timeouts; clears debuffs; prevents cheese. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework | [Core Combat] Death & respawn | DoD: Death screen; corpse; respawn points; penalties. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework / [Core Combat] Death & respawn | [Core Combat] Downed state | DoD: Optional downed/bleedout; ally revive; PvP rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework / [Core Combat] Death & respawn | [Core Combat] Revive / resurrection | DoD: Self/ally revive; consumables; restrictions; timers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework / [Core Combat] Death & respawn | [Core Combat] Combat resurrection limits | DoD: Limit battle res per encounter; tracking; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems | [Core Combat] Combat Effect Systems | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems | [Core Combat] Buff/debuff framework | DoD: Timed effects; stacking rules; dispels; persistence rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems | [Core Combat] Rested/bonus XP | DoD: Accumulation rules; display; consumption. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems | [Core Combat] Player Status Effects | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems / [Core Combat] Player Status Effects | Water/fire, water/electricity etc | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Targeting & Validation | [Core Combat] Combat Targeting & Validation | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Targeting & Validation | [Core Combat] Friendly targeting rules | DoD: Heal/assist selection; smart targeting; party priority. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Targeting & Validation | [Core Combat] Targeting system | DoD: Tab target/soft target/action target; line-of-sight; range. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Combat Hit & Damage Processing | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Hit resolution | DoD: Server-authoritative hit checks; latency compensation; anti-cheat. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Damage/healing pipeline | DoD: Mitigation; crit; resist; shields; overheal; logs. ¦ Comments: In progress as a part of combat system ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Diminishing returns framework | DoD: DR categories; reset timers; UI tooltip for immunity. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Cooldown reduction stacking rules | DoD: CDR caps; multiplicative/additive; UI shows effective CD. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Interactions | [Core Combat] Combat Interactions | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Interactions | [Core Combat] Combo/proc system | DoD: Conditional triggers; internal cooldowns; UI proc notification. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Interactions | [Core Combat] Dual Wielding | Comments: In progress ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat | [Core Combat] Ranged Combat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat | Ranged - Firearms |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat | Ranged - Two-handed weapons |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat | Ranged - Ammo |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] AI Combat Behavior | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] Threat/aggro system | DoD: NPC threat tables; taunts; drop rules; leashing. ¦ Comments: In progress as a part of combat system ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] NPC combat AI | DoD: Decision trees/BT; ability use; pathing; kiting protection. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] Elite/boss AI mechanics | DoD: Telegraphs; phases; enrage; target swaps. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] Mob spawning & population | DoD: Spawn points; density; scaling; despawn; roaming. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] Named/rare spawns | DoD: Timers; announcements; loot rules; anti-camp. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] Line-of-sight & cover checks | DoD: LOS uses server raycasts; prevents shooting through walls. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] PvP Combat System | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] Battleground arenas | DoD: Matchmaking; teams; scoring; maps; rewards. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] World PvP objectives | DoD: Capture points; resource control; buffs; timers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] MMR / ranking ladder | DoD: Rating calculation; seasons; decay; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] Anti-wintrading detection | DoD: Detect collusion; suspicious patterns; enforcement. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] Spectator mode | DoD: View matches; delay; privacy; anti-stream-snipe. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] PvP gear normalization | DoD: Stat templates; scaling; separate PvP stats. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] Queue types (solo/duo/premade) | DoD: Different queues; matchmaking constraints; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] PvP toxicity controls | DoD: Match chat restrictions; report in match; auto penalties. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry | [Core Combat] Combat UX & Telemetry | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry | [Core Combat] Floating combat text | DoD: Damage/heal numbers; filters; crit styling; toggle. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry | [Core Combat] Combat log | DoD: Detailed log; filtering; export; support for addons if allowed. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry | Post-match checks on cheats |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core | [Combat Abilities] Ability Core | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core | [Combat Abilities] Ability data definitions | DoD: Cooldown/cast time/cost/range; tags; scaling; ranks. ¦ Comments: In progress as a part of combat system ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core | [Combat Abilities] Global cooldown rules | DoD: Optional GCD; exceptions; UI indicators. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core | [Combat Abilities] Resource systems (mana/energy/rage) | DoD: Resources regenerate/spend; regen modifiers; UI bars. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core | [Combat Abilities] Ability queueing / buffering | DoD: Queue next ability within window; cancel rules; latency friendly. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics | [Combat Abilities] Casting Mechanics | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics | [Combat Abilities] Channeling abilities | DoD: Interrupt rules; movement rules; tick timing. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics | [Combat Abilities] Interrupts & crowd control | DoD: Stun/root/silence/fear; DR rules; break on damage. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics | [Combat Abilities] Cast bar & interrupt feedback | DoD: Cast bar shows progress; interrupt message; sound cue. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Area & Effect Handling | [Combat Abilities] Area & Effect Handling | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Area & Effect Handling | [Combat Abilities] Area-of-effect | DoD: Circles/cones/lines; ground-targeting; friendly fire rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Area & Effect Handling | [Combat Abilities] Status effects visuals | DoD: Buff/debuff icons; durations; stack count; tooltip. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / Combat UI & HUD | Combat UI & HUD |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space | User Space | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / User Space / [User Space] Server Support | [User Space] Server Support | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Server Support | [User Space] Player housing instance | DoD: Purchase/unlock; enter/exit; persistence; permissions. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Server Support | [User Space] Visitor permissions | DoD: Invite friends/guild/public listing; ban list. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Server Support | [User Space] Mobile front doors | DoD: Place your front door (portal) anywhere. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Decoration | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration / Buildings/parts of buildings placement/design | rooms, windows, etc |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Decoration placement | DoD: Place/move/rotate/scale; grid/snapping; collision; limits. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Crafting stations in housing | DoD: Place stations; buffs; restrictions; economy impacts. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Housing storage | DoD: Extra storage; access rules; anti-dupe. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Blueprints/presets | DoD: Save room layouts; share; import/export. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] World/activities distribution | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Lootable themed decorations per zone | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Minigames | Minigames | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / Minigames / [Minigames] Single-player minigames | [Minigames] Single-player minigames | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Minigames / [Minigames] Multiplayer minigames | [Minigames] Multiplayer minigames | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic | Items & Inventory System Epic |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System | Item Core System | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System | [Item System] |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] | [Item System] Initial Item Lists by type |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System | [Item System] Item Data & Rules | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules | [Item System] Item definition schema | DoD: Stats; rarity; binding; stacks; durability; unique limits. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules | [Item System] Item level / power scoring | DoD: Compute ilvl; gates content; display in UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules | [Item System] Item binding rules | DoD: Bind on pickup/equip/use; trade restrictions; UI labels. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules | [Item System] Durability & repair | DoD: Durability loss; repair cost; repair NPC; break rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System | [Item System] Item Lifecycle & Protection | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Lifecycle & Protection | [Item System] Destroy item confirmation | DoD: Prompt for rare/bound; type-to-confirm option. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Lifecycle & Protection | [Item System] Item locking / favorites | DoD: Lock items to prevent delete/sell; favorite marking. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Lifecycle & Protection | [Item System] Loot protection | DoD: Duplicate protection for certain rewards; soulbound rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Lifecycle & Protection | [Item System] Loot lock & corpse ownership | DoD: Prevent looting by others; timeouts; group access. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System | [Item System] Cosmetic & Appearance as Items | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Cosmetic & Appearance as Items | [Item System] Cosmetic transmog/glamour | DoD: Apply appearances independent of stats; unlock collection. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Cosmetic & Appearance as Items | [Item System] Dye system | DoD: Recolor gear/skins; channels; preview; saved palettes. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Cosmetic & Appearance as Items | [Item System] Appearance collection tracking | DoD: Unlock appearances on obtain; UI collection; duplicates handling. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Cosmetic & Appearance as Items | [CC & Management] Titles & vanity | DoD: Earned/equipped titles; vanity slots; preview. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic | [CC & Management] Emotes & gestures | DoD: Emote list; unlocks; chat integration; animations. ¦ Comments: We have something we need to review ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic | [World & Zones] In-game maps | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | Inventory System | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Player-Carried Storage | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Bag/backpack system | DoD: Slot-based; stacking; sorting; auto-loot; overflow handling. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Auto-sort rules | DoD: Sort by type/rarity/ilvl; custom categories. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Split stacks & stack merging | DoD: Split stack UI; partial moves; merge behavior. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Junk tagging & vendor sell-all | DoD: Mark junk; sell all junk; confirm; blacklist. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Long-Term Storage | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Bank/storage system | DoD: Extra storage; tabs; search; sorting; permissions. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Account-wide stash | DoD: Shared across characters; restrictions; currency. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Mail attachments as overflow | DoD: Send items/currency via mail; anti-abuse; return on expiry. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Search in bank/stash | DoD: Search by name/tag; filters; highlight. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Item models |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Item icons |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Buy/Sell (Vendor transfer) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Loot transfer/item drops |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Item editor and tools |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Inventory UI | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | Equipment System | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Equipment UI | Comments: In progress ¦ Owner: UX/UI Lead ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Equipment slots | DoD: Equip/unequip; validation; visual swaps; two-hand rules. ¦ Comments: In progress ¦ Owner: UX/UI Lead ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Item comparison tooltips | DoD: Compare to equipped; stat deltas; advanced tooltip toggle. ¦ Comments: Not started ¦ Owner: UX/UI Lead ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Enchanting/augment slots | DoD: Attach augments; remove rules; caps; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Upgrade system | DoD: Upgrade ilvl with materials/currency; caps; UI preview. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Item reforging/rerolling | DoD: Change secondary stats; costs; RNG; limits. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Set bonuses | DoD: Track sets; activate bonuses; UI indicators. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Gathering System] Gathering Equipment | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | Equipment] Armour and Kit list |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Gathering System] Tool durability/quality | DoD: Tools affect yield; durability; repairs; sinks. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets | Pets | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets | [Combat] Combat companions |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets | [CC & Management] Pet/companion system | DoD: Summon pets; cosmetic/combat; commands; persistence. ¦ Comments: In progress, needs review ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets | [CC & Management] Pets Customization | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets / [CC & Management] Pets Customization | [CC & Management] Pets Naming | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets / [CC & Management] Pets Customization | [CC & Management] Pets Clothes/Accessories | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Forge System | Forge System | Comments: In research ¦ Owner: Game Design, Char Art ¦ Integration: Char & Techart | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Forge System | [Equipment] Forge Crafting system |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Forge System | [Equipment] Forge Item list |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Forge System | [Equipment] Forge models and icons |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | Loot Distribution Systems | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | [Loot Distribution] Loot Drop Generation | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | [Loot Distribution] Loot tables & drops | DoD: Per-NPC loot tables; weighted rolls; guarantees; pity timers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | [Loot Distribution] Personal vs shared loot | DoD: Loot mode selection; group rules; loot lockouts. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | [Loot Distribution] Group Loot Distribution | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | [Loot Distribution] Need/greed roll | DoD: Group roll UI; timeouts; master looter optional. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy | In-game economy | Comments: In progress, very basic ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / In-game economy / Currency System | Currency System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Currency System | Sources and drains |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Currency System | Crafting Economy |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Currency System | Profession economies / boosts |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Currency System | Reward Economy / Loot Value |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Currency System | [Trading] Multiple currencies | DoD: Gold + premium + tokens; wallet UI; caps; sinks. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Currency System | [Trading] Currency flows | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Currency System | [Trading] Currency transactions ledger | DoD: Server-side ledger; audit trails; rollback support. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | Trading system | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Direct player trade | DoD: Trade window; confirm; prevents scams; distance; locks. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Trading system | COD (cash on delivery) | DoD: Optional COD; safe transaction; escrow; cancel rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Trade restrictions | DoD: Level/region limits; bind rules; rate limits; anti-RMT flags. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Search filters (ilvl, stats) | DoD: Advanced filters; saved searches; controller friendly. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Tax & fee tuning | DoD: Configurable fees; sinks; tooltips show net proceeds. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Buyback tab | DoD: Buyback recently sold items; timer; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] In-game store UI | DoD: Browse items; featured; categories; preview; wishlist. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] NPC vendors | DoD: Buy/sell; limited stock; reputation discounts; restock timers. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Repair & services vendors | DoD: Repair, respec, travel fees; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Token/vendor catch-up gear | DoD: Earn tokens; purchase gear; caps; season rollover rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Suspicious trade detection | DoD: Heuristics for laundering; alerts; thresholds; review queue. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Listing limits & anti-snipe | DoD: Limit listings; anti-bot; purchase confirmation for high value. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Auction house / market board | Auction house / market board | DoD: List/buy/sell; taxes; duration; search/sort; history. ¦ Comments: Paused ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Auction house / market board | [Trading Market] Auction building |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Feature | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / In-game economy / Auction house / market board | [Trading] Market price history | DoD: Display last N sales; volume; API rate limits. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Auction house / market board | [Trading] Market tools (retrieval, reversal) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Auction house / market board | [Trading] Offline sales delivery | DoD: Sales settle offline; proceeds via mail; cancel listing. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System | Quest System | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quests Backend/Tooling | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest definitions & scripting | DoD: Define quests with steps/conditions/rewards; scripting hooks. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest acceptance/turn-in | DoD: NPC/auto acceptance; checks prereqs; reward selection. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest log | DoD: List/track/abandon; sorting; categories; limits. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Objective tracking | DoD: Kill/collect/explore/talk/use; partial credit; reset rules. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Location-based objectives | DoD: Trigger volumes; map pin; completion criteria. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Branching choices | DoD: Mutually exclusive branches; flags; consequences; replay rules. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Dialogue system | DoD: Branching dialogue; localization; VO triggers; skip/cinematics. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Cinematics / cutscenes | DoD: In-engine/Video; skip vote in groups; replay. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest markers & breadcrumbs | DoD: HUD markers; world indicators; distance; toggle. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest exploit prevention | DoD: Detect repeat abuse; reset logic; server-side validation. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest item delivery | DoD: Auto-grant quest items; reclaim if deleted; prevent softlocks. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | Quest Editor |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Reward framework | DoD: XP/currency/items/rep; choice rewards; mail overflow. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests as Events | [Quest System] Quests as Events | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests as Events | [Quest System] Repeatable quests | DoD: Daily/weekly timers; reset schedule; caps. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests as Events | [Quest System] Bounties/contract board | DoD: Procedural quest offering; expiration; difficulty tiers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests as Events | [Quest System] World events as quests | DoD: Dynamic objectives with time limit; public participation; scaling. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Multiplayer | [Quest System] Quest Multiplayer | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Multiplayer | [Quest System] Shared/group quest progress | DoD: Rules for party contribution; credit radius; loot sharing. ¦ Comments: In progress, needs review with code and design ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Multiplayer | [Quest System] Quest sharing | DoD: Share quest to party; eligibility checks; cooldown. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | [Quest System] Quest Types | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | [Quest System] Escort AI missions | DoD: Escort NPC path; fail conditions; scaling. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | [Quest System] Timed objectives | DoD: Countdown timers; failure state; UI urgency cues. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Gather Resources |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Collect Unique Item |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Interact with Objects |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Kill Enemies |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Kill & Collect |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Investigate / Track |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Explore Area |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Cleanse Area of corruption |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Challenge / Minigame |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Puzzle |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Riddle / Dialogue |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Narrative | [Quest System] Quest Narrative | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Narrative | [Quest System] Lore codex unlocks | DoD: Unlock lore entries from exploration/quests; UI browse/search. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Narrative | Quest Localization |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Player Chat | Comments: In progress ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] General chat channels | DoD: Global/zone/local/party/guild/whisper; moderation hooks. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Backend Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Chat UI & history | DoD: Scrollable chat; tabs; filters; timestamps; copy/paste. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Backend Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Profanity filter | DoD: Locale-aware filter; user toggle; strict mode for minors. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Spam throttling | DoD: Rate limits; mutes; anti-flood; link limits. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Emojis/stickers | DoD: Emoji support; custom stickers; entitlement gating. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Backend Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Block/mute players | DoD: Block whispers/invites; mute chat; persistence. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Voice chat integration | DoD: In-game voice or platform; push-to-talk; mute; reporting. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Player reporting | DoD: Report chat/name/behavior; attach evidence; routing. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Slash commands framework | DoD: Commands (/w,/invite,/ignore,/roll); autocompletion; help. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Chat link items/achievements | DoD: Clickable links to items/quests; safe rendering; spoof prevention. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Chat Moderation | Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat / [Social Systems] Chat Moderation | [Social Systems] Chat moderation automation | DoD: Keyword triggers; auto-mute thresholds; escalation. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat / [Social Systems] Chat Moderation | [Social Systems] Language tags / auto-translate (optional) | DoD: Detect language; tag; optional translate; privacy notice. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat / [Social Systems] Chat Moderation | [Social Systems] Chat moderation tools | DoD: Mute, shadowmute, channel bans; audit trail. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat / [Social Systems] Chat Moderation | [Social Systems] Chat logs retrieval tooling | DoD: Secure access for moderators; retention rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | Tagging/credit rules | DoD: First hit vs contribution; shared credit; anti-ninja. ¦ Comments: ? ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Friends | [Social Systems] Friends | Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Friends | [Social Systems] Friends list | DoD: Add/remove; requests; blocks; notes; presence. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Friends | [Social Systems] Presence/status | DoD: Online/away/busy; current zone/activity; privacy settings. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Friends | [Social Systems] Friend notes/nicknames | DoD: Local nicknames/notes; private; sync optional. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Friends | [Social Systems] Friend suggestions | DoD: Suggest from mutual guild/party; privacy-respecting. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Multiplayer - Co-op | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Party formation | DoD: Invite/accept; role slots; leader; kick; loot rules. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Matchmaking / LFG | DoD: Queue for dungeons/raids; role selection; MMR optional. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Cross-server grouping | DoD: Invite across servers; instancing; chat routing. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Co-op Ready check | DoD: Ready prompt; timeout; kick logic for queues. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Dungeon finder deserter penalty | DoD: Leaving early adds debuff/timeout; exemptions for kicks. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Role enforcement & composition rules | DoD: Tank/healer/DPS validation; flexible rules; warnings. We may not require this. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Instance vote kick | DoD: Vote kick with reasons; cooldowns; abuse prevention. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Player inspect | DoD: Inspect gear/build; privacy toggle; compare. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Player profile card | DoD: Name, titles, achievements, guild; report/block buttons. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Matchmaking service | DoD: Queue management; skill/role matching; timeouts; penalties. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Multiplayer - Raids | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Raid group sizes | DoD: Flexible/fixed sizes; role requirements; scaling. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Raid lockouts & saves | DoD: Weekly lockouts; save states; partial clears; resets. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Dungeon/raid loot distribution | DoD: Personal loot; token systems; currencies; pity timers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Mythic+/keystone system (if used) | DoD: Scaling difficulty; affixes; timed runs; leaderboards. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Raid finder difficulty (if used) | DoD: Automated raid matching; simplified mechanics; lockouts. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Core Combat] Dueling | [Core Combat] Dueling | DoD: Invite/accept; safe boundaries; rewards none; anti-grief. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / Guild System | Guild System | Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Identity & Structure | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Identity & Structure | [Guilds] Guild creation | DoD: Name/tag validation; cost; leadership assignment. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Identity & Structure | [Guilds] Guild ranks & permissions | DoD: Configurable roles; bank permissions; invite/kick; logs. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Identity & Structure | [Guilds] Guild emblem/branding | DoD: Create emblem/colors; displays on banners/tabards. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Communication | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Communication | [Guilds] Guild chat & MOTD | DoD: Dedicated chat; announcements; pinned messages. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Membership Visibility | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Membership Visibility | [Guilds] Guild roster & profiles | DoD: Member list; last online; notes; applications. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Membership Visibility | [Guilds] Guild recruitment board | DoD: Post recruitment; applications; auto-accept rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Administrative Tools | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Administrative Tools | [Guilds] Guild moderation tools | DoD: Remove offenders; audit logs; reporting; name policy. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Administrative Tools | [Guilds] Guild activity logs | DoD: Logs for invites/kicks/bank transactions; export. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Administrative Tools | [Guilds] Guild ranks & permissions controls | DoD: Configurable roles; bank permissions; invite/kick; logs. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Meta Systems | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Meta Systems | [Guilds] Guild progression/perks | DoD: Guild XP; unlock bonuses; caps; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Meta Systems | [Guilds] Guild perks management UI | DoD: Select perks; show costs; cooldowns; permissions. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Shared Resources | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Shared Resources | [Guilds] Guild bank | DoD: Shared storage; tabs; permissions; logs; withdrawal limits. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Events | Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Events | [Guilds] Guild calendar/events | DoD: Schedule raids; RSVPs; reminders; timezones. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Events | [Guilds] Guild competitions | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Physical Presence | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Physical Presence | [Guilds] Guild housing/instances | DoD: Access rules; Bans/kicks; Customisation ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] In-game Mail | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] In-game mail send/receive | DoD: Send mail to players; delivery delay; inbox UI; unread indicators. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] Mail attachments | DoD: Attach items/currency; limits; return on expiry; anti-dupe checks. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] Mail enhancements |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] mail box models |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] Mail expiry & cleanup | DoD: Messages expire; warnings; auto-return attachments; logs. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Notifications | [Social Systems] Notifications | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Notifications | Social notifications |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Notifications | [Social Systems] Red dot system | DoD: Friend online, invite, guild events; settings. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces | Game Interfaces | Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] HUD & In-Game Interface | Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Health/resource bars | DoD: Player/target frames; buffs/debuffs; cast bars. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Action bars & hotkeys | DoD: Multiple bars; paging; keybind display; cooldown swipe. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Damage direction indicators | DoD: Indicators for incoming hits; toggle; accessibility. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Buff/debuff management UI | DoD: Separate sections; whitelist; enlarge important debuffs. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Quest tracker widget | DoD: Track active objectives; collapse; click-to-navigate. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Group UI frames | DoD: Party/raid frames; role icons; ready checks; sorting. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] UI Framework & UX Standards | Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Notifications/toasts | DoD: Loot, XP, achievements; rate limiting; accessibility. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Settings menu | DoD: Graphics/audio/controls/gameplay; apply/revert; presets. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] UI scaling | DoD: Scale UI; safe areas; font size; per-platform. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Search within menus | DoD: Search options/collections; highlight results. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Rich tooltips | DoD: Compare, show sources, show requirements; controller friendly. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Localization-ready UI | DoD: No hard-coded text; supports RTL; font fallback; truncation. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] UI mod/addon support (if allowed) | DoD: API sandbox; permissions; versioning; anti-cheat constraints. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Notification center | DoD: History of messages/rewards; clears; filters. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Keybind UI & conflict resolver | DoD: Shows conflicts; reset to default; import/export binds. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Error handling & messaging | DoD: Human-readable errors; retry prompts; offline handling. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls | Controls | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls | [Controls] General game settings | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Rebindable controls | DoD: Full keybinds; per-device profiles; conflict resolution. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Gamepad support | DoD: UI navigation; aim assist options; prompts; vibration. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Controller glyph switching | DoD: Auto-detect input; display correct glyph set. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Toggle/hold options | DoD: Hold-to-sprint, hold-to-aim, etc. configurable. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] 3rd/1st person camera | DoD: Orbit/zoom; collision; FOV; shoulder swap; sensitivity. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Loadout switching | DoD: Save/restore gear+skills+UI; restrictions in combat. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Loadout presets | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations | UX Optimizations | Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations | [UX] Modern UI/UX Expectations | Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Search everywhere | DoD: Search inventory, bank, auction, codex, settings. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Ping/marker system | DoD: World pings; group visible markers; expiration. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Photo mode | DoD: Free cam; filters; hide UI; poses. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Reconnect & session resume | DoD: Reconnect to same instance; preserve party; grace timers. ¦ Comments: In progress ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] AFK detection | DoD: AFK timers; kick from queues; status display. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Combat readability options | DoD: Reduce clutter; highlight enemy casts; outline allies. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Tooltip explanation mode | DoD: Explain stats/formulas; beginner mode; toggles. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Account-wide unlocks | DoD: Mounts/pets/cosmetics shared; rule exceptions. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Returner experience | DoD: Welcome back rewards; recap; suggestions. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Community safety onboarding | DoD: First-time prompts; reporting tutorial; safe comms. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility | Accessibility | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility | [Accessibility] Visual Accessibility | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Visual Accessibility | [Accessibility] Colorblind modes | DoD: Filter presets; test patterns; applies to UI and telegraphs. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Visual Accessibility | [Accessibility] Reduce motion | DoD: Disable camera shake/motion blur; simplified VFX option. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Visual Accessibility | [Accessibility] High-contrast UI mode | DoD: Contrast theme; outlines; readability. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Visual Accessibility | [Accessibility] Screen reader hints | DoD: UI labels for screen readers where supported; navigation cues. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility | [Accessibility] Audio & Communication Accessibility | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Audio & Communication Accessibility | [Accessibility] Subtitles & captions | DoD: Subtitles for dialogue; speaker labels; size options. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Audio & Communication Accessibility | [Accessibility] Audio cues alternatives | DoD: Visual indicators for important sounds; UI pings. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Audio & Communication Accessibility | [Accessibility] Speech-to-text (STT) for voice | DoD: Optional captions for voice; privacy notices. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Audio & Communication Accessibility | [Accessibility] Text-to-speech (TTS) for chat | DoD: Optional TTS; profanity safe; volume/rate controls. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility | [Accessibility] Input & Control Accessibility | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Input & Control Accessibility | [Accessibility] Remappable UI navigation | DoD: Full remap; controller/KB; one-handed presets optional. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Input & Control Accessibility | [Accessibility] Toggle rapid actions | DoD: Auto-repeat for held inputs; accessibility options. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Input & Control Accessibility | [Accessibility] Input smoothing options | DoD: Adjust dead zones, sensitivity curves; presets. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility | [Accessibility] Learning & Guidance Accessibility | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Learning & Guidance Accessibility | [Accessibility] Tutorial replay & hints | DoD: Replay tutorial; contextual hints; can disable. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion | Presentation & Immersion | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion | [Presentation] Visual Presentation | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Visual Presentation | [Presentation] Telegraph / readability VFX | DoD: Clear telegraphs; scalable; performance tiers. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Visual Presentation | [Presentation] Ability animation system | DoD: Sync animation to ability timings; cancel windows; blend. ¦ Comments: In progress ¦ Owner: UX/UI Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Visual Presentation | [Presentation] Emote animation library | DoD: Emote playback; loop; cancel; network sync. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion | [Presentation] Audio Presentation | Owner: Audio Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] 3D positional audio | DoD: Spatial audio; occlusion; distance falloff; mix. (PS5 support in future) ¦ Comments: Not started ¦ Owner: Audio Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] Adaptive music | DoD: Dynamic music by zone/combat; transitions. ¦ Comments: Not started ¦ Owner: Audio Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] UI SFX | Comments: In progress ¦ Owner: Audio Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] Other SFX | Comments: In progress ¦ Owner: Audio Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] Ambience Music | Comments: In progress ¦ Owner: Audio Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] User Space music | Comments: Not started ¦ Owner: Audio Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] Zone Music | Comments: In progress ¦ Owner: Audio Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion | [Presentation] VFX | Comments: In progress ¦ Owner: VFX Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] VFX | Multiple VFX examples | Comments: In progress ¦ Owner: VFX Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Platform | Platform | Comments: To be reviewed ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Account Creation/Deletion | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Account creation / registration | DoD: User can create account; validates email/username/password; handles errors; stores profile. ¦ Comments: Done or partially done. I don't think we're storing profiles atm ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Display name policy & rename | DoD: Unique rules; profanity filter; rename tokens; history. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Ban/suspension state handling | DoD: Account state blocks login appropriately; shows reason codes. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Character delete | DoD: Delete with confirmation; cooldown; prevents deleting last char if needed. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Name validation | DoD: Uniqueness rules; reserved words; profanity; unicode handling. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Account Authentification | DoD: Verification email sent; account gated until verified; resend + rate limits. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Email verification | Comments: Done or partially done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Login / authentication | DoD: Secure login; session tokens; remember-me; logout all devices. ¦ Comments: Partially done. We have basic login system ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Password reset | DoD: Self-serve reset via email/SMS; token expiry; audit event. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Multi-factor authentication (MFA) | DoD: Optional/required MFA; recovery codes; device trust. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Sign-in Methods | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with email | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with Google | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with Discord | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Account recovery workflow | DoD: Support-assisted recovery; ownership proof; lockout handling. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Account linking (Steam/PSN/Xbox/Epic/CH) | DoD: Link/unlink external identities; conflict resolution. ¦ Comments: Paused - decided not to link Steam. Needs additional discussion ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | License/ownership check | DoD: Validate game license and DLC/expansions entitlements. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | Cross-progression entitlements | DoD: Entitlements reconcile across platforms; prevents dupes. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Account Privacy Settings & Legal | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Consent management | DoD: Track and store consent for ToS/Privacy/marketing; versioned. ¦ Comments: Not started though we have a confirmed version of ToU ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Data export (GDPR/CCPA) | DoD: User can request export; generates bundle; authenticated delivery. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Account deletion / erasure | DoD: User can request deletion; cool-off; deletes/anonymizes per policy. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Age gating / parental controls | DoD: Age check; chat restrictions; spending limits; COPPA flows. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal / [Platform] Age gating / parental controls | Age gating restriction flow for the game | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal / [Platform] Age gating / parental controls | Age gating process for 3rd party game partners | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Platform] [Player Dashboard] Player Account Features | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Account Info Display | Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Nickname | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Default profile picture | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Account avatar upload | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Account level | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Log out | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Player Achievements | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] CH currency wallet | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Account Settings | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Support & FAQ | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Platform] [Player Dashboard] Game Dashboard | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Partner Games Display | Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | All games | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Unlocked games | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Quests required to unlock | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Steam key redemption | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Partner Assets (items) display | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Assets (items) display | Inventory section | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Available Quests Tracking | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Launcher Download | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Community Hub | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Featured Games section | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Friends | [Platform] [Player Dashboard] Friends | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Friends | [Player Dashboard] Friend List Management | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Friends | [Player Dashboard] Chat | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Platform] [Player Dashboard] Search & Notifications | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Player Dashboard] Search | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Player Dashboard] Web notifications/red dots | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Marketplace | [Platform] [Player Dashboard] Marketplace | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Marketplace | [Player Dashboard] P2P Marketplace | Comments: Not started, needs discussion ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Platform] [Developer Dashboard] Developer Account | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Account creation/sign in | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Company Info Form | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Manage account | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Platform] [Developer Dashboard] Game Dashboard | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Games management | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Keys management | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Analytics | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Settings & Support | [Platform] [Developer Dashboard] Settings & Support | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Settings & Support | [Developer Dashboard] contact support & FAQ | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] Quest Tracking | [Platform] Quest Tracking | DoD: Designers create quests; Translation/Localisation links; Dialogue/Narrative links. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Quest Tracking | [Platform] Quest Input System | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Quest Tracking | [Platform] Partner Quest Integration | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Platform Certification | [Platform] Platform Certification | DoD: PS/Xbox/Nintendo TRCs; submission checklists. Steam also needs this if we decide to go there ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Platform Certification | [Platform] Platform certification requirements | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Payment Processing | [Platform] Payment Processing | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Payment Processing | [Platform] Payment System Integration | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Online Services & Backend | DoD: Transactional emails; throttling; deliverability. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Session concurrency limits | DoD: Limit simultaneous logins; kick/notify; anti-abuse. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Email/SMS service integration | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Patch/manifest CDN | DoD: Serve patches; delta patching; region caches; integrity. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Account-wide settings service | DoD: Store settings server-side; sync; conflict resolution. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Notification/push service | DoD: Send push for events (optional); opt-in; region compliance. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Regional routing / shard selection | DoD: User chooses region/shard; can transfer with rules. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Launcher & Distribution | DoD: Self-update; verify files; repair; disk space checks. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Patch/update system | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Launcher integration | DoD: News, login, patch; SSO; crash log upload. ¦ Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Crossplay toggle | DoD: User setting; matchmaking rules; compliance. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Cross-save | DoD: Upload/download save; conflict resolution; offline behavior. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Screenshot/video capture hooks | DoD: Share on platform; privacy; parental settings. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Offline mode behavior | DoD: If offline allowed: restrict features; queue actions; messaging. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Hardware detection & defaults | DoD: Detect hardware; set recommended settings; benchmark optional. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Input method auto-switching | DoD: Instant switch between KB/mouse and controller; UI updates. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Multiple language packs | DoD: Download language packs; switch without reinstall; UI. ¦ Comments: We have something on localization, needs check ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Cross-session settings sync | DoD: Settings stored server-side; per-platform overrides. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Desktop App (?) | [Platform] Desktop App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Mobile App (?) | [Platform] Mobile App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Systems / Player Progression | Player Progression |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Player Progression] Level Up | [Player Progression] Level Up |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Player Progression] Achievements | [Player Progression] Achievements |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Player Progression] Factions | [Player Progression] Factions |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Player Progression] In-game Tutorial | [Player Progression] In-game Tutorial |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Professions] Fishing | [Professions] Fishing |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Professions] Gathering | [Professions] Gathering |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Professions] Crafting System | [Professions] Crafting System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / Character Creation & Management | Character Creation & Management |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [CC & Management] Garment System | [CC & Management] Garment System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [CC & Management] Character Stats | [CC & Management] Character Stats |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [CC & Management] Pets | [CC & Management] Pets |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [CC & Management] CC & Garment UI | [CC & Management] CC & Garment UI |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / Talent/Skill System | Talent/Skill System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems | World Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Corruption | Corruption |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Movement System | Movement System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Navigation | Navigation |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Instancing | Instancing |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Day/night cycle | Day/night cycle |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Dynamic weather | Dynamic weather |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / World Resources | World Resources |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat | Combat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat Framework | [Core Combat] Combat Framework |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat Effect Systems | [Core Combat] Combat Effect Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat Targeting & Validation | [Core Combat] Combat Targeting & Validation |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Combat Hit & Damage Processing |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat Interactions | [Core Combat] Combat Interactions |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Ranged Combat | [Core Combat] Ranged Combat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Magic | [Core Combat] Magic |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] AI Combat Behavior | [Core Combat] AI Combat Behavior |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] PvP Combat System | [Core Combat] PvP Combat System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat UX & Telemetry | [Core Combat] Combat UX & Telemetry |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Combat Abilities] Ability Core | [Combat Abilities] Ability Core |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Combat Abilities] Casting Mechanics | [Combat Abilities] Casting Mechanics |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Combat Abilities] Area & Effect Handling | [Combat Abilities] Area & Effect Handling |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / User Space & Minigames | User Space & Minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / User Space & Minigames / [User Space] Server Support | [User Space] Server Support |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / User Space & Minigames / [User Space] Decoration | [User Space] Decoration |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / User Space & Minigames / [Minigames] Single-player minigames | [Minigames] Single-player minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / User Space & Minigames / [Minigames] Multiplayer minigames | [Minigames] Multiplayer minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory | Items & Inventory |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory / Item Core System | Item Core System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory / Inventory System | Inventory System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory / Equipment System | Equipment System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory / Loot Distribution Systems | Loot Distribution Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory / Trading System | Trading System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System | Quest System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quests Backend/Tooling |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quests as Events | [Quest System] Quests as Events |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quest Multiplayer | [Quest System] Quest Multiplayer |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quest Rewards | [Quest System] Quest Rewards |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quest Types | [Quest System] Quest Types |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quest Narrative | [Quest System] Quest Narrative |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems | Multiplayer Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Chat | Chat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Friends | Friends |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Party (co-op) | Party (co-op) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Multiplayer - raids | Multiplayer - raids |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / In-game mail | In-game mail |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Notifications | Notifications |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Guild System | Guild System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI | UX/UI |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] HUD & In-Game Interface |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] UI Framework & UX Standards |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / Controls | Controls |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / UX Optimizations | UX Optimizations |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / Accessibility | Accessibility |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / Presentation & Immersion | Presentation & Immersion |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform | Platform |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Account Creation/Deletion | [Platform] Account Creation/Deletion |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Account Authentification | [Platform] Account Authentification |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Account Privacy Settings & Legal |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Player Dashboard] Player Account Features | [Platform] [Player Dashboard] Player Account Features |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Player Dashboard] Game Dashboard | [Platform] [Player Dashboard] Game Dashboard |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Player Dashboard] Friends | [Platform] [Player Dashboard] Friends |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Player Dashboard] Search & Notifications | [Platform] [Player Dashboard] Search & Notifications |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Player Dashboard] Marketplace | [Platform] [Player Dashboard] Marketplace |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Developer Dashboard] Developer Account | [Platform] [Developer Dashboard] Developer Account |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Platform] [Developer Dashboard] Game Dashboard |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Developer Dashboard] Settings & Support | [Platform] [Developer Dashboard] Settings & Support |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Quest Tracking | [Platform] Quest Tracking |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Platform Certification | [Platform] Platform Certification |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Payment Processing | [Platform] Payment Processing |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Online Services & Backend | [Platform] Online Services & Backend |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Launcher & Distribution | [Platform] Launcher & Distribution |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Desktop App (?) | [Platform] Desktop App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Mobile App (?) | [Platform] Mobile App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend | Online Services & Backend | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] Multiplayer Backend & Simulation Systems | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] Authoritative server simulation | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] Character persistence | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] Inventory persistence | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] Economy ledger | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] API versioning & schema migrations | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System | Player Support System | Comments: Not started ¦ Owner: CS Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Player Support Tools | Comments: Not started ¦ Owner: CS Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] In-game help & ticketing | Comments: Not started ¦ Owner: CS Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Knowledge base integration | Comments: Not started ¦ Owner: CS Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Report triage queue | Comments: Not started ¦ Owner: CS Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Harassment protection | Comments: Not started ¦ Owner: CS Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Appeals workflow | Comments: Not started ¦ Owner: CS Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Name change enforcement | Comments: Not started ¦ Owner: CS Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System | Analytics System | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Gameplay & Product Analytics | [Analytics] Gameplay & Product Analytics | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Gameplay & Product Analytics | [Analytics] Core gameplay events | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Gameplay & Product Analytics | [Analytics] Onboarding funnel | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Gameplay & Product Analytics | [Analytics] Economy monitoring | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Gameplay & Product Analytics | [Analytics] Feature flag analytics | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Performance & Technical Telemetry | [Analytics] Performance & Technical Telemetry | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Performance & Technical Telemetry | [Analytics] Client/server perf telemetry | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Performance & Technical Telemetry | [Analytics] Telemetry privacy controls | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Business Intelligence | [Analytics] Business Intelligence | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Business Intelligence | [Analytics] KPI dashboards | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Business Intelligence | [Analytics] Data warehouse & governance | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Alerts System | [Analytics] Alerts System | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Alerts System | [Analytics] Anomaly detection alerts | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability | Performance & Reliability | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Client Performance | [Performance] Client Performance | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Client Performance | [Performance] Graphics scalability | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Client Performance | [Performance] Memory management | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Client Performance | [Performance] Asset optimization pipeline | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Client Performance | [Performance] Tick rate & scaling | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Network & Simulation Performance | [Performance] Network & Simulation Performance | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Network & Simulation Performance | [Performance] Latency management | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Network & Simulation Performance | [Performance] Network latency indicators | Owner: Backend Team | Not started | High |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Infrastructure Scalability | [Performance] Infrastructure Scalability | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Infrastructure Scalability | [Performance] Data consistency checks | Comments: Not started ¦ Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Infrastructure Scalability | [Performance] Autoscaling policies | Comments: Not started ¦ Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Reliability & Resilience | [Performance] Reliability & Resilience | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Reliability & Resilience | [Performance] Backups & disaster recovery | Comments: Not started ¦ Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Reliability & Resilience | [Performance] Incident response runbooks | Comments: Not started ¦ Owner: Backend Team | Not started | High |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Reliability & Resilience | [Performance] Chaos testing / fault injection | Comments: Not started ¦ Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Service Quality Monitoring | [Performance] Service Quality Monitoring | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Service Quality Monitoring | [Performance] SLOs/SLAs tracking | Comments: Not started ¦ Owner: Backend Team | Not started | High |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering | QA & Release Engineering | Comments: Not started ¦ Owner: QA Lead/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] QA Tools | Comments: Not started ¦ Owner: QA Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Automated tests | Comments: Not started ¦ Owner: QA Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Feature flags | Comments: Not started ¦ Owner: QA Lead | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Test environments | Comments: Not started ¦ Owner: QA Lead | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Crash reporting | Comments: Not started ¦ Owner: QA Lead | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Replay/record system for bugs | Comments: Not started ¦ Owner: QA Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Load testing | Comments: Not started ¦ Owner: QA Lead | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] Release Tools | [QA & Release Engineering] Release Tools | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] Release Tools | [QA & Release Engineering] CI/CD pipeline | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] Release Tools | [QA & Release Engineering] Automated rollback | Comments: Not started ¦ Owner: Backend Team | Not started | High |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] Release Tools | [QA & Release Engineering] Client signing / anti-tamper build steps | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] Release Tools | [QA & Release Engineering] Stable daily builds provision | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools | DevOps & Tools | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Content Creation Tools | [DevOps] Content Creation Tools | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Content Creation Tools | [DevOps] Content editor tooling | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Content Creation Tools | [DevOps] World building tools | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Globalization Pipeline | [DevOps] Globalization Pipeline | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Globalization Pipeline | [DevOps] Localization pipeline | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Globalization Pipeline | [DevOps] Localization QA tooling | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | High |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Data & Observability Platform | [DevOps] Data & Observability Platform | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Data & Observability Platform | [DevOps] Log aggregation | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Data & Observability Platform | [DevOps] Telemetry schema registry | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Build & Content Validation | [DevOps] Build & Content Validation | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Build & Content Validation | [DevOps] Asset validation pipeline | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Platform Features / Platform, Security & Compliance | Platform, Security & Compliance |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform | Platform | Comments: To be reviewed ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Account Creation/Deletion | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Account creation / registration | DoD: User can create account; validates email/username/password; handles errors; stores profile. ¦ Comments: Done or partially done. I don't think we're storing profiles atm ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Display name policy & rename | DoD: Unique rules; profanity filter; rename tokens; history. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Ban/suspension state handling | DoD: Account state blocks login appropriately; shows reason codes. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Character delete | DoD: Delete with confirmation; cooldown; prevents deleting last char if needed. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Name validation | DoD: Uniqueness rules; reserved words; profanity; unicode handling. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Account Authentification | DoD: Verification email sent; account gated until verified; resend + rate limits. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Email verification | Comments: Done or partially done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Login / authentication | DoD: Secure login; session tokens; remember-me; logout all devices. ¦ Comments: Partially done. We have basic login system ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Password reset | DoD: Self-serve reset via email/SMS; token expiry; audit event. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Multi-factor authentication (MFA) | DoD: Optional/required MFA; recovery codes; device trust. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Sign-in Methods | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with email | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with Google | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with Discord | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Account recovery workflow | DoD: Support-assisted recovery; ownership proof; lockout handling. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Account linking (Steam/PSN/Xbox/Epic/CH) | DoD: Link/unlink external identities; conflict resolution. ¦ Comments: Paused - decided not to link Steam. Needs additional discussion ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | License/ownership check | DoD: Validate game license and DLC/expansions entitlements. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | Cross-progression entitlements | DoD: Entitlements reconcile across platforms; prevents dupes. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Account Privacy Settings & Legal | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Consent management | DoD: Track and store consent for ToS/Privacy/marketing; versioned. ¦ Comments: Not started though we have a confirmed version of ToU ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Data export (GDPR/CCPA) | DoD: User can request export; generates bundle; authenticated delivery. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Account deletion / erasure | DoD: User can request deletion; cool-off; deletes/anonymizes per policy. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Age gating / parental controls | DoD: Age check; chat restrictions; spending limits; COPPA flows. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal / [Platform] Age gating / parental controls | Age gating restriction flow for the game | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal / [Platform] Age gating / parental controls | Age gating process for 3rd party game partners | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Platform] [Player Dashboard] Player Account Features | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Account Info Display | Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Nickname | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Default profile picture | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Account avatar upload | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Account level | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Log out | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Player Achievements | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] CH currency wallet | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Account Settings | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Support & FAQ | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Platform] [Player Dashboard] Game Dashboard | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Partner Games Display | Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | All games | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Unlocked games | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Quests required to unlock | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Steam key redemption | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Partner Assets (items) display | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Assets (items) display | Inventory section | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Available Quests Tracking | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Launcher Download | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Community Hub | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Featured Games section | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Friends | [Platform] [Player Dashboard] Friends | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Friends | [Player Dashboard] Friend List Management | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Friends | [Player Dashboard] Chat | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Platform] [Player Dashboard] Search & Notifications | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Player Dashboard] Search | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Player Dashboard] Web notifications/red dots | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Marketplace | [Platform] [Player Dashboard] Marketplace | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Marketplace | [Player Dashboard] P2P Marketplace | Comments: Not started, needs discussion ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Platform] [Developer Dashboard] Developer Account | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Account creation/sign in | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Company Info Form | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Manage account | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Platform] [Developer Dashboard] Game Dashboard | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Games management | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Keys management | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Analytics | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Settings & Support | [Platform] [Developer Dashboard] Settings & Support | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Settings & Support | [Developer Dashboard] contact support & FAQ | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Quest Tracking | [Platform] Quest Tracking | DoD: Designers create quests; Translation/Localisation links; Dialogue/Narrative links. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Quest Tracking | [Platform] Quest Input System | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Quest Tracking | [Platform] Partner Quest Integration | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Platform Certification | [Platform] Platform Certification | DoD: PS/Xbox/Nintendo TRCs; submission checklists. Steam also needs this if we decide to go there ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Platform Certification | [Platform] Platform certification requirements | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Payment Processing | [Platform] Payment Processing | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Payment Processing | [Platform] Payment System Integration | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Online Services & Backend | DoD: Transactional emails; throttling; deliverability. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Session concurrency limits | DoD: Limit simultaneous logins; kick/notify; anti-abuse. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Email/SMS service integration | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Patch/manifest CDN | DoD: Serve patches; delta patching; region caches; integrity. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Account-wide settings service | DoD: Store settings server-side; sync; conflict resolution. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Notification/push service | DoD: Send push for events (optional); opt-in; region compliance. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Regional routing / shard selection | DoD: User chooses region/shard; can transfer with rules. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Launcher & Distribution | DoD: Self-update; verify files; repair; disk space checks. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Patch/update system | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Launcher integration | DoD: News, login, patch; SSO; crash log upload. ¦ Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Crossplay toggle | DoD: User setting; matchmaking rules; compliance. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Cross-save | DoD: Upload/download save; conflict resolution; offline behavior. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Screenshot/video capture hooks | DoD: Share on platform; privacy; parental settings. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Offline mode behavior | DoD: If offline allowed: restrict features; queue actions; messaging. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Hardware detection & defaults | DoD: Detect hardware; set recommended settings; benchmark optional. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Input method auto-switching | DoD: Instant switch between KB/mouse and controller; UI updates. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Multiple language packs | DoD: Download language packs; switch without reinstall; UI. ¦ Comments: We have something on localization, needs check ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Cross-session settings sync | DoD: Settings stored server-side; per-platform overrides. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Desktop App (?) | [Platform] Desktop App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Mobile App (?) | [Platform] Mobile App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance | Compliance | Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Mandatory Legal Docs & Procedures | Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Terms of Service / EULA acceptance | DoD: Must accept before play; versioning; re-consent. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Privacy policy presentation | DoD: Accessible in-game; locale; versioning. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Cookie/consent for web components | DoD: If web views used; region rules. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Loot box odds disclosure | DoD: Display odds where required; logs; audits. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Data retention & deletion policy | DoD: Retention windows; deletion jobs; backup handling. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Vulnerability disclosure process | DoD: Security contact; bug bounty policy optional. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Accessibility compliance checks | DoD: WCAG-inspired checks for UI; console TRCs; docs. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Regional content ratings | DoD: ESRB/PEGI/USK; descriptors; age gating. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention | Security & Abuse Prevention | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Access & Capacity Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Login queue | DoD: Queue when servers full; ETA; priority lanes; disconnect handling. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Rate limiting & abuse protection | DoD: Global per-IP/account rate limits; WAF; alerts. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] DDoS mitigation | DoD: Traffic scrubbing; rate limits; failover. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Anti-Cheat | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Anti-tamper / integrity checks | DoD: Detect modified clients; secure bootstraps; update enforcement. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Server-side cheat detection | DoD: Speed/teleport; impossible actions; DPS anomalies; flags. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Client-side anti-cheat (if used) | DoD: Kernel/user mode as appropriate; privacy notices; compatibility. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Communication & Data Security | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Encryption in transit | DoD: TLS everywhere; cert pinning optional; secure websockets. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Secrets management | DoD: No secrets in client; rotate keys; least privilege. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] Economic & Transaction Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] Fraud & chargeback handling | DoD: Detect suspicious purchases; velocity limits; chargeback workflows. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] RMT mitigation | DoD: Trade caps; detection; escrow; enforcement tooling. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Behavioral Abuse Prevention | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Botting mitigation | DoD: Behavioral detection; captcha in web; in-game friction; bans. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Account takeover prevention | DoD: Suspicious login alerts; device fingerprint; step-up auth. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Compliance & Data Protection | [Security] Compliance & Data Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Compliance & Data Protection | [Security] Secure logging & PII redaction | DoD: Redact PII in logs; access controls; audit. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Live Service Features / LiveOps System | LiveOps System | Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Events | [LiveOps] Events | Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Events | [LiveOps] Public events | DoD: Spawn triggers; participation; scaling; reward distribution. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Events | [LiveOps] Seasonal events | DoD: Timed live events; themed rewards; calendar scheduling. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Events | [LiveOps] World bosses | DoD: Schedule/spawn rules; scaling; loot lockouts. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Seasonal Content | [LiveOps] Seasonal Content | Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Seasonal Content | [LiveOps] Season rollover & rewards | DoD: End-of-season rewards; rank snapshots; soft reset rules. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Seasonal Content | [LiveOps] Battle pass / season track | DoD: XP track; rewards; premium track; catch-up; UI. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Seasonal Content | [Core Combat] PvP rewards & seasons | DoD: Seasonal resets; cosmetics; currency; anti-farm caps. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Retention Activities | [LiveOps] Retention Activities | Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Retention Activities | [LiveOps] Daily/weekly objectives | DoD: Rotating objectives; reset schedule; streaks; UI. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Retention Activities | [LiveOps] Catch-up mechanics | DoD: Boosts for new/returning; cap removals; UI messaging. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Service Reliability | [LiveOps] Live Service Reliability | Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Service Reliability | [LiveOps] Telemetry pipeline | DoD: Event ingestion; batching; privacy flags; schema versioning. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Service Reliability | [LiveOps] Service health checks | DoD: Heartbeat endpoints; SLO monitoring; dashboards. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Service Reliability | [LiveOps] Graceful degradation | DoD: If service down (e.g., store), game continues with limits. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Live Patching | Comments: Not started ¦ Owner: EP/LiveOps Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Server-side config / tuning | DoD: Hotfix values without client patch; versioned configs. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Content patch pipeline | DoD: Build, validate, publish; rollback; partial rollout. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Event scheduling system | DoD: Schedule start/end; timezones; rewards; announcements. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] In-game announcements | DoD: MOTD, banners, popups; targeting; localization. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Experiment framework | DoD: Randomized assignment; metrics; kill switches; ethics. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Server restart/maintenance mode | DoD: Broadcast; safe shutdown; kick timers; maintenance page. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Localization hotfixes | DoD: Update text assets without full patch; cache busting. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Rollback / restore tooling | DoD: Restore character/inventory from backups; transaction replays. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] LiveOps Tools | Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] GM tools (admin) | DoD: Teleport, spawn, inspect, ban/mute; audit logs. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] Ban waves & enforcement tooling | DoD: Bulk actions; evidence; appeal flags; audit. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] Server-side reward grants | DoD: Grant compensation; targeted cohorts; logs; idempotent. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] Customer messaging for incidents | DoD: Status page integration; in-game banner; localized. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] Feature configuration UI | DoD: Non-dev tuning UI; permissioned; change tracking. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] Content permissions & approvals | DoD: Role-based approvals; publish gates; audit logs. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization | Player Monetization | Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Purchases | Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Purchase flow | DoD: Platform payment; confirmations; error handling; receipts. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Entitlement delivery | DoD: Grant items/currency; idempotent; offline delivery; logs. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Refund processing | DoD: Revoke entitlements where possible; currency sinks; logs. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Spending limits & transparency | DoD: Purchase confirmations; spending history; parental controls. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Premium currency wallet | DoD: Purchase/spend; display rates; region pricing. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Regional pricing & taxes | DoD: Price tiers by region; VAT; platform rules. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Gift purchases | DoD: Gift items to others; fraud controls; delivery confirmation. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Monetization Types | [Monetization] Monetization Types | Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Monetization Types | [Monetization] Subscription benefits | DoD: Monthly perks; renewal; grace period; messaging. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Monetization Types | [Monetization] Loot boxes / random packs (if used) | DoD: Odds disclosure; pity timers; regulation compliance; age gate. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Monetization Types | [Monetization] Cosmetic preview & dressing room | DoD: Try on skins; preview in different lighting; share. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Partner Monetization | [Monetization] Partner Monetization | Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Partner Monetization | [Monetization] Subsidized Game Purchase | Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Partner Monetization | [Monetization] Partner Assets Purchase | Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance | Compliance | Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Mandatory Legal Docs & Procedures | Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Terms of Service / EULA acceptance | DoD: Must accept before play; versioning; re-consent. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Privacy policy presentation | DoD: Accessible in-game; locale; versioning. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Cookie/consent for web components | DoD: If web views used; region rules. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Loot box odds disclosure | DoD: Display odds where required; logs; audits. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Data retention & deletion policy | DoD: Retention windows; deletion jobs; backup handling. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Vulnerability disclosure process | DoD: Security contact; bug bounty policy optional. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Accessibility compliance checks | DoD: WCAG-inspired checks for UI; console TRCs; docs. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Regional content ratings | DoD: ESRB/PEGI/USK; descriptors; age gating. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention | Security & Abuse Prevention | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Access & Capacity Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Login queue | DoD: Queue when servers full; ETA; priority lanes; disconnect handling. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Rate limiting & abuse protection | DoD: Global per-IP/account rate limits; WAF; alerts. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] DDoS mitigation | DoD: Traffic scrubbing; rate limits; failover. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Anti-Cheat | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Anti-tamper / integrity checks | DoD: Detect modified clients; secure bootstraps; update enforcement. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Server-side cheat detection | DoD: Speed/teleport; impossible actions; DPS anomalies; flags. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Client-side anti-cheat (if used) | DoD: Kernel/user mode as appropriate; privacy notices; compatibility. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Communication & Data Security | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Encryption in transit | DoD: TLS everywhere; cert pinning optional; secure websockets. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Secrets management | DoD: No secrets in client; rotate keys; least privilege. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] Economic & Transaction Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] Fraud & chargeback handling | DoD: Detect suspicious purchases; velocity limits; chargeback workflows. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] RMT mitigation | DoD: Trade caps; detection; escrow; enforcement tooling. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Behavioral Abuse Prevention | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Botting mitigation | DoD: Behavioral detection; captcha in web; in-game friction; bans. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Account takeover prevention | DoD: Suspicious login alerts; device fingerprint; step-up auth. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Compliance & Data Protection | [Security] Compliance & Data Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Compliance & Data Protection | [Security] Secure logging & PII redaction | DoD: Redact PII in logs; access controls; audit. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Content / Player Progression | Player Progression |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Player Progression] Level Up | [Player Progression] Level Up |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Player Progression] Level Up | Level Up UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Level Up | Level Up VFX | Art team: VFX ¦ Comments: Scale Healing VFX ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Achievements | [Player Progression] Achievements |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Player Progression] Achievements | Achievements UI VFX | Art team: VFX ¦ Comments: Extra SS effects ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Achievements | Achievements UI | Art team: UX/UI, Concept ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Achievements | Achievements Icons | Art team: Concept ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Factions | [Player Progression] Factions |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Player Progression] Factions | Factions NPCs | Art team: Concept, Character, Animations, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Factions | Faction player clothing | Art team: Character, Concept, TechArt, Animations ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Factions | Faction dialogue UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Factions | Factions Banners/Symbols | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] In-game Tutorial | [Player Progression] In-game Tutorial |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Player Progression] In-game Tutorial | Tutorial Archive UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] In-game Tutorial | Tutorial VFX (arrows) | Art team: VFX ¦ Comments: Mesh + VFX ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] In-game Tutorial | Tutorial UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | [Professions] Fishing |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing Animations | Art team: Animations, TechArt ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing Rod Model | Art team: Concept, Character ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fish Models + inventory | Art team: Concept, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing Sign Model/icon | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Aquarium Model | Art team: Concept, Environment, VFX, TechArt ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing shop | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing profession UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing VFX | Art team: VFX ¦ Comments: Water material + additional VFX ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gear | [Professions] Gear |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Professions] Gear | Torches, magic crystals, shields and other non-weapon equippables | Art team: Character, TechArt, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | [Professions] Gathering |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering Animations | Art team: Animations, TechArt, VFX ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering VFX | Art team: VFX ¦ Comments: Design and concept art ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering profession UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering inventory items | Art team: Concept ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering Tools Models | Art team: Concept, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | [Professions] Crafting System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting Animations | Art team: Animations, VFX, TechArt ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting VFX | Art team: VFX ¦ Comments: Props proposition and concepts ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting profession UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting material icons | Art team: Concept ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting Tools Models | Art team: Concept, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Character Creation & Management |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Base face models | Art team: Animations, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Base body models with variations (gender/proportions) | Art team: Animations, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Appearance Elements Sets (eyes, hair, lips etc) | Art team: Animations, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Character UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Races variations | Art team: Animations, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | [CC & Management] Garment System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Basic garment options | Art team: Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Garment variations for slots | Art team: Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Skins | Art team: Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Armour models | Art team: Concept, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Armour UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Armour slot crystals | Art team: Concept, UX/UI, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Partner skins | Art team: Concept, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Character Stats | [CC & Management] Character Stats |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [CC & Management] Character Stats | Skill Tree UI icons | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Character Stats | Stats UI Icons + interface | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | [CC & Management] Pets |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Pets Models | Art team: Concept, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Pets Animations | Art team: Concept, Animations, TechArt ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Partner Pets | Art team: Concept, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Pets VFX (trails, summon) | Art team: Concept, Animations, TechArt, VFX ¦ Comments: Characters guidelines ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Pets Appearance Customization Options | Art team: Concept, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Pets Garments (collars?) | Art team: Concept, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] CC & Garment UI | [CC & Management] CC & Garment UI |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] CC & Garment UI | CC & Garment Menus | Art team: Concept, UX/UI ¦ Comments: Devs implement. ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] CC & Garment UI | CC & Garment Presets | Art team: UX/UI, Character, TechArt ¦ Comments: Tech validation from Char. Art ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] CC & Garment UI | CC & Garment Randomizer | Art team: UX/UI, Character, TechArt ¦ Comments: Ready to use, DA, Maya scipt ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Talent/Skill System | Talent/Skill System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / Talent/Skill System | Talent System UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Talent/Skill System | Talent Upgrade VFX | Art team: VFX ¦ Comments: Design and Chars (?) ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems | World Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / World Ambience | World Ambience |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / World Ambience | Ambient area VFX | Art team: VFX ¦ Comments: Env. ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corruption |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Corruption | Different corruption types support (TechArt) | Art team: Concept, TechArt, VFX ¦ Comments: Mechanics and material visual, VFX support following phase ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corruption cleansing mechanic | Art team: TechArt, VFX ¦ Comments: Ready, optimization pass 1 done ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corruption weapon | Art team: Concept, Character, TechArt, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corrupted enemies | Art team: Concept, Animations, Character, TechArt, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corrupted models | Art team: Concept, Character, TechArt, VFX, Environment ¦ Comments: Volumetric and Painting ready to be implemented, Designers and Env to feedback possible upgrade in shape and underneath material ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corruption VFX | Art team: Concept, Character, TechArt, VFX ¦ Comments: Co-dev with TA ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Movement System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Movement System | Basic Movement Animations (walk, run, sprint, jump) | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Gliding Animations | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Gliding Device | Art team: Concept, Character, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Grappling Animations | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Grappling Hook Device | Art team: Concept, Character, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Ziplines Animations | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Grappling Hook Points | Art team: Concept, VFX ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Zipline device | Art team: Concept, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Vaulting animations | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Avoidance anims | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Launch anims | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Dodge anims | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Slide, Crouch, land, strafe | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Movement VFX | Art team: VFX ¦ Comments: Trails + further concepts ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Ziplines Model | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Navigation |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Navigation | World Map UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Minimap UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Compass UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Portals | Art team: Concept, VFX, Environment ¦ Comments: Upgrade present with no performance heavy solutions ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Archway race VFX | Art team: VFX, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Teleportation scrolls/VFX | Art team: Concept, TechArt, VFX ¦ Comments: Scalable ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Day/night cycle | Day/night cycle |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Day/night cycle | Dynamic day/night cycle | Art team: Environment, TechArt, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Day/night cycle | Town lighting (when dark) | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Day/night cycle | Dynamic lighting | Art team: Environment, TechArt, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Dynamic weather | Dynamic weather |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Dynamic weather | Cloud system | Art team: Environment, TechArt ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Dynamic weather | Define the weather cycle and needs | Art team: Environment, TechArt, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / World Resources | World Resources |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / World Resources | Collectible resources models | Art team: Concept, Environment, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / World Resources | Destructible resources models & VFX | Art team: Concept, Environment, VFX, TechArt ¦ Comments: Explored and planned, start with barrels/crate, expand ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / World Resources | Chests | Art team: Concept, Animations, Environment, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Initial Island Layout | Initial Island Layout | DoD: Digit Isle 1 9 initial zones, 2D map design, layout | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Initial Island Layout | Initial Island Blockouts | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Initial Island Layout | Initial island Biomes Definition | Art team: Concept, Environment ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Initial Island Layout | Initial Island Zones Scope and Sizes | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Points of interest (POIs) | DoD: POI definitions; discovery; map markers; tooltips. | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | List all zones and POIs | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Dungeons layout and set dressing | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Concept all zones and POIs | Art team: Concept, Environment ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | POIs set dressing | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Props | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Vegetation | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Environmental VFX | Art team: Environment, VFX ¦ Comments: List ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Curved Horizon R&D | Curved Horizon R&D |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Curved Horizon R&D | Decide if we proceed with this idea and how | Art team: Concept, Environment, TechArt ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat | Combat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Framework | Combat Animations (player, AI) | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: Title not in classification file - sheet-based default
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Framework | Combat VFX | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: Title not in classification file - sheet-based default
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Framework | Weapons models (melee, ranged, magic) | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: Title not in classification file - sheet-based default
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Framework | Combat UI | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: Title not in classification file - sheet-based default
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Framework | Combat abilities animations & VFX | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: Title not in classification file - sheet-based default
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Effect Systems | [Core Combat] Combat Effect Systems | Art team: Animations, VFX ¦ Comments: Melee w/o weapons ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Combat Hit & Damage Processing | Art team: Animations, VFX, UX/UI ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Interactions | [Core Combat] Combat Interactions | Art team: Animations, VFX, UX/UI ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Core Combat] Ranged Combat | [Core Combat] Ranged Combat | Art team: Animations, VFX, UX/UI ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Core Combat] Magic | [Core Combat] Magic | Art team: Animations, VFX, UX/UI ¦ Comments: Weapon + Magic spells, coord with Combat Dept ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Core Combat] AI Combat Behavior | [Core Combat] AI Combat Behavior | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Combat Abilities] Skill Tree Abilities for melee weapons | [Combat Abilities] Skill Tree Abilities for melee weapons | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Combat Abilities] Casting Mechanics | [Combat Abilities] Casting Mechanics | Art team: Animations, VFX, UX/UI ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Combat Abilities] Area & Effect Handling | [Combat Abilities] Area & Effect Handling | Art team: Animations, VFX, UX/UI ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / PVP Combat | PVP Combat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Combat / PVP Combat | PvP Arena Layout & Set dressing | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Enemies] Content | [Enemies] Content |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Combat / [Enemies] Content | Enemies types 3D support (define with design) | Art team: Concept, Animations, Character, TechArt, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Enemies] Content | Enemies animations & VFX per type | Art team: Concept, Animations, VFX ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Enemies] Content | Bosses & mini-bosses artwork (models, animations, VFX) | Art team: Concept, Animations, Character, TechArt, VFX ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Enemies] Content | Corrupted enemies | Art team: Concept, Animations, Character, TechArt, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames | User Space & Minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | [User Space] Decoration |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | Decoration/furniture sets | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | External balcony doors | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | Partner US objects/trophies | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | Furniture inventory items | Art team: Concept, Environment | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | Object addition VFX | Art team: VFX ¦ Comments: Scalable VFX ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | Interactive US objects & animations/UI | Art team: Concept, UX/UI, Animations ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [Minigames] Single-player minigames | [Minigames] Single-player minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / User Space & Minigames / [Minigames] Single-player minigames | Lockpicking UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [Minigames] Single-player minigames | Arcade cabinet for US (review existing one) | Art team: Environment, Concept ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [Minigames] Multiplayer minigames | [Minigames] Multiplayer minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / User Space & Minigames / [Minigames] Multiplayer minigames | Speed archway in Downtime (review models, VFX) | Art team: Concept, Environment, VFX ¦ Comments: Design, art concept and upgrade (logic ready) ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory | Items & Inventory |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Items & Inventory / Item Core System | Item Core System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Items & Inventory / Item Core System | Static items (collectibles, crafting items, quest items) | Art team: Concept, Environment, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Item Core System | Interactive items (destructibles) | Art team: Concept, Environment, TechArt, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Inventory System | Inventory System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Items & Inventory / Inventory System | Inventory UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Equipment System | Equipment System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Equipment System | Equipment UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Trading System | Trading System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Items & Inventory / Trading System | Trading UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Trading System | Vendors NPC | Art team: Concept, Animations, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Trading System | Vendors Animations | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Trading System | Shops Buildings & Props | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Quest System | Quest System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Quest System / [Quest System] Quest UI | [Quest System] Quest UI | Art team: Concept, UX/UI | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Quest System / Quest Tracking (exclamation marks, search area etc) | Quest Tracking (exclamation marks, search area etc) | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Quest System / Quest Special NPCs models | Quest Special NPCs models | Art team: Concept, Animations, Character, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems | Multiplayer Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Multiplayer Systems / Chat | Chat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Multiplayer Systems / Chat | Chat UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Friends | Friends |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Multiplayer Systems / Friends | Friends UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Party (co-op) | Party (co-op) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Party (co-op) | Party UI/HUD | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / In-game mail | In-game mail |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Multiplayer Systems / In-game mail | Mail UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Notifications | Notifications |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Multiplayer Systems / Notifications | Notifications UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Guild System | Guild System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Guild System | Guild UI & chat | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Guild System | Guild TV + portals | Art team: Concept, Environment, VFX ¦ Comments: Engineering support and co-dev ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Guild System | Guild Space (guild house/user space) | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI | UX/UI |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / [Game Interfaces] HUD & In-Game Interface | The current UX/UI throughout the game needs review and decision if we change the style/flows or proceed with the current ones. Each feature needs supporting interfaces | Art team: Concept, VFX, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] UI Framework & UX Standards | Art team: UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / Controls | Controls | Art team: UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / UX Optimizations | UX Optimizations | Art team: UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Polish | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / Accessibility | Accessibility | Art team: UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Polish | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / Presentation & Immersion | Presentation & Immersion | Art team: UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Level Up | V3: Player gains XP from gameplay actions and levels up. Basic UI/VFX. Placeholder progression balance ¦ V4: Final XP rules, sources, pacing, rewards, and polished level-up presentation ¦ V5: Bug fixing, performance improvements, and XP/reward balancing based on playtests or release data | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Character Stats | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define stats definition and behavior, do competitor research, prepare documentation ¦ V2: Implement and playtest basic stats ¦ V3: Implement all desired stats and test out their connection with other sustems in the game (economy, quests, combat etc) ¦ V4: Final stats functionality and balance across all game systems ¦ V5: Bug fixing, performance improvements, and stats balancing based on playtests or release data ¦ V6: Adding new stats, UI improvements, tooltips, presets ¦ V7: Character stats/progression system improvements and tool for designers to work with it | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Talent/Skill System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define talents and skill paths, talent points getting and distribution rules, prepare documentation ¦ V2: One skill path implemented with placeholder UI; skill points gain and distribution implemented ¦ V3: All desired skill paths designed ad implementation started. Connection and affect to other gameplay system in testing ¦ V4: All desired skill paths are implemented in the release quality. Final UI and efefcts. Balance and progression configration is final ¦ V5: Bug fixing, performance improvements, and skills balancing based on playtests or release data ¦ V6: Adding new skill paths, expanding the existing ones, further balance tweaks, UI/UX improvements ¦ V7: Overall skill system optimization and improvement in line with live operations strategy | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Achievements/Trophies | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Achievements conditions and rewards defined, scope confirmed, documentation prepared ¦ V2: Basic achievements functionality implemented (player performs an action - player gets the achievement) ¦ V3: Basic UI and effects implemented. UX tested, if achievements are more than cosmetic - connection with other systems tested ¦ V4: All achievements are implemented with final UX/UI and effects. Achievement getting conditions are tested. Achievements are tracked at the Platform layer ¦ V5: Bug fixes and optimizations ¦ V6: New achievements addition, achievements rarity, special achievements based on community demand ¦ V7: Achievement system improvements across game, web and mobile layers | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Factions | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Factions defined, each faction reputation gain rules are set and designed, faction content and narrative ready, documentation finished ¦ V2: Faction content in production (areas, NPCs, symbols etc), demo faction quests implemented, basic reputation gain fuctionality implemented ¦ V3: All factions visible in game with placeholder dialogues in quests and WIP content. Factions reputation progression finalized and tested with other game systems ¦ V4: Faction content final and implemented, factions reputation progression balanced, all needed quest lines are implemented and tested ¦ V5: Bug fixes and improvements, dialogue/localization tweaks, UX/UI improvements ¦ V6: More faction quests, reputation tree expanded/deepened, new factions, seasonal faction content ¦ V7: Reputation system expanded or applied to other systems in the game that use similar mechanics | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | In-game Tutorial | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: First-time player experience goals defined, player journey described. All systems, features and content participating in FTUE defined, the scope confirmed. Tutotial pop-ups/tooltips described/written. Tutorial segment is included as a part of documentation template for all new features ¦ V2: Basic in-game tutorial implemented, feedback for player implemented, temporary tutorial area exists ¦ V3: Tutorial rules finalized and implemented, design/level design close to final. Player progression through tutorial is in testing. Help codex basic fuctionality is implemented, tooltips across the game implemented ¦ V4: Full tutorial segment is implemented in final quality with all needed UX/UI passes. Tutorial progression is balanced, XP gain set. The player gets access to all needed systems, the progression is not blocked. Each feature the player encounters for the first time has hints. Help codex is full and easily accessible ¦ V5: Bugfix and tweaks bacsed on playtesting/user feedback ¦ V6: Each new feature contains tutorial/tooltips and added to the help codex ¦ V7: Tutorial systems are used during the LiveOps stage for events | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Fishing | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Professions progression and skill points rules are defined and escribed in the documentation. The list of launch-needed professions is finalized ¦ V2: Basic fishing implemented with placeholder UI, animations and content ¦ V3: Fishing skill path implemented with progression rules in place; fishing is a part of trading and in-game economy. Basic aquarium functionality added. Placeholder UI ¦ V4: Fishing minigame and skill progression are final. UX/UI, content and effects are final. Enough content to support the progression. Economy/trading balance finalized. Fishing spot placement in the world is done. US aquarium finalized. Tutorial in place ¦ V5: Bug fixes and improvements based on user feedback ¦ V6: More content (fish types, fishing areas, rods, customization) based on global content expansions and events ¦ V7: Multiplayer fishing systems and competitions | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Gathering | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V2: Gathering mechanic implemented, items are added to the inventory; placeholder animations and effects ¦ V3: Gathering skill path implemented with progression rules in place with placeholder UI. Gathering is a part of trading and in-game economy ¦ V4: Gathering profession is fully implemented with final animations, content and configuration. Gathering nodes placement is finalized. Gathered resources balance is final. Gathering skill path UI is final ¦ V5: Bug fixes and improvements based on user feedback ¦ V6: More content (gathering spots, resource types etc) based on global content expansions and events | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Crafting System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V2: Basic crafting is implemented (items can be combined to get a new item) with placeholder effects and animations ¦ V3: Crafting stations implemented. Crafting skill path implemented with progression rules in place with placeholder UI. Crafting is a part of trading and in-game economy ¦ V4: Crafting profession is fully implemented with final animations, content and configuration. Crafted resources balance is final. Crafting skill path UI is final ¦ V5: Bug fixes and improvements based on user feedback ¦ V6: More content (new crafted items etc) based on global content expansions and events ¦ V7: Crafting nechanic is used as the base for new systems (like Forge), for more UGC content and events | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Magic | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Magic defined, main goals and rules of the mechanic set. Competitor research done. Documentation complete ¦ V2: Basic spell casting implemented with placeholder animations and effects. Placeholder magic configuration ¦ V3: Sufficient number of magic types is implemented and supported by animations and effects. Magic is tested as a part of combat/professions system. Magic profession skill path is implemented with placeholder UI ¦ V4: All types of magic are implemented and balanced, with final animations and effects in place. Skill path UI is final ¦ V5: Bug fixes, optimizations and balance tweaks ¦ V6: New magic types, magic-based puzzles, magic weapons/scrolls ¦ V7: Multiplayer magic usage | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Character Management | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Number of characters per server, char transfer rules, naming rules etc are defined and run through best pratices, competitor research done, documentation completed. Anti-cheat system designed ¦ V2: The game supports at least one character per server that can be renamed, deleted or transffered. Placeholder UI ¦ V3: All decided functionality implemented with temporary UI. UX is close to final. Basic anti-cheat protection implemented ¦ V4: Number of characters, transfer and naming rules etc are fully implemented, with final UX/UI and effects. Anti-cheat system is in place ¦ V5: Bug fixes and optimizations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Appearance customization | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: The limitations of appearance customization defined, with the minimum scope of content needed. Starting appearance defined. Rules of how players can change their appearance in the future explored and set ¦ V2: Basic appearance customization implemented with basic appearance parts to be changed. Placeholder UX/UI, limited customization options ¦ V3: All customization slots implemented with placeholder UI and limited options. Points of appearance customization in the game are implemented. Appearance items are included in the in-game economy with placeholder balance ¦ V4: Final UI and roaster of options. Final economy balance and configuration for tradable appearance items. Appearance presets ¦ V5: Bug fixes and optimizations ¦ V6: More appearance customization options, appearance randomizer ¦ V7: Appearance customization system expanded with more character's parts to alter. Deeper customization. Using the technology to add pets customization | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Garment System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: The limitations of garment choice and garment slots defined, with the minimum scope of content needed. Starting garments defined. Rules of how players can change their garments in the future explored and set ¦ V2: Basic garment system implemented with a limited number of slots to be changed. Placeholder UX/UI, limited customization options ¦ V3: All garment slots are changable with placeholder UI. More customization options added. Garment items are included into the game economy with placeholder balance. UX flow of changing the garments in-game (how do I change the garments - inventory, Barbersmith etc) implemented ¦ V4: Final UI and roaster of options. Final economy balance and configuration for tradable garment items. Garment presets ¦ V5: Bug fixes and optimizations ¦ V6: More garment options, garment sets randomizer, partner and seasonal/event garments ¦ V7: Improve clothing pipelines, performance, compatibility, and tooling to support large wardrobes and long-term live content growth. Support UGC garments | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Corruption | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Corruption types, cleansing mechanic and role in the world designed, documentation completed ¦ V2: Techart R&D completed with one type of corruption implemented. Corruption texture implemented. Corruption cleansing implemented. Corruptions visuals defined ¦ V3: 1-2 types of corruption fully supported with placeholder VFX. Corruption quests added. Corruption cleansing skill path added with placeholder UI and balance. One corrupted enemy supported. Corruption server/client behavior supported ¦ V4: 3-4 corruption types are added and placed around the world in accordance with player progression. Corruption cleansing skill path has final congfiguration with final UI and supported by quests. Final corruption weapon, enemies, animations and VFX in place ¦ V5: Bug fixes and optimizations ¦ V6: New corruption types, new weapons, new corrupted areas and enemies. Black hole as a part of corrupted area. Corruption-based events | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Movement System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define movement style, controls, responsiveness targets, and technical approach ¦ V2: Basic character locomotion with simple input and camera movement ¦ V3: Core movement functional with stable controls and essential traversal actions ¦ V4: Final movement set polished, responsive, and ready for full gameplay use ¦ V5: Improve feel, fix bugs, tune responsiveness, and refine animations/performance ¦ V6: Add advanced traversal options or new movement mechanics ¦ V7: Improve networking, performance, and support for many players or platforms | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Navigation | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define navigation model, world traversal rules, and pathfinding requirements ¦ V2: Basic pathfinding and movement across simple environments ¦ V3: Core navigation functional for standard maps and gameplay scenarios ¦ V4: Reliable navigation across full game content with finalized rules, final map and compass UX/UI ¦ V5: Improve path quality, fix stuck cases, and tune performance ¦ V6: Add advanced navigation features or support for new environment types ¦ V7: Support larger worlds, more agents, and faster content generation workflows | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Instancing | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define instancing goals, player flow, server model, and technical requirements. Documentation finished ¦ V2: Basic creation and joining of isolated test instances ¦ V3: Core instancing functional for key gameplay content and party access ¦ V4: Stable instancing with matchmaking, rules, and production readiness ¦ V5: Improve load times, stability, recovery, and resource efficiency ¦ V6: Add new instance types, rulesets, or player experiences ¦ V7: Support high concurrency, automation, and efficient server capacity growth | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Day/night cycle | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Day/night cycle rules defined, documentation ready ¦ V2: Techart R&D completed to figure out technical limitations. Demo cycle set ¦ V3: Day/night change functional and configurable with placeholder visuals ¦ V4: Final configuration and visuals implemented ¦ V5: Bug fixes and optimizations ¦ V6: Special day/night conditions added ¦ V7: Improve synchronization, performance, tooling, and support for large worlds, zones, and live content systems | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Dynamic weather | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Dynamic weather limitations and rules defined with every season/weather type specifics set and change rules/restrictions ¦ V2: Techart R&D completed to figure out technical limitations. Demo weather set with switch between two states ¦ V3: 1-2 weather types functional and configurable with placeholder visuals ¦ V4: All weather types and seasons implemented with cycle rules configured ¦ V5: Bug fixes and optimizations ¦ V6: New weather types and seasons added, special conditions for new zones and events ¦ V7: Support large worlds, zone-specific weather, synchronization, live events, and efficient content control | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Combat unified | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define combat vision, pacing, depth, skill ceiling, target audience ¦ V2: Basic melee combo / attack chain Basic shooting/projectile One enemy AI that attacks/chases Damage numbers / HP loss Placeholder animations/VFX PvP prototyped Test arena only ¦ V3: Core melee + ranged both functional Several enemy archetypes Basic abilities / cooldowns Hit reactions / dodge / interrupt basics Core stats affecting combat PvE encounters playable PvP arena playable ¦ V4: Final weapon/class kits Good responsiveness / animation quality Full enemy combat behavior set Balanced TTK / progression UI clarity / FX readability Stable multiplayer sync Combo systems Status effects ¦ V5: Balance classes/builds Fix frustrating AI Improve hit feel Reduce ability spam/ clunkiness Meta adjustments ¦ V6: New weapon archetypes New enemy mechanics Advanced builds ¦ V7: Large raids with many entities Server authority improvements Ability scripting tools Combat telemetry dashboards Faster content creation pipeline | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | User Space | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Competitor research and user space functionality defined; technical research on the system support ¦ V2: Basic user space instance functionality with furniture placement; placeholder objects, VFX and UI ¦ V3: Users can create and decorate their user space (added quest to get a user space); refined UX/UI and camera position; connection between user spaces explored ¦ V4: User space obtain, decorate and visit final functionality; a roaster of user space items; user space crafting stations; stable server support; conencted user spaces ¦ V5: Bugfix and stabilization ¦ V6: More user spaces items and trophies added; user space expansion (room -> several rooms -> house -> garden etc) ¦ V7: Reuse housing systems, permissions, and content pipelines to support guild houses and future shared spaces | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Minigames | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define the minigames mechanics we need, single-player/multiplayer and plan out minigames accessibility through the game. Prepare all needed documentation ¦ V2: 1-2 minigames core implemented on temporary assets ¦ V3: 1-2 minigames are fully functional with final assets and content. Server/client support and syncronization ¦ V4: All required minigames are implemented with final assets and content. Stable server/client support, progress save, multiplayer etc ¦ V5: Bugfix and stabilization ¦ V6: New minigames added, seasonal content and rewards ¦ V7: Expanding minigames mechanics into fully functional features/events | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Items & Inventory General Feature | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Combines R&D stages of item core, inventory, equipment and loot systems ¦ V2: Basic item creation, storage, equip, and drop loop works ¦ V3: Players can obtain, store, equip, and use items in core gameplay ¦ V4: Stable, polished, scalable item ecosystem ready for live players ¦ V5: QoL, balance, exploits, performance, UX improvement ¦ V6: Crafting hooks, rarity depth, loadouts, advanced loot rules, new item types ¦ V7: Shared backend/tools supporting large content volume and future systems | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Item Core System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define item architecture, data model, types, rarity, ownership, and technical foundations ¦ V2: Basic item definitions created and recognized by the game ¦ V3: Core item properties, usage rules, stacking, and persistence functional ¦ V4: Finalized item framework supporting all planned item categories and gameplay systems ¦ V5: Fix issues, improve data workflows, and tune item logic/performance ¦ V6: Add new item categories, advanced properties, and deeper system integrations ¦ V7: Data-driven architecture and tooling supporting large item libraries and future systems | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Inventory System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define inventory rules, capacity, UX flows, storage logic, and technical requirements ¦ V2: Basic item storage with add, remove, and move actions ¦ V3: Core inventory management functional with slots, stacking, and persistence ¦ V4: Final inventory UX, sorting, rules, and stable gameplay integration ready for release ¦ V5: Improve usability, fix bugs, and optimize performance/load times ¦ V6: Add filters, presets, extra storage types, and advanced management features ¦ V7: Support high item counts, shared storage, and efficient backend/content operations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Equipment System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define equipment slots, stat impact, restrictions, and progression goals ¦ V2: Basic equip/unequip actions with simple slot support ¦ V3: Core equipment slots, stat application, and visual updates functional ¦ V4: Final equipment rules, polished UX, full item support, and stable gameplay integration ¦ V5: Balance gear progression, fix issues, and improve usability/performance ¦ V6: Add loadouts, set bonuses, cosmetic slots, and advanced gear systems ¦ V7: Support many item types, reusable slot systems, and efficient content growth pipelines | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Loot Distribution Systems | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define loot sources, ownership rules, fairness model, and reward goals ¦ V2: Basic item drops from enemies or containers ¦ V3: Core loot drops and player acquisition rules functional for gameplay loops ¦ V4: Final loot tables, party rules, rarity balance, and polished reward presentation ¦ V5: Tune drop rates, fix exploits, and improve reward pacing ¦ V6: Add smart loot, group modes, event loot, and advanced reward systems ¦ V7: Support large content libraries, automated loot pipelines, and high concurrency gameplay | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Player Economy | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define player economy pillars, currency sources and sinks, main currency flows and rules. Perform competitor research and prepare documentation ¦ V2: Basic currencies, earning/spending flows, vendor transactions, and simple player trading tested to validate core value loops ¦ V3: Core economy functional with currencies, rewards, sinks, item pricing, vendors, and basic player exchange supporting regular gameplay progression ¦ V4: Final economy functionality with antii-cheat protection, server validation etc. Platform transactions are a part of the economy. LiveOps economy is included into overall balance. Tracking and BI in place ¦ V5: Bug fixes and improvements, UX/UI optimizations, balance tweaks ¦ V6: New currency sources/sinks, new currency types, LiveOps economy expansion ¦ V7: Advanced tools, analytics, automation, and balancing systems supporting large player populations, live operations, multiple markets, and long-term economic stability | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Trading System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define player-to-player and player-to-NPC trading rules, restrictions, pricing, and security needs ¦ V2: Basic item or currency exchange with players and NPC vendors functional ¦ V3: Core player trade and NPC buy/sell flows working reliably with item and currency transfer ¦ V4: Final trading UX, pricing rules, restrictions, safeguards, and stable gameplay integration ready for release ¦ V5: Improve usability, balance prices, prevent exploits, and refine speed/stability ¦ V6: Add gifting, barter, COD mail, reputation vendors, or advanced trading features ¦ V7: Support high trade volume, many vendors, cross-server systems, automation tools, and long-term live operations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Currency System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define currencies, sources, sinks, progression role, and balancing goals ¦ V2: Basic earning and spending of core currency functional ¦ V3: Core currencies integrated with rewards, vendors, and progression loops ¦ V4: Final currency balance, sinks, UI clarity, and stable economy integration ready for release ¦ V5: Tune inflation, rewards, sinks, and fix economy issues ¦ V6: Add premium, seasonal, faction, or specialized currencies ¦ V7: Advanced balancing tools, analytics, and support for multiple currencies across live operations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Auction House | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define marketplace goals, pricing model, taxes, and anti-abuse requirements ¦ V2: Basic item listing, browsing, and purchasing functional ¦ V3: Core marketplace flow with listings, purchases, expiration, and simple search/filter tools ¦ V4: Final marketplace UX, taxes/fees, safeguards, and stable production readiness ¦ V5: Improve search, pricing clarity, performance, and abuse prevention ¦ V6: Add bidding, advanced filters, history, smart pricing, or regional markets ¦ V7: Support high listing volume, cross-server markets, automation tools, and long-term economy management | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Pets | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Pets functionality defined and described; division between functional and cosmetic pets set; pets obtain flow defined ¦ V2: Player can get a cosmetic pet and equip/summon it; placeholder model/animations/effects ¦ V3: Player can get one cosmetic and one functional pet. Pet functionality works as intended with stats/ combat/ economy/ game interactions affect tested ¦ V4: Roaster of cosmetic and functional pets with final content is ready. Final economy/combat balance and defined pets sources ¦ V5: Bug fixes, optimizations and improvements ¦ V6: New pet types, themed and partner pets, new pet functionality introduced ¦ V7: Pet customization & garments shared pets, pet upgrade and development | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Forge System | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Quest System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define quest structure, content goals, progression role, tooling needs, and technical approach ¦ V2: Basic quest creation, acceptance, objective tracking, completion, and reward flow functional ¦ V3: Core quest types, progression integration, rewards, and essential UI fully playable ¦ V4: Final quest content framework, polished UX, reliable scripting, and stable gameplay integration ready for release ¦ V5: Improve pacing, fix bugs, refine rewards, readability, and content flow based on testing ¦ V6: Add advanced quest types, branching paths, dynamic events, chains, and richer narrative systems ¦ V7: Support large content volumes, designer-friendly tools, localization pipelines, live updates, and long-term content operations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Player Chat | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Prepare GDD and TDD on chat functionality, techology and limits ¦ V2: Basic chat with placeholder UX/UI with send-receive functionality ¦ V3: Send-receive functions, slash commands, more concurrent players support. Personal/party chat ¦ V4: Final UX/UI, emoji/colored text support, expanded functionality: block/report, add to friends, LFG. Profanity filters and chat moderation tools ¦ V5: Bug fixes and optimization ¦ V6: Voice chat support, more commands added ¦ V7: Chat technology used as the basis for guild functionality and friends. Overall chat system stability and load improvements and optimizations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Friends | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Prepare GDD and TDD on friends functionality, techology and limits ¦ V2: Basic Friend list with add/remove functionality, placeholder UI ¦ V3: Players can add, remove and block friends, open chat with them, check friends profiles, party. Adding to friends is available from different places of the game ¦ V4: Polished functionality and UX/UI implemented. Server support and syncronization across game and platform ¦ V5: Bug fixes and stability improvements ¦ V6: New friend features (gifts, etc), seasonal events for friends ¦ V7: Support large social graphs, cross-platform/cross-server connections, high concurrency, and efficient tools for managing long-term social features | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Multiplayer (Co-op, raids and dueling) | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define multiplayer architecture, modes, and rules ¦ V2: Basic co-op + simple duel + dummy raid instance ¦ V3: Functional co-op, duels, and basic raid loop ¦ V4: Polished multiplayer modes with full rulesets ¦ V5: Balance, latency fixes, UX improvements ¦ V6: New raid types, ranked duels, modifiers ¦ V7: Large-scale encounters, server optimization, tooling | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Guild System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define guild goals and functionality, prepare all needed documentation and best practices/competitor research ¦ V2: Basic create and join guild functionality with placeholder UI ¦ V3: Players can create, join, leave the guild, see the list of members, chat. Guild menu exists and players can check guild info. Placeholder UI ¦ V4: Fully functional guilds with menus, guild halls, shared bank and chats. Server stability ¦ V5: Bug fixes, server stability and syncronization improvements, UX/UI optimizations ¦ V6: Guild wars/events, guild halls expansions, guild cosmetics ¦ V7: Larger guilds support and overall system improvements | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | In-game Mail | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Notifications | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | HUD & In-Game Interface | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | UI Framework & UX Standards | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Controls | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | UX Optimizations | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Accessibility | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Presentation & Immersion | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Account Creation/Deletion | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Account Authentification | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Account Privacy Settings & Legal | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Player Dashboard] Player Account Features | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Player Dashboard] Game Dashboard | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Player Dashboard] Friends | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Player Dashboard] Search & Notifications | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Player Dashboard] Marketplace | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Developer Dashboard] Developer Account | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Developer Dashboard] Game Dashboard | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Developer Dashboard] Settings & Support | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Quest Tracking | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Platform Certification | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Payment Processing | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Online Services & Backend | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Launcher & Distribution | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Studio Operations / Org Design and Structure | Finalise org structure at offsite | Lock the "likely" structure shown in Glen's Miro (CEO/CD Aris, COO, CPO Glen, CTO vacant, with HR/Finance/IT/Legal/PM under COO and production tracks under Exec Prod) into the canonical org chart. Replace org_structure_likely_2026-04-26.md with org_structure_FINAL_<date>.md once agreed. | In progress | Critical ACT | Yellow | Strategy | Vardis/Aris/Glen |  | org_structure_likely_2026-04-26.md | Studio Operations |  |  |  | Agent / Studio Operations | Offsite output. Confirm Producer overlay convention, "Lead vs Leads" under CTO, and the second TD node.
Couch Heroes / Studio Operations / Org Design and Structure | Define COO scope of authority | Document the COO remit (HR, Finance, IT, Legal, PM) including budget authority, approval thresholds, hire/fire authority, and what escalates to CEO. Without this the COO cannot run the four ops functions cleanly. | Not started | High |  | Strategy | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Required before Aris signs off any ops spend.
Couch Heroes / Studio Operations / Org Design and Structure | Define CPO scope of authority | Document Glen's CPO remit (Marketing, Brand, PR, Community, BD, Web, Exec Prod oversight) and the boundary between CPO and Game Director (Robin) on creative direction. | Not started | High |  | Strategy | Vardis/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Fractional role - hours and decision rights need to be explicit.
Couch Heroes / Studio Operations / Org Design and Structure | Define Game Director scope vs CPO | Robin owns creative vision; CPO owns commercial outcomes. Codify where they meet (feature green-light, scope cuts, monetisation hooks). | Not started | High |  | Strategy | Robin/Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Most common friction point in studios this size.
Couch Heroes / Studio Operations / Org Design and Structure | Define Executive Producer remit | Graham starts ~May 18. Document what Exec Prod owns (cross-discipline scheduling, milestone delivery, dependency management) vs what each discipline lead owns (craft quality). | Not started | High |  | Strategy | Glen/Graham |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Onboarding artefact for Graham.
Couch Heroes / Studio Operations / Org Design and Structure | Producer overlay model | Confirm whether the violet "producer" boxes attached to QA/Audio/Art/Design/CTO are embedded production managers reporting to Exec Prod or dotted-line to discipline leads. Document the model. | Not started | High |  | Strategy | Glen/Graham |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Open question from Miro per org_structure_likely file.
Couch Heroes / Studio Operations / Org Design and Structure | RACI matrix for top 30 decisions | Build a RACI for the 30 most common cross-functional decisions (hire approval, scope change, tech spike approval, marketing spend, contract sign-off, vendor selection, etc). | Not started | High |  | Strategy | Aris/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Prevents the "who decides this" loop that kills small studios.
Couch Heroes / Studio Operations / Org Design and Structure | Decision log and governance cadence | Set up a single decision log (Notion/Confluence) and a weekly leadership stand-up (Vardis/Aris/Glen/Robin/Mustafa/Valeria/David/Lorenz). | Not started | High |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Pairs with RACI.
Couch Heroes / Studio Operations / Org Design and Structure | Org chart published artefact | Convert the agreed structure into a clean published org chart (PDF + interactive) for the company, investors, and Sponsor Licence application. | Not started | High |  | Implementation | Lorenz |  | org_structure_FINAL_<date>.md | Studio Operations |  |  |  | Agent / Studio Operations | Sponsor Licence application needs this.
Couch Heroes / Studio Operations / Org Design and Structure | Reporting lines in HRIS | Once HRIS is selected, configure reporting lines so they match the published org chart. Audit quarterly. | Not started | Medium |  | Ongoing Mgmt | Lorenz |  | HRIS selection (IT feature) | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Job family and levelling framework | Define job families (Engineering, Art, Design, Audio, QA, Production, Ops) and levels (IC1-IC6, M1-M3) with salary bands per level. Required for Sponsor Licence salary justification and for fair pay decisions. | Not started | High |  | Strategy | Lorenz/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Use SOC 2020 codes for Sponsor Licence alignment.
Couch Heroes / Studio Operations / Org Design and Structure | Salary banding by job family | Build UK salary bands per family/level using market data (Skillsearch, Hays Games, Datapeople). Bands must clear Skilled Worker thresholds (£41,700 general, £33,400 new entrant). | Not started | High |  | Research | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Critical for visa-route hires.
Couch Heroes / Studio Operations / Org Design and Structure | Approvals matrix for headcount | Document who can request a hire, who approves backfill, who approves a new role. Tie to budget. | Not started | Medium |  | Strategy | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Operating principles | Codify 5-7 studio operating principles (e.g. craft over speed, written decisions, async-first, etc) to anchor culture as headcount scales. | Not started | Medium |  | Strategy | Vardis/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Use brainstorming skill at offsite.
Couch Heroes / Studio Operations / Org Design and Structure | Studio comms architecture | Map the comms tools (Slack/Teams, email, Notion/Confluence, Jira/Linear, video, async memos) and the canonical use of each. Stops "where does this go" overhead. | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Meeting cadence framework | Define the recurring meeting set: weekly leadership, weekly all-hands, monthly business review, quarterly OKR review, monthly skip-levels. Document required attendees and outputs. | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | OKR/quarterly planning rhythm | Pick a planning system (OKRs vs V2MOM vs simple goals) and a quarterly cadence. Required for investor reporting maturity. | Not started | High |  | Strategy | Vardis/Aris/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Promotion and progression policy | Define how people move up levels - what's required, who decides, calibration cadence. Without this you get ad hoc promotions and pay drift. | Not started | Medium |  | Strategy | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Tie to job family framework.
Couch Heroes / Studio Operations / Org Design and Structure | Performance management system | Choose a performance management approach (continuous feedback vs annual review vs hybrid) and set up the tooling. | Not started | Medium |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Onboarding programme - all hires | Extend the existing onboarding checklist into a 30/60/90 day programme with role-specific tracks (eng, art, design, ops). | Not started | High |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Offboarding programme | Standard leaver process: notice handling, knowledge transfer, IP handover, access revocation, final pay, Home Office notification (if sponsored), exit interview. | Not started | Medium |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Different flows for sponsored vs non-sponsored leavers.
Couch Heroes / Studio Operations / Org Design and Structure | Cross-functional working groups | Establish standing working groups for cross-cutting concerns (Live Ops readiness, security, data, accessibility) with named owners. | Not started | Low |  | Strategy | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Premature now; revisit at ~30 headcount.
Couch Heroes / Studio Operations / Org Design and Structure | Org review cadence | Quarterly review of the org chart vs the work - are we structured for the work we're actually doing? | Not started | Medium |  | Ongoing Mgmt | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Team charters per discipline | Each discipline lead writes a one-pager: mission, scope, what we own, what we don't, how to engage us. | Not started | Medium |  | Implementation | Discipline leads |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Useful onboarding asset.
Couch Heroes / Studio Operations / Org Design and Structure | Internal communications plan | Cadence for company-wide updates: weekly written update from CEO, monthly all-hands, quarterly state-of-the-studio. | Not started | Medium |  | Implementation | Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Studio values and behaviours | Document studio values and the observable behaviours that demonstrate them (used in hiring, performance, calibration). | Not started | Medium |  | Strategy | Vardis/Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Greece studio - structural fit | If the Greece initiative proceeds, decide where it sits in the org (subsidiary, branch, contractor pool) and the reporting lines. | Not started | High | Waiting on Client | Strategy | Vardis/Aris/Glen |  | Greece initiative (Legal feature) | Studio Operations |  |  |  | Agent / Studio Operations | Conflict risk: pre-empts Riley legal advice.
Couch Heroes / Studio Operations / Org Design and Structure | Contractor vs employee decision framework | Document when to use employees vs UK contractors vs overseas contractors vs outsourcers, with the IR35 and Sponsor Licence implications spelt out. | Not started | High |  | Strategy | Lorenz/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | UK IR35 rules apply if CH determines status.
Couch Heroes / Studio Operations / Org Design and Structure | Diversity and inclusion approach | Set the studio's D&I posture and any measurable commitments. Required for some publishers' inclusion riders and for grant applications. | Not started | Medium |  | Strategy | Lorenz/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Org dashboard - headcount and vacancies | Live dashboard showing actual vs planned headcount, open roles, time-to-hire, attrition. | Not started | Medium |  | Ongoing Mgmt | Lorenz |  | HRIS | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Succession planning - key roles | Identify key-person risks (CTO when filled, Game Director, Head of Production) and document succession or continuity plans. | Not started | Medium |  | Strategy | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Investors will ask in due diligence.
Couch Heroes / Studio Operations / Org Design and Structure | Role-based access matrix | Tie each role in the org chart to its access entitlements (systems, data, repos). Pairs with IT/identity work. | Not started | Medium |  | Implementation | Mustafa/Lorenz |  | IT identity setup | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Open UK business bank account | Open a GBP business current account for CH Game Development LTD (Tide, Starling Business, Allica, or Barclays). Must support multi-user access and accounting integration. | Not started | Critical ACT |  | Implementation | Aris |  | UK Co incorporation | Studio Operations |  |  |  | Agent / Studio Operations | Several need 2-4 weeks for KYC. Start immediately on incorporation.
Couch Heroes / Studio Operations / Finance | Set up multi-currency wallet | USD/EUR receiving capability for any US/EU revenue or grant inflow, and for paying overseas contractors. Wise Business or Airwallex. | Not started | High |  | Implementation | Aris |  | UK bank account | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Select and implement accounting software | Pick Xero or QuickBooks Online (Xero preferred for UK + ecosystem). Configure chart of accounts for a games studio (capitalisable dev costs vs opex, R&D-eligible, project-coded). | Not started | Critical ACT |  | Implementation | Aris/external accountant |  | UK bank account | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Appoint UK accountant/bookkeeper | Engage a UK accounting firm with games-industry experience (BDO, Saffery, Crowe, or boutique like Counterculture, Royce Peeling Green). Define scope: bookkeeping, year-end accounts, CT600, R&D claims. | Not started | Critical ACT |  | Implementation | Vardis/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Riley legal can probably refer.
Couch Heroes / Studio Operations / Finance | Chart of accounts design | Design CoA with project codes, capitalisation flags for dev costs, R&D-eligible expenditure tags, and grant-fund tracking. Wrong CoA early = painful re-coding later. | Not started | High |  | Implementation | External accountant |  | Accounting software | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Register for Corporation Tax | Register with HMRC for CT within 3 months of starting business activity. | Not started | Critical ACT |  | Implementation | External accountant |  | UK Co incorporation | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 5.4 Corporation Tax Registration - confirm at offsite. Per CH_Guidance section 5.
Couch Heroes / Studio Operations / Finance | VAT registration assessment | Monitor turnover vs the £90,000 VAT threshold. Voluntary registration may help if mostly B2B and reclaiming VAT on big purchases (Unreal seats, hardware). | Not started | High |  | Assessment | External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 5.5 VAT Registration - confirm at offsite. Decision before first invoice.
Couch Heroes / Studio Operations / Finance | Set up payroll provider | Engage a payroll bureau (Moorepay, MHR, ADP, or accountant-provided) or run in Xero Payroll. Must support RTI, auto-enrolment, statutory pay calculations, BACS. | Not started | Critical ACT |  | Implementation | Aris/Lorenz |  | UK bank account | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance section 4. Required before first payday.
Couch Heroes / Studio Operations / Finance | HMRC employer registration (PAYE) | Register as employer with HMRC; receive PAYE reference and Accounts Office reference. | Not started | Critical ACT |  | Implementation | External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 4.1.
Couch Heroes / Studio Operations / Finance | Auto-enrolment pension scheme | Set up qualifying workplace pension (NEST for low-cost; Aviva/Smart Pension/Penfold for richer features). 3% employer / 5% employee minimum. | Not started | Critical ACT |  | Implementation | Lorenz/Aris |  | Payroll provider | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 1.6 Pension Auto-Enrolment Letter - confirm at offsite. Per CH_Guidance section 2. £6,240-£50,270 qualifying band 2026/27.
Couch Heroes / Studio Operations / Finance | Pension declaration of compliance | Submit declaration of compliance to The Pensions Regulator within 5 months of duties starting. | Not started | High |  | Implementation | Lorenz |  | Pension scheme live | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 2.4.
Couch Heroes / Studio Operations / Finance | Pension re-enrolment cycle | Diary 3-yearly cyclical re-enrolment of opted-out employees. | Not started | Medium |  | Ongoing Mgmt | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Employers' Liability Insurance | Procure £5m minimum cover. Required by law and for Sponsor Licence application. Display certificate. | Not started | Critical ACT |  | Implementation | Aris/Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 1.7 EL Insurance Certificate - confirm at offsite. £250-£800/year per CH_Guidance 1.1.
Couch Heroes / Studio Operations / Finance | Professional Indemnity Insurance | Cover for advisory/contractual work. £1m+ recommended. | Not started | High |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | £150-£1,200/year.
Couch Heroes / Studio Operations / Finance | Cyber Insurance | Studio holds source code, builds, player data (eventually). £1-2m cover band. | Not started | High |  | Implementation | Aris/Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | £200-£2,500/year. Required by some publishers.
Couch Heroes / Studio Operations / Finance | Public Liability Insurance | If hosting visitors, events, playtests at the studio. | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | £80-£350/year.
Couch Heroes / Studio Operations / Finance | Equipment cover | Insurance on workstations and dev hardware. | Not started | Medium |  | Implementation | Aris/Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | £100-£450/year.
Couch Heroes / Studio Operations / Finance | Directors and Officers Insurance | D&O cover for directors. Investors will likely require post-Series A. | Not started | Medium |  | Implementation | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | £150-£800/year.
Couch Heroes / Studio Operations / Finance | Insurance renewal calendar | Single source of truth for all policy renewal dates with 60-day pre-renewal review trigger. | Not started | High |  | Ongoing Mgmt | Aris |  | All insurances | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Statutory accounts process | Annual filing process at Companies House and CT600 to HMRC. Define close, sign-off, audit (if/when applicable). | Not started | High |  | Ongoing Mgmt | External accountant/Aris |  | Accounting software, accountant | Studio Operations |  |  |  | Agent / Studio Operations | First filing window starts at year-end.
Couch Heroes / Studio Operations / Finance | Confirmation statement filing | Annual Companies House confirmation statement (PSC, share capital, registered office). | Not started | High |  | Ongoing Mgmt | External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 5.x Companies House Filings - confirm at offsite.
Couch Heroes / Studio Operations / Finance | Director Identity Verification | Per Economic Crime and Corporate Transparency Act 2023, directors must verify identity with Companies House. | Not started | High |  | Implementation | All directors |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 5.3 Director Identity Verification - confirm at offsite. Per CH_Guidance Priority 5.
Couch Heroes / Studio Operations / Finance | R&D Tax Relief claim process | Games studios qualify under the merged RDEC scheme. Claim covers eligible salaries, contractor costs, software. Material cash benefit (typically 16.2% of qualifying spend). | Not started | High |  | Strategy | External accountant/Aris |  | Chart of accounts (R&D tags) | Studio Operations |  |  |  | Agent / Studio Operations | Material to runway. Don't lose claim through poor categorisation.
Couch Heroes / Studio Operations / Finance | R&D claim documentation regime | Set up the technical narrative and project-time tracking required to substantiate R&D claims. HMRC scrutiny is high. | Not started | High |  | Ongoing Mgmt | Mustafa/Aris |  | R&D Tax Relief process | Studio Operations |  |  |  | Agent / Studio Operations | Mustafa documents the technical advance per claim period.
Couch Heroes / Studio Operations / Finance | Video Games Expenditure Credit assessment | Assess eligibility for VGEC (the games-specific credit replacing Video Games Tax Relief). 34% of qualifying core expenditure. Requires BFI cultural test certification. | Not started | High |  | Assessment | External accountant/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Significant - games studios usually claim VGEC OR R&D, not both for same expenditure.
Couch Heroes / Studio Operations / Finance | BFI cultural test application | Apply for Interim Certificate from BFI to support VGEC. Detailed scoring on cultural content/contribution/hubs/practitioners. | Not started | High |  | Implementation | Aris/Robin |  | VGEC assessment done | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Treasury policy | How much cash held where, in what currencies, FX hedging stance, counterparty bank limits. Critical when raise lands. | Not started | Medium |  | Strategy | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Pre-raise: lightweight. Post-raise: formal policy required by board.
Couch Heroes / Studio Operations / Finance | Cash flow forecast - 13 week | Rolling 13-week cash forecast updated weekly. Standard board ask. | Not started | High |  | Ongoing Mgmt | Aris |  | Accounting software | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Annual budget and operating plan | Build a bottoms-up annual budget with monthly phasing. Tied to headcount plan, milestones, and runway projection. | Not started | High |  | Strategy | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Long-range financial model | 3-year P&L, cash, headcount model. Used for fundraising and board. | Not started | High |  | Strategy | Aris/Glen |  | Annual budget | Studio Operations |  |  |  | Agent / Studio Operations | Glen has experience with games studio LRPs - leverage.
Couch Heroes / Studio Operations / Finance | Monthly close process | Define close calendar (D+5 target initially, D+3 once mature). Tasks, owners, dependencies. | Not started | High |  | Implementation | Aris/External accountant |  | Accounting software | Studio Operations |  |  |  | Agent / Studio Operations | Use finance:close-management skill when building.
Couch Heroes / Studio Operations / Finance | Bank reconciliation procedure | Monthly bank rec to GL. Document workflow and exception handling. | Not started | High |  | Ongoing Mgmt | External bookkeeper |  | Accounting software | Studio Operations |  |  |  | Agent / Studio Operations | finance:reconciliation skill.
Couch Heroes / Studio Operations / Finance | Monthly management accounts pack | P&L, balance sheet, cash, vs budget variance, headcount, runway. Distributed to leadership and investors. | Not started | High |  | Ongoing Mgmt | Aris |  | Monthly close, LRP | Studio Operations |  |  |  | Agent / Studio Operations | finance:financial-statements skill.
Couch Heroes / Studio Operations / Finance | Investor reporting cadence | Standardised investor update (monthly during raise, quarterly otherwise). KPIs, financials, risks, asks. | Not started | High |  | Ongoing Mgmt | Vardis/Aris |  | Monthly mgmt accounts | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Board reporting pack template | Quarterly board pack: financials, milestones, KPIs, risks, decisions sought. | Not started | Medium |  | Implementation | Vardis/Aris |  | Investor reporting | Studio Operations |  |  |  | Agent / Studio Operations | Triggered when first institutional money lands.
Couch Heroes / Studio Operations / Finance | Cap table management | Maintain a clean cap table (Carta, Capdesk, Ledgy or spreadsheet to start). Track ordinary, preference, options, vested/unvested, dilution scenarios. | Not started | High |  | Ongoing Mgmt | Vardis/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | EMI option scheme design | Design an Enterprise Management Incentive scheme to grant tax-advantaged options. Hiring competitiveness tool. | Not started | High |  | Strategy | Riley/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 4.12 EMI Share Scheme - confirm at offsite. Per CH_Guidance Priority 4 (optional but high-value).
Couch Heroes / Studio Operations / Finance | EMI valuation - HMRC agreement | Get HMRC agreement on share valuation (VAL231) before granting options. Avoids tax surprises later. | Not started | High |  | Implementation | External accountant/Riley |  | EMI scheme design | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Option grant administration | Process for issuing options, board minutes, option certificates, register, vesting tracking. | Not started | Medium |  | Ongoing Mgmt | Aris/Riley |  | EMI scheme live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Expenses policy and tooling | Policy + an expense tool (Pleo, Soldo, Spendesk, Brex). Card issuance per role. Limits per spender. | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Procurement and PO policy | Approval thresholds for purchases. Vendor onboarding (W-8/W-9, sanctions check, payment terms). | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Becomes important at ~15 headcount.
Couch Heroes / Studio Operations / Finance | Payment runs and approvals | Weekly or twice-monthly payment run with dual approval over a threshold. | Not started | Medium |  | Ongoing Mgmt | Aris |  | UK bank account | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Foreign currency policy | If contracting overseas talent or receiving foreign income, document FX handling - spot, forward, natural hedge. | Not started | Medium |  | Strategy | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Year-end audit readiness | Even pre-audit threshold, build clean books as if audited. Lowers cost when audit becomes required. | Not started | Medium |  | Ongoing Mgmt | External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | KPI definition and reporting | Define financial and operational KPIs (burn, runway, headcount, dev velocity proxy, milestone health). | Not started | High |  | Strategy | Aris/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Grant funding pipeline | Track UKGI Games Fund, BFI Filmmaking Fund (where applicable), Innovate UK, Creative Scotland (if applicable), Wales Interactive. | Not started | High |  | Research | Vardis/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Non-dilutive £25k-£500k bands. Glen has applied before.
Couch Heroes / Studio Operations / Finance | Grant compliance regime | Once any grant lands, set up the reporting, milestone evidencing, and audit trail required by the funder. | Not started | Medium |  | Ongoing Mgmt | Aris |  | First grant secured | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Equity vs debt financing strategy | Document the company's stance on different capital types: equity, convertible, SAFE, venture debt, publisher advances, revenue-share deals. | Not started | High |  | Strategy | Vardis/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Anchors fundraising conversations.
Couch Heroes / Studio Operations / Finance | Financial controls register | Document key controls: bank dual auth, payment approvals, payroll review, expense limits, journal review. | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Pre-audit hygiene.
Couch Heroes / Studio Operations / Finance | Tax calendar | All HMRC deadlines: PAYE monthly, VAT quarterly (if registered), CT instalments (if applicable), CT600, P11D, P60s. | Not started | High |  | Ongoing Mgmt | External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Fundraising strategy and ask | Define round size, instrument (priced equity vs SAFE/convertible), use of funds, milestone gating, target close. | In progress | Critical ACT | Yellow | Strategy | Vardis/Glen |  | LRP financial model | Studio Operations |  |  |  | Agent / Studio Operations | Live conversation with Alter Ego/Picks/Enoma/Madrona.
Couch Heroes / Studio Operations / Fundraising | Investor pipeline tracker | CRM-style tracker of every investor conversation: stage, last touch, next step, materials shared, blockers. | Not started | High |  | Implementation | Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Glen's experience: this gets out of hand fast without it.
Couch Heroes / Studio Operations / Fundraising | Pitch deck v1 | Build the canonical pitch deck. Vision, team, market, product, traction, business model, ask. | In progress | Critical ACT | Green | Implementation | Vardis/Glen |  | Vision doc, LRP | Studio Operations |  |  |  | Agent / Studio Operations | gi skill applies.
Couch Heroes / Studio Operations / Fundraising | Pitch deck investor variants | Tailored variants per investor archetype (publisher-style vs VC vs strategic). | Not started | High |  | Implementation | Glen |  | Pitch deck v1 | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Demo build for investors | Playable or video demo for investor meetings. Timing tied to vertical slice. | Not started | High |  | Implementation | Robin/Valeria |  | Vertical slice (Game project) | Studio Operations |  |  |  | Agent / Studio Operations | Most-asked artefact in pitches.
Couch Heroes / Studio Operations / Fundraising | Data room - structure and seed | Set up a secure data room (Notion vault, DocSend, Datasite). Folder structure, access controls, NDA gating. | Not started | High |  | Implementation | Aris/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | gi skill has data room template.
Couch Heroes / Studio Operations / Fundraising | Data room - corporate documents | Cert of incorp, articles, share register, cap table, board minutes, PSC register. | Not started | High |  | Implementation | Riley/Aris |  | UK Co fully set up | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Data room - financial documents | Historic accounts (when available), management accounts, budget, LRP, cap table, R&D status. | Not started | High |  | Implementation | Aris |  | Monthly close, LRP | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Data room - product documents | Vision doc, GDD, pillar docs, competitive analysis, market sizing, design samples. | Not started | High |  | Implementation | Robin/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Data room - team documents | Founder bios, key hires, org chart, hiring plan, employment contracts (templates), EMI scheme. | Not started | High |  | Implementation | Lorenz/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Data room - legal and IP | Cap table, options register, IP assignments confirmed, trademark filings, key contracts, insurance. | Not started | High |  | Implementation | Riley |  | IP register | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Investor due diligence Q&A doc | Standing Q&A doc populated as investors ask questions. Dramatically speeds subsequent conversations. | Not started | High |  | Ongoing Mgmt | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Reference call list | Vetted list of references by archetype (advisor, ex-colleague, customer, vendor) with intro scripts. | Not started | Medium |  | Implementation | Vardis/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Term sheet playbook | Documented positions on the standard term-sheet items (valuation, liquidation pref, anti-dilution, board, vesting, ROFR, drag, info rights). | Not started | High |  | Strategy | Glen/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | gi skill content.
Couch Heroes / Studio Operations / Fundraising | Investor meeting cadence and material reuse | System for what gets sent in advance, in the meeting, in follow-up. Avoids ad hoc material creation per meeting. | Not started | Medium |  | Implementation | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Alter Ego conversation tracker | Specific tracker for Alter Ego's process: who they've met, what they've asked, current stage, blockers, next step. | In progress | High | Green | Ongoing Mgmt | Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | One of four active investors.
Couch Heroes / Studio Operations / Fundraising | Picks Capital conversation tracker | Specific tracker for Picks Capital. | In progress | High | Green | Ongoing Mgmt | Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Enoma conversation tracker | Specific tracker for Enoma. | In progress | High | Green | Ongoing Mgmt | Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Madrona conversation tracker | Specific tracker for Madrona. | In progress | High | Green | Ongoing Mgmt | Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Investor outreach expansion | Pipeline build beyond the current four: identify and warm-intro to 20-30 additional relevant funds (gaming-focused, Series A/seed, EU/UK/US). | Not started | High |  | Research | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Glen's network applies.
Couch Heroes / Studio Operations / Fundraising | Strategic investor strategy | Decision on whether to take strategic capital (publisher, platform, IP holder) and on what terms. Has implications for distribution rights and valuation. | Not started | High |  | Strategy | Vardis/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Publisher conversations - parallel track | Run a parallel track with publishers as either co-fund or eventual deal partners. | Not started | Medium |  | Strategy | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | EIS/SEIS advance assurance | Apply for HMRC advance assurance for EIS (and SEIS if applicable) to enable UK individual angels to invest tax-efficiently. | Not started | High |  | Implementation | Riley/External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Material to UK angel rounds.
Couch Heroes / Studio Operations / Fundraising | Investor legal docs - SHA template | Standard shareholders' agreement template ready for the round. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Investor legal docs - articles update | Articles of association update for institutional round (preference share class, drag, tag, etc). | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Triggered at term sheet stage.
Couch Heroes / Studio Operations / Fundraising | Investor reporting commitments | Once a round closes, document the reporting commitments (frequency, format, KPIs) to investors. | Not started | High |  | Implementation | Aris/Vardis |  | Round close | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Board composition post-round | Decide on board seats (founders, investor, independent), governance committees if required, and chair role. | Not started | High |  | Strategy | Vardis/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Closing process plan | Step-by-step plan from term sheet to wired funds: DD, legal, signing, completion mechanics. | Not started | High |  | Implementation | Aris/Riley |  | Term sheet signed | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Use-of-funds tracker | Once funded, track actual spend vs the use-of-funds in the deck. Investors check this. | Not started | High |  | Ongoing Mgmt | Aris |  | Round close | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Bridge/extension contingency plan | If main round slips, what's the bridge plan? Convertible from existing investors, founder loan, cost cuts. | Not started | High |  | Strategy | Vardis/Aris/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Fundraising comms to staff | When and how to communicate fundraising progress internally. Closed-loop messaging to avoid uncertainty drag. | Not started | Medium |  | Strategy | Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Press and announce strategy | Launch announcement strategy when round closes. Tied to studio brand and recruiting. | Not started | Medium |  | Strategy | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Identity provider selection | Pick the SSO/identity backbone: Google Workspace, Microsoft 365, or Okta. All downstream tooling routes through it. | Not started | Critical ACT |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Highest-leverage IT decision.
Couch Heroes / Studio Operations / IT and Systems | Identity provider implementation | Roll out the chosen IdP, set up groups by team/role, configure SCIM provisioning to all major SaaS tools. | Not started | Critical ACT |  | Implementation | Mustafa |  | IdP selection | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | SSO enforcement on all SaaS | Mandatory SSO via the IdP for all business systems. No standalone passwords. | Not started | High |  | Implementation | Mustafa |  | IdP live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Password manager rollout | Deploy 1Password Business or Bitwarden for shared credentials and break-glass accounts. | Not started | High |  | Implementation | Mustafa |  | IdP live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Multi-factor authentication policy | Mandatory MFA on all business accounts. Hardware key (YubiKey) preferred for admins. | Not started | High |  | Implementation | Mustafa |  | IdP live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Workstation procurement standard | Standard hardware spec by role (engineering, art, design, ops). Apple Silicon vs Windows for Unreal-heavy roles. Volume purchase channel (CDW, Computacenter, Apple Business). | Not started | High |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Art/eng need beefy specs for Unreal.
Couch Heroes / Studio Operations / IT and Systems | Workstation procurement process | Define the order-to-desk flow including imaging, MDM enrolment, kit-out, handover, asset tagging. | Not started | High |  | Implementation | Mustafa |  | Workstation standard | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Mobile device management | Deploy MDM (Jamf for Apple, Intune for Windows, Kandji as alt) to manage all corporate devices. | Not started | High |  | Implementation | Mustafa |  | Workstation procurement | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Endpoint security standard | Encryption (FileVault/BitLocker), endpoint protection (CrowdStrike/SentinelOne or Defender for Business), patch policy, screen lock. | Not started | High |  | Implementation | Mustafa |  | MDM | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | VPN and remote access | Deploy a Zero Trust access tool (Tailscale, Cloudflare Access, Twingate) or traditional VPN for accessing the build farm and asset storage. | Not started | High |  | Implementation | Mustafa |  | IdP live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Office network design | If a physical office, design the network: VLAN segmentation, guest WiFi separation, wired backbone for Unreal teams. | Not started | Medium |  | Implementation | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Office decision dependency.
Couch Heroes / Studio Operations / IT and Systems | Source control - Perforce or Git LFS | Decide on Unreal-friendly version control: Perforce Helix (industry default for Unreal) or Git + LFS + UnrealGitPlugin. Perforce strongly preferred for art-heavy projects. | Not started | Critical ACT |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Hard to change later. Get this right.
Couch Heroes / Studio Operations / IT and Systems | Source control hosting | Host Perforce on AWS/Azure or use Assembla/Helix Cloud. Sizing, backup, region. | Not started | Critical ACT |  | Implementation | Mustafa |  | Source control choice | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Source control - branch and submit policy | Branching strategy (mainline, dev, feature streams), submit policy, code review hooks, locked file workflow for art assets. | Not started | High |  | Implementation | Mustafa |  | Source control hosted | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Build infrastructure - CI/CD | Build farm for Unreal: TeamCity, Jenkins, or BuildKite. Cooks per platform, cook caching, packaged builds for QA/playtest. | Not started | High |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Sized to Unreal cook times. Expensive but essential.
Couch Heroes / Studio Operations / IT and Systems | Build infrastructure - DDC and shader cache | Distributed Derived Data Cache and Shared Shader Cache to keep iteration time sane across team. | Not started | High |  | Implementation | Mustafa |  | Source control | Studio Operations |  |  |  | Agent / Studio Operations | Massive iteration-time saver.
Couch Heroes / Studio Operations / IT and Systems | Asset storage and review tooling | Where do art reviews and reference live - SyncSketch, ftrack, ShotGrid (Flow Production Tracking), or Plastic SCM? | Not started | Medium |  | Strategy | David/Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Art-specific decision.
Couch Heroes / Studio Operations / IT and Systems | Cloud platform standard | AWS or Azure or GCP as the primary cloud. Tied to build farm, asset storage, future game backend. | Not started | High |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Cloud account structure | Multi-account/subscription setup with separation of dev, staging, prod, build, sandbox. IAM/RBAC tied to IdP. | Not started | High |  | Implementation | Mustafa |  | Cloud platform, IdP | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Cost monitoring and FinOps | Cloud cost dashboards, alerts on anomalies, monthly review. Build farms and DDC can balloon fast. | Not started | High |  | Ongoing Mgmt | Mustafa/Aris |  | Cloud platform live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Backup and disaster recovery policy | What gets backed up, how often, where stored, retention, recovery time/point objectives. Source control snapshot, asset storage, business systems. | Not started | High |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Investor DD will ask.
Couch Heroes / Studio Operations / IT and Systems | Backup implementation | Implement the backup regime: Perforce snapshots, cloud cross-region replication, SaaS exports (Notion, Google Workspace). | Not started | High |  | Implementation | Mustafa |  | Backup policy | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | DR runbook and tabletop | Documented DR runbook, annual tabletop exercise, RPO/RTO commitments. | Not started | Medium |  | Implementation | Mustafa |  | Backup live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Information security policy | Comprehensive InfoSec policy: data classification, acceptable use, access control, incident response, vendor risk. | Not started | High |  | Strategy | Mustafa/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Required by some publishers/platform holders.
Couch Heroes / Studio Operations / IT and Systems | Acceptable use policy | Staff-facing AUP for company devices, networks, data. Tied to onboarding sign-off. | Not started | High |  | Implementation | Mustafa/Lorenz |  | InfoSec policy | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Data classification scheme | Public / Internal / Confidential / Restricted. Tag systems and data accordingly. | Not started | Medium |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Incident response plan | Steps for security incidents: detection, containment, eradication, recovery, post-mortem. Named on-call. | Not started | High |  | Implementation | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Vulnerability management | Patch cadence, vulnerability scanning, third-party dependency scanning. | Not started | Medium |  | Ongoing Mgmt | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Penetration test - annual | Annual external pen test of internal systems and (eventually) game backend. | Not started | Medium |  | Ongoing Mgmt | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Required at scale or by publishers.
Couch Heroes / Studio Operations / IT and Systems | ISO 27001 / Cyber Essentials assessment | Decide whether to pursue Cyber Essentials (low cost, UK gov-aligned) or full ISO 27001 (heavyweight). Cyber Essentials Plus often required by UK publishers and for government grants. | Not started | High |  | Assessment | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | SaaS tooling licence inventory | Single sheet of every SaaS tool, owner, seats, cost, renewal date. Stops licence sprawl. | Not started | High |  | Implementation | Mustafa/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Unreal Engine licensing | Confirm Unreal licence terms (royalty-based standard EULA vs custom licence). Track per-platform requirements. | Not started | High |  | Assessment | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Standard EULA = 5% over $1m gross.
Couch Heroes / Studio Operations / IT and Systems | DCC tool licences - art | Maya, ZBrush, Substance Suite, Houdini, Marvelous Designer, Photoshop. Volume licensing. | Not started | High |  | Implementation | David |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | DCC tool licences - audio | Wwise, FMOD, Pro Tools / Reaper, sound libraries. | Not started | Medium |  | Implementation | TBD (audio lead) |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Productivity tooling | Notion vs Confluence, Slack vs Teams, Zoom vs Meet, Loom for async, Miro/FigJam. | Not started | High |  | Strategy | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Tied to org comms architecture.
Couch Heroes / Studio Operations / IT and Systems | Project tooling | Jira, Linear, ShotGrid (Flow), or Hansoft for production tracking. Often differs by discipline. | Not started | High |  | Strategy | Valeria/Graham |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Production-side decision.
Couch Heroes / Studio Operations / IT and Systems | Email and calendar standard | Google Workspace or Microsoft 365 for email/calendar/storage. Tied to IdP decision. | Not started | High |  | Implementation | Mustafa |  | IdP selection | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Document storage standard | Google Drive vs SharePoint vs Notion vs combination. Retention and access policy. | Not started | Medium |  | Implementation | Mustafa |  | Email/calendar standard | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Studio onboarding IT pack | Day-one IT setup: account, device, MDM, SSO, email, Slack, source control access, productivity tools. Documented runbook. | Not started | High |  | Implementation | Mustafa |  | All identity + tooling live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Studio offboarding IT pack | Day-of-leaver: revoke SSO, MDM remote wipe (if BYOD policy), source control access removal, mailbox forwarding, asset return. | Not started | High |  | Implementation | Mustafa |  | All identity + tooling live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Help desk and ticketing | Internal IT support channel - shared Slack channel initially, ticketed system (Jira SM, Freshservice) once over ~25 staff. | Not started | Medium |  | Implementation | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Asset register - hardware | Inventory of all company hardware with assignee, serial, purchase date, warranty, refresh cycle. | Not started | Medium |  | Ongoing Mgmt | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Pairs with insurance equipment cover.
Couch Heroes / Studio Operations / IT and Systems | Vendor risk assessment process | Before adding a SaaS or vendor, review their security posture, data location, sub-processors, breach history. | Not started | Medium |  | Implementation | Mustafa/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Pairs with legal vendor-check skill.
Couch Heroes / Studio Operations / IT and Systems | Game backend platform decision | Decide on the live-services backend approach (PlayFab, AccelByte, Pragma, custom on AWS GameLift/etc). Material decision for an MMORPG. | Not started | High |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | MMORPG-specific. Don't skip.
Couch Heroes / Studio Operations / IT and Systems | Source-control IP audit pre-launch | Pre-launch sweep of source control to confirm only owned IP and licensed third-party assets are in the repo. | Not started | Medium |  | Implementation | Mustafa/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Tied to Legal IP register.
Couch Heroes / Studio Operations / IT and Systems | Build artefact retention | Retention of cooked builds, cook logs, symbols, crash dumps. Required for post-release support. | Not started | Medium |  | Implementation | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Telemetry and analytics platform | Player telemetry pipeline (eventually). Choose platform (Snowflake/BigQuery + GameAnalytics/Unity Analytics/custom). | Not started | Medium |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Post-vertical-slice decision.
Couch Heroes / Studio Operations / IT and Systems | Privacy by design technical controls | DSAR tooling, deletion workflows, consent management. Required for any game collecting player data. | Not started | Medium |  | Strategy | Mustafa/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Tied to UK GDPR/data protection.
Couch Heroes / Studio Operations / IT and Systems | IT runbook library | Documented runbooks for: new starter setup, leaver, lost device, suspicious email, source control restore, build farm outage. | Not started | Medium |  | Ongoing Mgmt | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Status page and on-call rota | Internal status page for major dev infra (Perforce, build farm, VPN) and an on-call rota once team is at scale. | Not started | Low |  | Implementation | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Premature now; revisit at ~25 headcount.
Couch Heroes / Studio Operations / Legal and Compliance | Riley/SayBrook engagement letter | Confirm the £1,500/week + £350/hr overage engagement scope, deliverables, and SLA. | In progress | Critical ACT | Yellow | Implementation | Vardis/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Reference doc Couch_Heroes_Legal_Function_Briefing_1.docx. Confirm whether £1.5k weekly is fixed scope or capped retainer.
Couch Heroes / Studio Operations / Legal and Compliance | Riley/SayBrook scope-of-work matrix | Matrix of which legal work is in-scope of weekly retainer vs hourly overage vs out-of-scope (specialist counsel). Stops overage drift. | Not started | High |  | Implementation | Aris |  | Engagement letter | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Riley weekly working session | Standing weekly call with Riley to review live matters, surface new ones, and prioritise. | In progress | High | Green | Ongoing Mgmt | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Specialist counsel panel | Pre-vetted specialist firms for areas Riley doesn't cover: immigration, IP/trade marks, tax, employment dispute, data protection. | Not started | High |  | Research | Riley/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Riley-led panel build.
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - employment | Master employment contract template incorporating CH_Guidance Appendix Two corrections (SSP, ERA 2025 references, day-one rights, IP assignment, restrictive covenants). | Not started | Critical ACT |  | Implementation | Riley |  | CH_Guidance_extracted.md s. Mandatory Corrections | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 1.1 Employment Contract - confirm at offsite. Riley owns drafting; CH approves.
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - contractor (UK) | UK contractor agreement template with IR35 status determination, IP assignment, confidentiality. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - contractor (overseas) | Overseas contractor template - tax residency declaration, IP assignment governed by English law, payment in GBP/USD. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - mutual NDA | Bilateral NDA for partner/publisher/investor conversations. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 2.3 Confidentiality / NDA - confirm at offsite.
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - inbound NDA review | Standing playbook for reviewing inbound NDAs (positions on jurisdiction, term, residual knowledge, IP carve-outs). | Not started | Medium |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | legal:triage-nda skill.
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - SOW master | Master Services Agreement + SOW template for service providers (audio outsource, art outsource, contractor agencies). | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - publisher heads of terms | Heads of terms template anchored to studio-favourable starting positions. | Not started | Medium |  | Implementation | Riley/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - asset licence (in) | Template for licensing third-party assets into the project. | Not started | Medium |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - asset licence (out) | Template for licensing CH assets out (e.g. for marketing partners). | Not started | Low |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract execution and CLM | E-signature platform (DocuSign, Dropbox Sign) + simple contract repository with renewal alerts. | Not started | High |  | Implementation | Aris/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract review playbook | Playbook for reviewing inbound contracts: red-line positions, fall-back positions, escalation triggers. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | legal:review-contract skill.
Couch Heroes / Studio Operations / Legal and Compliance | Legal calendar - statutory and renewal | Single legal calendar covering Companies House confirmation statement, accounts filing, CT600, sponsor licence renewal (4-yearly), insurance renewals, contract renewals, trademark renewals. | Not started | High |  | Ongoing Mgmt | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Sponsor Licence application | Apply for Skilled Worker sponsor licence. Requires HR systems evidence, EL insurance, key personnel appointed (Authorising Officer, Key Contact, Level 1 User). | In progress | Critical ACT | Yellow | Implementation | Lorenz/Riley/Patrice |  | UK Co incorp, EL insurance | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 3.x Sponsor Licence - confirm at offsite. Per CH_Guidance section 3. Patrice can act as L1 User.
Couch Heroes / Studio Operations / Legal and Compliance | Sponsor Licence HR Compliance Pack | Documented systems for tracking attendance, visa expiry, passport copies, reporting changes to Home Office. | Not started | Critical ACT |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 3.1 HR Compliance Pack - confirm at offsite. Per CH_Guidance Priority 3.
Couch Heroes / Studio Operations / Legal and Compliance | Sponsored worker file standard | Standardised personnel file structure for each sponsored worker. | Not started | High |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 3.2 Sponsored Worker File Template - confirm at offsite.
Couch Heroes / Studio Operations / Legal and Compliance | Sponsor Licence ongoing duties | Ongoing reporting of sponsored-worker changes to Home Office (salary, role, absence). Process and named owner. | Not started | High |  | Ongoing Mgmt | Lorenz |  | Sponsor Licence granted | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Sponsor Licence renewal | 4-yearly licence renewal. Diary 6 months ahead of expiry. | Not started | Medium |  | Ongoing Mgmt | Lorenz |  | Sponsor Licence granted | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Right to Work check process | Documented Right to Work check procedure with online checking service, document retention, audit trail. | Not started | Critical ACT |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 1.4 Right to Work Checks - confirm at offsite. Per CH_Guidance Priority 1.
Couch Heroes / Studio Operations / Legal and Compliance | Visa cost recovery prohibition - policy | Internal policy enforcing the post-2024 prohibition on recovering sponsorship costs from workers. Train recruiters/managers. | Not started | High |  | Implementation | Lorenz/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 3.8. Licence revocation risk if breached.
Couch Heroes / Studio Operations / Legal and Compliance | IP register | Register of all CH-owned IP: trademarks, copyrights, design rights, registered works. With renewal dates. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Trademark - studio name | UK and key territory trademark filing for "Couch Heroes" name and logo (UKIPO + EUIPO + USPTO). | Not started | High |  | Implementation | Riley + IP specialist |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Specialist IP counsel - not Riley core.
Couch Heroes / Studio Operations / Legal and Compliance | Trademark - game title | Trademark filing for the game title once locked. Class 9 (software), Class 41 (entertainment), Class 28 (toys), Class 25 (apparel). | Not started | High |  | Implementation | Riley + IP specialist |  | Game title lock | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Trademark watching service | Subscribe to a watching service to flag conflicting filings. | Not started | Medium |  | Ongoing Mgmt | Riley |  | Trademarks filed | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Domain portfolio | Acquire and hold key domains (.com, .co.uk, .io, .gg) for studio and game. Centralised registrar account. | Not started | High |  | Implementation | Mustafa/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Social handle portfolio | Reserve studio and game handles across major platforms (Twitter/X, BlueSky, Instagram, TikTok, YouTube, Twitch, Reddit, Discord). | Not started | High |  | Implementation | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | IP assignment - all current contributors | Confirm every current contributor (founders, contractors, advisors) has executed IP assignment to CH Game Development LTD. Backfill any gaps. | Not started | Critical ACT |  | Assessment | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | A common pre-funding diligence killer.
Couch Heroes / Studio Operations / Legal and Compliance | IP assignment - employment standard | Standalone IP assignment deed used alongside employment contract. | Not started | High |  | Implementation | Riley |  | Employment contract template | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Open source compliance policy | Policy on use of OSS in the codebase: allowed licences, prohibited (GPL/AGPL in shipped code), tracking, attribution. | Not started | High |  | Strategy | Mustafa/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Critical for an MMORPG. Wrong OSS = forced source disclosure.
Couch Heroes / Studio Operations / Legal and Compliance | Open source compliance tooling | Implement OSS scanning (Snyk, FOSSA, Black Duck) in CI. | Not started | Medium |  | Implementation | Mustafa |  | OSS policy | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Third-party asset register | Every middleware, plugin, audio library, art asset with its licence terms and obligations. | Not started | High |  | Implementation | Mustafa/David |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Diligence ask.
Couch Heroes / Studio Operations / Legal and Compliance | Confidentiality and NDA process | Process for issuing NDAs to inbound parties, signing inbound NDAs, and tracking what's covered by what. | Not started | Medium |  | Implementation | Aris |  | NDA template | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | UK GDPR compliance baseline | UK GDPR compliance posture: lawful basis register, employee privacy notice, candidate privacy notice, retention schedule, sub-processor list. | Not started | High |  | Implementation | Riley/Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance Priority 1.
Couch Heroes / Studio Operations / Legal and Compliance | Data Protection Officer determination | Assess whether a DPO is legally required (likely not at current scale) and designate a senior data lead. | Not started | Medium |  | Assessment | Lorenz/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | DPIA process and templates | Data Protection Impact Assessment template + process for triggering one (any new system processing personal data). | Not started | Medium |  | Implementation | Riley |  | UK GDPR baseline | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 2.5 DPIA Template - confirm at offsite. Per CH_Guidance Priority 2.
Couch Heroes / Studio Operations / Legal and Compliance | Cross-border data transfer agreement | If sharing employee/business data with NBI LLC US parent (or any non-UK entity), put a UK IDTA or UK Addendum to EU SCCs in place. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 2.6 Cross-Border Data Transfer Agreement - confirm at offsite. Per CH_Guidance Priority 2.
Couch Heroes / Studio Operations / Legal and Compliance | Vendor data processing agreements | DPAs with every SaaS vendor processing personal data (HRIS, payroll, email, productivity). | Not started | Medium |  | Ongoing Mgmt | Aris |  | UK GDPR baseline | Studio Operations |  |  |  | Agent / Studio Operations | legal:vendor-check skill.
Couch Heroes / Studio Operations / Legal and Compliance | Subject Access Request process | Documented DSAR handling process - intake, identity verification, search, redaction, response within 30 days. | Not started | Medium |  | Implementation | Lorenz/Riley |  | UK GDPR baseline | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Cookie and tracker compliance | Pre-launch website and (eventually) game compliance with PECR cookie rules. | Not started | Medium |  | Implementation | Glen/Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Health and Safety policy | Mandatory written H&S policy (5+ employees). DSE assessments for remote workers, fire safety, risk assessment process. | Not started | High |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 1.5 Health and Safety Policy - confirm at offsite. Per CH_Guidance Priority 1.
Couch Heroes / Studio Operations / Legal and Compliance | Employee handbook - full set | Disciplinary, grievance, sickness absence (updated for SSP changes), holiday and leave, family leave (maternity/paternity/adoption/shared parental/parental bereavement/neonatal), flexible working, equal opps, anti-harassment, whistleblowing, data protection, social media, IT AUP, expenses, probation, training, alcohol and drugs, redundancy. | Not started | High |  | Implementation | Riley/Lorenz |  | Employment contract template | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 2.1 Employee Handbook - confirm at offsite. Per CH_Guidance Priority 2. Full list.
Couch Heroes / Studio Operations / Legal and Compliance | ERA 2025 readiness - April 2026 | Review and update contracts/policies for April 2026 ERA changes: SSP from day one, paternity/parental leave day-one rights, collective redundancy doubling, whistleblowing extension. | Not started | Critical ACT |  | Implementation | Riley/Lorenz |  | Contracts and policies drafted | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance section 6.1. Hard date.
Couch Heroes / Studio Operations / Legal and Compliance | ERA 2025 readiness - October 2026 | Update for fire-and-rehire, sexual harassment "all reasonable steps" duty, third-party harassment liability, tribunal time limits to 6 months. | Not started | High |  | Strategy | Riley/Lorenz |  | ERA April 2026 work | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 6.2.
Couch Heroes / Studio Operations / Legal and Compliance | ERA 2025 readiness - January 2027 | Probation and dismissal procedure overhaul - unfair dismissal qualifying period drops from 2 years to 6 months. Anyone hired ~Jul/Aug 2026 may have unfair dismissal protection from Jan 2027. | Not started | High |  | Strategy | Riley/Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 6.3. Major implications for hiring approach.
Couch Heroes / Studio Operations / Legal and Compliance | Bribery Act 2010 procedures | Adequate procedures policy under Bribery Act 2010. | Not started | Medium |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 4.9 Bribery Act Policy - confirm at offsite. Per CH_Guidance Priority 4.
Couch Heroes / Studio Operations / Legal and Compliance | Anti-money-laundering posture | Assessment of AML obligations - games studio is mostly out of scope but check for any NFT/blockchain/marketplace plans. | Not started | Low |  | Assessment | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Modern Slavery Statement (deferred) | Required only above £36m turnover. Tracked as a "revisit" item. | Not started | Low |  | Assessment | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 4.10 Modern Slavery Statement - confirm at offsite. Per CH_Guidance Priority 4.
Couch Heroes / Studio Operations / Legal and Compliance | Greece initiative - legal structure | Legal structure for the Greece initiative (subsidiary, branch, contractor pool, EOR). Tax residency and PE risk analysis. | Not started | High | Waiting on Client | Strategy | Riley + Greek counsel |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Specialist Greek counsel needed. Conflict risk - decisions here affect org structure.
Couch Heroes / Studio Operations / Legal and Compliance | Greece initiative - employment law | Greek employment law obligations if hiring in Greece. Likely requires local payroll, social security registration. | Not started | High | Waiting on Client | Research | Greek counsel |  | Greece structure decision | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Greece initiative - IP flow | Ensure IP created in Greece flows back to CH Game Development LTD via assignment chain. | Not started | High | Waiting on Client | Strategy | Riley + Greek counsel |  | Greece structure decision | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Regulatory monitoring - employment | Monitor changes in UK employment law (ERA 2025 secondary regs, NMW updates, statutory rate updates). | Not started | Medium |  | Ongoing Mgmt | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Riley deliverable.
Couch Heroes / Studio Operations / Legal and Compliance | Regulatory monitoring - games | Monitor games-specific regulation: PEGI/ESRB, loot box, gambling adjacency, child safety (UK Children's Code/Age Appropriate Design Code), Online Safety Act, EU DSA. | Not started | High |  | Ongoing Mgmt | Riley + Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Online Safety Act + Age Appropriate Design Code apply to studios with UK player exposure.
Couch Heroes / Studio Operations / Legal and Compliance | Regulatory monitoring - data and privacy | Monitor UK GDPR/DPA 2018 evolution (DUA Bill etc), EU GDPR, US state laws once US presence material. | Not started | Medium |  | Ongoing Mgmt | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Investor legal - SHA negotiation | Negotiation of shareholders' agreement at term sheet stage. | Not started | High |  | Strategy | Riley |  | Term sheet signed (Fundraising) | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Investor legal - articles update | Update Articles of Association for institutional round (preference share rights, drag, tag, transfer restrictions). | Not started | High |  | Implementation | Riley |  | Term sheet signed | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Investor legal - subscription agreement | Subscription/investment agreement for the round. | Not started | High |  | Implementation | Riley |  | SHA agreed | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Investor legal - completion mechanics | Closing mechanics: signing, completion, share issuance, board changes, Companies House filings. | Not started | High |  | Implementation | Riley |  | Subscription agreement | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Insurance broker engagement | Single broker handling all studio insurances (EL, PI, cyber, PL, equipment, D&O). Reduces admin and surfaces gaps. | Not started | High |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Insurance claim runbook | Documented procedure for raising and managing an insurance claim. | Not started | Low |  | Implementation | Aris |  | Insurance broker | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Compliance register | Single register of all compliance obligations (statutory filings, regulatory, contractual) with owner, frequency, last date, next date. | Not started | High |  | Implementation | Aris/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | legal:compliance-check skill.
Couch Heroes / Studio Operations / Legal and Compliance | Document retention schedule | Per-record-type retention schedule (employment: 6 years post-leave, payroll: 3 years, accounting: 6 years, board minutes: indefinite). | Not started | Medium |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Litigation hold process | Process for issuing and managing litigation holds if a claim is anticipated. | Not started | Low |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Whistleblowing channel | Independent whistleblowing channel (e.g. SafeCall, Vault Platform) per Public Interest Disclosure Act. ERA 2025 extends to sexual harassment. | Not started | Medium |  | Implementation | Lorenz/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Anti-harassment training programme | Mandatory training for all staff. Tightened "all reasonable steps" duty from October 2026 makes documented training material. | Not started | High |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 6.2.
Couch Heroes / Studio Operations / Legal and Compliance | Director duties briefing | Briefing pack for directors (Vardis, Aris, others) on Companies Act 2006 s.171-177 duties. | Not started | Medium |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | PSC register maintenance | Quarterly check that the PSC register is current. | Not started | High |  | Ongoing Mgmt | Riley/External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance Priority 5.
Couch Heroes / Studio Operations / Legal and Compliance | Companies House filing calendar | Calendar of all CH filings: CS01, AA accounts, AP01/AP03 director changes, SH01 share allotments, PSC updates. | Not started | High |  | Ongoing Mgmt | External accountant/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Business / GTM and Forecasting | Define primary player segment profile (the Explorer) | Build a full ICP for the Explorer archetype: demographics, motivations, current MMO and adventure game habits, hours per week, spend pattern, content sources, social platforms used, why they would switch from their current main, what makes them lapse. Source from vision doc plus desk research on cosy MMO and exploration RPG audiences. Output as a one page ICP card. | Not started | Critical ACT |  | Research | Glen, Vardis |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Vision doc explicitly names Explorer as the primary persona; this is the foundation for every other GTM artifact ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Define secondary player segment profile (the Socialiser) | Full ICP for the Socialiser: relationship to Discord communities, housing game enthusiasm (Animal Crossing, FFXIV housing, Sims), guild history, why they leave games, what makes social spaces sticky for them. | Not started | High |  | Research | Glen, Vardis |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Socialiser is secondary persona; housing and partner worlds are their hooks ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Define tertiary player segment profile (the Achiever, collection focused) | Full ICP for Achievers in a cosmetic only economy: motivations when there is no power gear ladder, completionist behaviour, parallels to Pokemon Go, Genshin, FFXIV glamour. | Not started | High |  | Research | Glen, Vardis |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Achiever in CH means collection completion, not gear score; this reframing is non standard and needs explicit positioning ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Define supported player segment profile (the Killer, optional PvP) | ICP for the optional PvP audience. What competitive content do we offer them, and how do we avoid bleeding competitive design into the core experience as the vision doc forbids. | Not started | Medium |  | Research | Glen, Vardis |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Killer is supported not primary; profile exists to bound design decisions, not to drive marketing spend ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Audience research wave one: cosy MMO refugees survey | Field a survey targeted at lapsed players of FFXIV, Guild Wars 2, Wildstar nostalgia communities, Palia, Wynncraft. Test response to positioning statements, art style references, corruption mechanic concept, partner worlds concept, no stat gear concept. Sample size and screening criteria need agreement. | Not started | High |  | Research | Glen, Vardis |  | ICP cards | Studio Business |  |  |  | Agent / Studio Business | Glen to confirm budget for paid panel vs organic Reddit recruitment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Audience research wave two: qualitative interviews with Explorer archetype | Run twelve to twenty depth interviews with self identified Explorer type players. Probe on what makes a world feel alive, when they last got lost in a game and why, what kills exploration for them. | Not started | High |  | Research | Glen, Vardis |  | ICP cards | Studio Business |  |  |  | Agent / Studio Business | Use customer-research skill methodology; transcripts feed back into messaging work ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Competitor map: cosy MMO and exploration RPG landscape | Comprehensive teardown of Palia, Wynncraft, FFXIV, Guild Wars 2, Genshin, Wildstar, ESO, BDO, Throne and Liberty, Pax Dei, Dune Awakening, Ashes of Creation, Fellowship, Light No Fire. For each: positioning, audience, monetisation model, retention loops, social architecture, cosmetic economy, current Steam wishlist count, last twelve months press cadence, community size. | Not started | Critical ACT |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Light No Fire and Pax Dei are closest direct comparators; this map is referenced by every other GTM doc ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Competitor positioning matrix: where Couch Heroes sits | Two by two and radar plot mapping Couch Heroes against the competitor set on axes that matter: cosy vs hardcore, social pressure level, gear power dependence, exploration depth, partner content. Identifies where the white space is and where we are crowded. | Not started | High |  | Strategy | Glen, Vardis |  | Competitor map | Studio Business |  |  |  | Agent / Studio Business | Output is a slide for studio offsite plus pitch deck ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Anti positioning statement | Explicit statement of what Couch Heroes is NOT: not a gear treadmill, not raid centric, not PvP first, not a battle pass live service, not a chosen one fantasy. Positioning is as much about disqualifying as qualifying. | Not started | High |  | Strategy | Glen, Vardis |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Vision doc gives strong material here; this saves us from chasing audiences we cannot serve ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Core positioning statement | Single paragraph positioning: for the Explorer who is tired of gear treadmill MMOs, Couch Heroes is the cosy fantasy MMORPG where the world rewards your curiosity and the adventures you have shape who you are. Tested with audience research wave one. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Audience research, anti positioning | Studio Business |  |  |  | Agent / Studio Business | Glen to sign off after wave one results land ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Three message pillars derived from positioning | Pillar one: discovery is the reward. Pillar two: identity is earned not assigned. Pillar three: the home you come back to. Each pillar gets one supporting proof point and one anti claim it knocks down. | Not started | High |  | Strategy | Glen, Vardis |  | Positioning statement | Studio Business |  |  |  | Agent / Studio Business | Pillars feed press kit, website hero copy, trailer beats ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Tagline shortlist and test | Generate twenty taglines aligned to message pillars. Test top eight with audience research panel for memorability, comprehension, differentiation. Final selection by studio leadership. | Not started | Medium |  | Strategy | Glen, Vardis |  | Message pillars | Studio Business |  |  |  | Agent / Studio Business | Avoid generic adventure copy; the corruption and partner worlds angles are the hooks ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Brand voice and tone guidelines | Document the studio voice for marketing comms: young adult, edgy but not GTA, accessible fantasy, witty about the meta of MMOs, never cynical about its own world. Include do and do not phrases, sample social posts in voice, sample press release in voice. | Not started | High |  | Implementation | Glen, Vardis |  | Positioning, message pillars | Studio Business |  |  |  | Agent / Studio Business | Vision doc explicitly says young adult tone, edgy but not PG ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Visual identity brief for marketing assets | Brief for the visual style of marketing: how the byte punk in game art translates to social tiles, trailer cards, Steam capsules, banner ads, billboards. Where the corruption visuals fit. Constraint set so a freelancer can produce on brand. | Not started | High |  | Implementation | Glen, Vardis |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Coordinates with Director of Art (David); sits across game and marketing ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Pre launch revenue forecast model: base case | Build a bottom up forecast covering wishlist conversion at launch, day one units, week one units, month one, year one. Assumptions: Steam discoverability multiplier, average price point, refund rate, regional split. Driven by analogue games selected from competitor map. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Competitor map, Steam strategy | Studio Business |  |  |  | Agent / Studio Business | This is the primary investor and board number; Glen to set price assumption ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Pre launch revenue forecast: bull and bear cases | Two additional scenarios. Bull case assumes a viral moment (signature corruption clip, big streamer), strong wishlist trajectory. Bear case assumes flat wishlist, no breakout coverage, soft launch window. Each case lists the trigger conditions. | Not started | High |  | Strategy | Glen, Vardis |  | Base case | Studio Business |  |  |  | Agent / Studio Business | Provides decision framework for marketing spend tiers ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Live service revenue model: cosmetic only economy | Forecast model for post launch revenue across cosmetic store, partner item sales, expansion content. Must reconcile with vision pillar that gear has no stats; pricing tiers for cosmetic types, expected ARPDAU, expected paying user share. | Not started | High |  | Strategy | Glen, Vardis |  | Pricing strategy | Studio Business |  |  |  | Agent / Studio Business | Cosmetic only is unusual for MMO; benchmarks from FFXIV mog station, GW2, Genshin are reference points ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Lifetime value model by player segment | LTV projection split by Explorer, Socialiser, Achiever, Killer. Driver: cosmetic spend, partner game purchases through The Platform, subscription if applicable, expansion sales. Identifies which segment we under monetise and whether that is acceptable. | Not started | High |  | Strategy | Glen, Vardis |  | Live service model, ICP cards | Studio Business |  |  |  | Agent / Studio Business | Open question: subscription vs box plus cosmetic store. Needs Glen and CEO call ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Pricing strategy for base game | Recommendation on launch price band: premium box (around forty to sixty), mid (twenty to thirty five), free to play with cosmetic store, subscription. Each option has a wishlist conversion projection, an LTV projection, a positioning implication. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Live service model | Studio Business |  |  |  | Agent / Studio Business | Decision blocks Steam page setup; needs studio leadership decision ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Pricing strategy for cosmetic store | Item tiering, currency design, bundle structure, FOMO vs evergreen mix. Must align with vision pillar that the best things are found not purchased. | Not started | High |  | Strategy | Glen, Vardis |  | Pricing for base game | Studio Business |  |  |  | Agent / Studio Business | Tension to resolve: vision says best things are discovered, but a cosmetic store needs aspirational SKUs ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Marketing budget proposal: launch window | Total budget request for the launch window with allocation across paid social, influencer, PR retainer, trade events, asset production, Steam featuring deals, regional pushes. Tied to forecast scenarios. | Not started | High |  | Strategy | Glen, Vardis |  | Forecasts | Studio Business |  |  |  | Agent / Studio Business | Glen to define the affordability ceiling; the proposal sizes against forecast ROI ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Marketing budget: ongoing live service | Monthly budget envelope post launch covering content marketing, influencer programme, seasonal events, partner game cross promo, community ops. | Not started | Medium |  | Strategy | Glen, Vardis |  | Live service forecast | Studio Business |  |  |  | Agent / Studio Business | Needs CFO input; sits alongside live ops budget on the production side ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Channel strategy: paid acquisition mix | Recommendation across Meta, TikTok, YouTube, Reddit, Twitch ads, podcast sponsorship, Twitter or X, Discord ads. For each channel: audience match score, expected CPI band, creative format, role in funnel. | Not started | High |  | Strategy | Glen, Vardis |  | ICP cards, budget proposal | Studio Business |  |  |  | Agent / Studio Business | Cosy MMO audience indexes high on TikTok and YouTube long form ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Channel strategy: organic and earned | Plan covering content marketing, dev blog cadence, devstreams, community led content, fan creator support, Reddit AMAs, Twitter or X cadence. | Not started | High |  | Strategy | Glen, Vardis |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Earned media is disproportionately important for MMO genre ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Influencer tiering and target list | Tier one (one to five million followers) Tier two (hundred thousand to one million) Tier three (under hundred thousand, high niche fit). Initial target list of forty creators across cosy gaming, MMO commentary, exploration RPG, fantasy art, Twitch variety. Each entry gets fit rationale. | Not started | High |  | Research | Glen, Vardis |  | Channel strategy | Studio Business |  |  |  | Agent / Studio Business | Overlaps with BD influencer programme; this list is the marketing layer, the BD work is the deal layer ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Launch funnel definition | Define each funnel stage from awareness through wishlist through purchase through retention through monetisation. Conversion rate assumptions per stage drawn from genre benchmarks. | Not started | High |  | Strategy | Glen, Vardis |  | Forecasts | Studio Business |  |  |  | Agent / Studio Business | Used to brief paid creative and to triage where the funnel breaks ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Wishlist target setting | Set numerical wishlist targets at six, three and one month before launch. Based on competitor analogue trajectories. Each milestone has a contingency plan if undershot. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Competitor map, launch funnel | Studio Business |  |  |  | Agent / Studio Business | Steam visibility at launch is downstream of wishlist count; this is the single most important pre launch metric ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Wishlist campaign roadmap | Campaign plan from Steam page live through launch covering announcement beats, demo events (Steam Next Fest, Day of the Devs), trailer drops, festival submissions. Each beat has expected wishlist add range. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Wishlist target | Studio Business |  |  |  | Agent / Studio Business | Steam Next Fest participation is the single biggest wishlist driver outside paid; do not miss ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Steam page strategy: copy, capsule, screenshots | Full Steam page brief: short description, long description, capsule art, header art, screenshot plan, gif plan, trailer placement, tag selection, recommended for hooks. Optimised for Steam algorithm and for the audience research messaging. | Not started | High |  | Implementation | Glen, Vardis |  | Positioning, brand voice | Studio Business |  |  |  | Agent / Studio Business | Steam page is the highest leverage page on the internet for this game ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Steam page strategy: tag and category optimisation | Research and select Steam tags balancing discoverability with audience match. Genre tag fights to win. Track tag changes and impact. | Not started | Medium |  | Research | Glen, Vardis |  | Steam page brief | Studio Business |  |  |  | Agent / Studio Business | MMORPG tag is crowded; cosy and exploration tags may serve better ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Steam Next Fest plan | Demo content plan, slot strategy, event communications, post fest analysis loop. Demo content scoped against Gamescom vertical slice. | Not started | High |  | Strategy | Glen, Vardis |  | Wishlist roadmap, Gamescom build | Studio Business |  |  |  | Agent / Studio Business | Demo must show corruption mechanic; that is the highlight reel moment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Trailer plan: announcement, gameplay, launch | Three core trailers: announcement (mood, world, hook), gameplay (combat plus traversal plus corruption plus partner worlds), launch (review quotes, tone of arrival). Each trailer has key beats, length target, music direction, deployment plan. | Not started | High |  | Strategy | Glen, Vardis |  | Brand voice, Steam page | Studio Business |  |  |  | Agent / Studio Business | Vision doc explicitly worried about visuals feeling pedestrian; trailers must lean exotic ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Trailer production briefs and vendor selection | Briefs for external trailer house. Shortlist of vendors with track record on indie and mid sized RPGs. RFP and selection. | Not started | Medium |  | Implementation | Glen, Vardis |  | Trailer plan | Studio Business |  |  |  | Agent / Studio Business | Vendor shortlist: Derek Lieu, Hyped For This, M2H, Studios Trailer Park indie team ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Press release schedule across launch window | Calendar of press releases mapped to trailer beats and milestones. Each release has angle, target outlets, embargoed assets, spokesperson assignment. | Not started | Medium |  | Strategy | Glen, Vardis |  | Trailer plan, PR media list | Studio Business |  |  |  | Agent / Studio Business | Coordinated with PR sub feature; the calendar is shared ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Demo, beta, early access decision | Strategic call on whether to do paid early access (Wynncraft, Palia model), free beta (FFXIV model), demo only. Each option has wishlist, revenue, risk implications. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Forecasts, Steam strategy | Studio Business |  |  |  | Agent / Studio Business | Glen and CEO decision; impacts every other GTM artefact ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Localisation plan | Languages at launch: minimum English; recommendation set of French, Italian, German, Spanish, Brazilian Portuguese, Russian, Simplified Chinese, Japanese, Korean. Each language with audience size, MMO genre uptake, vendor estimate. | Not started | Medium |  | Strategy | Glen, Vardis |  | Forecasts | Studio Business |  |  |  | Agent / Studio Business | Asia uptake of cosy MMO is significant; CN approval is its own track ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Region strategy: Europe focus, NA, APAC | Phased launch rollout across regions, balancing simultaneous global launch versus staggered. Each region with channel mix and partner needs. | Not started | Medium |  | Strategy | Glen, Vardis |  | Localisation | Studio Business |  |  |  | Agent / Studio Business | UK studio with EU centric story leans European primary; APAC needs partner ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Launch milestone plan: external beats | Map every external visible milestone from now to launch: trailers, festivals, conventions, betas, store updates. Master calendar shared with PR, BD, Community. | Not started | High |  | Strategy | Glen, Vardis |  | All other GTM items | Studio Business |  |  |  | Agent / Studio Business | This is the calendar the studio offsite uses to plan capacity ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Launch milestone plan: internal gates | Internal go no go gates against the external plan. What needs to be true at each gate to commit to the next external beat. | Not started | High |  | Strategy | Glen, Vardis |  | External milestone plan | Studio Business |  |  |  | Agent / Studio Business | Gates protect the studio from over commitment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Post launch year one content cadence | Content drop cadence post launch: major patch frequency, seasonal events, partner world introductions, expansion windows. Each drop has a marketing beat and a community moment attached. | Not started | Medium |  | Strategy | Glen, Vardis |  | Live service forecast | Studio Business |  |  |  | Agent / Studio Business | Vision pillar of partner world launches as biggest social moments shapes this ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Forecast tracking dashboard | Live dashboard tracking actual versus forecast on wishlist, social follower growth, press mentions, demo participants, beta sign ups. Updated weekly. | Not started | Medium |  | Implementation | Glen, Vardis |  | Forecasts, channel strategy | Studio Business |  |  |  | Agent / Studio Business | Owned by GTM lead; lives in WorkSage or Notion ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Marketing playbook compiled | Single document compiling positioning, messaging, channel strategy, calendar, budget, brand assets, voice guide, tactics. The reference any new marketing hire reads on day one. | Not started | High |  | Implementation | Glen, Vardis |  | All upstream items | Studio Business |  |  |  | Agent / Studio Business | The deliverable from this entire feature ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Crisis comms plan | Pre planned playbooks for the foreseeable bad days: server outage at launch, community manager incident, partner studio controversy, layoff news, financing news, scope cut announcement. Each has decision tree, draft statements, escalation. | Not started | Medium |  | Strategy | Glen, Vardis |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Live service games attract drama; preparation is cheap, reaction is expensive ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Genre repositioning research: cosy vs cosy MMO vs exploration RPG | Decide which genre flag to plant. Cosy MMO is becoming a category. Risks of being mislabelled either way. Wins from leaning cosy. | Not started | High |  | Research | Glen, Vardis |  | Competitor map | Studio Business |  |  |  | Agent / Studio Business | Vision doc says cosy MMORPG; need to confirm market reception of the cosy framing for an action combat game ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Founder media training programme | Train Vardis, Aris and Robin for spokesperson duty: interview technique, message pillar discipline, hostile question handling, video presence, podcast performance. | Not started | Medium |  | Implementation | Glen, Vardis |  | Brand voice, message pillars | Studio Business |  |  |  | Agent / Studio Business | Founders are the face of the studio; coverage hinges on them ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Quote bank for spokespeople | Approved quote bank by topic for press use: corruption mechanic, partner worlds, no stat gear, social architecture, single player first. | Not started | Medium |  | Implementation | Glen, Vardis |  | Founder media training | Studio Business |  |  |  | Agent / Studio Business | Lets press extract quotes without misquoting; speeds inbound coverage ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Awards strategy | Map of award programmes (BAFTA, Develop, GDCA, IGF, Indie Megabooth, Indie Cade) with submission windows, entry fees, fit assessment. | Not started | Medium |  | Strategy | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Coordinated with PR; awards drive press cycles ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Steam Festivals and storefront feature plan | Map of every Steam discoverability moment beyond Next Fest: themed sales, daily deals, hub features, curator programme. Each one has a fit and submission plan. | Not started | Medium |  | Strategy | Glen, Vardis |  | Steam page brief | Studio Business |  |  |  | Agent / Studio Business | Steam featured slots are a relationship business with Valve ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | KPI definition for marketing function | Define the metrics marketing is accountable for: wishlist count, wishlist quality (conversion at launch), media share of voice, follower growth, sentiment score, paid CPI, organic share, attributed sales. Targets per quarter. | Not started | High |  | Strategy | Glen, Vardis |  | All other GTM items | Studio Business |  |  |  | Agent / Studio Business | Without KPIs, this entire backlog is theatre ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Build target publishing partner longlist | Generate a longlist of around forty publishers across full publishing partners, marketing only deals, regional partners, platform first parties. Each entry: track record, recent deals, MMO history, cosy genre history, financial health, strategic fit. | Not started | High |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Hooded Horse, Devolver, 505, Krafton, Tencent (Level Infinite), NetEase, Embracer remnants, Iceberg, PLAION, Kepler, Coffee Stain Publishing among likely fits ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Publisher fit and shortlist | Score the longlist against criteria: capital fit, audience fit, MMO and live service capability, partner game enthusiasm, contractual reasonableness, recent successes vs failures. Shortlist of ten. | Not started | High |  | Strategy | Glen, Vardis |  | Publisher longlist | Studio Business |  |  |  | Agent / Studio Business | Live service MMO is a small subset of publisher capability; shortlist will be smaller than expected ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Publisher pitch deck | Sales deck targeting publishers: vision, team, market opportunity, traction, monetisation model, partner worlds upside, ask. Tuned by deal type (full publish vs marketing only vs regional). | Not started | Critical ACT |  | Implementation | Glen, Vardis |  | Forecasts, positioning | Studio Business |  |  |  | Agent / Studio Business | Glen has gi skill assets and pitch deck experience; reuse and adapt ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Publisher data room build | Diligence ready data room: cap table, team CVs, GDD, milestones, financials, build access, demo access, telemetry plan, IP ownership, partner agreements. | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Greenlight Glen on which fields are commercially sensitive vs share early ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Publisher outreach campaign | Structured outreach with personalised pitch to top ten publishers. Track first contact, first meeting, second meeting, term sheet stage, decision. CRM hygiene. | Not started | High |  | Implementation | Glen, Vardis |  | Publisher pitch deck, data room | Studio Business |  |  |  | Agent / Studio Business | Apollo or Pipedrive for tracking; Glen approves all outbound external messages ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Term sheet template and red lines | Studio side template term sheet with our preferred terms and a documented red lines list (recoupment caps, IP retention, sequel rights, key person clauses). | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Built with legal counsel; reuse across publisher discussions ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Decision framework: publish vs self publish | Quantitative and qualitative comparison of self publishing vs publisher deal. Inputs: capital available, team capacity for marketing, publisher economics, control. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Forecasts, term sheet template | Studio Business |  |  |  | Agent / Studio Business | Decision belongs to CEO and board; BD prepares the paper ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Steam platform onboarding | Set up Steamworks, configure store presence, set up build pipeline, set up partner billing, set up Steam Direct, register all team accounts. | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Required regardless of publisher decision ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Steam playtest and demo configuration | Configure Steam playtest gating, demo branch, password protected builds for press, key issuance via Keymailer or similar. | Not started | Medium |  | Implementation | Glen, Vardis |  | Steam onboarding | Studio Business |  |  |  | Agent / Studio Business | Operational; coordinates with PR keys distribution ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Epic Games Store onboarding | Apply for Epic Store presence, evaluate exclusivity offer if extended, set up Epic Online Services if used. | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Epic exclusivity offers are publishing relationships; coordinated with publisher decision ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | GOG submission and assessment | Evaluate GOG fit (DRM free), submission, marketing benefit. | Not started | Low |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Smaller revenue but cult audience for fantasy RPG ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | PlayStation submission programme | Apply for SIE developer status, submit concept for PS5 evaluation, plan certification, identify required middleware compliance, plan first party feature support (DualSense, Activities). | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | First party submissions take time; start the registration well before it is needed ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Xbox submission programme (ID@Xbox or full developer) | ID@Xbox application, evaluate full developer status, plan certification, plan Game Pass discussion. | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Game Pass for an MMO is a strategic discussion; sits alongside publisher decision ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Switch 2 submission programme | Nintendo developer registration, evaluate fit (Switch 2 hardware capability vs MMO requirements), plan certification approach. | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Switch 2 capability for MMO scope is unconfirmed; flag for studio Tech (Mustafa) input ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Cross play and account model decision | Decision on whether the game supports cross play across platforms and how player accounts unify (publisher account vs platform account vs both). | Not started | High |  | Strategy | Glen, Vardis |  | First party submissions | Studio Business |  |  |  | Agent / Studio Business | Cross play is a vision pillar future state; structural decisions need to be made early to avoid platform rebuild later ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Hardware partner outreach (controllers, peripherals) | Hardware brand partnerships: gamepads, headsets, RGB. Co marketing potential and bundle potential. | Not started | Low |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Logitech G, Razer, SteelSeries, 8BitDo are the obvious fits; co marketing is cheaper than pure cash deals ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Hardware partner outreach (PC OEMs) | PC OEM partnerships: Asus ROG, MSI, Alienware, Lenovo Legion. Bundle potential with launch SKUs. | Not started | Low |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | OEM bundles are typically post launch when retail can move them ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Co marketing pipeline framework | Standard process for co marketing deals: opportunity intake, fit scoring, deal structure templates, asset exchange, measurement. | Not started | Medium |  | Implementation | Glen, Vardis |  | Brand assets | Studio Business |  |  |  | Agent / Studio Business | Without a framework every deal becomes bespoke and slow ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Distribution partnerships outside Steam (key resellers) | Decisions on Humble, Fanatical, Green Man Gaming, Epic Direct distribution. Greylist of grey market resellers we will not work with. | Not started | Low |  | Strategy | Glen, Vardis |  | Steam onboarding, Epic onboarding | Studio Business |  |  |  | Agent / Studio Business | Grey market is a long running headache for live service; decide policy now ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Influencer programme structure | Tiered programme design: founder creators (long term partners), launch creators (campaign tier), seeded creators (key drops). Contracts, exclusivity, deliverables. | Not started | High |  | Strategy | Glen, Vardis |  | Influencer target list | Studio Business |  |  |  | Agent / Studio Business | Coordinates with GTM influencer list; this is the deal layer ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Influencer outreach to top tier (Tier one) | Direct outreach to top tier creators with bespoke pitch, demo access, founder call offer. Maximum five at a time to manage relationship quality. | Not started | High |  | Implementation | Glen, Vardis |  | Influencer programme structure | Studio Business |  |  |  | Agent / Studio Business | Top tier creator buy in is the single biggest organic accelerant; do this well or skip it ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Influencer outreach mid tier | Tier two and three outreach. Volume game with a structured ask: demo key, talking points, drop window, asset pack. | Not started | Medium |  | Implementation | Glen, Vardis |  | Influencer programme structure | Studio Business |  |  |  | Agent / Studio Business | Volume management means a CRM and clear template messaging ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Streamer programme: live launch coverage | Programme to lock in coverage for launch day: paid talent, organic talent, embed support, day one bug response. | Not started | High |  | Implementation | Glen, Vardis |  | Influencer programme structure | Studio Business |  |  |  | Agent / Studio Business | Launch day livestream coverage shapes wishlist conversion through reviews window ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Tournament partnerships and esports stance | Position on whether the optional PvP gets a competitive scene. If yes, partnerships with tournament organisers and broadcasters. If no, declare it. | Not started | Low |  | Strategy | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Vision doc says PvP is supported not central; default position is no formal esports ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Partner game integration deal pipeline | The signature BD work for Couch Heroes: pipeline of partner studios whose games integrate as portals. Outreach list, deal templates, technical onboarding spec, revenue share model, exclusivity terms. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Partner worlds is a defining pillar; this pipeline is unique to Couch Heroes and central to the live service hypothesis ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Partner game target longlist | Identify thirty partner game candidates across indie and mid scale studios whose IP fits the byte punk world: roguelikes, mini RPGs, puzzle games, racing, narrative shorts, retro arcade. | Not started | High |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | First wave should be friendly indie studios with low integration cost; later waves can be bigger names ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Partner game integration tech spec for partners | Public facing technical brief for partner studios: API spec, art constraints, integration cost, certification process, IP rights, marketing commitments. The thing that lets a partner studio say yes without a sales call. | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Head of Tech (Mustafa); turns BD work into a self serve funnel ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Partner game contract template | Standard partner integration agreement: rev share, marketing obligations, certification, IP carve outs, term, termination, dispute resolution. | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Built with legal counsel; expected to evolve over the first ten partner deals ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | First five partner game deals: targeted outreach | Hand picked first five partner game deals chosen for buzz, fit, and case study value. Personal outreach by founders. | Not started | Critical ACT |  | Implementation | Glen, Vardis |  | Partner pipeline, contract template | Studio Business |  |  |  | Agent / Studio Business | The first five partners are a marketing story; pick studios people will write about ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Partner discovery showcase format | Plan for the first partner game showcase event (in game or external) where partner studios are presented to the community. | Not started | Medium |  | Strategy | Glen, Vardis |  | Partner deals | Studio Business |  |  |  | Agent / Studio Business | Partner showcases become ongoing social moments per the vision doc ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Brand and IP partnerships outreach (non game) | Non gaming brand partnerships for crossovers: music labels, streetwear, animation studios, food brands. Targeted at the cosy Explorer audience. | Not started | Low |  | Implementation | Glen, Vardis |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Genshin and FFXIV cross brand activations are the model ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Investor pipeline (BD adjacent) | Maintain investor list for follow on rounds: gaming VCs, family offices, strategic LPs. Updates and check ins. | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Glen has gi skill and investor materials; this is the BD touchpoint not the deck building ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Government grant and tax relief programmes | UK Video Games Tax Relief, UK Games Fund, Innovate UK, Creative Europe (depending on scope), Horizon Europe. Applications and compliance. | Not started | High |  | Research | Glen, Vardis |  | Studio company structure | Studio Business |  |  |  | Agent / Studio Business | UK VGTR is material to the financials; do not miss ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Banking and financial services partnerships | Strategic banking relationships, payment processors (Stripe, Xsolla, Adyen), foreign exchange, transaction cost negotiation. | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Operational rather than strategic but adds up at scale ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Localisation vendor selection | Vendor shortlist for localisation: Keywords, Side, Lionbridge Games, Native Prime, Lokalise, plus indie LQA shops. Selection by language coverage, MMO experience, price. | Not started | Medium |  | Research | Glen, Vardis |  | Localisation plan in GTM | Studio Business |  |  |  | Agent / Studio Business | Coordinated with GTM localisation plan ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | QA outsource partner selection | If internal QA is supplemented, vendor shortlist for outsource QA: PTW, Keywords, Testronic, Lionbridge Games. | Not started | Medium |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Live service launch QA spike usually exceeds in house capacity ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Customer service partner selection | Vendor shortlist for player support: Keywords Helpshift, Helpshift direct, 5CA, customer support specialists. Required volume scaling. | Not started | Medium |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Player support is non trivial for an MMO; underbudgeting here is a known live service mistake ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Anti cheat and trust partner selection | Anti cheat vendor decision: Easy Anti Cheat, BattlEye, in house. Plus account fraud, payment fraud, content moderation tooling. | Not started | Medium |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Cosy MMO with PvP optional reduces but does not eliminate cheat risk ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Media buy agency relationship | Performance marketing agency relationship for paid acquisition. Shortlist of agencies with games experience. Or in house build. | Not started | Medium |  | Strategy | Glen, Vardis |  | Channel strategy | Studio Business |  |  |  | Agent / Studio Business | In house is cheaper at scale; agency is faster to start ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Convention and trade show booth contracts | Booth contracts and partner negotiations for Gamescom, GDC, PAX, EGX. Includes shared booth opportunities and indie hubs. | Not started | High |  | Implementation | Glen, Vardis |  | PR conference plan | Studio Business |  |  |  | Agent / Studio Business | Coordinated with PR conference plan; this is the contractual layer ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Contract pipeline tracking | CRM or pipeline tracker for all BD activity: each deal gets stage, value, probability, next action, owner. Reviewed weekly. | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | BD without a pipeline tracker is an open invitation to drop deals ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | BD KPI definition | Define metrics for BD: deals closed, partners onboarded, partner game integrations live, platform certifications complete, key contract renewals. | Not started | Medium |  | Strategy | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Without KPIs the BD function is invisible to leadership ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press kit core build | Studio and game press kit: logo pack, key art, screenshots, gif loops, b roll, fact sheet, founder bios, headshots, quote bank, reviewer guide, embed code. Hosted on a press portal. | Not started | Critical ACT |  | Implementation | Glen |  | Visual identity, brand voice | Studio Business |  |  |  | Agent / Studio Business | Press kit absence kills inbound press cycles; must exist before any major announcement ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press kit fact sheet | One pager with all the critical facts: studio location, founding date, team size, platforms, genre, release window, USPs, contact. The thing journalists copy and paste from. | Not started | High |  | Implementation | Glen |  | Press kit core | Studio Business |  |  |  | Agent / Studio Business | Use Couch Heroes Vision doc, vision pillars, batch handoff doc ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Reviewer guide | Document for press explaining what is in the build, what is intentionally absent, what to focus reviews on, known issues, embargo terms. | Not started | High |  | Implementation | Glen |  | Press kit core | Studio Business |  |  |  | Agent / Studio Business | Sets press expectations; reduces unfair review framing ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Story angles document | Living document of pitchable story angles by outlet type: corruption mechanic depth dive, no stat MMO economy, partner worlds as platform, cosy MMO category builders, UK studio profile, founder background. | Not started | High |  | Implementation | Glen |  | Positioning | Studio Business |  |  |  | Agent / Studio Business | Each angle is matched to outlet type; some only fit trade press, some fit consumer press ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press release template and approval flow | Template for press releases with approval flow (Glen, CEO, CMO equivalent). Boilerplate at bottom. Assets attached separately. | Not started | Medium |  | Implementation | Glen |  | Press kit core | Studio Business |  |  |  | Agent / Studio Business | Reuse across announcements ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Studio launch communications plan | If studio has not had a public launch yet (and the vision doc material suggests low public profile), build the announcement plan: founder story, mission, hiring, vision teaser. | Not started | High |  | Strategy | Glen |  | Studio naming, brand voice | Studio Business |  |  |  | Agent / Studio Business | Glen to confirm whether studio has been formally announced; if not this is the first major PR moment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: tier one games trade list | Tier one list with named contacts: GamesIndustry.biz, Edge, Eurogamer, IGN, Polygon, Kotaku, PC Gamer, RPS, Game Developer, GDC press team, Gamesradar. | Not started | High |  | Research | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Tier one tracks studio profile and major beats; relationships not transactions ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: MMO and RPG specialist outlets | Specialist list: MMORPG.com, Massively OP, MMO Fallout, RPG Site, RPGFan, PCGamesN MMO desk, MMO Champion, plus YouTube and podcast equivalents. | Not started | High |  | Research | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | These outlets are where genre fans actually live; conversion to wishlist is high ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: cosy and lifestyle gaming list | Outlets and creators in the cosy gaming space: Cozy Gamer, NookNet for Animal Crossing crossover, lifestyle creators on YouTube, dedicated podcasts. | Not started | High |  | Research | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Cosy MMO is an emerging category; creator friendships in this space are gold ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: regional press (UK and EU) | UK trade and consumer press, plus French, German, Polish, Spanish equivalents. | Not started | Medium |  | Research | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | UK studio means UK trade coverage is structurally easier; do not waste it ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: APAC press | Famitsu, 4Gamer, Inven, Bahamut, IGN Japan, Game Watch. Likely needs partner or local PR support. | Not started | Medium |  | Research | Glen |  | Regional strategy | Studio Business |  |  |  | Agent / Studio Business | Coordinated with localisation plan and regional partner work in BD ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: streamer press hybrids | YouTube journalists and dedicated commentators: Force Gaming, Asmongold (with care given the pillar tone), Josh Strife Hayes, NoClip, IGN First, Game Maker's Toolkit. | Not started | Medium |  | Research | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Long form video commentary is the high value PR slot for MMO genre ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Embargo policy | Standard embargo terms by content type. Process for handling break embargoes. Outlet specific exclusives policy. | Not started | Medium |  | Implementation | Glen |  | Press relationships | Studio Business |  |  |  | Agent / Studio Business | Without policy embargoes get botched; basic asset ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Exclusive coverage strategy | Pre planned exclusive opportunities by beat: announcement to one outlet, gameplay reveal to another, deep dive to a specialist. Tradeoffs and rules. | Not started | High |  | Strategy | Glen |  | Press relationships, story angles | Studio Business |  |  |  | Agent / Studio Business | Exclusives are how trade press relationships are kept warm ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Spokesperson assignment matrix | Which founder or team lead speaks on which topic. Robin on game design and pillars, Vardis on studio mission, David on art direction, Mustafa on tech and partner integration, Valeria on production, Lorenz on hiring story, Glen on commercial strategy. | Not started | Medium |  | Strategy | Glen |  | Founder media training | Studio Business |  |  |  | Agent / Studio Business | Topic ownership prevents off message comments ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Founder profile pieces strategy | Targeted founder profile pitches to outlets that do them: Edge, GamesIndustry.biz, Game Developer. Pre seeded narrative, photoshoot, anchor topic. | Not started | Medium |  | Strategy | Glen |  | Spokesperson matrix | Studio Business |  |  |  | Agent / Studio Business | Founder profiles drive perception of studio quality and improve hiring funnel ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: GDC | GDC participation: talks submitted, side meetings, networking events, parties, recruiting. | Not started | High |  | Strategy | Glen |  | Founder media training | Studio Business |  |  |  | Agent / Studio Business | GDC is the industry relationship cycle; non negotiable for live service ambition ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: Gamescom | Gamescom strategy across business and consumer halls. Booth, partner meetings, press briefings, livestream slots. | Not started | Critical ACT |  | Strategy | Glen |  | Booth contracts | Studio Business |  |  |  | Agent / Studio Business | Gamescom is the studio's stated next milestone; this is the high stakes external moment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: PAX | PAX (PAX East, West, Aus, Online) participation: Indie Megabooth, panels, signings, fan engagement. | Not started | Medium |  | Strategy | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | PAX is more consumer oriented; great for community moments ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: EGX | EGX UK presence given studio is UK based. Local press flock here. | Not started | Medium |  | Strategy | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | EGX London is a structural advantage for UK studio ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: GDC Europe and Develop Brighton | Develop Brighton, Reboot Develop, Pocket Gamer Connects (if mobile platform component grows). | Not started | Low |  | Strategy | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | UK conferences for trade and recruiting ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: TGS, BitSummit | Tokyo Game Show and BitSummit if APAC presence develops. Likely partner needed. | Not started | Low |  | Strategy | Glen |  | APAC strategy | Studio Business |  |  |  | Agent / Studio Business | Coordinated with regional plan ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Award submissions tracker | Schedule of award submissions: BAFTA, GDCA, IGF, IndieCade, Develop, MCV, Mwave, Develop Star, Independent Games Festival, Webby. With deadlines and submission formats. | Not started | Medium |  | Implementation | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Awards drive press cycles even when you do not win ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Trade events and side events plan | Side events at major shows: Day of the Devs, Future Games Show, Future of Play Direct, Wholesome Direct, Guerrilla Collective, MIX, Devolver Direct equivalents. | Not started | High |  | Strategy | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Wholesome Direct is the bullseye event for cosy positioning; do not miss ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Case study programme: feature dev blogs | Long form dev blog series unpacking each pillar: how corruption works, why no stat gear, how partner worlds integrate. Quotable, screenshotable, reblogable. | Not started | High |  | Implementation | Glen |  | Brand voice, content strategy | Studio Business |  |  |  | Agent / Studio Business | Dev blogs serve PR cycles, hiring funnel, and community engagement simultaneously ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Case study programme: postmortems | Public postmortem cadence: closed beta postmortem, Steam Next Fest postmortem, launch postmortem. Builds reputation for professionalism. | Not started | Low |  | Implementation | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Postmortems differentiate at GDC and Game Developer the publication ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Blog cadence (PR sliver) | Editorial calendar for studio blog: weekly cadence target, content slots (dev blog, community spotlight, partner game profile, behind the scenes). | Not started | Medium |  | Strategy | Glen |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Community feature; blog is dual owned ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Podcast appearance plan | Target podcasts for founder appearances: NoClip (NoClip Podcast), GamesIndustry.biz Microcast, IGN Unfiltered, Triple Click, Friends Per Second, Defining Duke, MMOpinions, Game Maker's Notebook. | Not started | Medium |  | Implementation | Glen |  | Spokesperson matrix | Studio Business |  |  |  | Agent / Studio Business | Long form audio reaches the deep audience ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Crisis communications plan (PR layer) | Specific PR plays during crisis: holding statements, escalation contact tree, response time targets, social vs media split. | Not started | High |  | Strategy | Glen |  | GTM crisis comms | Studio Business |  |  |  | Agent / Studio Business | Lives alongside GTM crisis comms but with PR specific tactics ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Reactive PR monitoring | Daily monitoring for press mentions, social mentions, review aggregators. Alert thresholds and triage process. | Not started | Medium |  | Implementation | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Mention.com, Brand24, or similar tooling; coordinated with community sentiment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Quarterly press briefings rhythm | Off the record quarterly briefings with tier one press once a relationship cadence is established. Maintains presence between announcement beats. | Not started | Low |  | Strategy | Glen |  | Press relationships | Studio Business |  |  |  | Agent / Studio Business | The thing that keeps trade press warm in quiet periods ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Localisation of press materials | Translated press kits for FR, DE, ES, IT, JP, KR, ZH plus regional adaptation. | Not started | Medium |  | Implementation | Glen |  | Localisation, press kit | Studio Business |  |  |  | Agent / Studio Business | Localisation skip is the most common PR mistake at international launch ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press portal build (web) | The actual web destination for press: press portal page, asset downloads, press kit download, contact form, account requests for embargoed material. | Not started | High |  | Implementation | Glen |  | Website iteration, press kit core | Studio Business |  |  |  | Agent / Studio Business | Coordinated with website feature; this is the press facing surface ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | PR agency assessment and hire (or in house decision) | Decision on whether to retain a PR agency (Plan of Attack, Stride PR, Renaissance PR, Sandbox Strategies, Hooch and Bish, ICO Partners) or build in house. Each path scoped. | Not started | High |  | Strategy | Glen |  | Budget proposal | Studio Business |  |  |  | Agent / Studio Business | Glen and CEO call; PR agency selection drives all the relationship work ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | KPI definition for PR function | Metrics: tier one mentions, share of voice vs competitor set, sentiment, founder speaking slots, press portal traffic, asset downloads. | Not started | Medium |  | Strategy | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Without KPIs PR is invisible to leadership and gets cut first when budgets shrink ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry analyst relationships | Newzoo, Niko Partners, Omdia, DFC, Ampere. Briefings on the studio and category. | Not started | Low |  | Implementation | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Analyst briefings shape industry conventional wisdom; a long term play ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Discord server architecture | Channel structure design: announcements, general, regional channels, role channels, partner game channels, support, suggestions, lore corner, fan creators, voice rooms. Permission roles. | Not started | Critical ACT |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Discord is the primary community platform for MMO genre; the architecture decision sets a multi year context ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Discord onboarding flow | Welcome flow for new members: role selection, code of conduct accept, channel guide, links to game store and website. Bot configuration. | Not started | High |  | Implementation | Glen, Barb |  | Discord architecture | Studio Business |  |  |  | Agent / Studio Business | Onboarding flow is the difference between active community and ghost server ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Discord moderation policy and tools | Code of conduct, escalation procedure, banned content list, mod team structure (volunteer vs staff), moderation tools (auto mod, MEE6, Carl bot, custom), audit trail. | Not started | High |  | Implementation | Glen, Barb |  | Discord architecture | Studio Business |  |  |  | Agent / Studio Business | Cosy community attracts harassment; tone moderation protects the audience the studio promises ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Discord bots and integrations | Selection and configuration of bots: moderation, roles, levels, partner game widgets, Twitch integration, Twitter or X integration, GitHub or status integration. | Not started | Medium |  | Implementation | Glen, Barb |  | Discord architecture | Studio Business |  |  |  | Agent / Studio Business | Bots multiply moderator productivity; under invest and Barb burns out ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Discord server launch event | Launch event for the Discord with founder Q&A, sneak peek content, server tier rewards. | Not started | Medium |  | Implementation | Glen, Barb |  | Discord architecture | Studio Business |  |  |  | Agent / Studio Business | Soft launch first to test, then external announcement ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community calendar template and rhythm | Annual community calendar template: weekly standing items (developer streams, community spotlight, art Friday), monthly items (Q&A, contest, partner spotlight), seasonal events. | Not started | High |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Calendar is the operating system for Community function ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community Manager onboarding plan: Barb specifically | Specific 30 day plan for Barb (10 hours per week): tools access, brand voice training, escalation paths, content authorisation matrix, schedule template, check in cadence with Glen. | Not started | Critical ACT |  | Implementation | Glen, Barb |  | Brand voice, Discord architecture | Studio Business |  |  |  | Agent / Studio Business | Barb is the only Community headcount; her onboarding determines the whole function's success ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community Manager scope sheet (10 hr/week constraint) | Explicit list of what Barb does and what she does not. With ten hours per week the scope must be ruthlessly bounded; everything else needs an owner or stays undone. | Not started | Critical ACT |  | Implementation | Glen, Barb |  | Barb onboarding | Studio Business |  |  |  | Agent / Studio Business | Without a scope sheet ten hours becomes thirty in chaos; this is a protective document for Barb ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community Manager content authorisation matrix | What Barb can post without approval, what needs Glen sign off, what needs founder sign off. Speed of comms matters. | Not started | High |  | Implementation | Glen, Barb |  | Barb onboarding, brand voice | Studio Business |  |  |  | Agent / Studio Business | Stops the bottleneck of every post needing approval while protecting brand ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community Manager working tools setup | Tooling: Discord access, Twitter or X scheduler (Buffer, Hypefury), Twitch creator account, Reddit account, scheduling tool (Notion or Asana), analytics dashboard. | Not started | High |  | Implementation | Glen, Barb |  | Barb onboarding | Studio Business |  |  |  | Agent / Studio Business | Tools save hours; specifically scoped because Barb has ten of them ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Forum platform decision | Whether to run a forum (Discourse, in house, Reddit reliance only) or stick with Discord plus Reddit only. Each option has scaling implications. | Not started | Medium |  | Strategy | Glen, Barb |  | None | Studio Business |  |  |  | Agent / Studio Business | Forum is heavyweight; Reddit plus Discord is the modern default but loses search SEO benefits ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Reddit subreddit setup and moderation | Set up r/CouchHeroes (or studio renamed equivalent). Reserve username, define rules, recruit volunteer moderators, partnership with subreddit team. | Not started | High |  | Implementation | Glen, Barb |  | Studio naming | Studio Business |  |  |  | Agent / Studio Business | Reserving the subreddit early is critical; if a fan claims it first the dynamics get complicated ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Reddit engagement plan | Editorial plan for the studio's Reddit presence: AMAs, dev posts, response cadence, raid the leaderboard moments, weekly community threads. | Not started | High |  | Strategy | Glen, Barb |  | Reddit setup, brand voice | Studio Business |  |  |  | Agent / Studio Business | Reddit converts harder than Twitter for MMO genre ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Twitter or X engagement plan | Posting cadence, thread strategy, response policy, reply guy cadence, art share programme, partner studio amplification. | Not started | High |  | Strategy | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Despite churn, X remains where games trade press lives; cannot abandon ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Bluesky and Threads presence | Decision and execution on secondary social platforms. Rising audiences but smaller. | Not started | Low |  | Strategy | Glen, Barb |  | None | Studio Business |  |  |  | Agent / Studio Business | Cheap to maintain a presence; early moves can build follow before peers ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | TikTok strategy | Content strategy for TikTok: short clip plan, partner with creators, repurposing of trailer footage, behind the scenes vlogs. | Not started | Medium |  | Strategy | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | TikTok indexes high for cosy gaming audience and is a wishlist driver ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | YouTube channel strategy | Channel content plan: trailer drops, dev diaries, longform interviews, partner game spotlights, lore deep dives, livestream archives. | Not started | Medium |  | Strategy | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | YouTube is the long term content compounding asset ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Instagram presence | Instagram account for art and photo mode community. Lower priority but cheap to maintain. | Not started | Low |  | Strategy | Glen, Barb |  | None | Studio Business |  |  |  | Agent / Studio Business | Photo mode in vision; Instagram is the natural surface ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Player Q&A cadence (text and live) | Monthly text Q&A on Reddit. Quarterly live Q&A on stream. Semi annual founder Q&A. Each format with format brief and prep checklist. | Not started | High |  | Strategy | Glen, Barb |  | Spokesperson matrix | Studio Business |  |  |  | Agent / Studio Business | Q&A is the trust building ritual; consistency matters more than scale ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Beta tester programme: structure | Programme tiers: closed alpha (under 100), playtest (around 100, vision doc says Q1 2026), public alpha (Q4 2026 vision doc), beta. Each with selection criteria, NDA terms, feedback channels, reward for participation. | Not started | Critical ACT |  | Strategy | Glen, Barb |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Vision doc has explicit playtest milestones; the community structure for those needs to exist before the milestones ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Beta tester programme: selection process | Application form, scoring criteria, communication cadence with applicants, waitlist management. | Not started | High |  | Implementation | Glen, Barb |  | Beta programme structure | Studio Business |  |  |  | Agent / Studio Business | Applications come in floods; without a process the founders end up answering DMs ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Beta tester NDA and feedback policy | Standard NDA template. Public communication policy. Reward for adherence. Removal policy for breach. | Not started | High |  | Implementation | Glen, Barb |  | Beta programme structure | Studio Business |  |  |  | Agent / Studio Business | Built with legal counsel; reuse across all programme tiers ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Closed alpha logistics | Specific logistics for the first closed alpha: build distribution mechanism, feedback survey, bug report flow, weekly live chats with testers. | Not started | High |  | Implementation | Glen, Barb |  | Beta programme structure | Studio Business |  |  |  | Agent / Studio Business | The first closed alpha is a tone setter for the community's relationship with the dev team ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Developer streams cadence and format | Format design for studio streams: weekly producer update, monthly design deep dive, quarterly all hands stream, ad hoc partner game showcases. | Not started | High |  | Strategy | Glen, Barb |  | Spokesperson matrix | Studio Business |  |  |  | Agent / Studio Business | Vision doc emphasises community visibility; dev streams are how it manifests ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Twitch channel setup | Studio Twitch channel configuration: branding, panels, scheduling, raid programme, mod team. | Not started | Medium |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | The home for live streams; coordinated with YouTube for archival ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Streamer toolkit and assets | Toolkit for partnered streamers: overlays, alerts, sound packs, drops campaign assets. Lowers friction for creators to look on brand. | Not started | Medium |  | Implementation | Glen, Barb |  | Visual identity | Studio Business |  |  |  | Agent / Studio Business | Used in BD influencer outreach; reduces creator effort ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Drops campaign design | Twitch Drops, YouTube Gaming drops, partner game cross drops. Reward design that respects vision pillar of best things found not bought. | Not started | Medium |  | Strategy | Glen, Barb |  | Cosmetic store, BD influencer | Studio Business |  |  |  | Agent / Studio Business | Drops fuel coverage at minimal cost when designed right ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Fan art programme | Structured fan art programme: monthly themes, weekly highlights, official cosmetic inspired by player art, attribution and consent flow. | Not started | Medium |  | Strategy | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Fan art communities create marketing asset surplus; explicit recognition keeps them feeding the brand ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Fan creator support programme (broader than streamers) | Programme for cosplayers, fan fiction writers, machinima makers, content creators outside Twitch and YouTube. Asset access, recognition, occasional sponsorship. | Not started | Low |  | Strategy | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Cosy MMO genre attracts diverse creator types; recognise them or watch them defect ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Player Council programme | A formal player council of around twenty engaged players with regular access to dev team, advance preview of features, structured feedback channel. | Not started | Medium |  | Strategy | Glen, Barb |  | Beta programme | Studio Business |  |  |  | Agent / Studio Business | Ditto Genshin's Honkai survey programme model; converts passion to retention ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community moderation training and resources | Training material for volunteer moderators across Discord, Reddit, forum if applicable. Recognition and rewards for mods. | Not started | Medium |  | Implementation | Glen, Barb |  | Discord moderation policy | Studio Business |  |  |  | Agent / Studio Business | Volunteer moderators do the bulk of community ops; train them or watch the community degrade ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Code of conduct (player facing) | Public player facing code of conduct: harassment, hate speech, cheating, exploit reporting, DMCA. Consistent across game, Discord, Reddit, forums. | Not started | High |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Cosy positioning means the community expects high standards; this document is the floor ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Reporting and ban appeal flow | Player facing reporting of misconduct. Studio facing review process. Appeal flow with documented criteria. | Not started | Medium |  | Implementation | Glen, Barb |  | Code of conduct | Studio Business |  |  |  | Agent / Studio Business | Operational; gets used more than expected at MMO scale ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community sentiment dashboard | Dashboard tracking sentiment across Discord, Reddit, Twitter, Steam reviews, press. Weekly summary to founders. | Not started | Medium |  | Implementation | Glen, Barb |  | Reactive PR monitoring | Studio Business |  |  |  | Agent / Studio Business | Coordinates with PR monitoring tooling ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Partner game cross promo cadence | Calendar of cross promotional moments with partner game studios: their players in our community channels, our players in theirs, joint events. | Not started | High |  | Strategy | Glen, Barb |  | BD partner deals | Studio Business |  |  |  | Agent / Studio Business | Vision doc identifies partner world launches as biggest social moments; this is the operational layer ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Seasonal event playbook | Template for seasonal community events: holiday themes, in game tie ins, social posts, community contests, partner participation. | Not started | Medium |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Reusable templates save Barb's hours ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | New player welcome programme | Programme to welcome new players post launch: in game greeting, Discord welcome, mentor programme connecting new players to veterans. | Not started | Low |  | Strategy | Glen, Barb |  | Discord onboarding | Studio Business |  |  |  | Agent / Studio Business | Vision pillar of voluntary social makes mentor programmes natural fits ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Lapsed player win back programme | Programme to win back lapsed players: communications cadence, return events, comeback rewards, content reintroduction. | Not started | Low |  | Strategy | Glen, Barb |  | Live service forecast | Studio Business |  |  |  | Agent / Studio Business | Costs a fraction of acquisition; high ROI in live service ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community Manager handover document | Document built so that if Barb leaves or is unavailable, another person can step in without everything stopping. | Not started | Medium |  | Implementation | Glen, Barb |  | Barb onboarding | Studio Business |  |  |  | Agent / Studio Business | Bus factor protection; Glen has feedback_verify_work principles relevant here ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community KPI definition | Metrics: Discord MAU, Reddit subscribers, sentiment score, response time, retention proxy via community participation. | Not started | Medium |  | Strategy | Glen, Barb |  | Sentiment dashboard | Studio Business |  |  |  | Agent / Studio Business | Without KPIs the function is invisible at leadership level ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community resource library (player wiki seed) | Seed structured resources to support the inevitable player wiki: character model, location guides, partner studio bios, dev team intros. Often the wiki community organises around these. | Not started | Low |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Wikis form whether the studio supports them or not; better to seed them ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Live ops community calendar (post launch) | Post launch event calendar covering seasonal events, partner showcases, in game contests, community initiated events. | Not started | Medium |  | Strategy | Glen, Barb |  | Community calendar template | Studio Business |  |  |  | Agent / Studio Business | Coordinated with live ops production calendar ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community manager succession and scaling plan | Plan for when ten hours per week becomes insufficient: triggers for adding hours, hire criteria for second CM, regional CM expansion at international launch. | Not started | Medium |  | Strategy | Glen, Barb |  | Barb onboarding | Studio Business |  |  |  | Agent / Studio Business | Recognise that at launch the function will need more headcount; pre plan ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Audit current website (the one that is being replaced) | Documented audit of current site: pages, content, traffic, SEO state, brand consistency, mobile state, conversion paths, technical debt. Output is a teardown that informs the next iteration. | Not started | High |  | Research | Mustafa, Glen |  | Existing site | Studio Business |  |  |  | Agent / Studio Business | Glen says current site is pretty terrible; the audit document the why so the next iteration does not repeat mistakes ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Status of in flight site rebuild | Document the current state of the three month full stack rebuild. What is shipped, what is broken, what is missing, what was scope cut, what the dev team owner thinks the next iteration needs. | Not started | Critical ACT |  | Research | Mustafa, Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Glen says step up iteration but needs further iteration; this audit lights the path ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Site architecture and information architecture | Full site map: top nav, page hierarchy, URL structure, taxonomy. Includes recruitment portal, press portal, blog, partner portal, investor portal, asset library. | Not started | Critical ACT |  | Strategy | Mustafa, Glen |  | Audit, status of rebuild | Studio Business |  |  |  | Agent / Studio Business | Use site-architecture skill principles; this is the structural decision under all other site work ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Information architecture: hub and spoke decision | Decision on whether the site is a single domain with sub paths or multiple subdomains (press.studio, blog.studio, partners.studio). SEO and operational implications. | Not started | High |  | Strategy | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Single domain is usually better for SEO and brand; multi subdomain is better for operational independence ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | URL structure and slug conventions | Permanent URL structure decisions: trailing slash, capitalisation, locale prefixes, content type prefixes. Hard to change later. | Not started | High |  | Strategy | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Get this right once; URL changes break SEO and bookmarks ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Homepage iteration: hero copy and CTA | Hero copy aligned to message pillars. Single primary CTA (wishlist on Steam) plus supporting paths (community, press, careers). | Not started | Critical ACT |  | Implementation | Mustafa, Glen |  | Message pillars | Studio Business |  |  |  | Agent / Studio Business | The single highest leverage block of copy on the site ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Homepage iteration: visual treatment | Hero visual: animated background, looping b roll, trailer embed. Must convey the byte punk world per vision doc. | Not started | High |  | Implementation | Mustafa, Glen |  | Visual identity | Studio Business |  |  |  | Agent / Studio Business | Vision doc explicitly notes visuals can feel pedestrian; lean exotic ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Game page (the deep dive) | Game page covering features, world, characters, partner worlds concept. The destination for visitors who want more after the homepage. | Not started | High |  | Implementation | Mustafa, Glen |  | Message pillars, brand voice | Studio Business |  |  |  | Agent / Studio Business | Sells the game in detail; supports press deep linking ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | About the studio page | Studio story, founders, mission, location, hiring plug. Distinct from the game itself. | Not started | High |  | Implementation | Mustafa, Glen |  | Studio naming, brand voice | Studio Business |  |  |  | Agent / Studio Business | Coordinated with studio naming decision; cannot be finished until name is settled ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | News and blog section | Blog index and article template. Categories: dev blog, partner spotlight, community, announcements. RSS, share buttons, related posts. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Blog is critical for SEO and community; do not skip on the rebuild ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Recruitment portal | Career page with role listings, application flow, life at studio content, benefits. Integrated with ATS or built standalone. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Studio is hiring; recruitment portal is direct revenue protection (hiring delays cost more than the build) ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Recruitment portal: roles content | Role descriptions for currently open positions plus future openings. Each role with team, location, level, hiring story. | Not started | High |  | Implementation | Mustafa, Glen |  | Recruitment portal build | Studio Business |  |  |  | Agent / Studio Business | Coordinated with HR (Lorenz) and the existing hiring plan documents ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Press portal | Press portal page with kit downloads, asset library, contact form, embargo request flow, latest news. | Not started | High |  | Implementation | Mustafa, Glen |  | Press kit | Studio Business |  |  |  | Agent / Studio Business | Coordinated with PR press kit work ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Press portal asset library | Backend for asset library: logo pack, key art, screenshots, gif loops, b roll, headshots, factsheet PDF. CDN delivered. | Not started | High |  | Implementation | Mustafa, Glen |  | Press kit | Studio Business |  |  |  | Agent / Studio Business | Press will not chase you for assets; if not on the portal, they use the wrong ones ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Partner portal | Page for partner studios explaining the integration opportunity, with API spec download, contact form, partner game gallery. | Not started | High |  | Implementation | Mustafa, Glen |  | BD partner pipeline | Studio Business |  |  |  | Agent / Studio Business | Partner BD funnel needs a self serve top of funnel; this is the page ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Investor portal | Gated page for investor materials: deck, data room access request, investor news. | Not started | Low |  | Implementation | Mustafa, Glen |  | BD investor pipeline | Studio Business |  |  |  | Agent / Studio Business | Lightweight; gate is identity capture ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Asset library (broader than press) | Player facing wallpaper downloads, social profile pictures, fan kit assets, banner kits for community use. | Not started | Low |  | Implementation | Mustafa, Glen |  | Visual identity | Studio Business |  |  |  | Agent / Studio Business | Cosy gaming audience values fan kits highly ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Brand consistency audit | Cross site audit of brand consistency: typography, colour palette, voice, logo usage, image treatment. Finding the gaps. | Not started | Medium |  | Research | Mustafa, Glen |  | Visual identity | Studio Business |  |  |  | Agent / Studio Business | After the audit comes the cleanup; coordinated with Director of Art ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Brand guidelines document | Public brand guidelines covering logo do and do not, colour palette, typography, voice and tone, partner usage rules. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Visual identity | Studio Business |  |  |  | Agent / Studio Business | Required for partner studios using the brand in their materials ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | SEO baseline audit | Technical SEO audit: crawlability, sitemap, robots.txt, structured data, meta tags, canonical URLs, page speed, Core Web Vitals, mobile friendliness, hreflang for localisation. | Not started | Critical ACT |  | Research | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Use seo-audit skill; this surfaces every technical SEO debt that the rebuild has ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | SEO baseline content audit | Audit of content for SEO: title tags, H1s, internal linking, content depth, keyword targeting, image alt text. | Not started | High |  | Research | Mustafa, Glen |  | SEO audit | Studio Business |  |  |  | Agent / Studio Business | Content side of SEO; usually where the most quick wins live ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Keyword strategy and target rankings | Target keyword research: branded (couch heroes), category (cosy MMO, exploration MMO), comparison (palia alternative, light no fire alternative), informational (corruption mechanic). Initial ranking targets. | Not started | High |  | Research | Mustafa, Glen |  | Positioning, competitor map | Studio Business |  |  |  | Agent / Studio Business | Use competitor-alternatives skill methodology; alternative pages are high intent traffic ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Comparison and alternative pages | Alternative pages: Couch Heroes vs Palia, vs Light No Fire, vs FFXIV (cosy comparison), vs Wynncraft. Each page hand built to high standard, not generic vs page. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Keyword strategy, competitor map | Studio Business |  |  |  | Agent / Studio Business | Use competitor-alternatives skill; high commercial intent SEO traffic ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Topic clusters and pillar pages | Pillar pages on big themes: cosy MMO, exploration RPG, corruption mechanic, partner worlds. Each pillar with cluster of supporting articles. | Not started | Medium |  | Strategy | Mustafa, Glen |  | Content strategy | Studio Business |  |  |  | Agent / Studio Business | Use content-strategy skill; topic clusters dominate informational SERPs ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Editorial calendar (website blog) | Calendar of blog post topics aligned to message pillars, SEO targets, marketing milestones. | Not started | Medium |  | Strategy | Mustafa, Glen |  | Keyword strategy, brand voice | Studio Business |  |  |  | Agent / Studio Business | Coordinated with PR blog cadence and Community Reddit plan ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Analytics setup: GA4 plus Plausible or Fathom | Decision on analytics stack. GA4 for depth, Plausible or Fathom for privacy compliant simple metrics. Configuration of events, conversions, audiences. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Without analytics every other GTM and PR claim is unverifiable ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Analytics setup: events and conversions | Custom event mapping: wishlist click, press kit download, role application start, role application submit, demo request, beta sign up, blog read time. | Not started | High |  | Implementation | Mustafa, Glen |  | Analytics setup base | Studio Business |  |  |  | Agent / Studio Business | This is where signal vs noise differentiation happens ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Tag management setup | Google Tag Manager or equivalent for managing tracking pixels: Meta, TikTok, Reddit, X, LinkedIn for hiring, Google Ads. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Analytics setup | Studio Business |  |  |  | Agent / Studio Business | Reduces dev team interruption for marketing changes ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Cookie consent and privacy compliance | GDPR and CCPA compliant consent banner, privacy policy, cookie policy, data subject request flow. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | UK and EU operating; non negotiable from day one ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Newsletter signup and email programme | Email collection on site, ESP selection (Beehiiv, Substack, Customer.io), welcome flow, monthly newsletter template, segmentation. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Email is owned audience; the only thing that does not depend on platform algorithms ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Site search | On site search functionality: Algolia, internal, or none. Decision based on content volume. | Not started | Low |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Likely overkill at current size; revisit as content grows ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Performance optimisation | Page speed, image optimisation, asset bundling, caching strategy, CDN, lazy loading. Core Web Vitals targets. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | SEO and conversion both depend on speed; cosy audience often on lower spec mobile ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Mobile experience | Mobile responsive design pass across all pages. Touch targets, scroll behaviour, performance on mid tier Android. | Not started | High |  | Implementation | Mustafa, Glen |  | Performance optimisation | Studio Business |  |  |  | Agent / Studio Business | Cosy gaming audience indexes higher on mobile browsing than core gamer audiences ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Accessibility compliance | WCAG 2.1 AA pass: keyboard navigation, screen reader, contrast, alt text, ARIA. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Use design accessibility-review skill; vision pillar of accessibility extends beyond the game ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Internationalisation and localisation framework | Site structure to support multiple languages: locale routing, content translation workflow, language selector, hreflang, locale specific assets. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Localisation plan | Studio Business |  |  |  | Agent / Studio Business | Coordinated with GTM localisation plan; site is the second highest priority surface to localise after the game ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Content management workflow | CMS choice and editorial workflow: who can publish what, draft and review process, scheduled posts, version history. | Not started | Medium |  | Strategy | Mustafa, Glen |  | Editorial calendar | Studio Business |  |  |  | Agent / Studio Business | Without workflow the blog dies in week three ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Hosting and infrastructure | Hosting decision (Vercel, Netlify, AWS, Cloudflare Pages), DNS, email, monitoring, uptime SLA. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Tech (Mustafa); operational concern ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Security baseline | HTTPS enforcement, security headers (CSP, HSTS, X Frame Options), DDoS protection, dependency scanning, penetration test. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Hosting | Studio Business |  |  |  | Agent / Studio Business | Live service brand cannot afford a defaced website during launch window ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Status page | Public status page for game services. Likely separate domain (status.studio). | Not started | Low |  | Implementation | Mustafa, Glen |  | Hosting | Studio Business |  |  |  | Agent / Studio Business | When servers go down players check this first; absence breeds frustration ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | A/B testing framework | Lightweight A/B testing on hero copy, CTA, layout. Tooling decision: VWO, Optimizely, in house with feature flags. | Not started | Low |  | Implementation | Mustafa, Glen |  | Analytics setup | Studio Business |  |  |  | Agent / Studio Business | Premature optimisation if traffic is low; revisit at scale ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Support and help centre | Help articles, FAQ, contact form. Coordinated with player support partner if used. | Not started | Medium |  | Implementation | Mustafa, Glen |  | BD customer service partner | Studio Business |  |  |  | Agent / Studio Business | Reduces support ticket volume; basic SEO benefit on long tail ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Vision doc and lore wiki seed | Public lore section seeding the world: factions, characters, history. Where the player goes deep on the world before buying. | Not started | Low |  | Implementation | Mustafa, Glen |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Vision doc has rich lore; surfacing it on the site differentiates ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Site KPI definition and dashboard | KPIs: organic sessions, wishlist conversions, press kit downloads, role applications, partner enquiries, time on page on key sections. | Not started | Medium |  | Strategy | Mustafa, Glen |  | Analytics setup | Studio Business |  |  |  | Agent / Studio Business | Without KPIs the site is vanity work ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Quarterly site review rhythm | Quarterly review of site analytics, content performance, SEO position, conversion rates. Action item generation. | Not started | Low |  | Implementation | Mustafa, Glen |  | KPI dashboard | Studio Business |  |  |  | Agent / Studio Business | Continuous improvement loop ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Domain portfolio management | Register and renew core domain plus defensive variations (.com, .co.uk, .gg, .games, common typos). Decide which redirect, which sit dormant. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Studio naming | Studio Business |  |  |  | Agent / Studio Business | Coordinated with studio naming decision ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Vendor selection: agency vs in house for next iteration | Decision on whether the next iteration is built by current team, an agency, or hybrid. Each path scoped on cost, speed, control. | Not started | High |  | Strategy | Mustafa, Glen |  | Status of rebuild audit | Studio Business |  |  |  | Agent / Studio Business | Glen and CEO call; impacts every other website item ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Resolve studio name vs game name decision | Single decision: is the studio called Couch Heroes and the game also called Couch Heroes, or do they split. Per Granola Apr 2 discussion this is unsettled. Decision is foundational for every brand artefact downstream. | Not started | Critical ACT |  | Strategy | Vardis, Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Granola Apr 2 discussion identified this; cannot be deferred indefinitely ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Studio naming workshop facilitation | Facilitated naming workshop with founders. Brief, brainstorm, themes, shortlist, gut check, feedback round. Output a studio name shortlist. | Not started | High |  | Strategy | Vardis, Glen |  | Naming decision | Studio Business |  |  |  | Agent / Studio Business | Use brainstorming skill; structured naming reduces founder bias toward first ideas ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Game name reaffirmation or replacement | Decision on whether the game name remains Couch Heroes or changes. Vision doc consistently uses Couch Heroes; the burden of proof is on a change, not on continuity. | Not started | Critical ACT |  | Strategy | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Glen pointed out the unsettled question; founders to resolve ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Naming criteria and constraints document | Constraints for naming: pronounceability across languages, .com domain availability, social handle availability, trademark clearability, distinctiveness from competitors, founders' personal connection. | Not started | High |  | Implementation | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Without explicit criteria the workshop circles ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Trademark search: studio name shortlist | Trademark availability search across UK IPO, EUIPO, USPTO, WIPO Madrid. Each shortlist candidate scored on clearability. | Not started | High |  | Research | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Cheap to run; expensive to discover after launch ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Trademark search: game name | Same trademark search for the game name (whether Couch Heroes or alternative). | Not started | High |  | Research | Vardis, Glen |  | Game name decision | Studio Business |  |  |  | Agent / Studio Business | Often the game name is the more contested namespace; gaming companies file aggressively ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Domain availability check: studio name shortlist | .com availability, .co.uk, .gg, .games, .studio. Cost of acquiring squatted domains. | Not started | High |  | Research | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Cheap; do this before any external announcement of name ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Domain availability check: game name | Same domain check for game name. | Not started | High |  | Research | Vardis, Glen |  | Game name decision | Studio Business |  |  |  | Agent / Studio Business | Coordinated with studio domain check ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Social handle availability: studio | @StudioName on X, Instagram, TikTok, YouTube, Discord vanity, Reddit subreddit. Each platform with claim cost in time and effort. | Not started | High |  | Research | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Reserve before announcement; once leaked, squatters move fast ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Social handle availability: game | Same social handle check for game. | Not started | High |  | Research | Vardis, Glen |  | Game name decision | Studio Business |  |  |  | Agent / Studio Business | Coordinated with studio handle check ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Steam developer name reservation | Steamworks developer name once chosen. Visible on every store listing. | Not started | Medium |  | Implementation | Vardis, Glen |  | BD Steam onboarding | Studio Business |  |  |  | Agent / Studio Business | Coordinate with Steam onboarding ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Trademark filing: studio name | UK IPO and US filing for studio name. Decision on classes (gaming, software, merchandise, services). | Not started | High |  | Implementation | Vardis, Glen |  | Trademark search | Studio Business |  |  |  | Agent / Studio Business | Built with legal counsel; classes selection is more strategic than it looks ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Trademark filing: game name | Same trademark filing for game name. | Not started | High |  | Implementation | Vardis, Glen |  | Trademark search | Studio Business |  |  |  | Agent / Studio Business | Coordinated with studio trademark filing ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Defensive trademark and domain protection | List of close variants, common typos, malicious lookalikes. Decision on which to defensively register. | Not started | Low |  | Implementation | Vardis, Glen |  | Trademark filings | Studio Business |  |  |  | Agent / Studio Business | Operational hygiene; budget for it ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Brand identity brief: studio | Brief for studio brand identity work covering logo, wordmark, colour palette, typography system, voice anchors. | Not started | High |  | Implementation | Vardis, Glen |  | Naming decision, brand voice | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Director of Art (David); studio brand may differ from game brand ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Brand identity brief: game | Brief for game brand identity work, integrated with the byte punk art direction. | Not started | High |  | Implementation | Vardis, Glen |  | Naming decision, visual identity | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Director of Art (David) ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Logo design: studio | Studio logo design. Wordmark, mark only, lockup variants, colour, mono, reverse. | Not started | High |  | Implementation | Vardis, Glen |  | Brand identity brief studio | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Director of Art; external designer often used ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Logo design: game | Game logo design. Sits adjacent to studio logo, may share or diverge in language. | Not started | High |  | Implementation | Vardis, Glen |  | Brand identity brief game | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Director of Art ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Logo usage guidelines | How the logos are used together and apart: lockup spacing, minimum size, clear space, partner co branding rules. | Not started | Medium |  | Implementation | Vardis, Glen |  | Logo designs | Studio Business |  |  |  | Agent / Studio Business | Required for partner studios using the logos ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Naming announcement plan | Communications plan for revealing the chosen names: order of channels, embargo strategy, founder posts, press release. | Not started | High |  | Strategy | Vardis, Glen |  | Naming decision | Studio Business |  |  |  | Agent / Studio Business | If the names change from current Couch Heroes use, this is a community moment requiring care ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Cultural and linguistic check on candidates | Check candidate names for unintended meanings in target language regions: French, German, Italian, Spanish, Brazilian Portuguese, Japanese, Korean, Mandarin Chinese. | Not started | Medium |  | Research | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Cheap; humour aside, mistakes here become long term tax ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Sound and pronunciation check | Native speaker check on pronunciation across target regions. The thing native English speakers consistently get wrong. | Not started | Low |  | Research | Vardis, Glen |  | Cultural check | Studio Business |  |  |  | Agent / Studio Business | Audio recording for spokesperson reference; reduces internal inconsistency ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Backup name reserves | Hold a few backup names with cleared trademarks and domains in case of legal challenge or change of heart. Cost is small, optionality is meaningful. | Not started | Low |  | Implementation | Vardis, Glen |  | Trademark search | Studio Business |  |  |  | Agent / Studio Business | Cheap insurance ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Studio name vs game name positioning rules | Rules for how the two names appear in marketing: studio always preceded game on first mention vs not, copy phrasing across press releases, social, website. | Not started | Medium |  | Implementation | Vardis, Glen |  | Naming decision, brand voice | Studio Business |  |  |  | Agent / Studio Business | Avoids inconsistency that erodes brand recognition ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Update existing assets with new name(s) | Audit and update all existing studio assets with new name(s) where they differ from current Couch Heroes use: website, decks, social handles, email signatures, contracts. | Not started | High |  | Implementation | Vardis, Glen |  | Naming announcement | Studio Business |  |  |  | Agent / Studio Business | Coordinated rollout to avoid mixed signals during transition ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Email and identity infrastructure update | Email addresses, internal branding, business cards, sign in providers, internal documentation rebranded. | Not started | Medium |  | Implementation | Vardis, Glen |  | Naming announcement | Studio Business |  |  |  | Agent / Studio Business | Operational; sometimes underestimated and slips ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Companies House and corporate name reconciliation | If the legal entity name differs from the trading name, document the relationship clearly. Update Companies House records as needed. | Not started | Medium |  | Implementation | Vardis, Glen |  | Naming decision | Studio Business |  |  |  | Agent / Studio Business | Coordinated with legal; UK corporate rules must align with trading name ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Founder narrative for the name | Story behind the name to use in interviews and pitches. Founders rehearsed on it. | Not started | Low |  | Implementation | Vardis, Glen |  | Naming announcement, founder media training | Studio Business |  |  |  | Agent / Studio Business | The thing journalists ask first when a name is unusual ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Existing community migration plan (if game name changes) | Specific plan for migrating current Couch Heroes community references (Discord, Reddit, social) to a new game name if that path is taken. | Not started | Medium |  | Strategy | Vardis, Glen |  | Naming announcement | Studio Business |  |  |  | Agent / Studio Business | Branch only triggered if game name changes; otherwise no op ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Studio name vs game name decision context capture | Document the rationale and tradeoffs of the final decision so future hires understand the context. | Not started | Low |  | Implementation | Vardis, Glen |  | Naming decision | Studio Business |  |  |  | Agent / Studio Business | Institutional memory; avoids relitigating the decision in two years ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / AI / Usage Policy and Governance | Draft v1 of the studio AI Acceptable Use Policy | Single source-of-truth policy document covering scope, definitions, principles, allowed use, prohibited use, exceptions process, and review cadence. Must distinguish generative AI, predictive AI, and AI-assisted features inside the game. Owned by the Producer with Legal sign-off. | Not started | Critical ACT | Red | Implementation | Producer; Legal |  | None | AI Governance |  |  |  | Agent / AI Project | Foundation document. Needs Glen input on whether to use NBI's draft policy as a template.
Couch Heroes / AI / Usage Policy and Governance | Define what counts as "AI" within the policy | Scope definition: which tools and techniques fall under the policy (LLMs, image generators, voice synthesis, code copilots, upscalers, animation tools, automated QA bots, telemetry-driven tooling). Avoids the typical loophole of staff arguing a tool "isn't really AI". | Not started | High | Red | Implementation | Producer; Tech Lead |  | AI policy v1 draft | AI Governance |  |  |  | Agent / AI Project | Be explicit: Adobe Firefly, Photoshop generative fill, Premiere AI features, etc. all count.
Couch Heroes / AI / Usage Policy and Governance | Define acceptable internal-use cases | List the use cases the studio actively endorses: ideation, summarisation, internal documentation, code completion under review, asset reference research, internal mockups, internal localisation drafts. Must specify "internal only" boundary. | Not started | High | Yellow | Implementation | Producer; Department Heads |  | AI scope definition | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on which cases the studio leadership wants to actively encourage.
Couch Heroes / AI / Usage Policy and Governance | Define prohibited use cases | Hard prohibitions: shipping unreviewed AI output as final asset, training third-party models on Couch Heroes IP, replacing voice actors with cloned voices, using AI for any narrative on minors, using AI to generate likenesses of real people without contract. | Not started | Critical ACT | Red | Implementation | Producer; Legal |  | AI scope definition | AI Governance |  |  |  | Agent / AI Project | Voice cloning prohibition is non-negotiable post-2024 SAG-AFTRA strike.
Couch Heroes / AI / Usage Policy and Governance | Define IP safeguards in the policy | Policy clauses preventing studio confidential information, GDD content, source code, art assets, and partner IP from being submitted to public AI tools. Explicit ban on prompting with proprietary text from the GDD outside approved enterprise tools. | Not started | Critical ACT | Red | Implementation | Producer; Legal; Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Critical because partner IP exposure could breach existing licensing deals.
Couch Heroes / AI / Usage Policy and Governance | Define output ownership clarification | Per-tool clarity on who owns AI outputs (studio, individual contributor, tool vendor, no one). Reference each tool's ToS. Default position: outputs created in the course of work belong to Couch Heroes; staff may not retain personal rights. | Not started | High | Yellow | Implementation | Legal; Producer |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | Some tools (Midjourney standard tier) grant non-exclusive licences; flag those.
Couch Heroes / AI / Usage Policy and Governance | Define mandatory human review requirements | Specify which output types require human review before use: all art assets, all narrative copy, all code committed to main, all marketing copy, all communications sent to partners or platforms. Reviewer cannot be the same person who generated the output. | Not started | High | Red | Implementation | Producer; Department Heads |  | None | AI Governance |  |  |  | Agent / AI Project | This is the structural enforcement of "AI-assisted, not AI-authored".
Couch Heroes / AI / Usage Policy and Governance | Define platform-specific AI disclosure rules | Per-platform disclosure matrix: Steam (mandatory pre-recorded vs live-generated AI disclosure since Jan 2024), PlayStation, Nintendo, Xbox, Epic. Maps studio obligations to each storefront. Updated every quarter as platforms revise terms. | Not started | Critical ACT | Red | Ongoing Mgmt | Producer; Publishing Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Steam disclosure form is mandatory; non-disclosure is grounds for store removal.
Couch Heroes / AI / Usage Policy and Governance | Define vendor security review process | Security questionnaire any new AI tool must pass before use: data residency, retention, training-data opt-out, SSO support, breach history, indemnification, sub-processor list. Bound to ICO/GDPR requirements. | Not started | High | Red | Ongoing Mgmt | Tech Lead; Legal |  | None | AI Governance |  |  |  | Agent / AI Project | UK studio = ICO jurisdiction. Needs DPIA for any tool processing employee or player data.
Couch Heroes / AI / Usage Policy and Governance | Define renewal and audit cadence | Quarterly review of approved tool list, annual policy review, ad-hoc review on any platform-rules change or breach incident. Documented in a governance calendar with named owners. | Not started | Medium | Yellow | Ongoing Mgmt | Producer |  | AI policy v1 draft | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Usage Policy and Governance | Define breach response playbook | Playbook for what happens when AI policy is breached (e.g., proprietary code leaked into a public LLM, unreviewed AI asset shipped, voice cloning incident). Roles, communication tree, legal escalation, partner notification, ICO notification thresholds. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer; Tech Lead |  | AI policy v1 draft | AI Governance |  |  |  | Agent / AI Project | Mirror existing data-breach playbook structure.
Couch Heroes / AI / Usage Policy and Governance | Legal review of full policy | External legal counsel sign-off on the complete policy before staff rollout. Cover IP, employment law, GDPR, contract risk with partners, platform compliance. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; External Counsel |  | All policy items | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on whether Couch Heroes has standing legal counsel or needs introduction.
Couch Heroes / AI / Usage Policy and Governance | Staff communications and rollout plan | All-hands briefing, written FAQ, manager talking points, signed acknowledgement from every staff member that they have read and understood the policy. Acknowledgement stored in HR system. | Not started | High | Yellow | Implementation | People Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Signed acknowledgement is the audit trail when something goes wrong.
Couch Heroes / AI / Usage Policy and Governance | Establish AI Governance Committee | Standing committee meeting monthly to review tool requests, exceptions, incidents, and policy updates. Composition: Producer, Tech Lead, Legal, an Art rep, a Narrative rep, an Engineering rep. | Not started | High | Yellow | Ongoing Mgmt | Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Cross-discipline reps prevent the policy being captured by any one department.
Couch Heroes / AI / Usage Policy and Governance | Define exceptions and waivers process | Formal request form for staff who want to use a tool not on the approved list or for a use case the policy restricts. Time-bound waivers with sunset dates and named approver. | Not started | Medium | Yellow | Ongoing Mgmt | Producer |  | AI Governance Committee | AI Governance |  |  |  | Agent / AI Project | Without a clean exceptions path, staff route around the policy entirely.
Couch Heroes / AI / Usage Policy and Governance | Whistleblower channel for AI policy violations | Anonymous reporting route for staff to flag misuse without fear of retaliation. Integrate with existing HR whistleblower process if one exists, otherwise create. | Not started | Medium | Yellow | Ongoing Mgmt | People Lead; Legal |  | AI policy v1 draft | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on existing whistleblower infrastructure at Couch Heroes.
Couch Heroes / AI / Usage Policy and Governance | Map policy obligations to publisher contracts | Cross-reference the AI policy against active publisher and platform contracts. Identify clauses where the policy must be more restrictive than internal preference because a contract demands it. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Publishing Lead |  | AI policy v1 draft; Contract inventory | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on which publisher contracts are active or in negotiation.
Couch Heroes / AI / Usage Policy and Governance | Investor disclosure position on AI | Standard answer pack for the question "what is your AI usage and exposure?" used in investor calls, due diligence packs, and pitch decks. One narrative, consistent across spokespeople. | Not started | High | Yellow | Implementation | Producer; Finance |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Investors are increasingly listing AI governance in due diligence checklists.
Couch Heroes / AI / Usage Policy and Governance | Press and community position on AI | Public-facing statement on how the studio uses AI, ready for community questions. Non-defensive, specific, and refreshed when the policy changes. | Not started | High | Yellow | Implementation | Marketing; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Concept artist communities will Google this; vague answers are worse than honest ones.
Couch Heroes / AI / Usage Policy and Governance | Subcontractor and contractor AI clause | Standard clause inserted into all freelancer and outsource contracts: confirms whether the contractor is permitted to use AI in their deliverable, requires disclosure if they do, and confirms IP transfer covers AI-derived elements. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Outsource art studios are the largest single source of unattributed AI content risk.
Couch Heroes / AI / Usage Policy and Governance | Insurance review for AI-related risks | Review existing studio insurance (E&O, cyber, IP infringement) for AI-related exclusions and coverage gaps. Engage broker on AI-specific endorsements. | Not started | Medium | Yellow | Ongoing Mgmt | Finance; Legal |  | None | AI Governance |  |  |  | Agent / AI Project | Insurers are starting to add AI-output exclusions; check the small print.
Couch Heroes / AI / Usage Policy and Governance | DPIA for AI tools processing personal data | Data Protection Impact Assessment for any AI tool that touches employee or player personal data. ICO-aligned template. | Not started | High | Red | Ongoing Mgmt | Legal; Tech Lead |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | Mandatory under UK GDPR for high-risk processing.
Couch Heroes / AI / Usage Policy and Governance | Records retention rule for AI prompts and outputs | Define how long AI prompt/output logs are retained, where, and who can access. Balance audit needs against data minimisation. | Not started | Medium | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | AI policy v1 draft | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Usage Policy and Governance | Annual policy effectiveness review | Yearly retrospective on whether the policy is achieving its objectives: incidents avoided, exceptions granted, staff confidence, platform compliance status. | Not started | Low | Green | Ongoing Mgmt | Producer |  | One year of policy operation | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Usage Policy and Governance | Cross-reference NBI's AI policy as starting point | Pull NBI Analytics' existing AI usage policy as a structural template (NBI is itself a heavy AI user). Adapt for game-studio-specific risks. | Not started | Low | Green | Research | Producer |  | None | AI Governance |  |  |  | Agent / AI Project | Glen has internal NBI policy; can be supplied as a starter.
Couch Heroes / AI / Usage Policy and Governance | "AI Policy: verify final presentation item" | Existing CSV item rolled into this backlog. Confirms the AI policy is the single deliverable Couch Heroes presents externally and that the Gamescom-track build is not contingent on AI assistance that breaches the policy. | Not started | High | Red | Assessment | Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | This is the original item from the Couch Heroes CSV.
Couch Heroes / AI / Tool Selection and Licensing | Inventory current AI tools across the studio | Department-by-department survey of every AI tool currently in use, including personal accounts being used for work. Survey covers tool name, vendor, use case, who uses it, paid/free, account ownership (studio vs personal). | Not started | Critical ACT | Red | Research | Producer; Department Heads |  | None | AI Governance |  |  |  | Agent / AI Project | This is the foundation. Without this you cannot govern what you don't know about. Needs Glen input on whether the studio has done any prior audit.
Couch Heroes / AI / Tool Selection and Licensing | Licence terms review for each tool in inventory | For every tool in the inventory, capture: commercial-use rights, training-data opt-out availability, data residency, output ownership, indemnification, termination clauses. Tabulated and red/amber/green rated. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | Most consumer-tier AI tools forbid commercial use or claim a licence to outputs.
Couch Heroes / AI / Tool Selection and Licensing | Identify tools using studio data for model training | Flag any tool whose default ToS allows the vendor to train future models on studio inputs. Force-migrate to enterprise tier with training opt-out, or remove the tool. | Not started | Critical ACT | Red | Ongoing Mgmt | Tech Lead; Legal |  | Tool inventory; Licence review | AI Governance |  |  |  | Agent / AI Project | OpenAI ChatGPT free/Plus, default Midjourney, default Anthropic Claude consumer tier all need attention.
Couch Heroes / AI / Tool Selection and Licensing | Establish approved tool list (positive list) | Curated list of tools that staff are permitted to use for studio work, by department and use case. Anything not on the list requires a waiver. | Not started | Critical ACT | Red | Ongoing Mgmt | AI Governance Committee |  | Tool inventory; Licence review | AI Governance |  |  |  | Agent / AI Project | Positive list is more defensible than a blocked list.
Couch Heroes / AI / Tool Selection and Licensing | Establish blocked tool list with rationale | Explicit list of tools that are not permitted, with a one-line reason. Includes consumer-tier versions of tools whose enterprise tier is allowed. | Not started | High | Yellow | Ongoing Mgmt | AI Governance Committee |  | Tool inventory; Licence review | AI Governance |  |  |  | Agent / AI Project | Spell out the rationale; staff need to understand why, not just what.
Couch Heroes / AI / Tool Selection and Licensing | Annual licence and pricing review | Yearly review of every active subscription: usage, ROI, alternatives, price changes, ToS updates. Decision per tool: renew, downgrade, replace, retire. | Not started | Medium | Yellow | Ongoing Mgmt | Producer; Finance |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Tool Selection and Licensing | Centralised cost tracking for AI tools | Single line of sight on monthly spend across all AI tools, by department. Catches the "twelve teams each pay for their own ChatGPT" problem. | Not started | High | Yellow | Ongoing Mgmt | Finance; Producer |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | Often reveals 2-3x savings by consolidating to studio enterprise plans.
Couch Heroes / AI / Tool Selection and Licensing | Tool retirement and data egress process | When a tool is retired, define: how staff are notified, how outputs are exported and stored, how accounts are closed, how the vendor confirms deletion. | Not started | Medium | Yellow | Ongoing Mgmt | Tech Lead; Producer |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | Often skipped; leaves stale accounts with studio data sitting in vendor systems.
Couch Heroes / AI / Tool Selection and Licensing | Evaluation criteria for new AI tools | Standardised scorecard for any proposed new tool: licensing, security, ROI estimate, integration overhead, staff training cost, alternative consideration. Required input before AI Governance Committee approval. | Not started | High | Red | Ongoing Mgmt | AI Governance Committee |  | None | AI Governance |  |  |  | Agent / AI Project | Forces consistent decision-making. Otherwise it's whoever shouts loudest in the room.
Couch Heroes / AI / Tool Selection and Licensing | Proof-of-concept and pilot framework | Structured pilot process: limited user group, defined success metrics, time-boxed evaluation, exit criteria. Prevents "we've been piloting this for nine months" drift. | Not started | Medium | Yellow | Ongoing Mgmt | Tech Lead |  | Evaluation criteria | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Tool Selection and Licensing | Enterprise vs consumer tier decision matrix | Decision rules for when a tool must be on enterprise tier (any studio data, any partner IP, any code) versus when a consumer tier is acceptable (purely personal learning). | Not started | High | Yellow | Ongoing Mgmt | Tech Lead; Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Default position: studio work requires enterprise tier.
Couch Heroes / AI / Tool Selection and Licensing | SSO and identity integration for approved tools | Wherever supported, route AI tool access through studio SSO so accounts can be revoked on offboarding. No personal-email accounts for studio work. | Not started | High | Yellow | Implementation | Tech Lead; IT |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Critical for offboarding. Personal accounts cannot be revoked.
Couch Heroes / AI / Tool Selection and Licensing | Data residency mapping per tool | For each approved tool, document where data is processed (UK, EU, US, elsewhere) and whether that meets contractual obligations to partners and platforms. | Not started | High | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | UK studios increasingly need data-residency answers from publishers.
Couch Heroes / AI / Tool Selection and Licensing | Sub-processor disclosure tracking | Many AI vendors use sub-processors (OpenAI on Azure, Anthropic on AWS, etc.). Track this chain for each approved tool so studio knows the full data path. | Not started | Medium | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Required for GDPR Article 28 compliance.
Couch Heroes / AI / Tool Selection and Licensing | Training-data provenance check per tool | For each tool, document what is publicly known about its training data sources. Flag tools trained on scraped artwork without consent (mid-2024 lawsuits ongoing). | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Art Director |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Stable Diffusion, Midjourney, several open-source models have known provenance issues.
Couch Heroes / AI / Tool Selection and Licensing | Vendor financial stability check | Quick financial-health check on AI vendors holding studio data. Many are early-stage and may close. Plan for vendor failure. | Not started | Low | Green | Ongoing Mgmt | Finance; Tech Lead |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Tool Selection and Licensing | API key and credential management | All API keys and tokens stored in studio secrets manager, rotated quarterly, attributed to a named owner. No keys in source code or shared documents. | Not started | High | Red | Implementation | Tech Lead; IT |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Standard security hygiene; often missed for AI tools because they feel "small".
Couch Heroes / AI / Tool Selection and Licensing | Local-only AI tool option for sensitive work | Maintain at least one locally-run model (Ollama, LM Studio, or equivalent) for use cases where no data may leave the building. Especially relevant for unreleased GDD content and partner IP. | Not started | Medium | Yellow | Implementation | Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Slower and weaker but eliminates external data exposure.
Couch Heroes / AI / Tool Selection and Licensing | Plugin and extension governance | Many AI tools (Claude, ChatGPT, Cursor, Copilot) accept third-party plugins or extensions. Define which plugins are approved and how new ones are reviewed. | Not started | Medium | Yellow | Ongoing Mgmt | Tech Lead |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Plugins effectively bypass the tool's own security model.
Couch Heroes / AI / Tool Selection and Licensing | Browser-based AI assistant policy | Browser extensions with AI assistants (Sider, Monica, Copilot for Edge, etc.) read everything on every page. Default position: not permitted on studio devices. | Not started | High | Red | Ongoing Mgmt | Tech Lead; IT |  | Blocked tool list | AI Governance |  |  |  | Agent / AI Project | Massive data-leak vector. Often invisible to IT.
Couch Heroes / AI / Tool Selection and Licensing | Mobile device AI app policy | Define which AI apps are permitted on studio-issued or BYOD devices accessing studio data. Voice assistants are a particular risk. | Not started | Medium | Yellow | Ongoing Mgmt | Tech Lead; IT |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Tool Selection and Licensing | Open-source AI tool licence review | Open-source models often carry licences with commercial-use restrictions (e.g., LLaMA 2 community licence, Stable Diffusion RAIL). Review per use case. | Not started | High | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | LLaMA 2 has user-count thresholds; some "free" models become paid above 700M MAU.
Couch Heroes / AI / Tool Selection and Licensing | Cost-per-output benchmarking | Where multiple tools serve the same use case (e.g., concept ideation), benchmark cost per useful output. Inform consolidation decisions. | Not started | Low | Green | Research | Producer; Finance |  | Cost tracking | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Tool Selection and Licensing | Cross-reference tool list against publisher allow-lists | Some publishers maintain lists of approved or banned AI tools for licensed projects. Cross-check the studio's approved list against any partner's list. | Not started | High | Yellow | Ongoing Mgmt | Publishing Lead; Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on which publishers are involved and whether they have published lists.
Couch Heroes / AI / Tool Selection and Licensing | Tool category gap analysis | Identify use cases where staff need an AI tool but no approved option exists, leading to shadow IT. Active gap-filling reduces policy circumvention. | Not started | Medium | Yellow | Research | AI Governance Committee |  | Approved tool list; Tool inventory | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Foundational AI literacy programme for all staff | One-hour module covering: what generative AI is, what it cannot do, how it can fail, why it matters for a games studio, how the studio's policy works. Mandatory for all staff including non-technical roles. | Not started | Critical ACT | Red | Implementation | People Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Without baseline literacy, the policy cannot be enforced because staff cannot interpret it.
Couch Heroes / AI / Training and Education | Designer-specific AI training module | Module for designers covering: ideation use cases, prohibited use cases, how to brief AI tools to get useful output, how to keep iteration loops with the team, why AI is not a substitute for design judgement. | Not started | High | Yellow | Implementation | Design Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Programmer-specific AI training module | Module for engineers covering: code copilot use, security risks of pasting code into LLMs, licence-aware prompting, mandatory review process for AI-suggested code, prohibited repos and codebases for AI tools. | Not started | High | Yellow | Implementation | Tech Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Heavily test-coupled; should reference the studio's CI gating rules.
Couch Heroes / AI / Training and Education | Artist-specific AI training module | Module for artists covering: when AI is acceptable for reference and ideation, when it is prohibited (final asset, character likeness, style transfer of named artists), platform disclosure obligations, community-perception risks. | Not started | Critical ACT | Red | Implementation | Art Director; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Highest reputational risk department. Must be precise.
Couch Heroes / AI / Training and Education | Producer-specific AI training module | Module for producers covering: how to estimate work that involves AI, how to review schedules for AI-related risk, how to enforce policy in sprint planning, how to escalate breaches. | Not started | Medium | Yellow | Implementation | Producer; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | QA-specific AI training module | Module for QA covering: AI-assisted test case generation, AI-assisted bug triage, what AI cannot reliably test, how to validate that AI testing tools haven't missed anything. | Not started | Medium | Yellow | Implementation | QA Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Gaming QA has been an early adopter of AI tooling; needs structure.
Couch Heroes / AI / Training and Education | Writer-specific AI training module | Module for narrative team covering: ideation use, prohibition on shipped narrative copy without rewrite, voice consistency risks, partner-IP narrative safeguards, lore continuity risks from generated text. | Not started | High | Yellow | Implementation | Narrative Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Narrative is a high-disclosure category on Steam.
Couch Heroes / AI / Training and Education | Marketing and community team AI training | Module for marketing covering: AI use in copy and imagery, disclosure requirements, community perception of AI marketing assets, social listening tools that use AI. | Not started | High | Yellow | Implementation | Marketing Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Community can detect AI marketing imagery quickly; sensitivity is high.
Couch Heroes / AI / Training and Education | Voice and audio team AI training | Module covering voice cloning prohibitions, music model licensing risks, sound effect generation, union obligations in voice work, mixing AI-assisted and human-recorded audio. | Not started | Critical ACT | Red | Implementation | Audio Director; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Post-2024 SAG-AFTRA strike; this is one of the highest-risk areas.
Couch Heroes / AI / Training and Education | Onboarding AI module for new starters | AI literacy and policy module added to standard onboarding, completed before new staff get access to AI tools. Acknowledgement signed during onboarding. | Not started | High | Yellow | Implementation | People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | External speaker series on AI in games | Quarterly or bi-annual session bringing in external speakers (academic, legal, industry, union reps) to broaden internal thinking. Open to whole studio. | Not started | Low | Green | Implementation | People Lead |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Internal AI working group | Standing cross-discipline group meeting monthly to share experiments, surface new tools, raise risks. Pipeline into the AI Governance Committee for formal decisions. | Not started | High | Yellow | Ongoing Mgmt | Producer |  | None | AI Governance |  |  |  | Agent / AI Project | Where the actual learning happens; the policy alone won't drive adoption.
Couch Heroes / AI / Training and Education | Best-practice prompt library | Internal library of vetted prompts and prompt patterns by use case: concept ideation, code review, narrative draft, summarisation. Reduces the "everyone reinvents prompting" problem. | Not started | Medium | Yellow | Implementation | AI Working Group |  | Internal AI working group | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Prompt engineering training course | Hands-on course covering structured prompting, chain-of-thought, few-shot, output formatting, evaluation. Open to any staff member. | Not started | Medium | Yellow | Implementation | Tech Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Internal AI failure case library | Curated library of real failure modes: hallucinated lore, wrong citations, plausible-but-wrong code, copyright collisions, biased outputs. Used in training to build healthy scepticism. | Not started | High | Yellow | Implementation | AI Working Group |  | None | AI Governance |  |  |  | Agent / AI Project | Most effective single training intervention. Concrete examples beat abstract warnings.
Couch Heroes / AI / Training and Education | Refresher training cadence | Annual refresher for all staff, triggered earlier if policy changes or major industry incident occurs. | Not started | Medium | Yellow | Implementation | People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Manager training on AI policy enforcement | Module specifically for managers and leads on how to spot policy breaches, how to handle conversations about AI use, how to escalate, how to approve exceptions. | Not started | High | Yellow | Implementation | People Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | The policy lives or dies at the manager-direct-report layer.
Couch Heroes / AI / Training and Education | Contractor and freelancer briefing pack | Short document and acknowledgement form given to every contractor at engagement, covering studio AI rules and disclosure obligations. | Not started | High | Yellow | Implementation | Producer; Legal |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Contractors are typically the weakest compliance link.
Couch Heroes / AI / Training and Education | Knowledge base of approved tool how-tos | Per-tool how-to guides for the approved tool list. Lowers friction so staff stay on approved tools rather than going off-piste. | Not started | Medium | Yellow | Implementation | AI Working Group |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Tabletop exercise on AI incidents | Quarterly tabletop run-throughs of AI incident scenarios (leaked code, voice cloning complaint, platform-disclosure failure). Tests the breach playbook. | Not started | Medium | Yellow | Ongoing Mgmt | Producer; Legal |  | Breach response playbook | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Cross-training with NBI or external AI consultancy | Bring in external expertise (NBI Analytics or equivalent) for advanced topics where in-house knowledge is thin. Avoid the "AI literacy gap = AI policy gap" trap. | Not started | Low | Green | Implementation | Producer |  | None | AI Governance |  |  |  | Agent / AI Project | Glen's NBI infrastructure is a candidate provider.
Couch Heroes / AI / Training and Education | Department lead AI champion programme | Named AI champion in each department who attends working group, fields department questions, surfaces emerging needs. | Not started | Medium | Yellow | Ongoing Mgmt | Producer |  | Internal AI working group | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Critical-thinking module on AI bias and limits | Module on the limits of LLMs, image models, and predictive systems: hallucination, bias, training-data cutoff, brittleness. Important for staff who haven't worked with these tools deeply. | Not started | High | Yellow | Implementation | People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Most underrated training topic.
Couch Heroes / AI / Training and Education | Q&A session series with Legal and Producer | Recurring open Q&A where staff can ask anonymous questions about AI policy and use without risk. Surfaces real concerns the policy misses. | Not started | Medium | Green | Implementation | Producer; Legal |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Training completion tracking and reporting | Dashboard showing completion rates of mandatory AI training by team. Reported quarterly to leadership. | Not started | Medium | Yellow | Ongoing Mgmt | People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Industry-event attendance for AI topics | Budget and approvals process for staff to attend AI-relevant industry events (GDC AI track, Develop, AIAS, IGN Fan Fest panels, regional games AI summits). | Not started | Low | Green | Ongoing Mgmt | Producer; Finance |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Internal Wiki section on AI governance | Single discoverable home for the policy, approved tools, training materials, FAQ, and contact points. Linked from staff onboarding and from every department's page. | Not started | High | Yellow | Implementation | People Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Discoverability is the difference between a policy used and a policy ignored.
Couch Heroes / AI / Production Integration | AI-assisted concept art guidelines | Department guideline document: when concept artists may use AI for ideation and reference, when they may not, mandatory human-redraw step before any output enters the asset pipeline, attribution rules. Includes good and bad examples. | Not started | Critical ACT | Red | Implementation | Art Director; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | The single highest community-perception risk. Must be specific, not aspirational.
Couch Heroes / AI / Production Integration | AI-assisted code generation guidelines | Engineering guideline: which repos and codebases AI tools may see, mandatory human review for any AI-suggested code, licence-aware prompting, prohibition on AI-generated commits without review tags, exclusions for security-sensitive code. | Not started | Critical ACT | Red | Implementation | Tech Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Code generation is the highest-volume AI use case in most studios.
Couch Heroes / AI / Production Integration | AI-assisted narrative writing guidelines | Narrative guideline: AI for brainstorming and structural exploration, prohibition on shipped quest text without full rewrite by human writer, lore consistency check, character-voice preservation rules. | Not started | High | Yellow | Implementation | Narrative Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Couch Heroes' "no disposable photo-copied quests" pillar makes this especially important.
Couch Heroes / AI / Production Integration | AI-assisted asset pipeline assessment | Map every step in the art pipeline (concept, modelling, texturing, rigging, animation, VFX) and identify where AI could legitimately accelerate work, where it cannot, and where the risk outweighs the benefit. | Not started | High | Yellow | Research | Art Director; Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Required before any pipeline tool decision. Otherwise the studio is buying tools without a target use case.
Couch Heroes / AI / Production Integration | Quality gates for AI-generated content | Define gating criteria any AI-influenced asset must pass before integration: human review, IP check, style consistency check, technical spec check, test coverage where applicable. | Not started | Critical ACT | Red | Ongoing Mgmt | Producer; Department Heads |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Quality gate is the structural enforcement layer.
Couch Heroes / AI / Production Integration | Per-discipline review and sign-off workflow | Sign-off matrix: who must approve AI-influenced output before it enters main builds. Different rules per asset category. Documented in JIRA/Hansoft templates. | Not started | High | Yellow | Ongoing Mgmt | Producer; Department Heads |  | Quality gates | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Asset attribution metadata standard | Every asset in the pipeline carries metadata indicating: human-authored / AI-assisted / AI-derived, tools used, prompts used, reviewer. Required for audit, platform disclosure, and IP defence. | Not started | Critical ACT | Red | Implementation | Tech Lead; Producer |  | None | AI Governance |  |  |  | Agent / AI Project | This is the audit trail. Without it, no defensible disclosure is possible.
Couch Heroes / AI / Production Integration | Audit trail requirements per asset category | Define what counts as a sufficient audit trail per asset category (concept, model, texture, animation, VFX, audio, code, text). Some need full prompt history, some need only flag. | Not started | High | Yellow | Ongoing Mgmt | Producer; Tech Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | AI-assisted upscaling and texture enhancement guidelines | Specific rules for upscaling tools (ESRGAN, Topaz, etc.) used on textures and reference imagery. These are widely used and often forgotten in policy. | Not started | Medium | Yellow | Implementation | Art Director; Tech Lead |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Upscaling tools are used quietly across most studios; surface them.
Couch Heroes / AI / Production Integration | AI-assisted animation assistance guidelines | Rules for tools that retarget, clean, or generate animation (Cascadeur, DeepMotion, RADiCAL, Move.ai). Particularly fraught with motion-capture actor likeness issues. | Not started | High | Yellow | Implementation | Animation Lead; Legal |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Mocap actor likeness rights are an emerging litigation area.
Couch Heroes / AI / Production Integration | AI-assisted voice and audio guidelines | Rules for voice synthesis, voice cloning prohibition, AI-generated SFX, AI-assisted music, mastering tools. Includes union-obligation flagging and mandatory contract clauses for voice actors. | Not started | Critical ACT | Red | Implementation | Audio Director; Legal |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Voice cloning prohibition must be unambiguous and contract-enforced.
Couch Heroes / AI / Production Integration | AI-assisted localisation guidelines | Rules for using AI in localisation: machine translation as draft only, human linguist review mandatory for all shipped strings, cultural review unchanged, partner-IP language preservation. | Not started | High | Yellow | Implementation | Localisation Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Common cost-cutting target; usually goes wrong.
Couch Heroes / AI / Production Integration | AI-assisted QA tooling guidelines | Rules for AI-assisted test generation, automated bug triage, automated regression analysis, AI-driven smoke tests. What can be automated vs what must remain human-driven. | Not started | Medium | Yellow | Implementation | QA Lead; Tech Lead |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | AI in marketing asset creation guidelines | Rules for marketing imagery, social copy, trailer assistance, B-roll generation. Public-facing means highest scrutiny. | Not started | High | Yellow | Implementation | Marketing Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Public AI marketing imagery has triggered review-bombing in 2024-2026.
Couch Heroes / AI / Production Integration | Steam AI disclosure form workflow | Operational workflow for completing and updating the Steam AI disclosure form: who fills it, who reviews, when it must be updated, what happens if disclosure changes mid-development. | Not started | Critical ACT | Red | Ongoing Mgmt | Producer; Publishing Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | Mandatory for every Steam release; cannot be left to launch week.
Couch Heroes / AI / Production Integration | PlayStation, Xbox, Nintendo, Epic disclosure workflow | Equivalent workflow for each non-Steam platform with AI disclosure obligations. Tracked separately because requirements differ. | Not started | Critical ACT | Red | Ongoing Mgmt | Producer; Publishing Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | Console platforms are catching up to Steam; expect tightening.
Couch Heroes / AI / Production Integration | AI-assisted UI/UX design guidelines | Rules for AI in UI mockup generation, layout exploration, copywriting on UI strings, accessibility checks. | Not started | Medium | Yellow | Implementation | UX Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | AI-generated content removal procedure | Defined procedure for pulling AI-generated content from a build if a problem is discovered: which assets, how to identify them via metadata, fallback assets, time-to-replace estimate. | Not started | High | Yellow | Ongoing Mgmt | Tech Lead; Producer |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | If a model later turns out to be tainted, the studio needs to act fast.
Couch Heroes / AI / Production Integration | Partner-IP firewall in AI workflows | Hard rule: assets, copy, or code derived from partner IP cannot be passed through public AI tools. Enforcement via tooling restrictions, not just policy. | Not started | Critical ACT | Red | Implementation | Tech Lead; Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Couch Heroes' partner integration model means this is a contractual obligation.
Couch Heroes / AI / Production Integration | Pipeline integration testing for AI tools | Before any AI tool enters the production pipeline, run integration testing: file format compatibility, source-control implications, build-time impact, asset-bake impact. | Not started | Medium | Yellow | Implementation | Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Often missed; AI tools land in pipelines without testing the pipeline.
Couch Heroes / AI / Production Integration | Reviewer training for AI-output review | Reviewers signing off on AI output need specific training on what to look for: hallucination, plausibility traps, copyright collision, style drift, security flaws. | Not started | High | Yellow | Implementation | Producer; Department Heads |  | Quality gates | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Sprint-planning AI-impact tag | New JIRA/Hansoft tag for sprint items that involve AI assistance, so sprint reviews can track AI usage in completed work. | Not started | Medium | Green | Ongoing Mgmt | Producer |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Outsource studio AI disclosure requirement | Any outsource partner delivering assets must disclose what AI was used and provide audit trail. Backed by contractual clause. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer |  | Subcontractor and contractor AI clause | AI Governance |  |  |  | Agent / AI Project | Largest unknown surface area in most studios.
Couch Heroes / AI / Production Integration | AI-generated asset rejection criteria | Defined criteria for refusing to integrate an AI-generated asset: provenance unclear, IP risk, quality below bar, style inconsistent. Reviewer's right to reject is explicit. | Not started | High | Yellow | Ongoing Mgmt | Producer; Department Heads |  | Quality gates | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Concept artist red-line process | Specifically for the concept art workflow: every AI-influenced concept goes through a named human concept artist who redraws, modifies, or rejects. Output credited to the human artist, not the AI tool. | Not started | Critical ACT | Red | Ongoing Mgmt | Art Director |  | AI-assisted concept art guidelines | AI Governance |  |  |  | Agent / AI Project | This is how the studio defends against the concept artist boycott concerns.
Couch Heroes / AI / Production Integration | AI-assisted prototyping guidelines | Distinct rules for AI use in prototyping (lower bar, throwaway code) versus production code (full review). Allows velocity in prototyping without leaking into production. | Not started | Medium | Yellow | Implementation | Tech Lead |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Generated content tagging in source control | Source-control hooks or pre-commit checks that prompt the committer to flag AI-derived content. Provides automated audit trail. | Not started | Medium | Yellow | Implementation | Tech Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Build-pipeline AI usage report | Automated report at every build showing aggregate count of AI-tagged assets and code, by category. Visible in producer dashboards. | Not started | Low | Green | Implementation | Tech Lead; Producer |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Discipline-specific FAQ on AI integration | Living FAQ per discipline answering "can I use AI for X" questions surfaced by staff. Maintained by the AI Working Group. | Not started | Medium | Yellow | Implementation | AI Working Group |  | Internal AI working group | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Audit AI clauses in active publisher contracts | Read every active publisher and platform contract for AI-related clauses: warranty of human authorship, indemnification, audit rights, termination triggers. Build a clause matrix. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Publishing Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on which contracts are in scope. Some 2024-2026 publisher contracts include AI warranties that the studio may already be tripping.
Couch Heroes / AI / IP Safeguards | Audit AI clauses in partner-IP licensing agreements | Couch Heroes' partner-game integration model brings external IP into the world. Each licensing contract needs an AI-clause review: can partner IP be processed by AI tools, are derivatives owned by partner or studio, are AI-generated promotional images permitted. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Publishing Lead |  | None | AI Governance |  |  |  | Agent / AI Project | This is a structural risk because the partner-integration model is a Couch Heroes pillar.
Couch Heroes / AI / IP Safeguards | Confirm training data sources are clean for each tool | For each approved tool, document the vendor's published position on training data and any active litigation. Flag tools whose training-data position is unsettled. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Tech Lead |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Stable Diffusion, Midjourney, Suno, several others have unresolved litigation as of 2026.
Couch Heroes / AI / IP Safeguards | Output ownership clarification per tool | For each approved tool, capture in writing: who owns outputs, what licence the studio holds, can the studio commercialise, does the vendor retain rights. Stored in tool inventory. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Many vendors grant non-exclusive licences; this is not the same as ownership.
Couch Heroes / AI / IP Safeguards | Trademark and copyright check process for AI assets | Workflow: any AI-generated asset entering production gets a reverse-image search and trademark database check before sign-off. Automated where possible. | Not started | High | Yellow | Ongoing Mgmt | Legal; Art Director |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | Catches accidental brand or character collisions before they become a takedown notice.
Couch Heroes / AI / IP Safeguards | Open-source AI tool licensing review | Specific deep-dive on open-source AI models in use: licence type, commercial-use permission, attribution requirements, derivative-work obligations, MAU thresholds. | Not started | High | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | LLaMA, Stable Diffusion, Mistral, Whisper all have nuanced terms.
Couch Heroes / AI / IP Safeguards | Takedown and removal process for AI-derived assets | Defined process for receiving an IP claim against an AI-derived asset, investigating, removing if warranted, replacing with clean asset, communicating with claimant. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Tech Lead; Producer |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | Speed matters; most platforms expect response within days.
Couch Heroes / AI / IP Safeguards | Source-control flagging of AI-generated content | Required tag in commit messages or asset metadata identifying AI-derived content. Enables fast filtering during incident response. | Not started | High | Yellow | Implementation | Tech Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | Same control listed in Production Integration; cross-listed because IP-incident response depends on it.
Couch Heroes / AI / IP Safeguards | Legal indemnification position for AI tools | For each approved tool, document the vendor's IP indemnification: do they cover the studio if outputs infringe, what are the conditions, what is the cap. | Not started | High | Yellow | Ongoing Mgmt | Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | OpenAI Enterprise, Microsoft Copilot, Adobe Firefly offer indemnification with conditions. Worth pursuing.
Couch Heroes / AI / IP Safeguards | Establish IP defensibility narrative | Public-facing narrative the studio can stand behind on AI and IP: "human-authored core, AI-assisted only where disclosed, no shipped voice or likeness cloning, full audit trail." Used in press, investor, and partner contexts. | Not started | High | Yellow | Implementation | Producer; Marketing |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Coherent narrative > defensive scrambling at incident time.
Couch Heroes / AI / IP Safeguards | Voice actor likeness and consent contract clause | Standard clause in voice actor contracts: explicit rights granted, prohibition on AI training use, prohibition on voice cloning beyond contract scope, residuals for AI re-use. SAG-AFTRA-aligned where applicable. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Audio Director |  | None | AI Governance |  |  |  | Agent / AI Project | Post-2024 SAG-AFTRA strike standard. UK Equity has parallel demands.
Couch Heroes / AI / IP Safeguards | Mocap and performance capture AI clause | Clause in performance capture contracts addressing AI use of captured data, retraining prohibitions, likeness protection, and re-use scope. | Not started | High | Yellow | Ongoing Mgmt | Legal; Animation Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Performance capture is a related but distinct risk to voice.
Couch Heroes / AI / IP Safeguards | Concept artist contract AI clause | Clause in concept artist contracts confirming output is human-authored or, if AI-assisted, disclosed and approved. Protects studio against post-hoc claims. | Not started | High | Yellow | Ongoing Mgmt | Legal; Art Director |  | None | AI Governance |  |  |  | Agent / AI Project | Cuts both ways: also confirms artist hasn't trained models on studio-supplied references.
Couch Heroes / AI / IP Safeguards | Player UGC and AI policy interface | If players can submit user-generated content (community art, mods, screenshots), define how AI-generated submissions are handled and whether disclosure is required. | Not started | Medium | Yellow | Implementation | Community; Legal |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Trademark portfolio review for AI risk | Review studio's own trademarks and IP for AI-related dilution risk: are bots scraping in-game brand names, are AI tools generating outputs that resemble studio IP, monitor accordingly. | Not started | Medium | Yellow | Ongoing Mgmt | Legal; Marketing |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Monitor active AI-IP litigation | Standing watch on the AI-IP litigation landscape (NYT v OpenAI, Getty v Stability, Concord Music v Anthropic, ongoing concept artist class actions). Quarterly summary to AI Governance Committee. | Not started | High | Yellow | Ongoing Mgmt | Legal |  | None | AI Governance |  |  |  | Agent / AI Project | Settlements and rulings will reshape vendor liability and tool eligibility.
Couch Heroes / AI / IP Safeguards | Insurance position on AI-IP claims | Confirm whether E&O and IP infringement insurance covers AI-derived assets. Push broker for explicit coverage or accept exclusion in writing. | Not started | High | Yellow | Ongoing Mgmt | Finance; Legal |  | Insurance review | AI Governance |  |  |  | Agent / AI Project | Often a hidden exclusion; surface it.
Couch Heroes / AI / IP Safeguards | Platform takedown response playbook | Playbook for handling a platform-issued takedown of AI-derived content: triage, replacement, comms, post-mortem. Distinct from a third-party DMCA. | Not started | High | Yellow | Ongoing Mgmt | Producer; Legal |  | Takedown and removal process | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | DMCA response playbook for AI-derived content | DMCA-specific response process: counter-notice criteria, evidence requirements (audit trail), deadlines, escalation. | Not started | High | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Partner notification process for AI-derived partner content | If AI is used in producing partner-related content (promo art for a partner game's quest line, partner-themed cosmetic), notify partner with audit trail before publication. | Not started | Critical ACT | Red | Ongoing Mgmt | Producer; Publishing Lead |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Partner contracts may require pre-approval; default to disclosing.
Couch Heroes / AI / IP Safeguards | Voice actor union liaison plan | Identify which actor unions (Equity UK, SAG-AFTRA for US talent) Couch Heroes will work with and document their AI position. Maintain a liaison contact. | Not started | High | Yellow | Ongoing Mgmt | Audio Director; Producer |  | None | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on whether the studio is using union or non-union talent.
Couch Heroes / AI / IP Safeguards | Fan community communication position | Pre-drafted messaging on AI use ready for community manager, addressing common community concerns: "are you using AI to replace artists" "is the lore AI-generated" "are voice actors being cloned". Honest, specific, refreshed quarterly. | Not started | High | Yellow | Implementation | Community; Marketing |  | IP defensibility narrative | AI Governance |  |  |  | Agent / AI Project | Communities will detect evasion faster than they detect AI.
Couch Heroes / AI / IP Safeguards | Pre-launch IP audit | Before any external release (Gamescom build, alpha, beta, launch), full audit of all AI-derived content in the build against IP register, audit trail, and disclosure obligations. Sign-off by Legal. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | The single highest-leverage gate. Catches everything before it ships.
Couch Heroes / AI / IP Safeguards | Investor due diligence pack on AI/IP | Standard pack for investor due diligence covering tool list, policy, audit process, indemnification position, contract clauses, current incidents. Refreshed quarterly. | Not started | High | Yellow | Implementation | Producer; Finance |  | All IP safeguard items | AI Governance |  |  |  | Agent / AI Project | Investors are starting to score this in due diligence.
Couch Heroes / AI / IP Safeguards | Vendor breach notification clause | Contractual requirement for AI vendors to notify the studio within a defined window if their tool's training data, ToS, or ownership terms change in a way that affects studio outputs. | Not started | Medium | Yellow | Ongoing Mgmt | Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Ahead of the curve, but worth attempting in negotiation.
Couch Heroes / AI / IP Safeguards | Cross-check Gamescom build for AI-derived content | Specific pre-Gamescom audit on the demo build: every asset, every line of code, every audio clip, every UI string. Disclosure-ready before show floor. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer; Department Heads |  | Pre-launch IP audit | AI Governance |  |  |  | Agent / AI Project | Demo builds get more scrutiny than retail because press are watching for stories.
Couch Heroes / AI / IP Safeguards | Maintain "human-only" reference build | Maintain at least one full content category (e.g., main character art, principal voice) with documented zero AI involvement, as a defensibility anchor. | Not started | Medium | Yellow | Ongoing Mgmt | Producer; Department Heads |  | None | AI Governance |  |  |  | Agent / AI Project | Useful both for marketing and for legal defence.
Couch Heroes / AI / IP Safeguards | Reverse-image search service for asset checks | Operational tooling: subscription to a reverse-image-search service or pipeline integration so any AI-generated asset can be checked against a corpus before release. | Not started | Medium | Yellow | Implementation | Tech Lead; Art Director |  | Trademark and copyright check process | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Retention and disposal of AI prompts and outputs | Define retention periods for AI prompt logs, outputs, and intermediate assets in a way that supports IP defence without retaining unnecessary risk. Aligns with records retention rule. | Not started | Medium | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Quarterly IP-and-AI risk review | Standing quarterly review by the AI Governance Committee covering: new litigation, new platform rules, new vendor terms, new partner contracts, incidents, near-misses. Output: action items for the next quarter. | Not started | High | Yellow | Ongoing Mgmt | AI Governance Committee |  | AI Governance Committee | AI Governance |  |  |  | Agent / AI Project | The cadence ensures the work keeps up with the field.
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define JIRA project taxonomy | Decide project per feature team vs single project with components, name conventions, key prefixes | Not started | High | Yellow | Implementation | Glen, Valeria |  | none | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define issue type hierarchy | Initiative, epic, story, task, sub-task, bug, spike; map each to gate and team usage | Not started | High | Yellow | Implementation | Valeria |  | Project taxonomy | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Configure custom fields | Gate, feature team, discipline, risk level, dependency link, art pipeline stage, tech debt flag | Not started | High | Yellow | Implementation | Valeria |  | Issue type hierarchy | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Configure permissions and roles | Per-project role mapping for leads, ICs, producers, executives, external partners | Not started | High | Yellow | Implementation | Valeria |  | Project taxonomy | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Configure notification schemes | Reduce noise; route critical changes to leads, daily digest for ICs | Not started | Medium | Green | Implementation | Valeria |  | Permissions | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Configure screen schemes per issue type | Different fields visible for design, code, art, audio, QA, production tickets | Not started | Medium | Green | Implementation | Valeria |  | Custom fields | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build automation rules | Auto-link epics to gate, auto-transition on PR merge, auto-assign on triage, escalate stalled tickets | Not started | High | Yellow | Implementation | Valeria |  | Workflow rules | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Configure SLA and ageing rules | Triage SLA, blocked-ticket ageing, stale ticket sweeps | Not started | Medium | Green | Implementation | Valeria |  | Automation rules | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Set up programme-level boards | Studio overview board grouping all feature team boards by gate | Not started | High | Yellow | Implementation | Valeria |  | Master system board | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Set up feature team Kanban boards | One board per feature team with swimlanes by discipline | Not started | High | Yellow | Implementation | Valeria |  | Programme boards | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Set up sprint boards for Agilefall pilots | Two-week sprint boards aligned with pilot teams | Not started | High | Yellow | Implementation | Valeria |  | Feature team boards, Pilot teams selected | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build executive dashboard | Gate health, feature progress, blockers, burn-up across the studio | Not started | High | Yellow | Assessment | Glen, Valeria |  | Programme boards | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build feature team health dashboards | Per-team velocity, throughput, WIP, blocker ageing | Not started | Medium | Green | Assessment | Valeria |  | Feature team boards | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build risk and dependency dashboard | Live view of risks register and cross-team dependencies | Not started | High | Yellow | Assessment | Valeria |  | Risk register, dependency mapping | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build gate exit-criteria dashboard | Per-gate scorecard showing exit-criteria completion | Not started | High | Yellow | Assessment | Valeria |  | Gate exit criteria defined | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define backlog migration plan | Audit existing trackers and decide what migrates, what archives, what rewrites | Not started | High | Yellow | Implementation | Glen, Valeria |  | Production audit | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Migrate existing backlogs into JIRA | Execute migration with field mapping and traceability | Not started | High | Yellow | Implementation | Valeria |  | Backlog migration plan | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define Definition of Ready | Studio-wide DoR for stories entering a sprint | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW, ties to Agilefall
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define Definition of Done | Studio-wide DoD per discipline plus story-level DoD | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW, ties to Agilefall
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Integrate JIRA with source control | Link commits and PRs to issues for engineering teams | Not started | Medium | Green | Implementation | Mustafa, Valeria |  | Permissions | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Integrate JIRA with art pipeline tools | Connect Perforce or DAM to art tickets where feasible | Not started | Medium | Green | Implementation | David, Valeria |  | Permissions | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen confirmation on art tooling
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Integrate JIRA with Slack | Channel notifications for blockers, releases, gate-review outcomes | Not started | Low | Green | Implementation | Valeria |  | Notification schemes | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Integrate JIRA with Confluence | Link epics to spec pages, link gate reviews to decision logs | Not started | Medium | Green | Implementation | Valeria |  | Permissions | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on whether Confluence is in use
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build training package for leads | Slides and demo board for the leads walkthrough | Not started | High | Yellow | Implementation | Glen, Valeria |  | Master system board | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build training package for ICs | Quick-start guides per discipline plus screencasts | Not started | Medium | Green | Implementation | Valeria |  | Lead training | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build training package for producers | Sprint admin, board hygiene, reporting workflows | Not started | Medium | Green | Implementation | Valeria |  | Lead training | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define JIRA admin operating model | Who owns config changes, change-control for new fields, release cadence for tooling changes | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Permissions | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define reporting cadence | Weekly leads report, monthly executive pack, quarterly gate review pack | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Dashboards | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define ticket hygiene standards | Naming, descriptions, acceptance criteria, link types, label vocabulary | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | DoR, DoD | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Run JIRA pilot with two teams | Two-week shake-down on the pilot teams before studio rollout | Not started | High | Yellow | Implementation | Glen, Valeria |  | Sprint boards, Training | Production Strategy |  |  |  | Agent / Production Strategy | NEW, aligns with Agilefall pilot
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Capture pilot feedback and iterate | Retrospective on tooling friction, adjust before studio go-live | Not started | High | Yellow | Implementation | Glen, Valeria |  | JIRA pilot | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Studio cutover plan | Day-by-day rollout, support rota, fallback plan, comms script | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Pilot iteration | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Post-cutover hypercare | Two-week intensive support window after go-live | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Cutover | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define sprint cadence | Two-week sprints, planning day, mid-sprint check-in, demo, retro slots | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define ceremony catalogue | Sprint planning, daily stand-up, backlog refinement, sprint review, retro, gate review | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Sprint cadence | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define estimation approach | Story points vs t-shirt vs ideal days; reference stories per discipline | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define capacity planning model | Team capacity per sprint accounting for leave, support, ceremonies, tech debt | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Sprint cadence | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define velocity tracking method | How velocity is measured, normalised across teams, reported | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Estimation approach | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define cross-discipline RACI for product to tech to art handoffs | Who is responsible, accountable, consulted, informed at each handoff stage | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria, Robin, Mustafa, David |  | Feature team structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define design to implementation pipeline | Spec, prototype, vertical slice, full implementation stages and gating | Not started | High | Yellow | Ongoing Mgmt | Robin, Valeria |  | RACI | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define art pipeline within Agilefall | Concept, block-out, asset production, polish stages aligned to sprints and gates | Not started | High | Yellow | Ongoing Mgmt | David, Valeria |  | RACI | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define QA integration model | In-team QA vs central QA; bug triage SLAs; release-readiness gating | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | RACI | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on QA strategy
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define cross-team dependency rituals | Scrum-of-scrums or equivalent; cadence, attendees, outputs | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Feature team structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define retrospective programme | Format, cadence, themes, anonymous input, action follow-through, studio-level synthesis | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Ceremony catalogue | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define escalation paths | When and how to raise risks from team to leads to executives | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria, Aris |  | RACI | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define scope-control protocol | Mid-sprint change rules, mid-gate scope adjustments, change board | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define spike and research protocol | When to spike, time-boxing, output expectations, conversion to delivery work | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define tech debt protocol | Capture, prioritise, allocate sprint capacity to debt | Not started | Medium | Green | Ongoing Mgmt | Mustafa, Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define onboarding for new joiners under Agilefall | First-fortnight plan, ceremony attendance, productivity ramp | Not started | Medium | Green | Implementation | Lorenz, Valeria |  | Training package | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Pilot team selection | Choose two pilot teams that are representative but resilient | Not started | High | Yellow | Implementation | Glen, Valeria |  | Feature team structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Pilot success criteria | Measurable outcomes for the pilot before studio rollout | Not started | High | Yellow | Implementation | Glen, Valeria |  | Pilot team selection | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Pilot retrospective and decision gate | Pilot review with leads to decide go, adjust, or extend | Not started | High | Yellow | Implementation | Glen, Valeria |  | Pilot complete | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Studio-wide rollout sequencing | Order of teams adopting Agilefall after pilot | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Pilot decision | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Coaching plan for leads | One-to-one coaching for each lead through the first cycle | Not started | Medium | Green | Implementation | Glen, Valeria |  | Studio rollout | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Health-check survey | Periodic team health survey covering psychological safety, clarity, delivery | Not started | Medium | Green | Ongoing Mgmt | Lorenz, Valeria |  | Studio rollout | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Methodology iteration log | Living document of changes to the methodology with rationale | Not started | Low | Green | Ongoing Mgmt | Valeria |  | Studio rollout | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Map current state to nearest gate | Where the project stands today against the new gate structure | Not started | High | Yellow | Research | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Concept | Game pillars, vision deck, target audience, business case approved | Not started | High | Yellow | Strategy | Glen, Robin, Vardis |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Pre-production | Vertical slice plan, GDD baseline, tech feasibility, art pillars, team plan | Not started | High | Yellow | Strategy | Glen, Robin, Mustafa, David |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Start Production | Full GDD lock, pipelines stable, vertical slice playable, hiring plan signed | Not started | High | Yellow | Strategy | Glen, Valeria, Robin |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Mid-production | Feature-complete in greybox, primary content pipelines proven at scale | Not started | High | Yellow | Strategy | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Late Production | Content complete, polish underway, performance targets in sight | Not started | High | Yellow | Strategy | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Alpha | All features in some state, retention test ready, telemetry live | Not started | High | Yellow | Strategy | Glen, Valeria, Robin |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Beta | Content lock, performance lock, localisation in progress, launch readiness review | Not started | High | Yellow | Strategy | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Launch | Day-zero patch ready, marketing live, support model live, live-ops calendar in place | Not started | High | Yellow | Strategy | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Live Service 1 to 5 | Per-season exit criteria covering content delivery, retention metrics, monetisation health | Not started | Medium | Green | Strategy | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on per-season specifics
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate decision rights | Who chairs, who votes, who advises, who is informed | Not started | High | Yellow | Ongoing Mgmt | Glen, Vardis |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate review meeting format | Standing agenda, evidence pack, decision options, recording, distribution | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Decision rights | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate review evidence pack | Mandatory artefacts each lead brings: status, risks, dependencies, demo, asks | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Gate review format | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define pre-gate readiness checks | Two-week-out, one-week-out checklists per lead | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Gate review format | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate decision options | Pass, conditional pass with action list, hold, fail and re-plan | Not started | High | Yellow | Ongoing Mgmt | Glen |  | Decision rights | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define conditional-pass tracking | How conditions are logged, owned, reviewed, closed | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Decision options | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define escalation path between gates | Mid-gate red flags that trigger executive review without waiting for the formal gate | Not started | High | Yellow | Ongoing Mgmt | Glen, Vardis, Aris |  | Risk register | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define post-gate retrospective | Cross-discipline retro after every gate decision, output to methodology iteration log | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Gate review format | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate metrics | What is measured to evidence each exit criterion; baselining and target values | Not started | High | Yellow | Assessment | Glen, Valeria |  | Exit criteria | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Build gate decision log | Public record of every gate review, the call made, conditions, signatories | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Gate review format | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define inter-gate cadence | Mid-gate checkpoint cadence between formal gate reviews | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Gate review format | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Build gate playbook for leads | One-pager per lead with their evidence requirements per gate | Not started | High | Yellow | Implementation | Glen, Valeria |  | Evidence pack | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Map dependencies across gates | Cross-feature dependencies that constrain which gate a feature can sit in | Not started | High | Yellow | Strategy | Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate communication plan | How outcomes are communicated to studio, partners, investors, board | Not started | Medium | Yellow | Implementation | Glen, Vardis |  | Decision log | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define partner and external-stakeholder gate visibility | What partners and external collaborators see and when | Not started | Medium | Green | Ongoing Mgmt | Glen |  | Communication plan | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on partner list
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build studio Now Next Later roadmap | Public studio-level roadmap view tied to gates | Not started | High | Yellow | Strategy | Glen, Vardis, Robin |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build feature team roadmaps | Per-team Now Next Later, rolling up to studio roadmap | Not started | High | Yellow | Strategy | Valeria |  | Studio roadmap | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define quarterly planning agenda | Two-day session structure, prep work, attendees, outputs | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define monthly checkpoint format | Studio-wide monthly checkpoint with leads | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define weekly leadership health check | Standing weekly meeting agenda, attendees, output, decision log | Not started | High | Yellow | Ongoing Mgmt | Glen, Vardis, Aris, Valeria |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define studio OKR cycle | Annual themes, quarterly OKRs, monthly progress review, end-of-quarter scoring | Not started | High | Yellow | Ongoing Mgmt | Glen, Vardis |  | OKR tracking | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define team OKR cycle | Feature team quarterly OKRs derived from studio OKRs | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Studio OKR cycle | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build OKR scoring rubric | How team OKRs are scored, calibrated across teams, reported | Not started | Medium | Green | Ongoing Mgmt | Glen, Valeria |  | Team OKR cycle | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build dependency map | Cross-team dependency catalogue with owners and lead times | Not started | High | Yellow | Strategy | Valeria |  | Feature team roadmaps | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build risk register | Studio-level risks with owners, severity, mitigation, review cadence | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define risk review cadence | Weekly leadership health-check slot for top risks; monthly full review | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Risk register | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build assumption log | Tracked assumptions with validation status; review at quarterly planning | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Quarterly planning | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build decision log | Studio-level decision log so calls do not get re-litigated | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define roadmap change-control | How roadmap changes are proposed, evaluated, approved between quarters | Not started | High | Yellow | Ongoing Mgmt | Glen, Vardis |  | Studio roadmap | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define hiring plan integration | Hiring milestones tied to roadmap and gates | Not started | High | Yellow | Strategy | Lorenz, Vardis, Aris |  | Studio roadmap | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define budget and burn integration | Quarterly burn check tied to roadmap progress | Not started | High | Yellow | Ongoing Mgmt | Vardis, Aris |  | Quarterly planning | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on finance owner
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define partner and external commitments tracker | External milestones, demo dates, publishing or platform deadlines on the roadmap | Not started | Medium | Green | Ongoing Mgmt | Glen, Vardis |  | Studio roadmap | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define communication rhythm to studio | All-hands cadence, written updates, tone | Not started | Medium | Green | Implementation | Vardis, Lorenz |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define communication rhythm to investors and board | Quarterly investor update, board pack cadence, ad-hoc escalations | Not started | High | Yellow | Implementation | Vardis, Glen |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define metrics dashboard for cadence health | Sprint completion rate, ceremony attendance, roadmap-vs-actual drift, OKR confidence | Not started | Medium | Green | Assessment | Valeria |  | Dashboards | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Confirm attendees and roles per session | Who attends each session in driver, contributor, observer roles | Not started | High | Red | Implementation | Glen, Valeria |  | none | Production Strategy |  |  |  | Agent / Production Strategy | NEW, Critical ACT for Apr 27
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Pre-read pack for attendees | Methodology summary, gate structure, JIRA preview, current backlog snapshot | Not started | High | Red | Implementation | Glen, Valeria |  | none | Production Strategy |  |  |  | Agent / Production Strategy | NEW, Critical ACT
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Pre-offsite logistics | Room, AV, catering, remote dial-in, materials | Not started | High | Yellow | Implementation | Valeria |  | none | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on logistics owner
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Pre-offsite leads briefing | Short call with each lead before offsite to set expectations | Not started | High | Red | Implementation | Glen, Valeria |  | Attendees confirmed | Production Strategy |  |  |  | Agent / Production Strategy | NEW, Critical ACT
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Day 1 agenda Apr 27 | Production audit findings, current-state debrief, Agilefall principles intro | Not started | High | Yellow | Strategy | Glen, Valeria |  | Pre-read pack | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Day 2 agenda Apr 28 | Gate structure deep dive, exit-criteria drafting per gate, leads as co-authors | Not started | High | Yellow | Strategy | Glen, Valeria |  | Day 1 outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Day 3 agenda Apr 29 | Feature scoping against gates, dependency mapping, JIRA configuration walkthrough | Not started | High | Yellow | Strategy | Glen, Valeria |  | Day 2 outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Day 4 agenda Apr 30 | Vision and strategy session, roadmap commitment, OKR direction, closing actions | Not started | High | Yellow | Strategy | Glen, Vardis, Robin |  | Day 3 outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Live decision log during offsite | Decisions captured in real time with owner and date | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Offsite running | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Live action register during offsite | Actions captured with owner, deadline, success criteria | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Offsite running | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Live parking lot during offsite | Topics raised but deferred, with owner for follow-up | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Offsite running | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Daily wrap-up summary | End-of-day summary distributed to attendees each evening | Not started | Medium | Green | Implementation | Glen, Valeria |  | Offsite running | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Offsite outputs document | Single canonical document compiled within 48 hours of close | Not started | High | Yellow | Implementation | Glen, Valeria |  | Offsite complete | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Roadmap publication post-offsite | Publish updated Now Next Later roadmap derived from offsite outputs | Not started | High | Yellow | Implementation | Glen, Valeria |  | Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Leads-to-teams cascade comms | Each lead briefs their team within one week post-offsite | Not started | High | Yellow | Implementation | Glen, Valeria, all leads |  | Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | All-hands post-offsite session | Studio-wide all-hands within two weeks; vision, gate structure, methodology | Not started | High | Yellow | Implementation | Vardis, Glen |  | Cascade comms | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Post-offsite retrospective | Leadership retro on offsite itself; what to repeat for next offsite | Not started | Medium | Green | Ongoing Mgmt | Glen, Valeria |  | Offsite complete | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Graham onboarding pack tied to offsite outputs | Prep so Graham lands into a coherent picture from May 18 | Not started | High | Yellow | Implementation | Glen, Vardis, Lorenz |  | Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW, Graham starts ~May 18
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Post-offsite action follow-through cadence | Weekly check-in for the first month against the action register | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Action register | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Update studio risk register from offsite | New risks surfaced at offsite added to the register with owners | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Risk register, Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Update studio dependency map from offsite | New dependencies surfaced at offsite added with owners | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Dependency map, Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Pilot team kick-off post-offsite | Stand up the two pilot teams against the agreed methodology | Not started | High | Yellow | Implementation | Glen, Valeria |  | Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Confluence or equivalent home for offsite outputs | Permanent searchable home for the offsite documentation | Not started | Medium | Green | Implementation | Valeria |  | Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on tooling
Couch Heroes / HR / Hiring Pipeline - Engineering | CTO restart: source new candidates | Q1 (2026-04-26): Cam, Neil, Nia ALL DEAD. Restart sourcing from scratch with refreshed brief. | Not started | Critical ACT | Red | Implementation | Glen |  |  | Talent Acquisition |  |  |  | Q1 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Hiring Pipeline - Engineering | CTO scorecard refresh | Q1 (2026-04-26): Existing scorecard at Clients/Couch Heroes/CTO_Scorecard.xlsx. Review, refresh against new candidate criteria post-Cam/Neil/Nia. | Not started | High |  | Implementation | Glen |  | CTO_Scorecard.xlsx | Talent Acquisition |  |  |  | Q1 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Hiring Pipeline - Engineering | CTO question set refresh | Q1 (2026-04-26): Existing question set at Clients/Couch Heroes/CTO_Interview_Questions_Couch_Heroes.docx. Review and refresh. | Not started | High |  | Implementation | Glen |  | CTO_Interview_Questions_Couch_Heroes.docx | Talent Acquisition |  |  |  | Q1 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Hiring Pipeline - DONE | Document Lead Animator question set artifact | Q4 (2026-04-26): No separate question-set doc on disk for Lead Animator interview. ACTION: locate the questions actually used (likely informal / verbal / Slack), document them as a reusable artifact, attach to Lead Animator hiring story when uploading to WorkSage. | Not started | Medium |  | Implementation | Glen |  |  | Talent Acquisition |  |  |  | Q4 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Lili Zhao (Chief of Staff, ~£135k) | Q5 (2026-04-26): NEW HIRE separate from Lorenza (who is existing staff handling Dino transition). Per Granola SayBrook discussion ~£135k for COS role. | In progress | High |  | Implementation | Glen |  |  | Talent Acquisition |  |  |  | Q5 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Hiring Pipeline - Operations | HR Operations role - ongoing interviews | Q6 (2026-04-26): Two weak candidates interviewed; sourcing continues. Reference: Slack engineering candidates channel https://couchheroes.slack.com/archives/C0AJBRJTJTA + Google Sheet of all candidates https://docs.google.com/spreadsheets/d/1NaZABJP_8HQCVdrQR9Uoq9g3NYVYdyKHLB8qc3nSLRo/edit | In progress | High |  | Implementation | Glen |  | Slack channel C0AJBRJTJTA / Google Sheet | Talent Acquisition |  |  |  | Q6 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Staff Changes | Dino exit - transition + garden leave | Q7 (2026-04-26): Performance review DELIVERED. Exit timeline 1mo transition + 2mo garden leave is TENTATIVE. Decided Apr 9. Settlement details with Riley/legal. Lorenza extracting documentation. | In progress | High | Yellow | Implementation | Glen,Lorenza,Riley |  |  | HR Operations |  |  |  | Granola Apr 9 + Q7 (2026-04-26) | NEW from Q&A - dates tentative
Couch Heroes / Studio Operations / Org Design & Structure | Attach Miro org-structure artifact | Q8 (2026-04-26): Glen provided Miro screenshot of likely structure. Captured at Clients/Couch Heroes/org_structure_likely_2026-04-26.md. Replace with finalised version after Apr 27-30 offsite. | In progress | High |  | Strategy | Glen |  | org_structure_likely_2026-04-26.md | Org Design |  |  |  | Q8 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / 1:1s - Weekly Programme | Weekly 1:1 Programme (8 leads) | Q12 (2026-04-26): One programme story + 8 weekly sub-tasks per cycle. Leads: Dino, Lorenza, Vardis, Aris, Mustafa, Robin, David, Valeria. Bi-weekly 1:1s + weekly coaching cadence. | In progress | High | Green | Ongoing Mgmt | Glen |  |  | HR Operations |  |  |  | Q12 (2026-04-26) | NEW from Q&A - programme story

## Production Strategy & Implement
parent_path | title | description | status | priority | health_state | work_type | assignees | due_date | dependencies | practice_area | type | layer | confidence | source | notes
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | JIRA Implementation & Rollout | Configure and roll out JIRA across the studio with Agilefall workflows | In progress | High | Green |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 1
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Make the implementation plan more human-readable | Current plan is too technical for leads | In progress | High | Red |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 62
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Define exit criteria per gate | What must be true to pass each gate | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 64
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Draft rationale and full gate structure | Concept > Pre-Prod > Prod Start > Mid Prod > Late Prod > Alpha > Beta > Launch > First Release | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 65
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Build training sessions, quick-start guides, and recordings | Enablement materials for all staff | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 66
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Pilot in two teams for one cadence, capture improvements | Controlled test before full rollout | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 67
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Handle change communications | Studio-wide comms plan for the shift | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 68
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Roll out with department leads and sub-leads, get commits | Change management and buy-in | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 69
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define feature-based team structure (replacing department-based) | Structural shift from dept to feature teams | Planning | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 70
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define target ways of working: cadence, estimation, DoR/DoD, scope control | Target state documentation | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 72
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Production audit: review current backlogs, pipelines, rituals | Baseline assessment of current state | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 73
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Build out the Agilefall plan with Valeria | Core methodology design document | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 75
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Integrate production backlog into gate system | Align existing work to gate structure | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 77
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Gate System Design & Rollout | Define milestone gates from Concept through First Release with exit criteria and review process | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 81
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Agilefall Methodology Rollout | Design and roll out Agilefall production methodology studio-wide | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 82
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Get commits and go live | Final sign-off from leads | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 83
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Walk through with leads on February 18th | Presentation and Q&A with all department leads Q9 (2026-04-26): Postponed. Target ~2 weeks after offsite (mid-May), conditional on roadmap + process flow agreement first. | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 85
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Build Miro board implementation flow | Visual flow for how JIRA will be used | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 86
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Build Excel project plan for implementation | Detailed rollout timeline and dependencies | Drafted | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 87
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Build out master system board (with Valeria) | Central board setup and configuration | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 88
Couch Heroes / Production Strategy & Implementation / JIRA Implementation & Rollout | Define Jira rules and workflow configuration (with Valeria) | Rules for statuses, fields, transitions | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 89
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Studio walkthrough and commitment | Present to studio and get sign-off | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 90
Couch Heroes / Production Strategy & Implementation / Gate System Design & Rollout | Create risk and dependency register with owners and SLAs | Foundational risk tracking tied to gates | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 91
Couch Heroes / Production Strategy & Implementation / Roadmap & Cadence Rollout | Roadmap & Cadence Rollout | Establish roadmap-based production rhythm and rituals | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 107
Couch Heroes / Production Strategy & Implementation / Roadmap & Cadence Rollout | Configure goals and OKR tracking | Set up tracking infrastructure | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 117
Couch Heroes / Production Strategy & Implementation / Roadmap & Cadence Rollout | Align leadership on cadence: 2-day quarterly planning, 2-week sprints, weekly health checks | Get leadership buy-in on rhythm | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 118
Couch Heroes / Production Strategy & Implementation / Roadmap & Cadence Rollout | Move to roadmap-based production with feature-based teams | Shift from dept-based to feature-based delivery | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 120
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define JIRA project taxonomy | Decide project per feature team vs single project with components, name conventions, key prefixes | Not started | High | Yellow | Implementation | Glen, Valeria |  | none | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define issue type hierarchy | Initiative, epic, story, task, sub-task, bug, spike; map each to gate and team usage | Not started | High | Yellow | Implementation | Valeria |  | Project taxonomy | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Configure custom fields | Gate, feature team, discipline, risk level, dependency link, art pipeline stage, tech debt flag | Not started | High | Yellow | Implementation | Valeria |  | Issue type hierarchy | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Configure permissions and roles | Per-project role mapping for leads, ICs, producers, executives, external partners | Not started | High | Yellow | Implementation | Valeria |  | Project taxonomy | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Configure notification schemes | Reduce noise; route critical changes to leads, daily digest for ICs | Not started | Medium | Green | Implementation | Valeria |  | Permissions | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Configure screen schemes per issue type | Different fields visible for design, code, art, audio, QA, production tickets | Not started | Medium | Green | Implementation | Valeria |  | Custom fields | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build automation rules | Auto-link epics to gate, auto-transition on PR merge, auto-assign on triage, escalate stalled tickets | Not started | High | Yellow | Implementation | Valeria |  | Workflow rules | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Configure SLA and ageing rules | Triage SLA, blocked-ticket ageing, stale ticket sweeps | Not started | Medium | Green | Implementation | Valeria |  | Automation rules | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Set up programme-level boards | Studio overview board grouping all feature team boards by gate | Not started | High | Yellow | Implementation | Valeria |  | Master system board | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Set up feature team Kanban boards | One board per feature team with swimlanes by discipline | Not started | High | Yellow | Implementation | Valeria |  | Programme boards | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Set up sprint boards for Agilefall pilots | Two-week sprint boards aligned with pilot teams | Not started | High | Yellow | Implementation | Valeria |  | Feature team boards, Pilot teams selected | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build executive dashboard | Gate health, feature progress, blockers, burn-up across the studio | Not started | High | Yellow | Assessment | Glen, Valeria |  | Programme boards | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build feature team health dashboards | Per-team velocity, throughput, WIP, blocker ageing | Not started | Medium | Green | Assessment | Valeria |  | Feature team boards | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build risk and dependency dashboard | Live view of risks register and cross-team dependencies | Not started | High | Yellow | Assessment | Valeria |  | Risk register, dependency mapping | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build gate exit-criteria dashboard | Per-gate scorecard showing exit-criteria completion | Not started | High | Yellow | Assessment | Valeria |  | Gate exit criteria defined | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define backlog migration plan | Audit existing trackers and decide what migrates, what archives, what rewrites | Not started | High | Yellow | Implementation | Glen, Valeria |  | Production audit | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Migrate existing backlogs into JIRA | Execute migration with field mapping and traceability | Not started | High | Yellow | Implementation | Valeria |  | Backlog migration plan | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define Definition of Ready | Studio-wide DoR for stories entering a sprint | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW, ties to Agilefall
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define Definition of Done | Studio-wide DoD per discipline plus story-level DoD | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW, ties to Agilefall
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Integrate JIRA with source control | Link commits and PRs to issues for engineering teams | Not started | Medium | Green | Implementation | Mustafa, Valeria |  | Permissions | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Integrate JIRA with art pipeline tools | Connect Perforce or DAM to art tickets where feasible | Not started | Medium | Green | Implementation | David, Valeria |  | Permissions | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen confirmation on art tooling
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Integrate JIRA with Slack | Channel notifications for blockers, releases, gate-review outcomes | Not started | Low | Green | Implementation | Valeria |  | Notification schemes | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Integrate JIRA with Confluence | Link epics to spec pages, link gate reviews to decision logs | Not started | Medium | Green | Implementation | Valeria |  | Permissions | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on whether Confluence is in use
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build training package for leads | Slides and demo board for the leads walkthrough | Not started | High | Yellow | Implementation | Glen, Valeria |  | Master system board | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build training package for ICs | Quick-start guides per discipline plus screencasts | Not started | Medium | Green | Implementation | Valeria |  | Lead training | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Build training package for producers | Sprint admin, board hygiene, reporting workflows | Not started | Medium | Green | Implementation | Valeria |  | Lead training | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define JIRA admin operating model | Who owns config changes, change-control for new fields, release cadence for tooling changes | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Permissions | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define reporting cadence | Weekly leads report, monthly executive pack, quarterly gate review pack | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Dashboards | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Define ticket hygiene standards | Naming, descriptions, acceptance criteria, link types, label vocabulary | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | DoR, DoD | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Run JIRA pilot with two teams | Two-week shake-down on the pilot teams before studio rollout | Not started | High | Yellow | Implementation | Glen, Valeria |  | Sprint boards, Training | Production Strategy |  |  |  | Agent / Production Strategy | NEW, aligns with Agilefall pilot
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Capture pilot feedback and iterate | Retrospective on tooling friction, adjust before studio go-live | Not started | High | Yellow | Implementation | Glen, Valeria |  | JIRA pilot | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Studio cutover plan | Day-by-day rollout, support rota, fallback plan, comms script | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Pilot iteration | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / JIRA Implementation and Rollout | Post-cutover hypercare | Two-week intensive support window after go-live | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Cutover | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define sprint cadence | Two-week sprints, planning day, mid-sprint check-in, demo, retro slots | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define ceremony catalogue | Sprint planning, daily stand-up, backlog refinement, sprint review, retro, gate review | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Sprint cadence | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define estimation approach | Story points vs t-shirt vs ideal days; reference stories per discipline | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define capacity planning model | Team capacity per sprint accounting for leave, support, ceremonies, tech debt | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Sprint cadence | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define velocity tracking method | How velocity is measured, normalised across teams, reported | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Estimation approach | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define cross-discipline RACI for product to tech to art handoffs | Who is responsible, accountable, consulted, informed at each handoff stage | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria, Robin, Mustafa, David |  | Feature team structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define design to implementation pipeline | Spec, prototype, vertical slice, full implementation stages and gating | Not started | High | Yellow | Ongoing Mgmt | Robin, Valeria |  | RACI | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define art pipeline within Agilefall | Concept, block-out, asset production, polish stages aligned to sprints and gates | Not started | High | Yellow | Ongoing Mgmt | David, Valeria |  | RACI | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define QA integration model | In-team QA vs central QA; bug triage SLAs; release-readiness gating | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | RACI | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on QA strategy
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define cross-team dependency rituals | Scrum-of-scrums or equivalent; cadence, attendees, outputs | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Feature team structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define retrospective programme | Format, cadence, themes, anonymous input, action follow-through, studio-level synthesis | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Ceremony catalogue | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define escalation paths | When and how to raise risks from team to leads to executives | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria, Aris |  | RACI | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define scope-control protocol | Mid-sprint change rules, mid-gate scope adjustments, change board | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define spike and research protocol | When to spike, time-boxing, output expectations, conversion to delivery work | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define tech debt protocol | Capture, prioritise, allocate sprint capacity to debt | Not started | Medium | Green | Ongoing Mgmt | Mustafa, Valeria |  | Ways of working | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Define onboarding for new joiners under Agilefall | First-fortnight plan, ceremony attendance, productivity ramp | Not started | Medium | Green | Implementation | Lorenz, Valeria |  | Training package | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Pilot team selection | Choose two pilot teams that are representative but resilient | Not started | High | Yellow | Implementation | Glen, Valeria |  | Feature team structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Pilot success criteria | Measurable outcomes for the pilot before studio rollout | Not started | High | Yellow | Implementation | Glen, Valeria |  | Pilot team selection | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Pilot retrospective and decision gate | Pilot review with leads to decide go, adjust, or extend | Not started | High | Yellow | Implementation | Glen, Valeria |  | Pilot complete | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Studio-wide rollout sequencing | Order of teams adopting Agilefall after pilot | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Pilot decision | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Coaching plan for leads | One-to-one coaching for each lead through the first cycle | Not started | Medium | Green | Implementation | Glen, Valeria |  | Studio rollout | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Health-check survey | Periodic team health survey covering psychological safety, clarity, delivery | Not started | Medium | Green | Ongoing Mgmt | Lorenz, Valeria |  | Studio rollout | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Agilefall Methodology Rollout | Methodology iteration log | Living document of changes to the methodology with rationale | Not started | Low | Green | Ongoing Mgmt | Valeria |  | Studio rollout | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Map current state to nearest gate | Where the project stands today against the new gate structure | Not started | High | Yellow | Research | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Concept | Game pillars, vision deck, target audience, business case approved | Not started | High | Yellow | Strategy | Glen, Robin, Vardis |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Pre-production | Vertical slice plan, GDD baseline, tech feasibility, art pillars, team plan | Not started | High | Yellow | Strategy | Glen, Robin, Mustafa, David |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Start Production | Full GDD lock, pipelines stable, vertical slice playable, hiring plan signed | Not started | High | Yellow | Strategy | Glen, Valeria, Robin |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Mid-production | Feature-complete in greybox, primary content pipelines proven at scale | Not started | High | Yellow | Strategy | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Late Production | Content complete, polish underway, performance targets in sight | Not started | High | Yellow | Strategy | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Alpha | All features in some state, retention test ready, telemetry live | Not started | High | Yellow | Strategy | Glen, Valeria, Robin |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Beta | Content lock, performance lock, localisation in progress, launch readiness review | Not started | High | Yellow | Strategy | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Launch | Day-zero patch ready, marketing live, support model live, live-ops calendar in place | Not started | High | Yellow | Strategy | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define exit criteria for Live Service 1 to 5 | Per-season exit criteria covering content delivery, retention metrics, monetisation health | Not started | Medium | Green | Strategy | Glen, Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on per-season specifics
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate decision rights | Who chairs, who votes, who advises, who is informed | Not started | High | Yellow | Ongoing Mgmt | Glen, Vardis |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate review meeting format | Standing agenda, evidence pack, decision options, recording, distribution | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Decision rights | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate review evidence pack | Mandatory artefacts each lead brings: status, risks, dependencies, demo, asks | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Gate review format | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define pre-gate readiness checks | Two-week-out, one-week-out checklists per lead | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Gate review format | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate decision options | Pass, conditional pass with action list, hold, fail and re-plan | Not started | High | Yellow | Ongoing Mgmt | Glen |  | Decision rights | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define conditional-pass tracking | How conditions are logged, owned, reviewed, closed | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Decision options | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define escalation path between gates | Mid-gate red flags that trigger executive review without waiting for the formal gate | Not started | High | Yellow | Ongoing Mgmt | Glen, Vardis, Aris |  | Risk register | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define post-gate retrospective | Cross-discipline retro after every gate decision, output to methodology iteration log | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Gate review format | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate metrics | What is measured to evidence each exit criterion; baselining and target values | Not started | High | Yellow | Assessment | Glen, Valeria |  | Exit criteria | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Build gate decision log | Public record of every gate review, the call made, conditions, signatories | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Gate review format | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define inter-gate cadence | Mid-gate checkpoint cadence between formal gate reviews | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Gate review format | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Build gate playbook for leads | One-pager per lead with their evidence requirements per gate | Not started | High | Yellow | Implementation | Glen, Valeria |  | Evidence pack | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Map dependencies across gates | Cross-feature dependencies that constrain which gate a feature can sit in | Not started | High | Yellow | Strategy | Valeria |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define gate communication plan | How outcomes are communicated to studio, partners, investors, board | Not started | Medium | Yellow | Implementation | Glen, Vardis |  | Decision log | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Gate System Design and Rollout | Define partner and external-stakeholder gate visibility | What partners and external collaborators see and when | Not started | Medium | Green | Ongoing Mgmt | Glen |  | Communication plan | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on partner list
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build studio Now Next Later roadmap | Public studio-level roadmap view tied to gates | Not started | High | Yellow | Strategy | Glen, Vardis, Robin |  | Gate structure | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build feature team roadmaps | Per-team Now Next Later, rolling up to studio roadmap | Not started | High | Yellow | Strategy | Valeria |  | Studio roadmap | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define quarterly planning agenda | Two-day session structure, prep work, attendees, outputs | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define monthly checkpoint format | Studio-wide monthly checkpoint with leads | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define weekly leadership health check | Standing weekly meeting agenda, attendees, output, decision log | Not started | High | Yellow | Ongoing Mgmt | Glen, Vardis, Aris, Valeria |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define studio OKR cycle | Annual themes, quarterly OKRs, monthly progress review, end-of-quarter scoring | Not started | High | Yellow | Ongoing Mgmt | Glen, Vardis |  | OKR tracking | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define team OKR cycle | Feature team quarterly OKRs derived from studio OKRs | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Studio OKR cycle | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build OKR scoring rubric | How team OKRs are scored, calibrated across teams, reported | Not started | Medium | Green | Ongoing Mgmt | Glen, Valeria |  | Team OKR cycle | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build dependency map | Cross-team dependency catalogue with owners and lead times | Not started | High | Yellow | Strategy | Valeria |  | Feature team roadmaps | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build risk register | Studio-level risks with owners, severity, mitigation, review cadence | Not started | High | Yellow | Ongoing Mgmt | Glen, Valeria |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define risk review cadence | Weekly leadership health-check slot for top risks; monthly full review | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Risk register | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build assumption log | Tracked assumptions with validation status; review at quarterly planning | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Quarterly planning | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Build decision log | Studio-level decision log so calls do not get re-litigated | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define roadmap change-control | How roadmap changes are proposed, evaluated, approved between quarters | Not started | High | Yellow | Ongoing Mgmt | Glen, Vardis |  | Studio roadmap | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define hiring plan integration | Hiring milestones tied to roadmap and gates | Not started | High | Yellow | Strategy | Lorenz, Vardis, Aris |  | Studio roadmap | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define budget and burn integration | Quarterly burn check tied to roadmap progress | Not started | High | Yellow | Ongoing Mgmt | Vardis, Aris |  | Quarterly planning | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on finance owner
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define partner and external commitments tracker | External milestones, demo dates, publishing or platform deadlines on the roadmap | Not started | Medium | Green | Ongoing Mgmt | Glen, Vardis |  | Studio roadmap | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define communication rhythm to studio | All-hands cadence, written updates, tone | Not started | Medium | Green | Implementation | Vardis, Lorenz |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define communication rhythm to investors and board | Quarterly investor update, board pack cadence, ad-hoc escalations | Not started | High | Yellow | Implementation | Vardis, Glen |  | Cadence aligned | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Roadmap and Cadence Rollout | Define metrics dashboard for cadence health | Sprint completion rate, ceremony attendance, roadmap-vs-actual drift, OKR confidence | Not started | Medium | Green | Assessment | Valeria |  | Dashboards | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Confirm attendees and roles per session | Who attends each session in driver, contributor, observer roles | Not started | High | Red | Implementation | Glen, Valeria |  | none | Production Strategy |  |  |  | Agent / Production Strategy | NEW, Critical ACT for Apr 27
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Pre-read pack for attendees | Methodology summary, gate structure, JIRA preview, current backlog snapshot | Not started | High | Red | Implementation | Glen, Valeria |  | none | Production Strategy |  |  |  | Agent / Production Strategy | NEW, Critical ACT
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Pre-offsite logistics | Room, AV, catering, remote dial-in, materials | Not started | High | Yellow | Implementation | Valeria |  | none | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on logistics owner
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Pre-offsite leads briefing | Short call with each lead before offsite to set expectations | Not started | High | Red | Implementation | Glen, Valeria |  | Attendees confirmed | Production Strategy |  |  |  | Agent / Production Strategy | NEW, Critical ACT
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Day 1 agenda Apr 27 | Production audit findings, current-state debrief, Agilefall principles intro | Not started | High | Yellow | Strategy | Glen, Valeria |  | Pre-read pack | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Day 2 agenda Apr 28 | Gate structure deep dive, exit-criteria drafting per gate, leads as co-authors | Not started | High | Yellow | Strategy | Glen, Valeria |  | Day 1 outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Day 3 agenda Apr 29 | Feature scoping against gates, dependency mapping, JIRA configuration walkthrough | Not started | High | Yellow | Strategy | Glen, Valeria |  | Day 2 outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Day 4 agenda Apr 30 | Vision and strategy session, roadmap commitment, OKR direction, closing actions | Not started | High | Yellow | Strategy | Glen, Vardis, Robin |  | Day 3 outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Live decision log during offsite | Decisions captured in real time with owner and date | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Offsite running | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Live action register during offsite | Actions captured with owner, deadline, success criteria | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Offsite running | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Live parking lot during offsite | Topics raised but deferred, with owner for follow-up | Not started | Medium | Green | Ongoing Mgmt | Valeria |  | Offsite running | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Daily wrap-up summary | End-of-day summary distributed to attendees each evening | Not started | Medium | Green | Implementation | Glen, Valeria |  | Offsite running | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Offsite outputs document | Single canonical document compiled within 48 hours of close | Not started | High | Yellow | Implementation | Glen, Valeria |  | Offsite complete | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Roadmap publication post-offsite | Publish updated Now Next Later roadmap derived from offsite outputs | Not started | High | Yellow | Implementation | Glen, Valeria |  | Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Leads-to-teams cascade comms | Each lead briefs their team within one week post-offsite | Not started | High | Yellow | Implementation | Glen, Valeria, all leads |  | Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | All-hands post-offsite session | Studio-wide all-hands within two weeks; vision, gate structure, methodology | Not started | High | Yellow | Implementation | Vardis, Glen |  | Cascade comms | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Post-offsite retrospective | Leadership retro on offsite itself; what to repeat for next offsite | Not started | Medium | Green | Ongoing Mgmt | Glen, Valeria |  | Offsite complete | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Graham onboarding pack tied to offsite outputs | Prep so Graham lands into a coherent picture from May 18 | Not started | High | Yellow | Implementation | Glen, Vardis, Lorenz |  | Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW, Graham starts ~May 18
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Post-offsite action follow-through cadence | Weekly check-in for the first month against the action register | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Action register | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Update studio risk register from offsite | New risks surfaced at offsite added to the register with owners | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Risk register, Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Update studio dependency map from offsite | New dependencies surfaced at offsite added with owners | Not started | High | Yellow | Ongoing Mgmt | Valeria |  | Dependency map, Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Pilot team kick-off post-offsite | Stand up the two pilot teams against the agreed methodology | Not started | High | Yellow | Implementation | Glen, Valeria |  | Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW
Couch Heroes / Production Strategy & Implementation / Offsite Apr 27-30 and Post-Offsite | Confluence or equivalent home for offsite outputs | Permanent searchable home for the offsite documentation | Not started | Medium | Green | Implementation | Valeria |  | Offsite outputs | Production Strategy |  |  |  | Agent / Production Strategy | NEW, needs Glen on tooling

## HR
parent_path | title | description | status | priority | health_state | work_type | assignees | due_date | dependencies | practice_area | type | layer | confidence | source | notes
Couch Heroes / HR / Hiring Pipeline - Process | Decide whether to use True Recruitment Assessment Tool (with Lorenza) | Evaluate tool for hiring process - we don't believe that Tru's recruitment assessment tool is meaningful for Couch Heroes | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 2
Couch Heroes / HR / Coaching Programme | Department Leads Development | Training modules, role clarity, and stretch assignments for leads | In progress | Medium | Green |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 3
Couch Heroes / HR / Coaching Programme | Short written reflections after key meetings | Institutionalise learning | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 4
Couch Heroes / HR / Coaching Programme | Two observed live interactions per month with written feedback (ongoing) | Structured observation programme | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 5
Couch Heroes / HR / Coaching Programme | Field practice during real meetings with debriefs (ongoing) | Ongoing live coaching | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 6
Couch Heroes / HR / Coaching Programme | Build playbooks with step-by-step patterns | Practical coaching tool | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 7
Couch Heroes / HR / Coaching Programme | Define role charters, scope, and KPIs aligned to product goals | Role clarity for each lead | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 8
Couch Heroes / HR / Coaching Programme | Deliver micro-training modules: planning quality, estimation, stakeholder updates, risk language | Capability building for leads | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 9
Couch Heroes / HR / Coaching Programme | Executive Coaching Programme | Structured coaching: conflict playbook, live observations, reflections Q2 (2026-04-26): Moved from EP Hiring to HR → Coaching Programme. The coaching is separate work from hiring Graham (who has already accepted, ~May 18 start). | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 10
Couch Heroes / HR / Coaching Programme | Identify key strengths and weaknesses across C-level and department head staff to establish areas of work | Communication is spotty and erratic. Key elements of clarity are missing around core details such as: • roles and remits • clarity between roles • consistency of decision making • most critically, clarity on vision and overall direction of the game, which needs to be addressed the department has had no existing forum that was just for them. They were not in a place to challenge and support each other in a healthy way. Establishing the leads meeting has been met positively across department leads. They adapted to the hiring process quickly. They are fairly open about what's working well and what's not. The current sense of ownership is still a little tentative and will take time to establish but is already growing. So far they're a great group of people to work with. | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 11
Couch Heroes / HR / Coaching Programme | Assign stretch work: cross-team dependency burn-down, release readiness packs | Development through stretch assignments | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 12
Couch Heroes / HR / Hiring Pipeline - DONE | Lead Animator Hiring | Evaluate current candidate and prepare interview materials. David Luong is decision-maker Q3 (2026-04-26): Same role as Alon. Marked Done. | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 13
Couch Heroes / HR / Hiring Pipeline - Process | Write Anthony Marques JD and leveling guide | Role definition and leveling | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 15
Couch Heroes / HR / 1:1s - Weekly Programme | Weekly coaching: Department Leads + bi-weekly 1:1s | Recurring weekly coaching and bi-weekly one-to-ones with leads | In progress | Medium | Green |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 16
Couch Heroes / HR / Hiring Pipeline - Process | Fix hiring plan to add UI/UX staffing and reset Anthony Marques's role | Headcount gap identified in Valeria 1:1 - this was missed in the head cap plan and is an alert that needs to be brought back up to Aris and added | Not started | Critical ACT |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 17
Couch Heroes / HR / Hiring Pipeline - Process | Define the critical needed headcount for next steps | Priority roles for studio growth - department heads have come together to provide feedback. Headcount has been assembled and it is currently in review with the leadership of Couch Heroes for approval | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 18
Couch Heroes / HR / Hiring Pipeline - Process | Build out the initial staffing process for Couch Heroes | Define end-to-end hiring workflow - the end-to-end hiring process from selecting staff down through onboarding has been completed in Miro and needs to be put into a report and we need to define a dissemination process, whether it's on Confluence or somewhere else | Drafted | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 19
Couch Heroes / HR / Hiring Pipeline - Process | Link the MIRO board for recruitment workflow / RACI matrix | Connect recruitment process documentation | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 20
Couch Heroes / HR / Hiring Pipeline - Process | Hiring Process & Infrastructure | Build end-to-end hiring workflow and address headcount gaps | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 21
Couch Heroes / HR / Hiring Pipeline - Engineering | Realign Mustafa to new role, define new role scope | Part of CTO transition planning - Mustafa has very comfortably aligned to Principal Engineer this transition has so far gone smoothly | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 22
Couch Heroes / HR / Hiring Pipeline - Engineering | Help close the CTO role | Support offer and negotiation - Cam has a family situation that requires him to go to Australia and be there for an extended period of time. We have offered to Cam, as a studio, to work in an advisor capacity for the time being, with boots on the ground, helping him execute with the team and working with his guidance we are currently waiting on his response to that. Q1: Cam dead. Cancelled. | Cancelled | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 23
Couch Heroes / HR / Hiring Pipeline - Engineering | Participate in CTO interviews | Advisory role in interview panel | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 24
Couch Heroes / HR / Hiring Pipeline - Engineering | Build CTO interview structure and process | End-to-end interview design | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 25
Couch Heroes / HR / Hiring Pipeline - DONE | Build question set for Lead Animator interviews | Interview preparation - this was done and I attended the lead animator interview, asking questions directly Q4 (2026-04-26): Done. ACTION: locate the questions actually used (no separate doc on disk), document them, attach during WorkSage upload. | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 26
Couch Heroes / HR / Hiring Pipeline - Engineering | Identify key CTO candidates | Build target candidate list - our first candidate was Cam Dunn and he is the best out of the candidates they've delivered. There are complications that we're working through but confidence is high that this will continue to a full CTO roll Q1: Cam was the candidate. Cancelled. Need fresh candidate identification. | Cancelled | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 27
Couch Heroes / HR / Hiring Pipeline - Engineering | Find an executive recruiter for CTO role | Source specialist exec recruiter - this is Charlie at True | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 28
Couch Heroes / HR / 1:1s - Weekly Programme | Weekly coaching: Dino 1:1 | Recurring weekly 1:1 coaching sessions with Dino | In progress | High | Green |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 29
Couch Heroes / HR / Hiring Pipeline - Production & Design | Template for interview questions for EP | Standardised question set | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 31
Couch Heroes / HR / Pay & Performance | Give feedback on promotions presentation | Attachment: {"originalUrl":"https:\/\/couchheroes.slack.com\/archives\/C08L3QGJ0AE\/p1772630282819889","attachment":{},"displayAsUrl":false} | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 33
Couch Heroes / HR / Hiring Pipeline - Production & Design | create lead level designer JD | Build a job description for lead level designer and use the template, then get it approved so we can use that template boilerplate as the future structure for all job descriptions | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 47
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Dino | See Dino Notes for one-on-ones | In progress | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 48
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Lorenza | See Lorenza notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 49
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Vardis | See Vardis notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 50
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Aris | See artist notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 51
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Mustafa | See Mustafa notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 52
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Robin | See Robin notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 53
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with David | See David notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 54
Couch Heroes / HR / 1:1s - Weekly Programme | Establish and maintain one-on-ones with Valeria | See Valeria notes for one-on-ones | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 55
Couch Heroes / HR / Pay & Performance | Identify staff and salary bands for targeted new roles added in the hiring process | Take selected roles added in the hiring plan and establish salaries for the UK based on median salary in non-hub locations | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 56
Couch Heroes / HR / Pay & Performance | Build and gain commitment on Pay and performance process for future delivery | Process flow out all the steps and owners of the pay and performance review. The studio is identifying owners on specific areas and steps to go through. Create a Confluence-style article and Visio flow that supports us. | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 57
Couch Heroes / HR / Pay & Performance | Support Dept heads and Leads through delivery | 4 challenge deliveries thus far all have been worked through | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 58
Couch Heroes / HR / Hiring Pipeline - Engineering | CTO Hiring | Executive search for Chief Technology Officer Q1 (2026-04-26): Cam, Neil, Nia ALL DEAD. Restarting search. Question set staged at Clients/Couch Heroes/CTO_Interview_Questions_Couch_Heroes.docx. Scorecard at CTO_Scorecard.xlsx. Recruiting brief at CTO_Recruiting_Brief_v6.pdf. Need to refresh and resource new candidates. | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 60
Couch Heroes / HR / Hiring Pipeline - Production & Design | Build scorecard for EP interviews | Structured evaluation criteria | In progress | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 61
Couch Heroes / HR / Hiring Pipeline - Production & Design | Get bids for external UX research | Vendor evaluation for outsourced UX | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 63
Couch Heroes / HR / Hiring Pipeline - QA | Meet with Hannah: cover QA plan, headcount needs, internal vs external split | Foundational QA planning session | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 71
Couch Heroes / HR / Hiring Pipeline - QA | Review Hannah Pickard for combined QA / UX Research role | Evaluate candidate fit for dual role | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 74
Couch Heroes / HR / Hiring Pipeline - Production & Design | Send UX agency details | Share agency info with team | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 76
Couch Heroes / HR / Hiring Pipeline - QA | Set up one with Hannah | Set up a one-on-one with Hannah to support her as she is the solo QA. We will need to start doing builds and rapid iteration testing so we need to not only understand where she is, what she's already done, but establish what she needs in support of the edit workload coming her way | Not started | High | [5 empty] | Game Studio Operations |  |  |  | CSV row 78
Couch Heroes / HR / Hiring Pipeline - QA | Align with Hannah on overall team size at phases of development | Structure team and hiring process for expected needs going into heavier velocity production | Not started | High | [5 empty] | Game Studio Operations |  |  |  | CSV row 80
Couch Heroes / HR / Hiring Pipeline - Production & Design | Build/confirm interview brief for EP role | Equivalent to the one built for Cam's role | Done | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 92
Couch Heroes / HR / Pay & Performance | Performance Review Process | Complete current cycle actions and build infrastructure for next cycle | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 93
Couch Heroes / HR / Hiring Pipeline - Production & Design | Set up interview panel with Leads | Identify panel members and schedule | Done | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 94
Couch Heroes / HR / Hiring Pipeline - Process | Executive Producer Hiring | CRITICAL FIRST HIRE: Set up full interview process for EP role | In progress | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 95
Couch Heroes / HR / Pay & Performance | Follow back up with Raynor to confirm everything is copacetic | Check alignment on salary and bonus equity | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 99
Couch Heroes / HR / Pay & Performance | Structure salary bands for pay review | Compensation bands by level and role - celery pans globally were researched and identified and delivered and ingested into the existing staff files | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 100
Couch Heroes / HR / Pay & Performance | Decide on Dino's performance review (on hold until Aris) | BLOCKED: waiting on Aris decision Q7 (2026-04-26): Performance review was already DELIVERED. Exit timeline (1mo transition + 2mo garden leave) is TENTATIVE - see Dino exit story for tracking. | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 101
Couch Heroes / HR / Pay & Performance | Train leads on PIP handling and delivery | Capability building for difficult conversations | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 102
Couch Heroes / HR / Pay & Performance | Put coaching and performance check processes in place before next cycle | Prevent inaccurate ratings next round | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 103
Couch Heroes / HR / Pay & Performance | Book meeting with Aris about Valeria | Schedule once Aris is available | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 104
Couch Heroes / HR / Pay & Performance | Give Lorenza feedback on Valeria performance review template | Review the linked document and provide feedback | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 105
Couch Heroes / HR / Pay & Performance | Pay & Performance Governance | Build compensation governance framework for ongoing use | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 106
Couch Heroes / HR / Salary Review Delivery (CLOSED) | Share salary file with Heads of Departments | Distribute to HoDs so delivery conversations can start | Done | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 108
Couch Heroes / HR / Salary Review Delivery (CLOSED) | Fix the formula on the salary file | Formula issue blocking final version | Done | Medium |  |  | Lorenza |  |  | Game Studio Operations |  |  |  | CSV row 109
Couch Heroes / HR / Salary Review Delivery (CLOSED) | Send the final salary file worldwide | WIP, needs to go out ASAP | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 110
Couch Heroes / HR / Pay & Performance | Salary Review Delivery | URGENT: Complete and distribute salary file, enable delivery conversations across studio | Done | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 111
Couch Heroes / HR / Hiring Pipeline - DONE | Talk with David about Lead Animator (current candidate may not be best choice) | Get David's input on direction - this was done. He preferred his top candidate | Done | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 116
Couch Heroes / HR / Hiring Pipeline - DONE | Hire Lead Animator | We hired Alon who is working partial weeks until he finishes his contract with Rick Kindled over the next few months. Legal constraints and risks were assessed. Contracts were put in place. Dino reviewed. Lorenza set up all of the logistics. Alon is started. | Done | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 119
Couch Heroes / HR / Coaching Programme | Coaching Programme |  | Not started | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 121
Couch Heroes / HR / Hiring Pipeline - Art | Hire: TECHNICAL ANIMATOR (HIRED) | {'Role': 'TECHNICAL ANIMATOR (HIRED)', 'Annual Salary (000s)': 44160, 'Benchmark Salary': 60949.99999999999, 'Original Currency': 38400, 'Start Month': 2} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: CTO | {'Role': 'CTO', 'Annual Salary (000s)': 230000, 'Original Currency': 200000, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: EXECUTIVE PRODUCER | {'Role': 'EXECUTIVE PRODUCER', 'Annual Salary (000s)': 172500, 'Original Currency': 150000, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: LEVEL DESIGN LEAD | {'Role': 'LEVEL DESIGN LEAD', 'Annual Salary (000s)': 71300, 'Original Currency': 62000, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: SR CHARACTER MODELER | {'Role': 'SR CHARACTER MODELER', 'Annual Salary (000s)': 57499.99999999999, 'Original Currency': 50000, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: JIRA ADMIN CONTRACTOR | {'Role': 'JIRA ADMIN CONTRACTOR', 'Annual Salary (000s)': 57499.99999999999, 'Original Currency': 50000, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: HR OPERATIONS | {'Role': 'HR OPERATIONS', 'Annual Salary (000s)': 50024.99999999999, 'Original Currency': 43500, 'Start Month': 3} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: LEAD ANIMATOR (HIRED) | {'Role': 'LEAD ANIMATOR (HIRED)', 'Annual Salary (000s)': 114960, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: LEAD FULL STACK DEVELOPER | {'Role': 'LEAD FULL STACK DEVELOPER', 'Annual Salary (000s)': 92000, 'Original Currency': 80000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: LEAD GAMEPLAY DEVELOPER | {'Role': 'LEAD GAMEPLAY DEVELOPER', 'Annual Salary (000s)': 92000, 'Original Currency': 80000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: SNR NETWORK ENGINEER | {'Role': 'SNR NETWORK ENGINEER', 'Annual Salary (000s)': 70150, 'Original Currency': 61000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: HEAD OF FINANCE | {'Role': 'HEAD OF FINANCE', 'Annual Salary (000s)': 97749.99999999999, 'Original Currency': 85000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: GAME DESIGN LEAD | {'Role': 'GAME DESIGN LEAD', 'Annual Salary (000s)': 70150, 'Original Currency': 61000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: ART PRODUCER | {'Role': 'ART PRODUCER', 'Annual Salary (000s)': 54624.99999999999, 'Original Currency': 47500, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - QA | Hire: MID QA TESTER (CONTRACT) | {'Role': 'MID QA TESTER (CONTRACT)', 'Annual Salary (000s)': 33350, 'Original Currency': 29000, 'Start Month': 4} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: UI/UX LEAD (NEW) | {'Role': 'UI/UX LEAD (NEW)', 'Start Month': 5} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: IT LEAD | {'Role': 'IT LEAD', 'Annual Salary (000s)': 69000, 'Original Currency': 60000, 'Start Month': 6} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | Hire: TOOLS ENGINEER | {'Role': 'TOOLS ENGINEER', 'Annual Salary (000s)': 67850, 'Original Currency': 59000, 'Start Month': 8} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: TECH PRODUCER | {'Role': 'TECH PRODUCER', 'Annual Salary (000s)': 53474.99999999999, 'Original Currency': 46500, 'Start Month': 9} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: SNR TECHNICAL ARTIST | {'Role': 'SNR TECHNICAL ARTIST', 'Annual Salary (000s)': 66700, 'Original Currency': 58000, 'Start Month': 9} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: SENIOR LEVEL DESIGNER | {'Role': 'SENIOR LEVEL DESIGNER', 'Annual Salary (000s)': 54624.99999999999, 'Original Currency': 47500, 'Start Month': 9} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: SNR ENVIRO ARTIST | {'Role': 'SNR ENVIRO ARTIST', 'Annual Salary (000s)': 80500, 'Original Currency': 70000, 'Start Month': 9} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - QA | Hire: MID QA TESTER | {'Role': 'MID QA TESTER', 'Annual Salary (000s)': 33350, 'Original Currency': 29000, 'Start Month': 9} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: SR VFX ARTIST | {'Role': 'SR VFX ARTIST', 'Annual Salary (000s)': 61524.99999999999, 'Original Currency': 53500, 'Start Month': 10} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: MID GENERAL DESIGNER | {'Role': 'MID GENERAL DESIGNER', 'Annual Salary (000s)': 40250, 'Original Currency': 35000, 'Start Month': 10} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Audio | Hire: AUDIO MENTOR (3-MONTH CONTRACT) | {'Role': 'AUDIO MENTOR (3-MONTH CONTRACT)', 'Annual Salary (000s)': 69000, 'Original Currency': 60000, 'Start Month': 10} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Production & Design | Hire: ASSOC PRODUCER | {'Role': 'ASSOC PRODUCER', 'Annual Salary (000s)': 31050, 'Original Currency': 27000, 'Start Month': 11} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: SNR LIGHTING ARTIST | {'Role': 'SNR LIGHTING ARTIST', 'Annual Salary (000s)': 57499.99999999999, 'Original Currency': 50000, 'Start Month': 12} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: LEAD CONCEPT ARTIST | {'Role': 'LEAD CONCEPT ARTIST', 'Annual Salary (000s)': 71300, 'Original Currency': 62000, 'Start Month': 11} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Audio | Hire: AUDIO LEAD | {'Role': 'AUDIO LEAD', 'Annual Salary (000s)': 69000, 'Original Currency': 60000, 'Start Month': 10} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Headcount Totals | {'Role': 'Headcount Totals'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: COGS Headcount | {'Role': 'COGS Headcount', 'Cost Type': 'COGS'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: S&M Headcount | {'Role': 'S&M Headcount', 'Cost Type': 'S&M'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: R&D Headcount | {'Role': 'R&D Headcount', 'Cost Type': 'R&D'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: G&A Headcount | {'Role': 'G&A Headcount', 'Cost Type': 'G&A'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Total Headcount | {'Role': 'Total Headcount'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Salary Totals | {'Role': 'Salary Totals'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic Salary Subtotals | {'Role': 'Basic Salary Subtotals'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic COGS Salaries | {'Role': 'Basic COGS Salaries', 'Cost Type': 'COGS'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic S&M Salaries | {'Role': 'Basic S&M Salaries', 'Cost Type': 'S&M'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic R&D Salaries | {'Role': 'Basic R&D Salaries', 'Cost Type': 'R&D'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic G&A Salaries | {'Role': 'Basic G&A Salaries', 'Cost Type': 'G&A'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Basic Salary Subtotal | {'Role': 'Basic Salary Subtotal'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded Salary Subtotals | {'Role': 'Loaded Salary Subtotals'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: (Incl. benefits, employer taxes, + annual raises) | {'Role': '(Incl. benefits, employer taxes, + annual raises)'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded COGS Salaries | {'Role': 'Loaded COGS Salaries', 'Cost Type': 'COGS'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded S&M Salaries | {'Role': 'Loaded S&M Salaries', 'Cost Type': 'S&M'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded R&D Salaries | {'Role': 'Loaded R&D Salaries', 'Cost Type': 'R&D'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded G&A Salaries | {'Role': 'Loaded G&A Salaries', 'Cost Type': 'G&A'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Total Salaries (Loaded) | {'Role': 'Total Salaries (Loaded)'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Recruiting Fees | {'Role': 'Recruiting Fees'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Loaded Salaries + Recruiting | {'Role': 'Loaded Salaries + Recruiting'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Salary Assumptions | {'Role': 'Salary Assumptions'} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Payroll Load (Benefits & Taxes) | {'Role': 'Payroll Load (Benefits & Taxes)', 'Annual Salary (000s)': 0.15, 'Start Month': 0.15, 'Cost Type': 0.15} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Annual Salary Increase % | {'Role': 'Annual Salary Increase %', 'Start Month': 0.03, 'Cost Type': 0.03} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Recruiting Fee % | {'Role': 'Recruiting Fee %', 'Annual Salary (000s)': 0.2, 'Start Month': 0.2, 'Cost Type': 0.2} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Art | Hire: Recruiting Start Month | {'Role': 'Recruiting Start Month', 'Annual Salary (000s)': 13} | In progress | High |  | Implementation |  |  |  | Talent Acquisition |  |  |  | Hiring xlsx / C Level approved
Couch Heroes / HR / Hiring Pipeline - Engineering | CTO restart: source new candidates | Q1 (2026-04-26): Cam, Neil, Nia ALL DEAD. Restart sourcing from scratch with refreshed brief. | Not started | Critical ACT | Red | Implementation | Glen |  |  | Talent Acquisition |  |  |  | Q1 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Hiring Pipeline - Engineering | CTO scorecard refresh | Q1 (2026-04-26): Existing scorecard at Clients/Couch Heroes/CTO_Scorecard.xlsx. Review, refresh against new candidate criteria post-Cam/Neil/Nia. | Not started | High |  | Implementation | Glen |  | CTO_Scorecard.xlsx | Talent Acquisition |  |  |  | Q1 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Hiring Pipeline - Engineering | CTO question set refresh | Q1 (2026-04-26): Existing question set at Clients/Couch Heroes/CTO_Interview_Questions_Couch_Heroes.docx. Review and refresh. | Not started | High |  | Implementation | Glen |  | CTO_Interview_Questions_Couch_Heroes.docx | Talent Acquisition |  |  |  | Q1 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Hiring Pipeline - DONE | Document Lead Animator question set artifact | Q4 (2026-04-26): No separate question-set doc on disk for Lead Animator interview. ACTION: locate the questions actually used (likely informal / verbal / Slack), document them as a reusable artifact, attach to Lead Animator hiring story when uploading to WorkSage. | Not started | Medium |  | Implementation | Glen |  |  | Talent Acquisition |  |  |  | Q4 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Hiring Pipeline - Operations | Hire: Lili Zhao (Chief of Staff, ~£135k) | Q5 (2026-04-26): NEW HIRE separate from Lorenza (who is existing staff handling Dino transition). Per Granola SayBrook discussion ~£135k for COS role. | In progress | High |  | Implementation | Glen |  |  | Talent Acquisition |  |  |  | Q5 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Hiring Pipeline - Operations | HR Operations role - ongoing interviews | Q6 (2026-04-26): Two weak candidates interviewed; sourcing continues. Reference: Slack engineering candidates channel https://couchheroes.slack.com/archives/C0AJBRJTJTA + Google Sheet of all candidates https://docs.google.com/spreadsheets/d/1NaZABJP_8HQCVdrQR9Uoq9g3NYVYdyKHLB8qc3nSLRo/edit | In progress | High |  | Implementation | Glen |  | Slack channel C0AJBRJTJTA / Google Sheet | Talent Acquisition |  |  |  | Q6 (2026-04-26) | NEW from Q&A
Couch Heroes / HR / Staff Changes | Dino exit - transition + garden leave | Q7 (2026-04-26): Performance review DELIVERED. Exit timeline 1mo transition + 2mo garden leave is TENTATIVE. Decided Apr 9. Settlement details with Riley/legal. Lorenza extracting documentation. | In progress | High | Yellow | Implementation | Glen,Lorenza,Riley |  |  | HR Operations |  |  |  | Granola Apr 9 + Q7 (2026-04-26) | NEW from Q&A - dates tentative
Couch Heroes / HR / 1:1s - Weekly Programme | Weekly 1:1 Programme (8 leads) | Q12 (2026-04-26): One programme story + 8 weekly sub-tasks per cycle. Leads: Dino, Lorenza, Vardis, Aris, Mustafa, Robin, David, Valeria. Bi-weekly 1:1s + weekly coaching cadence. | In progress | High | Green | Ongoing Mgmt | Glen |  |  | HR Operations |  |  |  | Q12 (2026-04-26) | NEW from Q&A - programme story

## Studio Operations
parent_path | title | description | status | priority | health_state | work_type | assignees | due_date | dependencies | practice_area | type | layer | confidence | source | notes
Couch Heroes / Studio Operations / Org Design & Structure | QA Structure & UX Research | Define QA org, headcount, and UX research approach | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 14
Couch Heroes / Studio Operations / Org Design & Structure | Org Design Presentation & Strategy | Finalise 3-model org design presentation for exec team and address red team findings | In progress | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 30
Couch Heroes / Studio Operations / Org Design & Structure | Clarify ownership & decision making between designers and artists | Build a clear decision making flow and accountability to remove conflicts and uncertainty | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 32
Couch Heroes / Studio Operations / IT & Systems | Review and assess primary tool set, specifically test rail and purchase tool set | On top of test rail, look at AI implementations that could support and scale QA in a way that mitigates large team | Not started | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 79
Couch Heroes / Studio Operations / Org Design & Structure | Finalise org design presentation (3 models: A/B/C) | Three alternatives for executive leadership review | In progress | Urgent |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 84
Couch Heroes / Studio Operations / Org Design & Structure | Studio review, approval, and commitment | Studio-wide sign-off on framework | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 112
Couch Heroes / Studio Operations / Org Design & Structure | Build a RACI matrix | Clear ownership and accountability mapping | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 113
Couch Heroes / Studio Operations / Org Design & Structure | Build position and level grades per role | Leveling framework for all positions | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 114
Couch Heroes / Studio Operations / Org Design & Structure | Roles & Responsibilities Framework | Build leveling framework, RACI matrix, and get studio commitment | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 115
Couch Heroes / Studio Operations / Org Design and Structure | Finalise org structure at offsite | Lock the "likely" structure shown in Glen's Miro (CEO/CD Aris, COO, CPO Glen, CTO vacant, with HR/Finance/IT/Legal/PM under COO and production tracks under Exec Prod) into the canonical org chart. Replace org_structure_likely_2026-04-26.md with org_structure_FINAL_<date>.md once agreed. | In progress | Critical ACT | Yellow | Strategy | Vardis/Aris/Glen |  | org_structure_likely_2026-04-26.md | Studio Operations |  |  |  | Agent / Studio Operations | Offsite output. Confirm Producer overlay convention, "Lead vs Leads" under CTO, and the second TD node.
Couch Heroes / Studio Operations / Org Design and Structure | Define COO scope of authority | Document the COO remit (HR, Finance, IT, Legal, PM) including budget authority, approval thresholds, hire/fire authority, and what escalates to CEO. Without this the COO cannot run the four ops functions cleanly. | Not started | High |  | Strategy | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Required before Aris signs off any ops spend.
Couch Heroes / Studio Operations / Org Design and Structure | Define CPO scope of authority | Document Glen's CPO remit (Marketing, Brand, PR, Community, BD, Web, Exec Prod oversight) and the boundary between CPO and Game Director (Robin) on creative direction. | Not started | High |  | Strategy | Vardis/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Fractional role - hours and decision rights need to be explicit.
Couch Heroes / Studio Operations / Org Design and Structure | Define Game Director scope vs CPO | Robin owns creative vision; CPO owns commercial outcomes. Codify where they meet (feature green-light, scope cuts, monetisation hooks). | Not started | High |  | Strategy | Robin/Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Most common friction point in studios this size.
Couch Heroes / Studio Operations / Org Design and Structure | Define Executive Producer remit | Graham starts ~May 18. Document what Exec Prod owns (cross-discipline scheduling, milestone delivery, dependency management) vs what each discipline lead owns (craft quality). | Not started | High |  | Strategy | Glen/Graham |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Onboarding artefact for Graham.
Couch Heroes / Studio Operations / Org Design and Structure | Producer overlay model | Confirm whether the violet "producer" boxes attached to QA/Audio/Art/Design/CTO are embedded production managers reporting to Exec Prod or dotted-line to discipline leads. Document the model. | Not started | High |  | Strategy | Glen/Graham |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Open question from Miro per org_structure_likely file.
Couch Heroes / Studio Operations / Org Design and Structure | RACI matrix for top 30 decisions | Build a RACI for the 30 most common cross-functional decisions (hire approval, scope change, tech spike approval, marketing spend, contract sign-off, vendor selection, etc). | Not started | High |  | Strategy | Aris/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Prevents the "who decides this" loop that kills small studios.
Couch Heroes / Studio Operations / Org Design and Structure | Decision log and governance cadence | Set up a single decision log (Notion/Confluence) and a weekly leadership stand-up (Vardis/Aris/Glen/Robin/Mustafa/Valeria/David/Lorenz). | Not started | High |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Pairs with RACI.
Couch Heroes / Studio Operations / Org Design and Structure | Org chart published artefact | Convert the agreed structure into a clean published org chart (PDF + interactive) for the company, investors, and Sponsor Licence application. | Not started | High |  | Implementation | Lorenz |  | org_structure_FINAL_<date>.md | Studio Operations |  |  |  | Agent / Studio Operations | Sponsor Licence application needs this.
Couch Heroes / Studio Operations / Org Design and Structure | Reporting lines in HRIS | Once HRIS is selected, configure reporting lines so they match the published org chart. Audit quarterly. | Not started | Medium |  | Ongoing Mgmt | Lorenz |  | HRIS selection (IT feature) | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Job family and levelling framework | Define job families (Engineering, Art, Design, Audio, QA, Production, Ops) and levels (IC1-IC6, M1-M3) with salary bands per level. Required for Sponsor Licence salary justification and for fair pay decisions. | Not started | High |  | Strategy | Lorenz/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Use SOC 2020 codes for Sponsor Licence alignment.
Couch Heroes / Studio Operations / Org Design and Structure | Salary banding by job family | Build UK salary bands per family/level using market data (Skillsearch, Hays Games, Datapeople). Bands must clear Skilled Worker thresholds (£41,700 general, £33,400 new entrant). | Not started | High |  | Research | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Critical for visa-route hires.
Couch Heroes / Studio Operations / Org Design and Structure | Approvals matrix for headcount | Document who can request a hire, who approves backfill, who approves a new role. Tie to budget. | Not started | Medium |  | Strategy | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Operating principles | Codify 5-7 studio operating principles (e.g. craft over speed, written decisions, async-first, etc) to anchor culture as headcount scales. | Not started | Medium |  | Strategy | Vardis/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Use brainstorming skill at offsite.
Couch Heroes / Studio Operations / Org Design and Structure | Studio comms architecture | Map the comms tools (Slack/Teams, email, Notion/Confluence, Jira/Linear, video, async memos) and the canonical use of each. Stops "where does this go" overhead. | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Meeting cadence framework | Define the recurring meeting set: weekly leadership, weekly all-hands, monthly business review, quarterly OKR review, monthly skip-levels. Document required attendees and outputs. | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | OKR/quarterly planning rhythm | Pick a planning system (OKRs vs V2MOM vs simple goals) and a quarterly cadence. Required for investor reporting maturity. | Not started | High |  | Strategy | Vardis/Aris/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Promotion and progression policy | Define how people move up levels - what's required, who decides, calibration cadence. Without this you get ad hoc promotions and pay drift. | Not started | Medium |  | Strategy | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Tie to job family framework.
Couch Heroes / Studio Operations / Org Design and Structure | Performance management system | Choose a performance management approach (continuous feedback vs annual review vs hybrid) and set up the tooling. | Not started | Medium |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Onboarding programme - all hires | Extend the existing onboarding checklist into a 30/60/90 day programme with role-specific tracks (eng, art, design, ops). | Not started | High |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Offboarding programme | Standard leaver process: notice handling, knowledge transfer, IP handover, access revocation, final pay, Home Office notification (if sponsored), exit interview. | Not started | Medium |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Different flows for sponsored vs non-sponsored leavers.
Couch Heroes / Studio Operations / Org Design and Structure | Cross-functional working groups | Establish standing working groups for cross-cutting concerns (Live Ops readiness, security, data, accessibility) with named owners. | Not started | Low |  | Strategy | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Premature now; revisit at ~30 headcount.
Couch Heroes / Studio Operations / Org Design and Structure | Org review cadence | Quarterly review of the org chart vs the work - are we structured for the work we're actually doing? | Not started | Medium |  | Ongoing Mgmt | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Team charters per discipline | Each discipline lead writes a one-pager: mission, scope, what we own, what we don't, how to engage us. | Not started | Medium |  | Implementation | Discipline leads |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Useful onboarding asset.
Couch Heroes / Studio Operations / Org Design and Structure | Internal communications plan | Cadence for company-wide updates: weekly written update from CEO, monthly all-hands, quarterly state-of-the-studio. | Not started | Medium |  | Implementation | Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Studio values and behaviours | Document studio values and the observable behaviours that demonstrate them (used in hiring, performance, calibration). | Not started | Medium |  | Strategy | Vardis/Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Greece studio - structural fit | If the Greece initiative proceeds, decide where it sits in the org (subsidiary, branch, contractor pool) and the reporting lines. | Not started | High | Waiting on Client | Strategy | Vardis/Aris/Glen |  | Greece initiative (Legal feature) | Studio Operations |  |  |  | Agent / Studio Operations | Conflict risk: pre-empts Riley legal advice.
Couch Heroes / Studio Operations / Org Design and Structure | Contractor vs employee decision framework | Document when to use employees vs UK contractors vs overseas contractors vs outsourcers, with the IR35 and Sponsor Licence implications spelt out. | Not started | High |  | Strategy | Lorenz/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | UK IR35 rules apply if CH determines status.
Couch Heroes / Studio Operations / Org Design and Structure | Diversity and inclusion approach | Set the studio's D&I posture and any measurable commitments. Required for some publishers' inclusion riders and for grant applications. | Not started | Medium |  | Strategy | Lorenz/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Org dashboard - headcount and vacancies | Live dashboard showing actual vs planned headcount, open roles, time-to-hire, attrition. | Not started | Medium |  | Ongoing Mgmt | Lorenz |  | HRIS | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design and Structure | Succession planning - key roles | Identify key-person risks (CTO when filled, Game Director, Head of Production) and document succession or continuity plans. | Not started | Medium |  | Strategy | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Investors will ask in due diligence.
Couch Heroes / Studio Operations / Org Design and Structure | Role-based access matrix | Tie each role in the org chart to its access entitlements (systems, data, repos). Pairs with IT/identity work. | Not started | Medium |  | Implementation | Mustafa/Lorenz |  | IT identity setup | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Open UK business bank account | Open a GBP business current account for CH Game Development LTD (Tide, Starling Business, Allica, or Barclays). Must support multi-user access and accounting integration. | Not started | Critical ACT |  | Implementation | Aris |  | UK Co incorporation | Studio Operations |  |  |  | Agent / Studio Operations | Several need 2-4 weeks for KYC. Start immediately on incorporation.
Couch Heroes / Studio Operations / Finance | Set up multi-currency wallet | USD/EUR receiving capability for any US/EU revenue or grant inflow, and for paying overseas contractors. Wise Business or Airwallex. | Not started | High |  | Implementation | Aris |  | UK bank account | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Select and implement accounting software | Pick Xero or QuickBooks Online (Xero preferred for UK + ecosystem). Configure chart of accounts for a games studio (capitalisable dev costs vs opex, R&D-eligible, project-coded). | Not started | Critical ACT |  | Implementation | Aris/external accountant |  | UK bank account | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Appoint UK accountant/bookkeeper | Engage a UK accounting firm with games-industry experience (BDO, Saffery, Crowe, or boutique like Counterculture, Royce Peeling Green). Define scope: bookkeeping, year-end accounts, CT600, R&D claims. | Not started | Critical ACT |  | Implementation | Vardis/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Riley legal can probably refer.
Couch Heroes / Studio Operations / Finance | Chart of accounts design | Design CoA with project codes, capitalisation flags for dev costs, R&D-eligible expenditure tags, and grant-fund tracking. Wrong CoA early = painful re-coding later. | Not started | High |  | Implementation | External accountant |  | Accounting software | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Register for Corporation Tax | Register with HMRC for CT within 3 months of starting business activity. | Not started | Critical ACT |  | Implementation | External accountant |  | UK Co incorporation | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 5.4 Corporation Tax Registration - confirm at offsite. Per CH_Guidance section 5.
Couch Heroes / Studio Operations / Finance | VAT registration assessment | Monitor turnover vs the £90,000 VAT threshold. Voluntary registration may help if mostly B2B and reclaiming VAT on big purchases (Unreal seats, hardware). | Not started | High |  | Assessment | External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 5.5 VAT Registration - confirm at offsite. Decision before first invoice.
Couch Heroes / Studio Operations / Finance | Set up payroll provider | Engage a payroll bureau (Moorepay, MHR, ADP, or accountant-provided) or run in Xero Payroll. Must support RTI, auto-enrolment, statutory pay calculations, BACS. | Not started | Critical ACT |  | Implementation | Aris/Lorenz |  | UK bank account | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance section 4. Required before first payday.
Couch Heroes / Studio Operations / Finance | HMRC employer registration (PAYE) | Register as employer with HMRC; receive PAYE reference and Accounts Office reference. | Not started | Critical ACT |  | Implementation | External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 4.1.
Couch Heroes / Studio Operations / Finance | Auto-enrolment pension scheme | Set up qualifying workplace pension (NEST for low-cost; Aviva/Smart Pension/Penfold for richer features). 3% employer / 5% employee minimum. | Not started | Critical ACT |  | Implementation | Lorenz/Aris |  | Payroll provider | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 1.6 Pension Auto-Enrolment Letter - confirm at offsite. Per CH_Guidance section 2. £6,240-£50,270 qualifying band 2026/27.
Couch Heroes / Studio Operations / Finance | Pension declaration of compliance | Submit declaration of compliance to The Pensions Regulator within 5 months of duties starting. | Not started | High |  | Implementation | Lorenz |  | Pension scheme live | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 2.4.
Couch Heroes / Studio Operations / Finance | Pension re-enrolment cycle | Diary 3-yearly cyclical re-enrolment of opted-out employees. | Not started | Medium |  | Ongoing Mgmt | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Employers' Liability Insurance | Procure £5m minimum cover. Required by law and for Sponsor Licence application. Display certificate. | Not started | Critical ACT |  | Implementation | Aris/Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 1.7 EL Insurance Certificate - confirm at offsite. £250-£800/year per CH_Guidance 1.1.
Couch Heroes / Studio Operations / Finance | Professional Indemnity Insurance | Cover for advisory/contractual work. £1m+ recommended. | Not started | High |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | £150-£1,200/year.
Couch Heroes / Studio Operations / Finance | Cyber Insurance | Studio holds source code, builds, player data (eventually). £1-2m cover band. | Not started | High |  | Implementation | Aris/Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | £200-£2,500/year. Required by some publishers.
Couch Heroes / Studio Operations / Finance | Public Liability Insurance | If hosting visitors, events, playtests at the studio. | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | £80-£350/year.
Couch Heroes / Studio Operations / Finance | Equipment cover | Insurance on workstations and dev hardware. | Not started | Medium |  | Implementation | Aris/Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | £100-£450/year.
Couch Heroes / Studio Operations / Finance | Directors and Officers Insurance | D&O cover for directors. Investors will likely require post-Series A. | Not started | Medium |  | Implementation | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | £150-£800/year.
Couch Heroes / Studio Operations / Finance | Insurance renewal calendar | Single source of truth for all policy renewal dates with 60-day pre-renewal review trigger. | Not started | High |  | Ongoing Mgmt | Aris |  | All insurances | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Statutory accounts process | Annual filing process at Companies House and CT600 to HMRC. Define close, sign-off, audit (if/when applicable). | Not started | High |  | Ongoing Mgmt | External accountant/Aris |  | Accounting software, accountant | Studio Operations |  |  |  | Agent / Studio Operations | First filing window starts at year-end.
Couch Heroes / Studio Operations / Finance | Confirmation statement filing | Annual Companies House confirmation statement (PSC, share capital, registered office). | Not started | High |  | Ongoing Mgmt | External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 5.x Companies House Filings - confirm at offsite.
Couch Heroes / Studio Operations / Finance | Director Identity Verification | Per Economic Crime and Corporate Transparency Act 2023, directors must verify identity with Companies House. | Not started | High |  | Implementation | All directors |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 5.3 Director Identity Verification - confirm at offsite. Per CH_Guidance Priority 5.
Couch Heroes / Studio Operations / Finance | R&D Tax Relief claim process | Games studios qualify under the merged RDEC scheme. Claim covers eligible salaries, contractor costs, software. Material cash benefit (typically 16.2% of qualifying spend). | Not started | High |  | Strategy | External accountant/Aris |  | Chart of accounts (R&D tags) | Studio Operations |  |  |  | Agent / Studio Operations | Material to runway. Don't lose claim through poor categorisation.
Couch Heroes / Studio Operations / Finance | R&D claim documentation regime | Set up the technical narrative and project-time tracking required to substantiate R&D claims. HMRC scrutiny is high. | Not started | High |  | Ongoing Mgmt | Mustafa/Aris |  | R&D Tax Relief process | Studio Operations |  |  |  | Agent / Studio Operations | Mustafa documents the technical advance per claim period.
Couch Heroes / Studio Operations / Finance | Video Games Expenditure Credit assessment | Assess eligibility for VGEC (the games-specific credit replacing Video Games Tax Relief). 34% of qualifying core expenditure. Requires BFI cultural test certification. | Not started | High |  | Assessment | External accountant/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Significant - games studios usually claim VGEC OR R&D, not both for same expenditure.
Couch Heroes / Studio Operations / Finance | BFI cultural test application | Apply for Interim Certificate from BFI to support VGEC. Detailed scoring on cultural content/contribution/hubs/practitioners. | Not started | High |  | Implementation | Aris/Robin |  | VGEC assessment done | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Treasury policy | How much cash held where, in what currencies, FX hedging stance, counterparty bank limits. Critical when raise lands. | Not started | Medium |  | Strategy | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Pre-raise: lightweight. Post-raise: formal policy required by board.
Couch Heroes / Studio Operations / Finance | Cash flow forecast - 13 week | Rolling 13-week cash forecast updated weekly. Standard board ask. | Not started | High |  | Ongoing Mgmt | Aris |  | Accounting software | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Annual budget and operating plan | Build a bottoms-up annual budget with monthly phasing. Tied to headcount plan, milestones, and runway projection. | Not started | High |  | Strategy | Aris/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Long-range financial model | 3-year P&L, cash, headcount model. Used for fundraising and board. | Not started | High |  | Strategy | Aris/Glen |  | Annual budget | Studio Operations |  |  |  | Agent / Studio Operations | Glen has experience with games studio LRPs - leverage.
Couch Heroes / Studio Operations / Finance | Monthly close process | Define close calendar (D+5 target initially, D+3 once mature). Tasks, owners, dependencies. | Not started | High |  | Implementation | Aris/External accountant |  | Accounting software | Studio Operations |  |  |  | Agent / Studio Operations | Use finance:close-management skill when building.
Couch Heroes / Studio Operations / Finance | Bank reconciliation procedure | Monthly bank rec to GL. Document workflow and exception handling. | Not started | High |  | Ongoing Mgmt | External bookkeeper |  | Accounting software | Studio Operations |  |  |  | Agent / Studio Operations | finance:reconciliation skill.
Couch Heroes / Studio Operations / Finance | Monthly management accounts pack | P&L, balance sheet, cash, vs budget variance, headcount, runway. Distributed to leadership and investors. | Not started | High |  | Ongoing Mgmt | Aris |  | Monthly close, LRP | Studio Operations |  |  |  | Agent / Studio Operations | finance:financial-statements skill.
Couch Heroes / Studio Operations / Finance | Investor reporting cadence | Standardised investor update (monthly during raise, quarterly otherwise). KPIs, financials, risks, asks. | Not started | High |  | Ongoing Mgmt | Vardis/Aris |  | Monthly mgmt accounts | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Board reporting pack template | Quarterly board pack: financials, milestones, KPIs, risks, decisions sought. | Not started | Medium |  | Implementation | Vardis/Aris |  | Investor reporting | Studio Operations |  |  |  | Agent / Studio Operations | Triggered when first institutional money lands.
Couch Heroes / Studio Operations / Finance | Cap table management | Maintain a clean cap table (Carta, Capdesk, Ledgy or spreadsheet to start). Track ordinary, preference, options, vested/unvested, dilution scenarios. | Not started | High |  | Ongoing Mgmt | Vardis/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | EMI option scheme design | Design an Enterprise Management Incentive scheme to grant tax-advantaged options. Hiring competitiveness tool. | Not started | High |  | Strategy | Riley/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 4.12 EMI Share Scheme - confirm at offsite. Per CH_Guidance Priority 4 (optional but high-value).
Couch Heroes / Studio Operations / Finance | EMI valuation - HMRC agreement | Get HMRC agreement on share valuation (VAL231) before granting options. Avoids tax surprises later. | Not started | High |  | Implementation | External accountant/Riley |  | EMI scheme design | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Option grant administration | Process for issuing options, board minutes, option certificates, register, vesting tracking. | Not started | Medium |  | Ongoing Mgmt | Aris/Riley |  | EMI scheme live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Expenses policy and tooling | Policy + an expense tool (Pleo, Soldo, Spendesk, Brex). Card issuance per role. Limits per spender. | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Procurement and PO policy | Approval thresholds for purchases. Vendor onboarding (W-8/W-9, sanctions check, payment terms). | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Becomes important at ~15 headcount.
Couch Heroes / Studio Operations / Finance | Payment runs and approvals | Weekly or twice-monthly payment run with dual approval over a threshold. | Not started | Medium |  | Ongoing Mgmt | Aris |  | UK bank account | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Foreign currency policy | If contracting overseas talent or receiving foreign income, document FX handling - spot, forward, natural hedge. | Not started | Medium |  | Strategy | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Year-end audit readiness | Even pre-audit threshold, build clean books as if audited. Lowers cost when audit becomes required. | Not started | Medium |  | Ongoing Mgmt | External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | KPI definition and reporting | Define financial and operational KPIs (burn, runway, headcount, dev velocity proxy, milestone health). | Not started | High |  | Strategy | Aris/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Grant funding pipeline | Track UKGI Games Fund, BFI Filmmaking Fund (where applicable), Innovate UK, Creative Scotland (if applicable), Wales Interactive. | Not started | High |  | Research | Vardis/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Non-dilutive £25k-£500k bands. Glen has applied before.
Couch Heroes / Studio Operations / Finance | Grant compliance regime | Once any grant lands, set up the reporting, milestone evidencing, and audit trail required by the funder. | Not started | Medium |  | Ongoing Mgmt | Aris |  | First grant secured | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Finance | Equity vs debt financing strategy | Document the company's stance on different capital types: equity, convertible, SAFE, venture debt, publisher advances, revenue-share deals. | Not started | High |  | Strategy | Vardis/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Anchors fundraising conversations.
Couch Heroes / Studio Operations / Finance | Financial controls register | Document key controls: bank dual auth, payment approvals, payroll review, expense limits, journal review. | Not started | Medium |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Pre-audit hygiene.
Couch Heroes / Studio Operations / Finance | Tax calendar | All HMRC deadlines: PAYE monthly, VAT quarterly (if registered), CT instalments (if applicable), CT600, P11D, P60s. | Not started | High |  | Ongoing Mgmt | External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Fundraising strategy and ask | Define round size, instrument (priced equity vs SAFE/convertible), use of funds, milestone gating, target close. | In progress | Critical ACT | Yellow | Strategy | Vardis/Glen |  | LRP financial model | Studio Operations |  |  |  | Agent / Studio Operations | Live conversation with Alter Ego/Picks/Enoma/Madrona.
Couch Heroes / Studio Operations / Fundraising | Investor pipeline tracker | CRM-style tracker of every investor conversation: stage, last touch, next step, materials shared, blockers. | Not started | High |  | Implementation | Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Glen's experience: this gets out of hand fast without it.
Couch Heroes / Studio Operations / Fundraising | Pitch deck v1 | Build the canonical pitch deck. Vision, team, market, product, traction, business model, ask. | In progress | Critical ACT | Green | Implementation | Vardis/Glen |  | Vision doc, LRP | Studio Operations |  |  |  | Agent / Studio Operations | gi skill applies.
Couch Heroes / Studio Operations / Fundraising | Pitch deck investor variants | Tailored variants per investor archetype (publisher-style vs VC vs strategic). | Not started | High |  | Implementation | Glen |  | Pitch deck v1 | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Demo build for investors | Playable or video demo for investor meetings. Timing tied to vertical slice. | Not started | High |  | Implementation | Robin/Valeria |  | Vertical slice (Game project) | Studio Operations |  |  |  | Agent / Studio Operations | Most-asked artefact in pitches.
Couch Heroes / Studio Operations / Fundraising | Data room - structure and seed | Set up a secure data room (Notion vault, DocSend, Datasite). Folder structure, access controls, NDA gating. | Not started | High |  | Implementation | Aris/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | gi skill has data room template.
Couch Heroes / Studio Operations / Fundraising | Data room - corporate documents | Cert of incorp, articles, share register, cap table, board minutes, PSC register. | Not started | High |  | Implementation | Riley/Aris |  | UK Co fully set up | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Data room - financial documents | Historic accounts (when available), management accounts, budget, LRP, cap table, R&D status. | Not started | High |  | Implementation | Aris |  | Monthly close, LRP | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Data room - product documents | Vision doc, GDD, pillar docs, competitive analysis, market sizing, design samples. | Not started | High |  | Implementation | Robin/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Data room - team documents | Founder bios, key hires, org chart, hiring plan, employment contracts (templates), EMI scheme. | Not started | High |  | Implementation | Lorenz/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Data room - legal and IP | Cap table, options register, IP assignments confirmed, trademark filings, key contracts, insurance. | Not started | High |  | Implementation | Riley |  | IP register | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Investor due diligence Q&A doc | Standing Q&A doc populated as investors ask questions. Dramatically speeds subsequent conversations. | Not started | High |  | Ongoing Mgmt | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Reference call list | Vetted list of references by archetype (advisor, ex-colleague, customer, vendor) with intro scripts. | Not started | Medium |  | Implementation | Vardis/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Term sheet playbook | Documented positions on the standard term-sheet items (valuation, liquidation pref, anti-dilution, board, vesting, ROFR, drag, info rights). | Not started | High |  | Strategy | Glen/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | gi skill content.
Couch Heroes / Studio Operations / Fundraising | Investor meeting cadence and material reuse | System for what gets sent in advance, in the meeting, in follow-up. Avoids ad hoc material creation per meeting. | Not started | Medium |  | Implementation | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Alter Ego conversation tracker | Specific tracker for Alter Ego's process: who they've met, what they've asked, current stage, blockers, next step. | In progress | High | Green | Ongoing Mgmt | Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations | One of four active investors.
Couch Heroes / Studio Operations / Fundraising | Picks Capital conversation tracker | Specific tracker for Picks Capital. | In progress | High | Green | Ongoing Mgmt | Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Enoma conversation tracker | Specific tracker for Enoma. | In progress | High | Green | Ongoing Mgmt | Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Madrona conversation tracker | Specific tracker for Madrona. | In progress | High | Green | Ongoing Mgmt | Glen/Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Investor outreach expansion | Pipeline build beyond the current four: identify and warm-intro to 20-30 additional relevant funds (gaming-focused, Series A/seed, EU/UK/US). | Not started | High |  | Research | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Glen's network applies.
Couch Heroes / Studio Operations / Fundraising | Strategic investor strategy | Decision on whether to take strategic capital (publisher, platform, IP holder) and on what terms. Has implications for distribution rights and valuation. | Not started | High |  | Strategy | Vardis/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Publisher conversations - parallel track | Run a parallel track with publishers as either co-fund or eventual deal partners. | Not started | Medium |  | Strategy | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | EIS/SEIS advance assurance | Apply for HMRC advance assurance for EIS (and SEIS if applicable) to enable UK individual angels to invest tax-efficiently. | Not started | High |  | Implementation | Riley/External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Material to UK angel rounds.
Couch Heroes / Studio Operations / Fundraising | Investor legal docs - SHA template | Standard shareholders' agreement template ready for the round. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Investor legal docs - articles update | Articles of association update for institutional round (preference share class, drag, tag, etc). | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Triggered at term sheet stage.
Couch Heroes / Studio Operations / Fundraising | Investor reporting commitments | Once a round closes, document the reporting commitments (frequency, format, KPIs) to investors. | Not started | High |  | Implementation | Aris/Vardis |  | Round close | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Board composition post-round | Decide on board seats (founders, investor, independent), governance committees if required, and chair role. | Not started | High |  | Strategy | Vardis/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Closing process plan | Step-by-step plan from term sheet to wired funds: DD, legal, signing, completion mechanics. | Not started | High |  | Implementation | Aris/Riley |  | Term sheet signed | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Use-of-funds tracker | Once funded, track actual spend vs the use-of-funds in the deck. Investors check this. | Not started | High |  | Ongoing Mgmt | Aris |  | Round close | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Bridge/extension contingency plan | If main round slips, what's the bridge plan? Convertible from existing investors, founder loan, cost cuts. | Not started | High |  | Strategy | Vardis/Aris/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Fundraising comms to staff | When and how to communicate fundraising progress internally. Closed-loop messaging to avoid uncertainty drag. | Not started | Medium |  | Strategy | Vardis |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Fundraising | Press and announce strategy | Launch announcement strategy when round closes. Tied to studio brand and recruiting. | Not started | Medium |  | Strategy | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Identity provider selection | Pick the SSO/identity backbone: Google Workspace, Microsoft 365, or Okta. All downstream tooling routes through it. | Not started | Critical ACT |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Highest-leverage IT decision.
Couch Heroes / Studio Operations / IT and Systems | Identity provider implementation | Roll out the chosen IdP, set up groups by team/role, configure SCIM provisioning to all major SaaS tools. | Not started | Critical ACT |  | Implementation | Mustafa |  | IdP selection | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | SSO enforcement on all SaaS | Mandatory SSO via the IdP for all business systems. No standalone passwords. | Not started | High |  | Implementation | Mustafa |  | IdP live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Password manager rollout | Deploy 1Password Business or Bitwarden for shared credentials and break-glass accounts. | Not started | High |  | Implementation | Mustafa |  | IdP live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Multi-factor authentication policy | Mandatory MFA on all business accounts. Hardware key (YubiKey) preferred for admins. | Not started | High |  | Implementation | Mustafa |  | IdP live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Workstation procurement standard | Standard hardware spec by role (engineering, art, design, ops). Apple Silicon vs Windows for Unreal-heavy roles. Volume purchase channel (CDW, Computacenter, Apple Business). | Not started | High |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Art/eng need beefy specs for Unreal.
Couch Heroes / Studio Operations / IT and Systems | Workstation procurement process | Define the order-to-desk flow including imaging, MDM enrolment, kit-out, handover, asset tagging. | Not started | High |  | Implementation | Mustafa |  | Workstation standard | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Mobile device management | Deploy MDM (Jamf for Apple, Intune for Windows, Kandji as alt) to manage all corporate devices. | Not started | High |  | Implementation | Mustafa |  | Workstation procurement | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Endpoint security standard | Encryption (FileVault/BitLocker), endpoint protection (CrowdStrike/SentinelOne or Defender for Business), patch policy, screen lock. | Not started | High |  | Implementation | Mustafa |  | MDM | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | VPN and remote access | Deploy a Zero Trust access tool (Tailscale, Cloudflare Access, Twingate) or traditional VPN for accessing the build farm and asset storage. | Not started | High |  | Implementation | Mustafa |  | IdP live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Office network design | If a physical office, design the network: VLAN segmentation, guest WiFi separation, wired backbone for Unreal teams. | Not started | Medium |  | Implementation | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Office decision dependency.
Couch Heroes / Studio Operations / IT and Systems | Source control - Perforce or Git LFS | Decide on Unreal-friendly version control: Perforce Helix (industry default for Unreal) or Git + LFS + UnrealGitPlugin. Perforce strongly preferred for art-heavy projects. | Not started | Critical ACT |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Hard to change later. Get this right.
Couch Heroes / Studio Operations / IT and Systems | Source control hosting | Host Perforce on AWS/Azure or use Assembla/Helix Cloud. Sizing, backup, region. | Not started | Critical ACT |  | Implementation | Mustafa |  | Source control choice | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Source control - branch and submit policy | Branching strategy (mainline, dev, feature streams), submit policy, code review hooks, locked file workflow for art assets. | Not started | High |  | Implementation | Mustafa |  | Source control hosted | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Build infrastructure - CI/CD | Build farm for Unreal: TeamCity, Jenkins, or BuildKite. Cooks per platform, cook caching, packaged builds for QA/playtest. | Not started | High |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Sized to Unreal cook times. Expensive but essential.
Couch Heroes / Studio Operations / IT and Systems | Build infrastructure - DDC and shader cache | Distributed Derived Data Cache and Shared Shader Cache to keep iteration time sane across team. | Not started | High |  | Implementation | Mustafa |  | Source control | Studio Operations |  |  |  | Agent / Studio Operations | Massive iteration-time saver.
Couch Heroes / Studio Operations / IT and Systems | Asset storage and review tooling | Where do art reviews and reference live - SyncSketch, ftrack, ShotGrid (Flow Production Tracking), or Plastic SCM? | Not started | Medium |  | Strategy | David/Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Art-specific decision.
Couch Heroes / Studio Operations / IT and Systems | Cloud platform standard | AWS or Azure or GCP as the primary cloud. Tied to build farm, asset storage, future game backend. | Not started | High |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Cloud account structure | Multi-account/subscription setup with separation of dev, staging, prod, build, sandbox. IAM/RBAC tied to IdP. | Not started | High |  | Implementation | Mustafa |  | Cloud platform, IdP | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Cost monitoring and FinOps | Cloud cost dashboards, alerts on anomalies, monthly review. Build farms and DDC can balloon fast. | Not started | High |  | Ongoing Mgmt | Mustafa/Aris |  | Cloud platform live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Backup and disaster recovery policy | What gets backed up, how often, where stored, retention, recovery time/point objectives. Source control snapshot, asset storage, business systems. | Not started | High |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Investor DD will ask.
Couch Heroes / Studio Operations / IT and Systems | Backup implementation | Implement the backup regime: Perforce snapshots, cloud cross-region replication, SaaS exports (Notion, Google Workspace). | Not started | High |  | Implementation | Mustafa |  | Backup policy | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | DR runbook and tabletop | Documented DR runbook, annual tabletop exercise, RPO/RTO commitments. | Not started | Medium |  | Implementation | Mustafa |  | Backup live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Information security policy | Comprehensive InfoSec policy: data classification, acceptable use, access control, incident response, vendor risk. | Not started | High |  | Strategy | Mustafa/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Required by some publishers/platform holders.
Couch Heroes / Studio Operations / IT and Systems | Acceptable use policy | Staff-facing AUP for company devices, networks, data. Tied to onboarding sign-off. | Not started | High |  | Implementation | Mustafa/Lorenz |  | InfoSec policy | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Data classification scheme | Public / Internal / Confidential / Restricted. Tag systems and data accordingly. | Not started | Medium |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Incident response plan | Steps for security incidents: detection, containment, eradication, recovery, post-mortem. Named on-call. | Not started | High |  | Implementation | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Vulnerability management | Patch cadence, vulnerability scanning, third-party dependency scanning. | Not started | Medium |  | Ongoing Mgmt | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Penetration test - annual | Annual external pen test of internal systems and (eventually) game backend. | Not started | Medium |  | Ongoing Mgmt | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Required at scale or by publishers.
Couch Heroes / Studio Operations / IT and Systems | ISO 27001 / Cyber Essentials assessment | Decide whether to pursue Cyber Essentials (low cost, UK gov-aligned) or full ISO 27001 (heavyweight). Cyber Essentials Plus often required by UK publishers and for government grants. | Not started | High |  | Assessment | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | SaaS tooling licence inventory | Single sheet of every SaaS tool, owner, seats, cost, renewal date. Stops licence sprawl. | Not started | High |  | Implementation | Mustafa/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Unreal Engine licensing | Confirm Unreal licence terms (royalty-based standard EULA vs custom licence). Track per-platform requirements. | Not started | High |  | Assessment | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Standard EULA = 5% over $1m gross.
Couch Heroes / Studio Operations / IT and Systems | DCC tool licences - art | Maya, ZBrush, Substance Suite, Houdini, Marvelous Designer, Photoshop. Volume licensing. | Not started | High |  | Implementation | David |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | DCC tool licences - audio | Wwise, FMOD, Pro Tools / Reaper, sound libraries. | Not started | Medium |  | Implementation | TBD (audio lead) |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Productivity tooling | Notion vs Confluence, Slack vs Teams, Zoom vs Meet, Loom for async, Miro/FigJam. | Not started | High |  | Strategy | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Tied to org comms architecture.
Couch Heroes / Studio Operations / IT and Systems | Project tooling | Jira, Linear, ShotGrid (Flow), or Hansoft for production tracking. Often differs by discipline. | Not started | High |  | Strategy | Valeria/Graham |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Production-side decision.
Couch Heroes / Studio Operations / IT and Systems | Email and calendar standard | Google Workspace or Microsoft 365 for email/calendar/storage. Tied to IdP decision. | Not started | High |  | Implementation | Mustafa |  | IdP selection | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Document storage standard | Google Drive vs SharePoint vs Notion vs combination. Retention and access policy. | Not started | Medium |  | Implementation | Mustafa |  | Email/calendar standard | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Studio onboarding IT pack | Day-one IT setup: account, device, MDM, SSO, email, Slack, source control access, productivity tools. Documented runbook. | Not started | High |  | Implementation | Mustafa |  | All identity + tooling live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Studio offboarding IT pack | Day-of-leaver: revoke SSO, MDM remote wipe (if BYOD policy), source control access removal, mailbox forwarding, asset return. | Not started | High |  | Implementation | Mustafa |  | All identity + tooling live | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Help desk and ticketing | Internal IT support channel - shared Slack channel initially, ticketed system (Jira SM, Freshservice) once over ~25 staff. | Not started | Medium |  | Implementation | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Asset register - hardware | Inventory of all company hardware with assignee, serial, purchase date, warranty, refresh cycle. | Not started | Medium |  | Ongoing Mgmt | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Pairs with insurance equipment cover.
Couch Heroes / Studio Operations / IT and Systems | Vendor risk assessment process | Before adding a SaaS or vendor, review their security posture, data location, sub-processors, breach history. | Not started | Medium |  | Implementation | Mustafa/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Pairs with legal vendor-check skill.
Couch Heroes / Studio Operations / IT and Systems | Game backend platform decision | Decide on the live-services backend approach (PlayFab, AccelByte, Pragma, custom on AWS GameLift/etc). Material decision for an MMORPG. | Not started | High |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | MMORPG-specific. Don't skip.
Couch Heroes / Studio Operations / IT and Systems | Source-control IP audit pre-launch | Pre-launch sweep of source control to confirm only owned IP and licensed third-party assets are in the repo. | Not started | Medium |  | Implementation | Mustafa/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Tied to Legal IP register.
Couch Heroes / Studio Operations / IT and Systems | Build artefact retention | Retention of cooked builds, cook logs, symbols, crash dumps. Required for post-release support. | Not started | Medium |  | Implementation | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Telemetry and analytics platform | Player telemetry pipeline (eventually). Choose platform (Snowflake/BigQuery + GameAnalytics/Unity Analytics/custom). | Not started | Medium |  | Strategy | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Post-vertical-slice decision.
Couch Heroes / Studio Operations / IT and Systems | Privacy by design technical controls | DSAR tooling, deletion workflows, consent management. Required for any game collecting player data. | Not started | Medium |  | Strategy | Mustafa/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Tied to UK GDPR/data protection.
Couch Heroes / Studio Operations / IT and Systems | IT runbook library | Documented runbooks for: new starter setup, leaver, lost device, suspicious email, source control restore, build farm outage. | Not started | Medium |  | Ongoing Mgmt | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / IT and Systems | Status page and on-call rota | Internal status page for major dev infra (Perforce, build farm, VPN) and an on-call rota once team is at scale. | Not started | Low |  | Implementation | Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Premature now; revisit at ~25 headcount.
Couch Heroes / Studio Operations / Legal and Compliance | Riley/SayBrook engagement letter | Confirm the £1,500/week + £350/hr overage engagement scope, deliverables, and SLA. | In progress | Critical ACT | Yellow | Implementation | Vardis/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Reference doc Couch_Heroes_Legal_Function_Briefing_1.docx. Confirm whether £1.5k weekly is fixed scope or capped retainer.
Couch Heroes / Studio Operations / Legal and Compliance | Riley/SayBrook scope-of-work matrix | Matrix of which legal work is in-scope of weekly retainer vs hourly overage vs out-of-scope (specialist counsel). Stops overage drift. | Not started | High |  | Implementation | Aris |  | Engagement letter | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Riley weekly working session | Standing weekly call with Riley to review live matters, surface new ones, and prioritise. | In progress | High | Green | Ongoing Mgmt | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Specialist counsel panel | Pre-vetted specialist firms for areas Riley doesn't cover: immigration, IP/trade marks, tax, employment dispute, data protection. | Not started | High |  | Research | Riley/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Riley-led panel build.
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - employment | Master employment contract template incorporating CH_Guidance Appendix Two corrections (SSP, ERA 2025 references, day-one rights, IP assignment, restrictive covenants). | Not started | Critical ACT |  | Implementation | Riley |  | CH_Guidance_extracted.md s. Mandatory Corrections | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 1.1 Employment Contract - confirm at offsite. Riley owns drafting; CH approves.
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - contractor (UK) | UK contractor agreement template with IR35 status determination, IP assignment, confidentiality. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - contractor (overseas) | Overseas contractor template - tax residency declaration, IP assignment governed by English law, payment in GBP/USD. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - mutual NDA | Bilateral NDA for partner/publisher/investor conversations. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 2.3 Confidentiality / NDA - confirm at offsite.
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - inbound NDA review | Standing playbook for reviewing inbound NDAs (positions on jurisdiction, term, residual knowledge, IP carve-outs). | Not started | Medium |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | legal:triage-nda skill.
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - SOW master | Master Services Agreement + SOW template for service providers (audio outsource, art outsource, contractor agencies). | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - publisher heads of terms | Heads of terms template anchored to studio-favourable starting positions. | Not started | Medium |  | Implementation | Riley/Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - asset licence (in) | Template for licensing third-party assets into the project. | Not started | Medium |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract template - asset licence (out) | Template for licensing CH assets out (e.g. for marketing partners). | Not started | Low |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract execution and CLM | E-signature platform (DocuSign, Dropbox Sign) + simple contract repository with renewal alerts. | Not started | High |  | Implementation | Aris/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Contract review playbook | Playbook for reviewing inbound contracts: red-line positions, fall-back positions, escalation triggers. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | legal:review-contract skill.
Couch Heroes / Studio Operations / Legal and Compliance | Legal calendar - statutory and renewal | Single legal calendar covering Companies House confirmation statement, accounts filing, CT600, sponsor licence renewal (4-yearly), insurance renewals, contract renewals, trademark renewals. | Not started | High |  | Ongoing Mgmt | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Sponsor Licence application | Apply for Skilled Worker sponsor licence. Requires HR systems evidence, EL insurance, key personnel appointed (Authorising Officer, Key Contact, Level 1 User). | In progress | Critical ACT | Yellow | Implementation | Lorenz/Riley/Patrice |  | UK Co incorp, EL insurance | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 3.x Sponsor Licence - confirm at offsite. Per CH_Guidance section 3. Patrice can act as L1 User.
Couch Heroes / Studio Operations / Legal and Compliance | Sponsor Licence HR Compliance Pack | Documented systems for tracking attendance, visa expiry, passport copies, reporting changes to Home Office. | Not started | Critical ACT |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 3.1 HR Compliance Pack - confirm at offsite. Per CH_Guidance Priority 3.
Couch Heroes / Studio Operations / Legal and Compliance | Sponsored worker file standard | Standardised personnel file structure for each sponsored worker. | Not started | High |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 3.2 Sponsored Worker File Template - confirm at offsite.
Couch Heroes / Studio Operations / Legal and Compliance | Sponsor Licence ongoing duties | Ongoing reporting of sponsored-worker changes to Home Office (salary, role, absence). Process and named owner. | Not started | High |  | Ongoing Mgmt | Lorenz |  | Sponsor Licence granted | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Sponsor Licence renewal | 4-yearly licence renewal. Diary 6 months ahead of expiry. | Not started | Medium |  | Ongoing Mgmt | Lorenz |  | Sponsor Licence granted | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Right to Work check process | Documented Right to Work check procedure with online checking service, document retention, audit trail. | Not started | Critical ACT |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 1.4 Right to Work Checks - confirm at offsite. Per CH_Guidance Priority 1.
Couch Heroes / Studio Operations / Legal and Compliance | Visa cost recovery prohibition - policy | Internal policy enforcing the post-2024 prohibition on recovering sponsorship costs from workers. Train recruiters/managers. | Not started | High |  | Implementation | Lorenz/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 3.8. Licence revocation risk if breached.
Couch Heroes / Studio Operations / Legal and Compliance | IP register | Register of all CH-owned IP: trademarks, copyrights, design rights, registered works. With renewal dates. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Trademark - studio name | UK and key territory trademark filing for "Couch Heroes" name and logo (UKIPO + EUIPO + USPTO). | Not started | High |  | Implementation | Riley + IP specialist |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Specialist IP counsel - not Riley core.
Couch Heroes / Studio Operations / Legal and Compliance | Trademark - game title | Trademark filing for the game title once locked. Class 9 (software), Class 41 (entertainment), Class 28 (toys), Class 25 (apparel). | Not started | High |  | Implementation | Riley + IP specialist |  | Game title lock | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Trademark watching service | Subscribe to a watching service to flag conflicting filings. | Not started | Medium |  | Ongoing Mgmt | Riley |  | Trademarks filed | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Domain portfolio | Acquire and hold key domains (.com, .co.uk, .io, .gg) for studio and game. Centralised registrar account. | Not started | High |  | Implementation | Mustafa/Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Social handle portfolio | Reserve studio and game handles across major platforms (Twitter/X, BlueSky, Instagram, TikTok, YouTube, Twitch, Reddit, Discord). | Not started | High |  | Implementation | Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | IP assignment - all current contributors | Confirm every current contributor (founders, contractors, advisors) has executed IP assignment to CH Game Development LTD. Backfill any gaps. | Not started | Critical ACT |  | Assessment | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | A common pre-funding diligence killer.
Couch Heroes / Studio Operations / Legal and Compliance | IP assignment - employment standard | Standalone IP assignment deed used alongside employment contract. | Not started | High |  | Implementation | Riley |  | Employment contract template | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Open source compliance policy | Policy on use of OSS in the codebase: allowed licences, prohibited (GPL/AGPL in shipped code), tracking, attribution. | Not started | High |  | Strategy | Mustafa/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Critical for an MMORPG. Wrong OSS = forced source disclosure.
Couch Heroes / Studio Operations / Legal and Compliance | Open source compliance tooling | Implement OSS scanning (Snyk, FOSSA, Black Duck) in CI. | Not started | Medium |  | Implementation | Mustafa |  | OSS policy | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Third-party asset register | Every middleware, plugin, audio library, art asset with its licence terms and obligations. | Not started | High |  | Implementation | Mustafa/David |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Diligence ask.
Couch Heroes / Studio Operations / Legal and Compliance | Confidentiality and NDA process | Process for issuing NDAs to inbound parties, signing inbound NDAs, and tracking what's covered by what. | Not started | Medium |  | Implementation | Aris |  | NDA template | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | UK GDPR compliance baseline | UK GDPR compliance posture: lawful basis register, employee privacy notice, candidate privacy notice, retention schedule, sub-processor list. | Not started | High |  | Implementation | Riley/Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance Priority 1.
Couch Heroes / Studio Operations / Legal and Compliance | Data Protection Officer determination | Assess whether a DPO is legally required (likely not at current scale) and designate a senior data lead. | Not started | Medium |  | Assessment | Lorenz/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | DPIA process and templates | Data Protection Impact Assessment template + process for triggering one (any new system processing personal data). | Not started | Medium |  | Implementation | Riley |  | UK GDPR baseline | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 2.5 DPIA Template - confirm at offsite. Per CH_Guidance Priority 2.
Couch Heroes / Studio Operations / Legal and Compliance | Cross-border data transfer agreement | If sharing employee/business data with NBI LLC US parent (or any non-UK entity), put a UK IDTA or UK Addendum to EU SCCs in place. | Not started | High |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 2.6 Cross-Border Data Transfer Agreement - confirm at offsite. Per CH_Guidance Priority 2.
Couch Heroes / Studio Operations / Legal and Compliance | Vendor data processing agreements | DPAs with every SaaS vendor processing personal data (HRIS, payroll, email, productivity). | Not started | Medium |  | Ongoing Mgmt | Aris |  | UK GDPR baseline | Studio Operations |  |  |  | Agent / Studio Operations | legal:vendor-check skill.
Couch Heroes / Studio Operations / Legal and Compliance | Subject Access Request process | Documented DSAR handling process - intake, identity verification, search, redaction, response within 30 days. | Not started | Medium |  | Implementation | Lorenz/Riley |  | UK GDPR baseline | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Cookie and tracker compliance | Pre-launch website and (eventually) game compliance with PECR cookie rules. | Not started | Medium |  | Implementation | Glen/Mustafa |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Health and Safety policy | Mandatory written H&S policy (5+ employees). DSE assessments for remote workers, fire safety, risk assessment process. | Not started | High |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 1.5 Health and Safety Policy - confirm at offsite. Per CH_Guidance Priority 1.
Couch Heroes / Studio Operations / Legal and Compliance | Employee handbook - full set | Disciplinary, grievance, sickness absence (updated for SSP changes), holiday and leave, family leave (maternity/paternity/adoption/shared parental/parental bereavement/neonatal), flexible working, equal opps, anti-harassment, whistleblowing, data protection, social media, IT AUP, expenses, probation, training, alcohol and drugs, redundancy. | Not started | High |  | Implementation | Riley/Lorenz |  | Employment contract template | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 2.1 Employee Handbook - confirm at offsite. Per CH_Guidance Priority 2. Full list.
Couch Heroes / Studio Operations / Legal and Compliance | ERA 2025 readiness - April 2026 | Review and update contracts/policies for April 2026 ERA changes: SSP from day one, paternity/parental leave day-one rights, collective redundancy doubling, whistleblowing extension. | Not started | Critical ACT |  | Implementation | Riley/Lorenz |  | Contracts and policies drafted | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance section 6.1. Hard date.
Couch Heroes / Studio Operations / Legal and Compliance | ERA 2025 readiness - October 2026 | Update for fire-and-rehire, sexual harassment "all reasonable steps" duty, third-party harassment liability, tribunal time limits to 6 months. | Not started | High |  | Strategy | Riley/Lorenz |  | ERA April 2026 work | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 6.2.
Couch Heroes / Studio Operations / Legal and Compliance | ERA 2025 readiness - January 2027 | Probation and dismissal procedure overhaul - unfair dismissal qualifying period drops from 2 years to 6 months. Anyone hired ~Jul/Aug 2026 may have unfair dismissal protection from Jan 2027. | Not started | High |  | Strategy | Riley/Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 6.3. Major implications for hiring approach.
Couch Heroes / Studio Operations / Legal and Compliance | Bribery Act 2010 procedures | Adequate procedures policy under Bribery Act 2010. | Not started | Medium |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 4.9 Bribery Act Policy - confirm at offsite. Per CH_Guidance Priority 4.
Couch Heroes / Studio Operations / Legal and Compliance | Anti-money-laundering posture | Assessment of AML obligations - games studio is mostly out of scope but check for any NFT/blockchain/marketplace plans. | Not started | Low |  | Assessment | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Modern Slavery Statement (deferred) | Required only above £36m turnover. Tracked as a "revisit" item. | Not started | Low |  | Assessment | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | POSSIBLE DUPLICATE OF UK 4.10 Modern Slavery Statement - confirm at offsite. Per CH_Guidance Priority 4.
Couch Heroes / Studio Operations / Legal and Compliance | Greece initiative - legal structure | Legal structure for the Greece initiative (subsidiary, branch, contractor pool, EOR). Tax residency and PE risk analysis. | Not started | High | Waiting on Client | Strategy | Riley + Greek counsel |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Specialist Greek counsel needed. Conflict risk - decisions here affect org structure.
Couch Heroes / Studio Operations / Legal and Compliance | Greece initiative - employment law | Greek employment law obligations if hiring in Greece. Likely requires local payroll, social security registration. | Not started | High | Waiting on Client | Research | Greek counsel |  | Greece structure decision | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Greece initiative - IP flow | Ensure IP created in Greece flows back to CH Game Development LTD via assignment chain. | Not started | High | Waiting on Client | Strategy | Riley + Greek counsel |  | Greece structure decision | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Regulatory monitoring - employment | Monitor changes in UK employment law (ERA 2025 secondary regs, NMW updates, statutory rate updates). | Not started | Medium |  | Ongoing Mgmt | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Riley deliverable.
Couch Heroes / Studio Operations / Legal and Compliance | Regulatory monitoring - games | Monitor games-specific regulation: PEGI/ESRB, loot box, gambling adjacency, child safety (UK Children's Code/Age Appropriate Design Code), Online Safety Act, EU DSA. | Not started | High |  | Ongoing Mgmt | Riley + Glen |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Online Safety Act + Age Appropriate Design Code apply to studios with UK player exposure.
Couch Heroes / Studio Operations / Legal and Compliance | Regulatory monitoring - data and privacy | Monitor UK GDPR/DPA 2018 evolution (DUA Bill etc), EU GDPR, US state laws once US presence material. | Not started | Medium |  | Ongoing Mgmt | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Investor legal - SHA negotiation | Negotiation of shareholders' agreement at term sheet stage. | Not started | High |  | Strategy | Riley |  | Term sheet signed (Fundraising) | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Investor legal - articles update | Update Articles of Association for institutional round (preference share rights, drag, tag, transfer restrictions). | Not started | High |  | Implementation | Riley |  | Term sheet signed | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Investor legal - subscription agreement | Subscription/investment agreement for the round. | Not started | High |  | Implementation | Riley |  | SHA agreed | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Investor legal - completion mechanics | Closing mechanics: signing, completion, share issuance, board changes, Companies House filings. | Not started | High |  | Implementation | Riley |  | Subscription agreement | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Insurance broker engagement | Single broker handling all studio insurances (EL, PI, cyber, PL, equipment, D&O). Reduces admin and surfaces gaps. | Not started | High |  | Implementation | Aris |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Insurance claim runbook | Documented procedure for raising and managing an insurance claim. | Not started | Low |  | Implementation | Aris |  | Insurance broker | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Compliance register | Single register of all compliance obligations (statutory filings, regulatory, contractual) with owner, frequency, last date, next date. | Not started | High |  | Implementation | Aris/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations | legal:compliance-check skill.
Couch Heroes / Studio Operations / Legal and Compliance | Document retention schedule | Per-record-type retention schedule (employment: 6 years post-leave, payroll: 3 years, accounting: 6 years, board minutes: indefinite). | Not started | Medium |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Litigation hold process | Process for issuing and managing litigation holds if a claim is anticipated. | Not started | Low |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Whistleblowing channel | Independent whistleblowing channel (e.g. SafeCall, Vault Platform) per Public Interest Disclosure Act. ERA 2025 extends to sexual harassment. | Not started | Medium |  | Implementation | Lorenz/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | Anti-harassment training programme | Mandatory training for all staff. Tightened "all reasonable steps" duty from October 2026 makes documented training material. | Not started | High |  | Implementation | Lorenz |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance 6.2.
Couch Heroes / Studio Operations / Legal and Compliance | Director duties briefing | Briefing pack for directors (Vardis, Aris, others) on Companies Act 2006 s.171-177 duties. | Not started | Medium |  | Implementation | Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Legal and Compliance | PSC register maintenance | Quarterly check that the PSC register is current. | Not started | High |  | Ongoing Mgmt | Riley/External accountant |  |  | Studio Operations |  |  |  | Agent / Studio Operations | Per CH_Guidance Priority 5.
Couch Heroes / Studio Operations / Legal and Compliance | Companies House filing calendar | Calendar of all CH filings: CS01, AA accounts, AP01/AP03 director changes, SH01 share allotments, PSC updates. | Not started | High |  | Ongoing Mgmt | External accountant/Riley |  |  | Studio Operations |  |  |  | Agent / Studio Operations
Couch Heroes / Studio Operations / Org Design & Structure | Attach Miro org-structure artifact | Q8 (2026-04-26): Glen provided Miro screenshot of likely structure. Captured at Clients/Couch Heroes/org_structure_likely_2026-04-26.md. Replace with finalised version after Apr 27-30 offsite. | In progress | High |  | Strategy | Glen |  | org_structure_likely_2026-04-26.md | Org Design |  |  |  | Q8 (2026-04-26) | NEW from Q&A

## UK Company Setup
parent_path | title | description | status | priority | health_state | work_type | assignees | due_date | dependencies | practice_area | type | layer | confidence | source | notes
Couch Heroes / UK Company Setup / UK Transition Operational | Gather contractor / employee ID and info | Attachment: {"originalUrl":"https:\/\/docs.google.com\/spreadsheets\/d\/1J0-lJg8RrN7xkh0x1JVxtAYLQAi3WF33Td3pFQ-Ccvc\/edit?gid=0#gid=0","attachment":{},"displayAsUrl":false} | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 34
Couch Heroes / UK Company Setup / UK Transition Operational | Review FTE contract | Attachment: {"originalUrl":"https:\/\/drive.google.com\/drive\/folders\/14vYrPChhwqt9TK2EbxMOcLXMfVbhXdxm","attachment":{},"displayAsUrl":false} | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 35
Couch Heroes / UK Company Setup / UK Transition Operational | Handbook review and iteration | Attachment: {"originalUrl":"https:\/\/drive.google.com\/drive\/folders\/14vYrPChhwqt9TK2EbxMOcLXMfVbhXdxm","attachment":{},"displayAsUrl":false} | Not started | High |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 36
Couch Heroes / UK Company Setup / UK Transition Operational | Discuss next steps and risks (EOR, visa, etc.) | Risk assessment with Lorenza once unblocked | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 96
Couch Heroes / UK Company Setup / UK Transition Operational | Review Lorenza's finalised transition checklist | Checklist review once unblocked | Not started | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 97
Couch Heroes / UK Company Setup / UK Transition Operational | UK Transition Planning | Build out a complete and comprehensive plan on moving staff under an LLC in the UK establish the following categories: • Staff and staff regulation • Financing • Operational needs according to Home Office rules • Who handles tax? • Who handles budget? • Communications to staff on transition • Timing - schedule ◦ Legal Checklist ◦ Payroll check ◦ Communication checklist ◦ Certificate of Sponsorship Detail and Checklist | In progress | Medium | Yellow |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 98
Couch Heroes / UK Company Setup / Project Plan | PRIORITY 1: LEGALLY REQUIRED BEFORE FIRST HIRE | {'Priority': 'P1', 'Artifact Name': 'PRIORITY 1: LEGALLY REQUIRED BEFORE FIRST HIRE'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref
Couch Heroes / UK Company Setup / Project Plan | 1.1 Employment Contract (Section 1 Statement) | {'Ref': '1.1', 'Priority': 'P1', 'Artifact Name': 'Employment Contract (Section 1 Statement)', 'Description': 'Written statement of employment particulars. Must include all mandatory items per s.1 ERA 1996 as amended. Must incorporate SSP day-one changes, paternity/parental leave day-one rights, flexible working reference, IP assignment clause, moral rights waiver (CDPA 1988 s.87), restrictive covenants, and reference ERA 2025.', 'Legal Basis / Driver': 'Employment Rights Act 1996 s.1; Employment Rights Act 2025', 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'HR Lead + Legal', 'Status Change': 'updated', 'Status': 'DONE', 'ARTIFACTS': 'Legally compliant FTE Contract', 'Link to Artifacts': 'https://docs.google.com/document/d/1XCWALv3G2Ct1idEibBgs3m_2N1pOKsbq/edit', 'Dependencies': 'Legal review of current template; SSP clause rewrite', 'Notes': 'The existing Appendix Two template requires 11 mandatory corrections identified in the revised guide. Build from scratch reco | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.1
Couch Heroes / UK Company Setup / Project Plan | 1.2 Offer Letter Template | {'Ref': '1.2', 'Priority': 'P1', 'Artifact Name': 'Offer Letter Template', 'Description': 'Conditional offer letter including salary, start date, conditions (references, right to work), pension reference, Section 1 statement timing, acceptance deadline.', 'Legal Basis / Driver': 'Best practice; supports contractual clarity', 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'HR Lead', 'Status Change': 'updated', 'Status': 'Done', 'ARTIFACTS': 'Offer Letter ', 'Link to Artifacts': 'here: https://docs.google.com/document/d/1CTaE93VqWhhlAlZlOOrj4UbY3IPGNErp/edit?usp=drive_link&ouid=111631440583371827928&rtpof=true&sd=true ', 'Dependencies': 'Contract template (1.1) must be finalised first', 'Notes': 'Existing Appendix One needs corrections per revised guide.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.2
Couch Heroes / UK Company Setup / Project Plan | 1.3 Employee Privacy Notice (UK GDPR) | {'Ref': '1.3', 'Priority': 'P1', 'Artifact Name': 'Employee Privacy Notice (UK GDPR)', 'Description': 'Mandatory privacy notice for all employees. Must detail: categories of personal data collected, lawful bases, retention periods, recipients, data subject rights, cross-border transfers (to US parent NBI LLC), DPO contact if appointed.', 'Legal Basis / Driver': 'UK GDPR Articles 13-14; Data Protection Act 2018', 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'Legal / DPO', 'Status Change': 'updated', 'Status': 'In Review', 'ETA': '14/04/2026', 'ARTIFACTS': 'GDPR Letter to check with Dino\n\nupdate: letter ready to be sent with employment contract\n\nupdate 1: Glen having the policy reviewed. ', 'Link to Artifacts': 'here: https://drive.google.com/file/d/1PwL8hJR9n3zPpMPQhif1vqBcPxQSHQB4/view?usp=drive_link ', 'Dependencies': 'Cross-border data transfer agreement (2.6) must be planned in parallel', 'Notes': 'Required to be provided to every employee. Non-compliance is an | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.3
Couch Heroes / UK Company Setup / Project Plan | 1.4 Right to Work Checks Procedure | {'Ref': '1.4', 'Priority': 'P1', 'Artifact Name': 'Right to Work Checks Procedure', 'Description': 'Step-by-step procedure for verifying right to work. Must cover: manual checks, online checks (share codes/eVisa), Employer Checking Service, record-keeping requirements, anti-discrimination safeguards (must check everyone equally). State civil penalty: up to £45,000 first breach / £60,000 repeat breach. *** for UK citizens do the IDVT method ', 'Legal Basis / Driver': 'Immigration, Asylum and Nationality Act 2006; Home Office Employer Right to Work Checklist', 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'HR Lead', 'Status Change': 'WIP', 'Status': 'In Review', 'ETA': '15/04/2026', 'ARTIFACTS': 'Summary document and workflow tutorial', 'Link to Artifacts': 'Lorenza Menna', 'Dependencies': 'None', 'Notes': 'Criminal offence to knowingly employ an illegal worker. Also a sponsor licence compliance requirement.', "Lorenza's Notes": '- Flow chart for Right to work check '} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.4
Couch Heroes / UK Company Setup / Project Plan | 1.5 Health and Safety Policy | {'Ref': '1.5', 'Priority': 'P1', 'Artifact Name': 'Health and Safety Policy', 'Description': 'Written H&S policy mandatory for 5+ employees. Must include: general statement of intent, organisation and arrangements, risk assessment procedures, DSE assessments for remote/hybrid workers, fire safety, first aid, lone working, accident/incident reporting.', 'Legal Basis / Driver': 'Health and Safety at Work etc. Act 1974; Management of Health and Safety at Work Regulations 1999; Health and Safety (Display Screen Equipment) Regulations 1992', 'Deadline / Trigger': 'Before 5th employee starts (best practice: before first hire)', 'Owner': 'Operations Lead', 'Status Change': 'follow up with Glen', 'Status': 'Not started', 'ETA': '16/04/2026', 'ARTIFACTS': 'H&S policy ', 'Link to Artifacts': 'Glen Pryer to upload the document here: https://drive.google.com/drive/u/0/folders/14vYrPChhwqt9TK2EbxMOcLXMfVbhXdxm', 'Dependencies': 'Risk assessments must be completed for each workplace/role', 'Notes': | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.5
Couch Heroes / UK Company Setup / Project Plan | 1.6 Pension Auto-Enrolment Communication Letter | {'Ref': '1.6', 'Priority': 'P1', 'Artifact Name': 'Pension Auto-Enrolment Communication Letter', 'Description': 'Template letter to each employee within 6 weeks of assessment explaining pension rights, scheme details, contribution rates, opt-out rights.', 'Legal Basis / Driver': 'Pensions Act 2008; The Pensions Regulator guidance', 'Deadline / Trigger': "Within 6 weeks of first eligible employee's start date", 'Owner': 'Payroll / HR Lead', 'Status Change': 'follow up with Glen', 'Status': 'Not started\n\nA template could be usefull', 'ARTIFACTS': '- Pension Scheme\n- Pension Letter for employee to know they are autoenrolled + Pension Scheme\n- Policy (Handbook) + Letter for people if they want to remove themselves from Pension Scheme\n\n\n- ONBOARDING Workflow to check the 6 weeks deadline', 'Link to Artifacts': 'Lorenza Menna to start onboarding workflow', 'Dependencies': 'Pension scheme must be chosen and set up first', 'Notes': 'Can be templated and populated per employee.', 'Refere | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.6
Couch Heroes / UK Company Setup / Project Plan | 1.7 EL Insurance Certificate Display | {'Ref': '1.7', 'Priority': 'P1', 'Artifact Name': 'EL Insurance Certificate Display', 'Description': "Obtain Employers' Liability Insurance (£5m minimum). Display certificate physically or electronically where employees can access it.", 'Legal Basis / Driver': "Employers' Liability (Compulsory Insurance) Act 1969", 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'Finance / Operations', 'Status Change': 'updated', 'Status': 'Done', 'ARTIFACTS': '- EL Insurance Certificate Display', 'Link to Artifacts': 'here: https://drive.google.com/file/d/1bkCVdij9nYXPoHj31va8FlV6mg1mxu0X/view?usp=drive_link ', 'Dependencies': 'Insurance broker/provider selection', 'Notes': 'Fine of £2,500 per day without cover. Home Office requires sight of this for sponsor licence.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 1.7
Couch Heroes / UK Company Setup / Project Plan | PRIORITY 2: REQUIRED WITHIN FIRST MONTHS / BEFORE SCALING | {'Priority': 'P2', 'Artifact Name': 'PRIORITY 2: REQUIRED WITHIN FIRST MONTHS / BEFORE SCALING'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref
Couch Heroes / UK Company Setup / Project Plan | 2.1 Employee Handbook / Staff Handbook | {'Ref': '2.1', 'Priority': 'P2', 'Artifact Name': 'Employee Handbook / Staff Handbook', 'Description': 'Comprehensive handbook containing all workplace policies. See sub-items 2.1a-2.1q below.', 'Legal Basis / Driver': 'Various statutes; ACAS Code of Practice; best practice', 'Deadline / Trigger': 'Within first 3 months of first hire', 'Owner': 'HR Lead + Legal', 'Status Change': 'Glen to review it', 'Status': 'Not started', 'ARTIFACTS': 'Handbook (50 pages max) ', 'Link to Artifacts': '- Lorenza Menna \n\n1. SHORT VERSION: https://docs.google.com/document/d/1-mPTnXfYyHtZV5K8Q2S30yNlB4lCmxPd/edit\n2. LONG VERSION: https://docs.google.com/document/d/1N78tUcIctM6UnSXC-5zTqlh4zg7w155T/edit\n\n- Glen Pryer to review it tomorrow at 4.30 ', 'Dependencies': 'Contract template (1.1) must be finalised first', 'Notes': 'Single document or modular policy set. Must be reviewed annually.'} | In Review | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1
Couch Heroes / UK Company Setup / Project Plan | 2.1a -- Disciplinary Policy and Procedure | {'Ref': '2.1a', 'Priority': 'P2', 'Artifact Name': '-- Disciplinary Policy and Procedure', 'Description': 'Aligned with ACAS Code of Practice on Disciplinary and Grievance Procedures. Must cover investigation, hearing, appeal stages, right to be accompanied.', 'Legal Basis / Driver': 'ACAS Code of Practice; ERA 1996 s.98', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Notes': 'Tribunals can increase awards by 25% for failure to follow ACAS Code.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1a
Couch Heroes / UK Company Setup / Project Plan | 2.1b -- Grievance Policy and Procedure | {'Ref': '2.1b', 'Priority': 'P2', 'Artifact Name': '-- Grievance Policy and Procedure', 'Description': 'Aligned with ACAS Code. Must cover informal resolution, formal grievance, investigation, hearing, appeal.', 'Legal Basis / Driver': 'ACAS Code of Practice; ERA 1996', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1b
Couch Heroes / UK Company Setup / Project Plan | 2.1c -- Sickness Absence Policy | {'Ref': '2.1c', 'Priority': 'P2', 'Artifact Name': '-- Sickness Absence Policy', 'Description': 'Updated for SSP changes from 6 April 2026: no waiting days, no LEL, 80%-of-AWE rate. Cover self-certification (7 days), fit notes, return to work interviews, long-term absence management.', 'Legal Basis / Driver': 'ERA 2025; SSP Regulations', 'Deadline / Trigger': 'Part of handbook. URGENT: must reflect 6 April 2026 changes.', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Dependencies': 'SSP clause in contract (1.1)', 'Notes': 'Remove any reference to 3-day waiting period or earnings threshold.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1c
Couch Heroes / UK Company Setup / Project Plan | 2.1d -- Holiday and Leave Policy | {'Ref': '2.1d', 'Priority': 'P2', 'Artifact Name': '-- Holiday and Leave Policy', 'Description': 'Statutory minimum 5.6 weeks (28 days for 5-day week). Carry-over rules (including statutory right to carry over up to 20 days for sick workers for 18 months). Sickness during holiday conversion. Holiday accrual for irregular hours workers (12.07% method from April 2024).', 'Legal Basis / Driver': 'Working Time Regulations 1998 (as amended)', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1d
Couch Heroes / UK Company Setup / Project Plan | 2.1e -- Family Leave Policies | {'Ref': '2.1e', 'Priority': 'P2', 'Artifact Name': '-- Family Leave Policies', 'Description': "Maternity, Paternity (day-one right from 6 April 2026), Adoption, Shared Parental, Unpaid Parental Leave (day-one right from 6 April 2026), Parental Bereavement, Neonatal Care Leave (from April 2025), Bereaved Partner's Paternity Leave (from 6 April 2026).", 'Legal Basis / Driver': "ERA 1996; ERA 2025; Maternity and Parental Leave etc. Regulations 1999; Bereaved Partner's Paternity Leave Regulations 2026", 'Deadline / Trigger': 'Part of handbook. URGENT: day-one rights from 6 April 2026.', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Notes': 'Must remove old qualifying period references for paternity and unpaid parental leave.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1e
Couch Heroes / UK Company Setup / Project Plan | 2.1f -- Flexible Working Policy | {'Ref': '2.1f', 'Priority': 'P2', 'Artifact Name': '-- Flexible Working Policy', 'Description': 'Day-one right to request since 6 April 2024. 2 requests per year. Employer must decide within 2 months. Must consult before refusing. ERA 2025 will further require structured reasoning if refusing.', 'Legal Basis / Driver': 'ERA 1996 s.80F-80I (as amended); ERA 2025', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1f
Couch Heroes / UK Company Setup / Project Plan | 2.1g -- Anti-Harassment and Bullying Policy | {'Ref': '2.1g', 'Priority': 'P2', 'Artifact Name': '-- Anti-Harassment and Bullying Policy', 'Description': 'Must cover all protected characteristics (Equality Act 2010). Include sexual harassment specifically. Reference the preventative duty (reasonable steps from Oct 2024; all reasonable steps from Oct 2026). Include third-party harassment. Clear reporting routes.', 'Legal Basis / Driver': 'Equality Act 2010; Worker Protection (Amendment of Equality Act 2010) Act 2023; ERA 2025', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead + Legal', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Dependencies': 'Sexual Harassment Risk Assessment (2.8)', 'Notes': 'Compensation can be uplifted by 25% if employer cannot demonstrate preventative steps.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1g
Couch Heroes / UK Company Setup / Project Plan | 2.1h -- Equal Opportunities Policy | {'Ref': '2.1h', 'Priority': 'P2', 'Artifact Name': '-- Equal Opportunities Policy', 'Description': 'Cover all protected characteristics under Equality Act 2010. Apply to recruitment, promotion, training, pay, and termination.', 'Legal Basis / Driver': 'Equality Act 2010', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1h
Couch Heroes / UK Company Setup / Project Plan | 2.1i -- Whistleblowing Policy | {'Ref': '2.1i', 'Priority': 'P2', 'Artifact Name': '-- Whistleblowing Policy', 'Description': 'Public Interest Disclosure Act 1998 protections. Explain qualifying disclosures, how to raise concerns, protection from detriment. From April 2026, sexual harassment disclosures are qualifying disclosures.', 'Legal Basis / Driver': 'PIDA 1998; ERA 2025', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead + Legal', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1i
Couch Heroes / UK Company Setup / Project Plan | 2.1j -- Data Protection Policy | {'Ref': '2.1j', 'Priority': 'P2', 'Artifact Name': '-- Data Protection Policy', 'Description': 'UK GDPR and DPA 2018 compliance. Cover data handling, subject access requests, breach reporting, acceptable use of employee data.', 'Legal Basis / Driver': 'UK GDPR; DPA 2018', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'Legal / DPO', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Dependencies': 'Privacy notice (1.3)'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1j
Couch Heroes / UK Company Setup / Project Plan | 2.1k -- IT Acceptable Use and Social Media Policy | {'Ref': '2.1k', 'Priority': 'P2', 'Artifact Name': '-- IT Acceptable Use and Social Media Policy', 'Description': 'Cover use of company systems, personal devices, social media, email monitoring. Include reference to UK GDPR for monitoring.', 'Legal Basis / Driver': 'Best practice; supports disciplinary framework', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'IT Lead / HR', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1k
Couch Heroes / UK Company Setup / Project Plan | 2.1l -- Expenses Policy | {'Ref': '2.1l', 'Priority': 'P2', 'Artifact Name': '-- Expenses Policy', 'Description': 'Cover what is reimbursable, approval process, receipts, HMRC-approved mileage rates.', 'Legal Basis / Driver': 'Best practice; supports payroll and tax compliance', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'Finance / HR', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1l
Couch Heroes / UK Company Setup / Project Plan | 2.1m -- Probationary Period Policy | {'Ref': '2.1m', 'Priority': 'P2', 'Artifact Name': '-- Probationary Period Policy', 'Description': 'Define probation length, review process, extension mechanism, confirmation/termination. Note: from January 2027, UFD qualifying period drops to 6 months. Probation must be designed with this in mind.', 'Legal Basis / Driver': 'Contractual; informed by ERA 2025 UFD changes', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Dependencies': 'Contract template (1.1)', 'Notes': 'There is no statutory concept of probation. It is a contractual mechanism. ACAS Code compliance applies throughout.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1m
Couch Heroes / UK Company Setup / Project Plan | 2.1n -- Redundancy Policy | {'Ref': '2.1n', 'Priority': 'P2', 'Artifact Name': '-- Redundancy Policy', 'Description': "Cover consultation obligations (20+ redundancies: collective consultation with 45-day minimum period). Protective award now up to 180 days' pay from April 2026. From 2027, organisation-wide threshold may apply.", 'Legal Basis / Driver': 'Trade Union and Labour Relations (Consolidation) Act 1992; ERA 2025', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead + Legal', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1n
Couch Heroes / UK Company Setup / Project Plan | 2.1o -- Working Time and 48-Hour Week Policy | {'Ref': '2.1o', 'Priority': 'P2', 'Artifact Name': '-- Working Time and 48-Hour Week Policy', 'Description': 'Explain 48-hour average week limit, opt-out mechanism, rest breaks (20 min per 6 hours), daily rest (11 hours), weekly rest (24 hours). Address crunch periods specifically for gaming studio context.', 'Legal Basis / Driver': 'Working Time Regulations 1998', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook', 'Notes': 'Gaming industry is notorious for crunch. Policy must proactively manage this risk.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1o
Couch Heroes / UK Company Setup / Project Plan | 2.1p -- Alcohol and Drugs Policy | {'Ref': '2.1p', 'Priority': 'P2', 'Artifact Name': '-- Alcohol and Drugs Policy', 'Description': 'Testing, support, disciplinary implications.', 'Legal Basis / Driver': 'Best practice; H&S obligations', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1p
Couch Heroes / UK Company Setup / Project Plan | 2.1q -- Training and Development Policy | {'Ref': '2.1q', 'Priority': 'P2', 'Artifact Name': '-- Training and Development Policy', 'Description': 'Mandatory and optional training, time off for study, payment during training.', 'Legal Basis / Driver': 'ERA 1996 s.1 (mandatory particular); best practice', 'Deadline / Trigger': 'Part of handbook', 'Owner': 'HR Lead', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to check if we have this section int he Lean version of the handboook'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.1q
Couch Heroes / UK Company Setup / Project Plan | 2.2 IP Assignment Agreement | {'Ref': '2.2', 'Priority': 'P2', 'Artifact Name': 'IP Assignment Agreement', 'Description': 'Standalone deed or contract clause assigning all IP created during employment (code, artwork, game design, sound, trade secrets) to the company. Must include: moral rights waiver under CDPA 1988 s.87, future IP, work-for-hire provisions, obligations on termination.', 'Legal Basis / Driver': 'Copyright, Designs and Patents Act 1988; Patents Act 1977; common law', 'Deadline / Trigger': 'Before first creative/technical hire starts', 'Owner': 'Legal', 'Status': 'Not started', 'Dependencies': 'Contract template (1.1)', 'Notes': 'CRITICAL for a gaming studio. Without this, default UK law may not vest all IP in the employer.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.2
Couch Heroes / UK Company Setup / Project Plan | 2.3 Confidentiality / NDA (Standalone) | {'Ref': '2.3', 'Priority': 'P2', 'Artifact Name': 'Confidentiality / NDA (Standalone)', 'Description': 'Project-level NDA for contractors, partners, and specific projects beyond the general contractual confidentiality clause.', 'Legal Basis / Driver': 'Common law; contractual', 'Deadline / Trigger': 'As needed per project', 'Owner': 'Legal', 'Status': 'Not started', 'Dependencies': 'Contract template (1.1) has a general clause', 'Notes': 'Current contract has a confidentiality clause but may need strengthening for project-level use.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.3
Couch Heroes / UK Company Setup / Project Plan | 2.4 Post-Termination Restrictive Covenants | {'Ref': '2.4', 'Priority': 'P2', 'Artifact Name': 'Post-Termination Restrictive Covenants', 'Description': 'Non-compete, non-solicitation, non-dealing clauses tailored to gaming industry roles. Must be reasonable in scope, duration, and geography to be enforceable.', 'Legal Basis / Driver': 'Common law; must be reasonable to be enforceable', 'Deadline / Trigger': 'Build into contract template (1.1)', 'Owner': 'Legal', 'Status': 'Not started', 'Link to Artifacts': 'Lorenza to put link to the contract', 'Dependencies': 'Contract template (1.1)', 'Notes': 'Review in light of fire-and-rehire restrictions from October 2026.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.4
Couch Heroes / UK Company Setup / Project Plan | 2.5 DPIA Template | {'Ref': '2.5', 'Priority': 'P2', 'Artifact Name': 'DPIA Template', 'Description': 'Data Protection Impact Assessment template for high-risk processing activities (e.g. employee monitoring, CCTV, biometric data).', 'Legal Basis / Driver': 'UK GDPR Article 35', 'Deadline / Trigger': 'Before any high-risk processing begins', 'Owner': 'Legal / DPO', 'Status': 'Not started', 'ARTIFACTS': 'Link to a document + Handbook + Contract'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.5
Couch Heroes / UK Company Setup / Project Plan | 2.6 Cross-Border Data Transfer Agreement | {'Ref': '2.6', 'Priority': 'P2', 'Artifact Name': 'Cross-Border Data Transfer Agreement', 'Description': 'UK International Data Transfer Agreement (IDTA) or UK Addendum to EU Standard Contractual Clauses. Required for any transfer of employee personal data to NBI LLC (US parent).', 'Legal Basis / Driver': 'UK GDPR Chapter V; ICO guidance', 'Deadline / Trigger': 'Before any data is shared with US parent', 'Owner': 'Legal / DPO', 'Status': 'Not started', 'ARTIFACTS': 'Statement to put in the handbook.', 'Dependencies': 'Privacy notice (1.3) must reference transfers', 'Notes': 'ICO has published templates. Must be completed and signed before transfers begin.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.6
Couch Heroes / UK Company Setup / Project Plan | 2.7 Record Retention Policy | {'Ref': '2.7', 'Priority': 'P2', 'Artifact Name': 'Record Retention Policy', 'Description': 'Comprehensive policy covering: payroll/wage records (6 years), PAYE records (3 years), SSP records (3 years), maternity records (3 years), working time records (duration of employment + 2 years), pension records (6 years), recruitment records (6 months post-decision minimum), dismissal records (minimum 6 months to match new tribunal time limit from October 2026), accident reports (3 years), right to work records (2 years after termination).', 'Legal Basis / Driver': 'Various: Taxes Management Act 1970; WTR 1998; RIDDOR 2013; UK GDPR; ERA 2025', 'Deadline / Trigger': 'Within first 3 months', 'Owner': 'HR Lead / Legal', 'Status': 'Not started', 'ARTIFACTS': '- Statement in the handbook \n- Trackers/ document where we summarize where each excel spreadhseet/Hibob is', 'Notes': 'Must be updated when tribunal time limits extend to 6 months in October 2026.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.7
Couch Heroes / UK Company Setup / Project Plan | 2.8 Sexual Harassment Risk Assessment | {'Ref': '2.8', 'Priority': 'P2', 'Artifact Name': 'Sexual Harassment Risk Assessment', 'Description': 'Documented risk assessment identifying risks of sexual harassment in the workplace (including from third parties such as clients, players, online interactions). Must assess risks and document preventative steps.', 'Legal Basis / Driver': "Worker Protection (Amendment of Equality Act 2010) Act 2023; ERA 2025 (October 2026: 'all reasonable steps')", 'Deadline / Trigger': 'Before October 2026 (best practice: immediately)', 'Owner': 'HR Lead', 'Status': 'Not started', 'ARTIFACTS': '- Assessment Document internal confidential ', 'Dependencies': 'Anti-harassment policy (2.1g)', 'Notes': 'Without this, employer cannot demonstrate compliance with the preventative duty. 25% compensation uplift risk.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 2.8
Couch Heroes / UK Company Setup / Project Plan | PRIORITY 3: REQUIRED FOR SPONSOR LICENCE APPLICATION | {'Priority': 'P3', 'Artifact Name': 'PRIORITY 3: REQUIRED FOR SPONSOR LICENCE APPLICATION'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref
Couch Heroes / UK Company Setup / Project Plan | 3.1 Sponsor Licence HR Compliance Pack | {'Ref': '3.1', 'Priority': 'P3', 'Artifact Name': 'Sponsor Licence HR Compliance Pack', 'Description': 'Documented systems for: tracking attendance, visa expiry monitoring, passport/visa copy storage, Home Office reporting procedures. Must satisfy Home Office audit requirements.', 'Legal Basis / Driver': 'Immigration Rules; Sponsor Guidance Part 1 (version 03/26)', 'Deadline / Trigger': 'Before sponsor licence application', 'Owner': 'HR Lead', 'Status': 'Not started', 'Dependencies': 'HRIS platform selection (4.8)', 'Notes': 'Weak HR systems are the biggest reason for licence rejection.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 3.1
Couch Heroes / UK Company Setup / Project Plan | 3.2 Sponsored Worker File Template | {'Ref': '3.2', 'Priority': 'P3', 'Artifact Name': 'Sponsored Worker File Template', 'Description': 'Standardised personnel file structure per sponsored worker: CoS details, visa copy, passport copy, right to work check record, attendance records, salary details, role description matching SOC code.', 'Legal Basis / Driver': 'Sponsor Guidance Part 2 (version 03/26)', 'Deadline / Trigger': 'Before first CoS assignment', 'Owner': 'HR Lead', 'Status': 'Not started', 'Dependencies': 'Sponsor licence granted'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 3.2
Couch Heroes / UK Company Setup / Project Plan | 3.3 Absence Reporting Procedure (Sponsored Workers) | {'Ref': '3.3', 'Priority': 'P3', 'Artifact Name': 'Absence Reporting Procedure (Sponsored Workers)', 'Description': 'Procedure for reporting unauthorised absences of 10+ consecutive working days to the Home Office via SMS.', 'Legal Basis / Driver': 'Sponsor Guidance; Immigration Rules', 'Deadline / Trigger': 'Before first CoS assignment', 'Owner': 'HR Lead', 'Status': 'Not started', 'Dependencies': 'Sponsor licence granted', 'Notes': 'Failure to report can result in licence downgrade or revocation.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 3.3
Couch Heroes / UK Company Setup / Project Plan | 3.4 Salary and Role Change Reporting Procedure | {'Ref': '3.4', 'Priority': 'P3', 'Artifact Name': 'Salary and Role Change Reporting Procedure', 'Description': "Procedure for notifying the Home Office of changes to sponsored workers' salary, role, job title, or working location.", 'Legal Basis / Driver': 'Sponsor Guidance; Immigration Rules', 'Deadline / Trigger': 'Before first CoS assignment', 'Owner': 'HR Lead', 'Status': 'Not started', 'Dependencies': 'Sponsor licence granted'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 3.4
Couch Heroes / UK Company Setup / Project Plan | PRIORITY 4: OPERATIONAL AND BEST-PRACTICE DOCUMENTS | {'Priority': 'P4', 'Artifact Name': 'PRIORITY 4: OPERATIONAL AND BEST-PRACTICE DOCUMENTS'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref
Couch Heroes / UK Company Setup / Project Plan | 4.1 Job Description Templates | {'Ref': '4.1', 'Priority': 'P4', 'Artifact Name': 'Job Description Templates', 'Description': 'Standardised templates for all roles. Must include SOC 2020 occupation codes (for sponsor licence use) and salary benchmarking.', 'Legal Basis / Driver': 'Best practice; supports sponsor licence compliance and equal pay', 'Deadline / Trigger': 'Before first recruitment round', 'Owner': 'HR Lead', 'Status': 'Not started'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.1
Couch Heroes / UK Company Setup / Project Plan | 4.2 Interview Scoring Matrix | {'Ref': '4.2', 'Priority': 'P4', 'Artifact Name': 'Interview Scoring Matrix', 'Description': 'Structured scoring template for fair, consistent candidate evaluation. Aligned with Equality Act 2010 requirements.', 'Legal Basis / Driver': 'Best practice; Equality Act 2010', 'Deadline / Trigger': 'Before first recruitment round', 'Owner': 'HR Lead', 'Status': 'Not started'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.2
Couch Heroes / UK Company Setup / Project Plan | 4.3 Onboarding Checklist | {'Ref': '4.3', 'Priority': 'P4', 'Artifact Name': 'Onboarding Checklist', 'Description': 'Comprehensive checklist: contract signing, right to work check, pension enrolment, IT setup, policy acknowledgements, training, DSE assessment, emergency contacts.', 'Legal Basis / Driver': 'Best practice; consolidates legal requirements', 'Deadline / Trigger': 'Before first employee starts', 'Owner': 'HR Lead / Operations', 'Status': 'Not started', 'Dependencies': 'Contract (1.1), RTW procedure (1.4), pension letter (1.6), H&S policy (1.5)'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.3
Couch Heroes / UK Company Setup / Project Plan | 4.4 Probation Review Template | {'Ref': '4.4', 'Priority': 'P4', 'Artifact Name': 'Probation Review Template', 'Description': 'Structured template for probation reviews: objectives, performance criteria, development areas, confirmation/extension/termination decision.', 'Legal Basis / Driver': 'Best practice; supports UFD defence from January 2027', 'Deadline / Trigger': 'Before first probation review', 'Owner': 'HR Lead', 'Status': 'Not started', 'Dependencies': 'Probation policy (2.1m)', 'Notes': 'Critical for managing early-stage performance given 6-month UFD from January 2027.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.4
Couch Heroes / UK Company Setup / Project Plan | 4.5 Performance Review Template | {'Ref': '4.5', 'Priority': 'P4', 'Artifact Name': 'Performance Review Template', 'Description': 'Annual/bi-annual performance review template.', 'Legal Basis / Driver': 'Best practice', 'Deadline / Trigger': 'Within first year', 'Owner': 'HR Lead', 'Status': 'Not started'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.5
Couch Heroes / UK Company Setup / Project Plan | 4.6 Exit Interview Template | {'Ref': '4.6', 'Priority': 'P4', 'Artifact Name': 'Exit Interview Template', 'Description': 'Standardised questions for departing employees.', 'Legal Basis / Driver': 'Best practice', 'Deadline / Trigger': 'Before first leaver', 'Owner': 'HR Lead', 'Status': 'Not started'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.6
Couch Heroes / UK Company Setup / Project Plan | 4.7 Leaver Checklist | {'Ref': '4.7', 'Priority': 'P4', 'Artifact Name': 'Leaver Checklist', 'Description': 'Final pay, pension cessation, return of property, revocation of IT access, IP confirmation, Home Office notification (if sponsored worker), reference policy.', 'Legal Basis / Driver': 'Best practice; sponsor licence compliance', 'Deadline / Trigger': 'Before first leaver', 'Owner': 'HR / Operations', 'Status': 'Not started'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.7
Couch Heroes / UK Company Setup / Project Plan | 4.8 HRIS Platform Selection and Implementation | {'Ref': '4.8', 'Priority': 'P4', 'Artifact Name': 'HRIS Platform Selection and Implementation', 'Description': 'Requirements spec for system integrating: personnel records, payroll, pension, recruitment, absence management, document storage, visa/sponsor tracking.', 'Legal Basis / Driver': 'Best practice; supports multiple compliance requirements', 'Deadline / Trigger': 'Within first 3 months', 'Owner': 'Operations / HR', 'Status': 'Not started', 'Notes': 'Payroll provider and pension provider must be selected first.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.8
Couch Heroes / UK Company Setup / Project Plan | 4.9 Bribery Act Compliance Policy | {'Ref': '4.9', 'Priority': 'P4', 'Artifact Name': 'Bribery Act Compliance Policy', 'Description': 'Adequate procedures to prevent bribery under Bribery Act 2010 s.7. Cover gifts, hospitality, facilitation payments, third-party due diligence.', 'Legal Basis / Driver': 'Bribery Act 2010', 'Deadline / Trigger': 'Within first 6 months', 'Owner': 'Legal / Finance', 'Status': 'Not started', 'ARTIFACTS': 'To check with Dino/Aris/LILI', 'Notes': "Defence of 'adequate procedures' requires documented policy."} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.9
Couch Heroes / UK Company Setup / Project Plan | 4.10 Modern Slavery Statement (OPTIONAL) | {'Ref': '4.10', 'Priority': 'P4', 'Artifact Name': 'Modern Slavery Statement (OPTIONAL)', 'Description': 'Statement of steps taken to prevent modern slavery in business and supply chains. Required if turnover exceeds £36m; good practice regardless.', 'Legal Basis / Driver': 'Modern Slavery Act 2015', 'Deadline / Trigger': 'When turnover threshold met (or voluntarily earlier)', 'Owner': 'Legal / Operations', 'Status': 'Not started', 'ARTIFACTS': 'To check with Dino/Aris/LILI', 'Notes': 'Only legally required if turnover exceeds £36 million. Not applicable at current scale.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.10
Couch Heroes / UK Company Setup / Project Plan | 4.12 EMI Share Scheme Documentation (OPTIONAL) | {'Ref': '4.12', 'Priority': 'P4', 'Artifact Name': 'EMI Share Scheme Documentation (OPTIONAL)', 'Description': 'Enterprise Management Incentives scheme: option agreement, scheme rules, HMRC notification, board resolutions, company valuation. Highly tax-efficient for UK tech startups.', 'Legal Basis / Driver': 'Income Tax (Earnings and Pensions) Act 2003; HMRC EMI guidance', 'Deadline / Trigger': 'When ready to offer equity incentives', 'Owner': 'Legal / Finance', 'Status': 'Not started', 'ARTIFACTS': 'To check with Dino/Aris/LILI', 'Dependencies': 'Company valuation required', 'Notes': 'Hiring competitiveness tool, not a legal requirement. Build when ready to offer equity incentives.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.12
Couch Heroes / UK Company Setup / Project Plan | 4.13 DSE Assessment Template | {'Ref': '4.13', 'Priority': 'P4', 'Artifact Name': 'DSE Assessment Template', 'Description': 'Display Screen Equipment assessment form for each employee (office and remote). Must cover workstation setup, screen position, chair, lighting, breaks.', 'Legal Basis / Driver': 'Health and Safety (Display Screen Equipment) Regulations 1992', 'Deadline / Trigger': 'Before each employee starts working at a screen', 'Owner': 'Operations / HR', 'Status': 'Not started', 'Dependencies': 'H&S Policy (1.5)', 'Notes': 'Particularly important for a studio where all staff use screens.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.13
Couch Heroes / UK Company Setup / Project Plan | 4.14 Trade Union Rights Communication Template | {'Ref': '4.14', 'Priority': 'P4', 'Artifact Name': 'Trade Union Rights Communication Template', 'Description': 'Template all-staff communication informing workers of their right to join a trade union and the protections that apply to union membership and activities.', 'Legal Basis / Driver': 'ERA 2025 (from October 2026)', 'Deadline / Trigger': 'Before October 2026', 'Owner': 'HR Lead', 'Status': 'Not started', 'Notes': 'New mandatory duty from October 2026.'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 4.14
Couch Heroes / UK Company Setup / Project Plan | PRIORITY 5: COMPANIES HOUSE AND CORPORATE GOVERNANCE | {'Priority': 'P5', 'Artifact Name': 'PRIORITY 5: COMPANIES HOUSE AND CORPORATE GOVERNANCE'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref
Couch Heroes / UK Company Setup / Project Plan | 5.1 Companies House Filing Calendar | {'Ref': '5.1', 'Priority': 'P5', 'Artifact Name': 'Companies House Filing Calendar', 'Description': 'Schedule for: confirmation statement (annual), annual accounts, PSC register maintenance, filing of any changes to directors/registered office/share capital.', 'Legal Basis / Driver': 'Companies Act 2006', 'Deadline / Trigger': 'Ongoing from incorporation', 'Owner': 'Finance / Legal', 'Status': 'Done', 'Notes': 'Late filing penalties apply.'} | Done | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.1
Couch Heroes / UK Company Setup / Project Plan | 5.2 PSC Register | {'Ref': '5.2', 'Priority': 'P5', 'Artifact Name': 'PSC Register', 'Description': 'Register of People with Significant Control. Must be kept up to date and filed with Companies House.', 'Legal Basis / Driver': 'Companies Act 2006 Part 21A', 'Deadline / Trigger': 'From incorporation', 'Owner': 'Legal / Company Secretary', 'Status': 'Done'} | Done | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.2
Couch Heroes / UK Company Setup / Project Plan | 5.3 Director Identity Verification | {'Ref': '5.3', 'Priority': 'P5', 'Artifact Name': 'Director Identity Verification', 'Description': 'Required under Economic Crime and Corporate Transparency Act 2023. Directors must verify their identity with Companies House.', 'Legal Basis / Driver': 'ECCTA 2023', 'Deadline / Trigger': 'When required by Companies House (phased implementation 2025/2026)', 'Owner': 'Directors / Legal', 'Status': 'Done', 'Notes': 'Check Companies House for current implementation status.'} | Done | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.3
Couch Heroes / UK Company Setup / Project Plan | 5.4 Corporation Tax Registration | {'Ref': '5.4', 'Priority': 'P5', 'Artifact Name': 'Corporation Tax Registration', 'Description': 'Register with HMRC for Corporation Tax within 3 months of starting business activity.', 'Legal Basis / Driver': 'Corporation Tax Act 2009', 'Deadline / Trigger': 'Within 3 months of starting activity', 'Owner': 'Finance', 'Status': 'Done'} | Done | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.4
Couch Heroes / UK Company Setup / Project Plan | 5.5 VAT Registration Assessment | {'Ref': '5.5', 'Priority': 'P5', 'Artifact Name': 'VAT Registration Assessment', 'Description': 'Assess whether turnover exceeds the £90,000 threshold (from April 2024). Register if required. Consider voluntary registration for input tax recovery.', 'Legal Basis / Driver': 'Value Added Tax Act 1994', 'Deadline / Trigger': 'Monitor ongoing; register when threshold reached', 'Owner': 'Finance', 'Status': 'Done', 'Notes': 'Gaming studio may benefit from voluntary registration for input VAT recovery on equipment/services.'} | Done | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.5
Couch Heroes / UK Company Setup / Project Plan | 5.6 R&D Tax Relief Assessment (OPTIONAL) | {'Ref': '5.6', 'Priority': 'P5', 'Artifact Name': 'R&D Tax Relief Assessment (OPTIONAL)', 'Description': 'Assess eligibility for R&D tax relief (SME scheme or RDEC). Game development typically qualifies. Can be worth 10-33% of qualifying R&D expenditure.', 'Legal Basis / Driver': 'Corporation Tax Act 2009 Part 13; Finance Act 2024', 'Deadline / Trigger': 'First Corporation Tax return', 'Owner': 'Finance / Tax Advisor', 'Status': 'in progress', 'ARTIFACTS': 'to check with Aris', 'Notes': 'Tax optimisation, not a compliance requirement. Pursue with tax advisor at first CT return.'} | In progress | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Project Plan / ref 5.6
Couch Heroes / UK Company Setup / Red Team Findings | Section 6; Artifacts list | {'2': '3', 'Sexual harassment risk assessment not listed as standalone artifact': 'Trade union communication obligation (October 2026) not mentioned', 'HIGH': 'MEDIUM', 'Artifacts list; H&S': 'Section 6; Artifacts list', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add to ERA 2025 timeline (Section 6.2) and create template artifact (4.14)', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Section 4.13; Artifacts list | {'2': '4', 'Sexual harassment risk assessment not listed as standalone artifact': "Record retention policy not listed as artifact. Payroll record retention stated as '3 years' but wage records require 6 years.", 'HIGH': 'HIGH', 'Artifacts list; H&S': 'Section 4.13; Artifacts list', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add Record Retention Policy as artifact (2.7). Correct 6-year obligation for payroll/wage records.', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Section 5; Handbook | {'2': '7', 'Sexual harassment risk assessment not listed as standalone artifact': 'Working Time Regulations 48-hour week / crunch culture risk not addressed', 'HIGH': 'MEDIUM', 'Artifacts list; H&S': 'Section 5; Handbook', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add Working Time and 48-Hour Week Policy to handbook (2.1o). Address crunch periods specifically.', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Section 5; RTW procedure | {'2': '8', 'Sexual harassment risk assessment not listed as standalone artifact': 'Right to work civil penalty amounts not stated (£45k first / £60k repeat)', 'HIGH': 'MEDIUM', 'Artifacts list; H&S': 'Section 5; RTW procedure', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add penalty figures to RTW Checks Procedure (1.4)', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Artifacts list; Contract | {'2': '9', 'Sexual harassment risk assessment not listed as standalone artifact': 'IP assignment: moral rights waiver (CDPA 1988 s.87) not specified', 'HIGH': 'HIGH', 'Artifacts list; H&S': 'Artifacts list; Contract', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add moral rights waiver requirement to IP Assignment Agreement spec (2.2) and contract (1.1)', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | H&S Policy; Artifacts list | {'2': '10', 'Sexual harassment risk assessment not listed as standalone artifact': 'DSE Assessment not listed as standalone artifact template', 'HIGH': 'MEDIUM', 'Artifacts list; H&S': 'H&S Policy; Artifacts list', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add DSE Assessment Template as artifact (4.13)', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Awareness only at current size | {'2': '11', 'Sexual harassment risk assessment not listed as standalone artifact': 'Equality (Race and Disability) Bill on legislative horizon for ethnicity/disability pay gap reporting (250+ employees). Not mentioned.', 'HIGH': 'LOW', 'Artifacts list; H&S': 'Awareness only at current size', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Note for future. Not actionable until enacted. Monitor progress.', 'YES': 'NO (future)'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Section 4.13 | {'2': '12', 'Sexual harassment risk assessment not listed as standalone artifact': '6-year record retention for payroll/wage records vs. 3 years stated in guide', 'HIGH': 'HIGH', 'Artifacts list; H&S': 'Section 4.13', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": "Correct Section 4.13 from 'at least 3 years' to 'at least 3 years (PAYE) / 6 years (payroll and wage records)'.", 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Red Team Findings | Corporate governance | {'2': '13', 'Sexual harassment risk assessment not listed as standalone artifact': 'R&D tax relief not mentioned. Gaming studios commonly qualify and the cash benefit is significant.', 'HIGH': 'MEDIUM', 'Artifacts list; H&S': 'Corporate governance', "Add as standalone artifact (2.8). Must be documented before October 2026 to demonstrate 'all reasonable steps'.": 'Add R&D Tax Relief Assessment as artifact (5.6)', 'YES': 'YES'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Red Team Findings / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.7 | {'Date': 'Before first hire', 'Change / Deadline': "Employers' Liability Insurance obtained and displayed", 'Category': 'Insurance', 'Impact on CH': 'Mandatory. £2,500/day fine without.', 'Artifact(s) Affected': '1.7'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1 | {'Date': 'Before first hire', 'Change / Deadline': 'Employment contract template finalised (with all 11 corrections)', 'Category': 'Contract', 'Impact on CH': 'Mandatory Section 1 statement from day one.', 'Artifact(s) Affected': '1.1'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.4 | {'Date': 'Before first hire', 'Change / Deadline': 'Right to work check procedure in place', 'Category': 'Immigration', 'Impact on CH': 'Up to £60,000 per illegal worker (repeat breach).', 'Artifact(s) Affected': '1.4'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.3 | {'Date': 'Before first hire', 'Change / Deadline': 'Employee privacy notice drafted', 'Category': 'Data Protection', 'Impact on CH': 'UK GDPR requirement. ICO enforcement risk.', 'Artifact(s) Affected': '1.3'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Section 4 | {'Date': 'Before first hire', 'Change / Deadline': 'HMRC employer registration completed', 'Category': 'Payroll', 'Impact on CH': 'Must register before first payday.', 'Artifact(s) Affected': 'Section 4'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.6 | {'Date': 'Before first hire', 'Change / Deadline': 'Pension scheme selected and set up', 'Category': 'Pensions', 'Impact on CH': 'Auto-enrolment duties begin with first eligible employee.', 'Artifact(s) Affected': '1.6'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Contract, payroll | {'Date': '1 April 2026', 'Change / Deadline': 'NMW/NLW rates increase (£12.71 for 21+)', 'Category': 'Pay', 'Impact on CH': 'All salaries must meet new minimums.', 'Artifact(s) Affected': 'Contract, payroll'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1, 2.1c | {'Date': '6 April 2026', 'Change / Deadline': 'SSP: waiting period removed, LEL removed, 80%-of-AWE rate', 'Category': 'Statutory Pay', 'Impact on CH': 'Contracts and policies must be updated. Payroll systems must handle new calculation.', 'Artifact(s) Affected': '1.1, 2.1c'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1, 2.1e | {'Date': '6 April 2026', 'Change / Deadline': 'Paternity leave becomes day-one right', 'Category': 'Family Leave', 'Impact on CH': 'Remove qualifying period from policies.', 'Artifact(s) Affected': '1.1, 2.1e'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1, 2.1e | {'Date': '6 April 2026', 'Change / Deadline': 'Unpaid parental leave becomes day-one right', 'Category': 'Family Leave', 'Impact on CH': 'Remove qualifying period from policies.', 'Artifact(s) Affected': '1.1, 2.1e'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1e | {'Date': '6 April 2026', 'Change / Deadline': "Bereaved Partner's Paternity Leave introduced", 'Category': 'Family Leave', 'Impact on CH': 'New entitlement. Add to family leave policies.', 'Artifact(s) Affected': '2.1e'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1n | {'Date': '6 April 2026', 'Change / Deadline': 'Collective redundancy protective award doubled to 180 days', 'Category': 'Redundancy', 'Impact on CH': 'Increased financial risk of getting consultation wrong.', 'Artifact(s) Affected': '2.1n'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1i | {'Date': '6 April 2026', 'Change / Deadline': 'Sexual harassment becomes qualifying whistleblowing disclosure', 'Category': 'Whistleblowing', 'Impact on CH': 'Update whistleblowing policy.', 'Artifact(s) Affected': '2.1i'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Awareness | {'Date': '6 April 2026', 'Change / Deadline': 'Fair Work Agency established', 'Category': 'Enforcement', 'Impact on CH': 'New enforcement body for NMW, holiday pay, SSP.', 'Artifact(s) Affected': 'Awareness'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Awareness | {'Date': '6 April 2026', 'Change / Deadline': 'Trade union recognition simplified; electronic balloting', 'Category': 'Trade Unions', 'Impact on CH': 'Lower threshold for union recognition.', 'Artifact(s) Affected': 'Awareness'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Section 4.12 | {'Date': '6 April 2026', 'Change / Deadline': 'Voluntary payrolling of BIK available (mandatory from April 2027)', 'Category': 'Payroll / Tax', 'Impact on CH': 'Optional to test systems. Mandatory from April 2027.', 'Artifact(s) Affected': 'Section 4.12'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Section 3 | {'Date': '8 April 2026', 'Change / Deadline': 'Immigration fee increases (~6-7%)', 'Category': 'Immigration', 'Impact on CH': 'Higher costs for sponsor licence and visa applications.', 'Artifact(s) Affected': 'Section 3'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1, 2.4 | {'Date': 'October 2026', 'Change / Deadline': 'Fire and rehire becomes automatically unfair', 'Category': 'Contracts', 'Impact on CH': 'Review variation clauses in contract template.', 'Artifact(s) Affected': '1.1, 2.4'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1g, 2.8 | {'Date': 'October 2026', 'Change / Deadline': "Sexual harassment duty tightened to 'all reasonable steps'", 'Category': 'Harassment', 'Impact on CH': 'Risk assessment must be documented. All reasonable steps demonstrated.', 'Artifact(s) Affected': '2.1g, 2.8'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1g, 2.8 | {'Date': 'October 2026', 'Change / Deadline': 'Third-party harassment liability reintroduced', 'Category': 'Harassment', 'Impact on CH': 'Assess risks from clients, players, online interactions.', 'Artifact(s) Affected': '2.1g, 2.8'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.7 | {'Date': 'October 2026', 'Change / Deadline': 'Tribunal time limits extended to 6 months', 'Category': 'Litigation', 'Impact on CH': 'Longer window for claims. Update record retention.', 'Artifact(s) Affected': '2.7'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 4.14 | {'Date': 'October 2026', 'Change / Deadline': 'Employer must inform workers of right to join a union', 'Category': 'Trade Unions', 'Impact on CH': 'Mandatory all-staff communication.', 'Artifact(s) Affected': '4.14'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 1.1, 2.1m, 4.4 | {'Date': 'January 2027', 'Change / Deadline': 'Unfair dismissal qualifying period drops to 6 months', 'Category': 'Dismissal', 'Impact on CH': 'Anyone hired from ~July 2026 gains UFD protection Jan 2027. Probation design critical.', 'Artifact(s) Affected': '1.1, 2.1m, 4.4'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | 2.1a, 2.1m | {'Date': 'January 2027', 'Change / Deadline': 'Unfair dismissal compensation cap removed', 'Category': 'Dismissal', 'Impact on CH': 'Unlimited compensatory awards. Getting dismissals wrong is now more expensive.', 'Artifact(s) Affected': '2.1a, 2.1m'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Section 4.12 | {'Date': 'April 2027', 'Change / Deadline': 'Mandatory payrolling of benefits in kind', 'Category': 'Payroll / Tax', 'Impact on CH': 'P11D no longer available for most benefits. Payroll systems must handle BIK reporting via RTI.', 'Artifact(s) Affected': 'Section 4.12'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Awareness | {'Date': '2027', 'Change / Deadline': 'Zero-hours contract guaranteed hours right', 'Category': 'Contracts', 'Impact on CH': 'If using ZHC workers, must offer guaranteed hours after reference period.', 'Artifact(s) Affected': 'Awareness'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref
Couch Heroes / UK Company Setup / Compliance Timeline | Future | {'Date': '2027', 'Change / Deadline': 'Mandatory equality action plans (250+ employers)', 'Category': 'Reporting', 'Impact on CH': 'Only applies if CH reaches 250 employees.', 'Artifact(s) Affected': 'Future'} | Not started | High |  | Implementation | Lorenza |  |  | Legal & Compliance |  |  |  | UK xlsx / Compliance Timeline / ref

## Studio Business
parent_path | title | description | status | priority | health_state | work_type | assignees | due_date | dependencies | practice_area | type | layer | confidence | source | notes
Couch Heroes / Studio Business / BD | Player target Segments |  | Not started | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 37
Couch Heroes / Studio Business / BD | Go To Market Strategy |  | Not started | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 38
Couch Heroes / Studio Business / BD | Build a solid website | There is an existing website. It's pretty terrible. They're replacing it with a new one. It's taken roughly three months to build using full-stack engineers. It'll be a step-up iteration. We need to plan the next iteration to get it viable for the studio. | In progress | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 39
Couch Heroes / Studio Business / GTM and Forecasting | Define primary player segment profile (the Explorer) | Build a full ICP for the Explorer archetype: demographics, motivations, current MMO and adventure game habits, hours per week, spend pattern, content sources, social platforms used, why they would switch from their current main, what makes them lapse. Source from vision doc plus desk research on cosy MMO and exploration RPG audiences. Output as a one page ICP card. | Not started | Critical ACT |  | Research | Glen, Vardis |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Vision doc explicitly names Explorer as the primary persona; this is the foundation for every other GTM artifact ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Define secondary player segment profile (the Socialiser) | Full ICP for the Socialiser: relationship to Discord communities, housing game enthusiasm (Animal Crossing, FFXIV housing, Sims), guild history, why they leave games, what makes social spaces sticky for them. | Not started | High |  | Research | Glen, Vardis |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Socialiser is secondary persona; housing and partner worlds are their hooks ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Define tertiary player segment profile (the Achiever, collection focused) | Full ICP for Achievers in a cosmetic only economy: motivations when there is no power gear ladder, completionist behaviour, parallels to Pokemon Go, Genshin, FFXIV glamour. | Not started | High |  | Research | Glen, Vardis |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Achiever in CH means collection completion, not gear score; this reframing is non standard and needs explicit positioning ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Define supported player segment profile (the Killer, optional PvP) | ICP for the optional PvP audience. What competitive content do we offer them, and how do we avoid bleeding competitive design into the core experience as the vision doc forbids. | Not started | Medium |  | Research | Glen, Vardis |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Killer is supported not primary; profile exists to bound design decisions, not to drive marketing spend ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Audience research wave one: cosy MMO refugees survey | Field a survey targeted at lapsed players of FFXIV, Guild Wars 2, Wildstar nostalgia communities, Palia, Wynncraft. Test response to positioning statements, art style references, corruption mechanic concept, partner worlds concept, no stat gear concept. Sample size and screening criteria need agreement. | Not started | High |  | Research | Glen, Vardis |  | ICP cards | Studio Business |  |  |  | Agent / Studio Business | Glen to confirm budget for paid panel vs organic Reddit recruitment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Audience research wave two: qualitative interviews with Explorer archetype | Run twelve to twenty depth interviews with self identified Explorer type players. Probe on what makes a world feel alive, when they last got lost in a game and why, what kills exploration for them. | Not started | High |  | Research | Glen, Vardis |  | ICP cards | Studio Business |  |  |  | Agent / Studio Business | Use customer-research skill methodology; transcripts feed back into messaging work ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Competitor map: cosy MMO and exploration RPG landscape | Comprehensive teardown of Palia, Wynncraft, FFXIV, Guild Wars 2, Genshin, Wildstar, ESO, BDO, Throne and Liberty, Pax Dei, Dune Awakening, Ashes of Creation, Fellowship, Light No Fire. For each: positioning, audience, monetisation model, retention loops, social architecture, cosmetic economy, current Steam wishlist count, last twelve months press cadence, community size. | Not started | Critical ACT |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Light No Fire and Pax Dei are closest direct comparators; this map is referenced by every other GTM doc ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Competitor positioning matrix: where Couch Heroes sits | Two by two and radar plot mapping Couch Heroes against the competitor set on axes that matter: cosy vs hardcore, social pressure level, gear power dependence, exploration depth, partner content. Identifies where the white space is and where we are crowded. | Not started | High |  | Strategy | Glen, Vardis |  | Competitor map | Studio Business |  |  |  | Agent / Studio Business | Output is a slide for studio offsite plus pitch deck ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Anti positioning statement | Explicit statement of what Couch Heroes is NOT: not a gear treadmill, not raid centric, not PvP first, not a battle pass live service, not a chosen one fantasy. Positioning is as much about disqualifying as qualifying. | Not started | High |  | Strategy | Glen, Vardis |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Vision doc gives strong material here; this saves us from chasing audiences we cannot serve ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Core positioning statement | Single paragraph positioning: for the Explorer who is tired of gear treadmill MMOs, Couch Heroes is the cosy fantasy MMORPG where the world rewards your curiosity and the adventures you have shape who you are. Tested with audience research wave one. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Audience research, anti positioning | Studio Business |  |  |  | Agent / Studio Business | Glen to sign off after wave one results land ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Three message pillars derived from positioning | Pillar one: discovery is the reward. Pillar two: identity is earned not assigned. Pillar three: the home you come back to. Each pillar gets one supporting proof point and one anti claim it knocks down. | Not started | High |  | Strategy | Glen, Vardis |  | Positioning statement | Studio Business |  |  |  | Agent / Studio Business | Pillars feed press kit, website hero copy, trailer beats ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Tagline shortlist and test | Generate twenty taglines aligned to message pillars. Test top eight with audience research panel for memorability, comprehension, differentiation. Final selection by studio leadership. | Not started | Medium |  | Strategy | Glen, Vardis |  | Message pillars | Studio Business |  |  |  | Agent / Studio Business | Avoid generic adventure copy; the corruption and partner worlds angles are the hooks ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Brand voice and tone guidelines | Document the studio voice for marketing comms: young adult, edgy but not GTA, accessible fantasy, witty about the meta of MMOs, never cynical about its own world. Include do and do not phrases, sample social posts in voice, sample press release in voice. | Not started | High |  | Implementation | Glen, Vardis |  | Positioning, message pillars | Studio Business |  |  |  | Agent / Studio Business | Vision doc explicitly says young adult tone, edgy but not PG ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Visual identity brief for marketing assets | Brief for the visual style of marketing: how the byte punk in game art translates to social tiles, trailer cards, Steam capsules, banner ads, billboards. Where the corruption visuals fit. Constraint set so a freelancer can produce on brand. | Not started | High |  | Implementation | Glen, Vardis |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Coordinates with Director of Art (David); sits across game and marketing ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Pre launch revenue forecast model: base case | Build a bottom up forecast covering wishlist conversion at launch, day one units, week one units, month one, year one. Assumptions: Steam discoverability multiplier, average price point, refund rate, regional split. Driven by analogue games selected from competitor map. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Competitor map, Steam strategy | Studio Business |  |  |  | Agent / Studio Business | This is the primary investor and board number; Glen to set price assumption ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Pre launch revenue forecast: bull and bear cases | Two additional scenarios. Bull case assumes a viral moment (signature corruption clip, big streamer), strong wishlist trajectory. Bear case assumes flat wishlist, no breakout coverage, soft launch window. Each case lists the trigger conditions. | Not started | High |  | Strategy | Glen, Vardis |  | Base case | Studio Business |  |  |  | Agent / Studio Business | Provides decision framework for marketing spend tiers ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Live service revenue model: cosmetic only economy | Forecast model for post launch revenue across cosmetic store, partner item sales, expansion content. Must reconcile with vision pillar that gear has no stats; pricing tiers for cosmetic types, expected ARPDAU, expected paying user share. | Not started | High |  | Strategy | Glen, Vardis |  | Pricing strategy | Studio Business |  |  |  | Agent / Studio Business | Cosmetic only is unusual for MMO; benchmarks from FFXIV mog station, GW2, Genshin are reference points ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Lifetime value model by player segment | LTV projection split by Explorer, Socialiser, Achiever, Killer. Driver: cosmetic spend, partner game purchases through The Platform, subscription if applicable, expansion sales. Identifies which segment we under monetise and whether that is acceptable. | Not started | High |  | Strategy | Glen, Vardis |  | Live service model, ICP cards | Studio Business |  |  |  | Agent / Studio Business | Open question: subscription vs box plus cosmetic store. Needs Glen and CEO call ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Pricing strategy for base game | Recommendation on launch price band: premium box (around forty to sixty), mid (twenty to thirty five), free to play with cosmetic store, subscription. Each option has a wishlist conversion projection, an LTV projection, a positioning implication. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Live service model | Studio Business |  |  |  | Agent / Studio Business | Decision blocks Steam page setup; needs studio leadership decision ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Pricing strategy for cosmetic store | Item tiering, currency design, bundle structure, FOMO vs evergreen mix. Must align with vision pillar that the best things are found not purchased. | Not started | High |  | Strategy | Glen, Vardis |  | Pricing for base game | Studio Business |  |  |  | Agent / Studio Business | Tension to resolve: vision says best things are discovered, but a cosmetic store needs aspirational SKUs ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Marketing budget proposal: launch window | Total budget request for the launch window with allocation across paid social, influencer, PR retainer, trade events, asset production, Steam featuring deals, regional pushes. Tied to forecast scenarios. | Not started | High |  | Strategy | Glen, Vardis |  | Forecasts | Studio Business |  |  |  | Agent / Studio Business | Glen to define the affordability ceiling; the proposal sizes against forecast ROI ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Marketing budget: ongoing live service | Monthly budget envelope post launch covering content marketing, influencer programme, seasonal events, partner game cross promo, community ops. | Not started | Medium |  | Strategy | Glen, Vardis |  | Live service forecast | Studio Business |  |  |  | Agent / Studio Business | Needs CFO input; sits alongside live ops budget on the production side ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Channel strategy: paid acquisition mix | Recommendation across Meta, TikTok, YouTube, Reddit, Twitch ads, podcast sponsorship, Twitter or X, Discord ads. For each channel: audience match score, expected CPI band, creative format, role in funnel. | Not started | High |  | Strategy | Glen, Vardis |  | ICP cards, budget proposal | Studio Business |  |  |  | Agent / Studio Business | Cosy MMO audience indexes high on TikTok and YouTube long form ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Channel strategy: organic and earned | Plan covering content marketing, dev blog cadence, devstreams, community led content, fan creator support, Reddit AMAs, Twitter or X cadence. | Not started | High |  | Strategy | Glen, Vardis |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Earned media is disproportionately important for MMO genre ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Influencer tiering and target list | Tier one (one to five million followers) Tier two (hundred thousand to one million) Tier three (under hundred thousand, high niche fit). Initial target list of forty creators across cosy gaming, MMO commentary, exploration RPG, fantasy art, Twitch variety. Each entry gets fit rationale. | Not started | High |  | Research | Glen, Vardis |  | Channel strategy | Studio Business |  |  |  | Agent / Studio Business | Overlaps with BD influencer programme; this list is the marketing layer, the BD work is the deal layer ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Launch funnel definition | Define each funnel stage from awareness through wishlist through purchase through retention through monetisation. Conversion rate assumptions per stage drawn from genre benchmarks. | Not started | High |  | Strategy | Glen, Vardis |  | Forecasts | Studio Business |  |  |  | Agent / Studio Business | Used to brief paid creative and to triage where the funnel breaks ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Wishlist target setting | Set numerical wishlist targets at six, three and one month before launch. Based on competitor analogue trajectories. Each milestone has a contingency plan if undershot. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Competitor map, launch funnel | Studio Business |  |  |  | Agent / Studio Business | Steam visibility at launch is downstream of wishlist count; this is the single most important pre launch metric ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Wishlist campaign roadmap | Campaign plan from Steam page live through launch covering announcement beats, demo events (Steam Next Fest, Day of the Devs), trailer drops, festival submissions. Each beat has expected wishlist add range. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Wishlist target | Studio Business |  |  |  | Agent / Studio Business | Steam Next Fest participation is the single biggest wishlist driver outside paid; do not miss ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Steam page strategy: copy, capsule, screenshots | Full Steam page brief: short description, long description, capsule art, header art, screenshot plan, gif plan, trailer placement, tag selection, recommended for hooks. Optimised for Steam algorithm and for the audience research messaging. | Not started | High |  | Implementation | Glen, Vardis |  | Positioning, brand voice | Studio Business |  |  |  | Agent / Studio Business | Steam page is the highest leverage page on the internet for this game ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Steam page strategy: tag and category optimisation | Research and select Steam tags balancing discoverability with audience match. Genre tag fights to win. Track tag changes and impact. | Not started | Medium |  | Research | Glen, Vardis |  | Steam page brief | Studio Business |  |  |  | Agent / Studio Business | MMORPG tag is crowded; cosy and exploration tags may serve better ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Steam Next Fest plan | Demo content plan, slot strategy, event communications, post fest analysis loop. Demo content scoped against Gamescom vertical slice. | Not started | High |  | Strategy | Glen, Vardis |  | Wishlist roadmap, Gamescom build | Studio Business |  |  |  | Agent / Studio Business | Demo must show corruption mechanic; that is the highlight reel moment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Trailer plan: announcement, gameplay, launch | Three core trailers: announcement (mood, world, hook), gameplay (combat plus traversal plus corruption plus partner worlds), launch (review quotes, tone of arrival). Each trailer has key beats, length target, music direction, deployment plan. | Not started | High |  | Strategy | Glen, Vardis |  | Brand voice, Steam page | Studio Business |  |  |  | Agent / Studio Business | Vision doc explicitly worried about visuals feeling pedestrian; trailers must lean exotic ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Trailer production briefs and vendor selection | Briefs for external trailer house. Shortlist of vendors with track record on indie and mid sized RPGs. RFP and selection. | Not started | Medium |  | Implementation | Glen, Vardis |  | Trailer plan | Studio Business |  |  |  | Agent / Studio Business | Vendor shortlist: Derek Lieu, Hyped For This, M2H, Studios Trailer Park indie team ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Press release schedule across launch window | Calendar of press releases mapped to trailer beats and milestones. Each release has angle, target outlets, embargoed assets, spokesperson assignment. | Not started | Medium |  | Strategy | Glen, Vardis |  | Trailer plan, PR media list | Studio Business |  |  |  | Agent / Studio Business | Coordinated with PR sub feature; the calendar is shared ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Demo, beta, early access decision | Strategic call on whether to do paid early access (Wynncraft, Palia model), free beta (FFXIV model), demo only. Each option has wishlist, revenue, risk implications. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Forecasts, Steam strategy | Studio Business |  |  |  | Agent / Studio Business | Glen and CEO decision; impacts every other GTM artefact ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Localisation plan | Languages at launch: minimum English; recommendation set of French, Italian, German, Spanish, Brazilian Portuguese, Russian, Simplified Chinese, Japanese, Korean. Each language with audience size, MMO genre uptake, vendor estimate. | Not started | Medium |  | Strategy | Glen, Vardis |  | Forecasts | Studio Business |  |  |  | Agent / Studio Business | Asia uptake of cosy MMO is significant; CN approval is its own track ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Region strategy: Europe focus, NA, APAC | Phased launch rollout across regions, balancing simultaneous global launch versus staggered. Each region with channel mix and partner needs. | Not started | Medium |  | Strategy | Glen, Vardis |  | Localisation | Studio Business |  |  |  | Agent / Studio Business | UK studio with EU centric story leans European primary; APAC needs partner ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Launch milestone plan: external beats | Map every external visible milestone from now to launch: trailers, festivals, conventions, betas, store updates. Master calendar shared with PR, BD, Community. | Not started | High |  | Strategy | Glen, Vardis |  | All other GTM items | Studio Business |  |  |  | Agent / Studio Business | This is the calendar the studio offsite uses to plan capacity ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Launch milestone plan: internal gates | Internal go no go gates against the external plan. What needs to be true at each gate to commit to the next external beat. | Not started | High |  | Strategy | Glen, Vardis |  | External milestone plan | Studio Business |  |  |  | Agent / Studio Business | Gates protect the studio from over commitment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Post launch year one content cadence | Content drop cadence post launch: major patch frequency, seasonal events, partner world introductions, expansion windows. Each drop has a marketing beat and a community moment attached. | Not started | Medium |  | Strategy | Glen, Vardis |  | Live service forecast | Studio Business |  |  |  | Agent / Studio Business | Vision pillar of partner world launches as biggest social moments shapes this ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Forecast tracking dashboard | Live dashboard tracking actual versus forecast on wishlist, social follower growth, press mentions, demo participants, beta sign ups. Updated weekly. | Not started | Medium |  | Implementation | Glen, Vardis |  | Forecasts, channel strategy | Studio Business |  |  |  | Agent / Studio Business | Owned by GTM lead; lives in WorkSage or Notion ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Marketing playbook compiled | Single document compiling positioning, messaging, channel strategy, calendar, budget, brand assets, voice guide, tactics. The reference any new marketing hire reads on day one. | Not started | High |  | Implementation | Glen, Vardis |  | All upstream items | Studio Business |  |  |  | Agent / Studio Business | The deliverable from this entire feature ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Crisis comms plan | Pre planned playbooks for the foreseeable bad days: server outage at launch, community manager incident, partner studio controversy, layoff news, financing news, scope cut announcement. Each has decision tree, draft statements, escalation. | Not started | Medium |  | Strategy | Glen, Vardis |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Live service games attract drama; preparation is cheap, reaction is expensive ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Genre repositioning research: cosy vs cosy MMO vs exploration RPG | Decide which genre flag to plant. Cosy MMO is becoming a category. Risks of being mislabelled either way. Wins from leaning cosy. | Not started | High |  | Research | Glen, Vardis |  | Competitor map | Studio Business |  |  |  | Agent / Studio Business | Vision doc says cosy MMORPG; need to confirm market reception of the cosy framing for an action combat game ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Founder media training programme | Train Vardis, Aris and Robin for spokesperson duty: interview technique, message pillar discipline, hostile question handling, video presence, podcast performance. | Not started | Medium |  | Implementation | Glen, Vardis |  | Brand voice, message pillars | Studio Business |  |  |  | Agent / Studio Business | Founders are the face of the studio; coverage hinges on them ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Quote bank for spokespeople | Approved quote bank by topic for press use: corruption mechanic, partner worlds, no stat gear, social architecture, single player first. | Not started | Medium |  | Implementation | Glen, Vardis |  | Founder media training | Studio Business |  |  |  | Agent / Studio Business | Lets press extract quotes without misquoting; speeds inbound coverage ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Awards strategy | Map of award programmes (BAFTA, Develop, GDCA, IGF, Indie Megabooth, Indie Cade) with submission windows, entry fees, fit assessment. | Not started | Medium |  | Strategy | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Coordinated with PR; awards drive press cycles ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | Steam Festivals and storefront feature plan | Map of every Steam discoverability moment beyond Next Fest: themed sales, daily deals, hub features, curator programme. Each one has a fit and submission plan. | Not started | Medium |  | Strategy | Glen, Vardis |  | Steam page brief | Studio Business |  |  |  | Agent / Studio Business | Steam featured slots are a relationship business with Valve ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / GTM and Forecasting | KPI definition for marketing function | Define the metrics marketing is accountable for: wishlist count, wishlist quality (conversion at launch), media share of voice, follower growth, sentiment score, paid CPI, organic share, attributed sales. Targets per quarter. | Not started | High |  | Strategy | Glen, Vardis |  | All other GTM items | Studio Business |  |  |  | Agent / Studio Business | Without KPIs, this entire backlog is theatre ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Build target publishing partner longlist | Generate a longlist of around forty publishers across full publishing partners, marketing only deals, regional partners, platform first parties. Each entry: track record, recent deals, MMO history, cosy genre history, financial health, strategic fit. | Not started | High |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Hooded Horse, Devolver, 505, Krafton, Tencent (Level Infinite), NetEase, Embracer remnants, Iceberg, PLAION, Kepler, Coffee Stain Publishing among likely fits ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Publisher fit and shortlist | Score the longlist against criteria: capital fit, audience fit, MMO and live service capability, partner game enthusiasm, contractual reasonableness, recent successes vs failures. Shortlist of ten. | Not started | High |  | Strategy | Glen, Vardis |  | Publisher longlist | Studio Business |  |  |  | Agent / Studio Business | Live service MMO is a small subset of publisher capability; shortlist will be smaller than expected ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Publisher pitch deck | Sales deck targeting publishers: vision, team, market opportunity, traction, monetisation model, partner worlds upside, ask. Tuned by deal type (full publish vs marketing only vs regional). | Not started | Critical ACT |  | Implementation | Glen, Vardis |  | Forecasts, positioning | Studio Business |  |  |  | Agent / Studio Business | Glen has gi skill assets and pitch deck experience; reuse and adapt ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Publisher data room build | Diligence ready data room: cap table, team CVs, GDD, milestones, financials, build access, demo access, telemetry plan, IP ownership, partner agreements. | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Greenlight Glen on which fields are commercially sensitive vs share early ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Publisher outreach campaign | Structured outreach with personalised pitch to top ten publishers. Track first contact, first meeting, second meeting, term sheet stage, decision. CRM hygiene. | Not started | High |  | Implementation | Glen, Vardis |  | Publisher pitch deck, data room | Studio Business |  |  |  | Agent / Studio Business | Apollo or Pipedrive for tracking; Glen approves all outbound external messages ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Term sheet template and red lines | Studio side template term sheet with our preferred terms and a documented red lines list (recoupment caps, IP retention, sequel rights, key person clauses). | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Built with legal counsel; reuse across publisher discussions ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Decision framework: publish vs self publish | Quantitative and qualitative comparison of self publishing vs publisher deal. Inputs: capital available, team capacity for marketing, publisher economics, control. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | Forecasts, term sheet template | Studio Business |  |  |  | Agent / Studio Business | Decision belongs to CEO and board; BD prepares the paper ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Steam platform onboarding | Set up Steamworks, configure store presence, set up build pipeline, set up partner billing, set up Steam Direct, register all team accounts. | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Required regardless of publisher decision ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Steam playtest and demo configuration | Configure Steam playtest gating, demo branch, password protected builds for press, key issuance via Keymailer or similar. | Not started | Medium |  | Implementation | Glen, Vardis |  | Steam onboarding | Studio Business |  |  |  | Agent / Studio Business | Operational; coordinates with PR keys distribution ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Epic Games Store onboarding | Apply for Epic Store presence, evaluate exclusivity offer if extended, set up Epic Online Services if used. | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Epic exclusivity offers are publishing relationships; coordinated with publisher decision ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | GOG submission and assessment | Evaluate GOG fit (DRM free), submission, marketing benefit. | Not started | Low |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Smaller revenue but cult audience for fantasy RPG ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | PlayStation submission programme | Apply for SIE developer status, submit concept for PS5 evaluation, plan certification, identify required middleware compliance, plan first party feature support (DualSense, Activities). | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | First party submissions take time; start the registration well before it is needed ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Xbox submission programme (ID@Xbox or full developer) | ID@Xbox application, evaluate full developer status, plan certification, plan Game Pass discussion. | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Game Pass for an MMO is a strategic discussion; sits alongside publisher decision ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Switch 2 submission programme | Nintendo developer registration, evaluate fit (Switch 2 hardware capability vs MMO requirements), plan certification approach. | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Switch 2 capability for MMO scope is unconfirmed; flag for studio Tech (Mustafa) input ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Cross play and account model decision | Decision on whether the game supports cross play across platforms and how player accounts unify (publisher account vs platform account vs both). | Not started | High |  | Strategy | Glen, Vardis |  | First party submissions | Studio Business |  |  |  | Agent / Studio Business | Cross play is a vision pillar future state; structural decisions need to be made early to avoid platform rebuild later ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Hardware partner outreach (controllers, peripherals) | Hardware brand partnerships: gamepads, headsets, RGB. Co marketing potential and bundle potential. | Not started | Low |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Logitech G, Razer, SteelSeries, 8BitDo are the obvious fits; co marketing is cheaper than pure cash deals ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Hardware partner outreach (PC OEMs) | PC OEM partnerships: Asus ROG, MSI, Alienware, Lenovo Legion. Bundle potential with launch SKUs. | Not started | Low |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | OEM bundles are typically post launch when retail can move them ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Co marketing pipeline framework | Standard process for co marketing deals: opportunity intake, fit scoring, deal structure templates, asset exchange, measurement. | Not started | Medium |  | Implementation | Glen, Vardis |  | Brand assets | Studio Business |  |  |  | Agent / Studio Business | Without a framework every deal becomes bespoke and slow ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Distribution partnerships outside Steam (key resellers) | Decisions on Humble, Fanatical, Green Man Gaming, Epic Direct distribution. Greylist of grey market resellers we will not work with. | Not started | Low |  | Strategy | Glen, Vardis |  | Steam onboarding, Epic onboarding | Studio Business |  |  |  | Agent / Studio Business | Grey market is a long running headache for live service; decide policy now ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Influencer programme structure | Tiered programme design: founder creators (long term partners), launch creators (campaign tier), seeded creators (key drops). Contracts, exclusivity, deliverables. | Not started | High |  | Strategy | Glen, Vardis |  | Influencer target list | Studio Business |  |  |  | Agent / Studio Business | Coordinates with GTM influencer list; this is the deal layer ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Influencer outreach to top tier (Tier one) | Direct outreach to top tier creators with bespoke pitch, demo access, founder call offer. Maximum five at a time to manage relationship quality. | Not started | High |  | Implementation | Glen, Vardis |  | Influencer programme structure | Studio Business |  |  |  | Agent / Studio Business | Top tier creator buy in is the single biggest organic accelerant; do this well or skip it ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Influencer outreach mid tier | Tier two and three outreach. Volume game with a structured ask: demo key, talking points, drop window, asset pack. | Not started | Medium |  | Implementation | Glen, Vardis |  | Influencer programme structure | Studio Business |  |  |  | Agent / Studio Business | Volume management means a CRM and clear template messaging ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Streamer programme: live launch coverage | Programme to lock in coverage for launch day: paid talent, organic talent, embed support, day one bug response. | Not started | High |  | Implementation | Glen, Vardis |  | Influencer programme structure | Studio Business |  |  |  | Agent / Studio Business | Launch day livestream coverage shapes wishlist conversion through reviews window ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Tournament partnerships and esports stance | Position on whether the optional PvP gets a competitive scene. If yes, partnerships with tournament organisers and broadcasters. If no, declare it. | Not started | Low |  | Strategy | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Vision doc says PvP is supported not central; default position is no formal esports ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Partner game integration deal pipeline | The signature BD work for Couch Heroes: pipeline of partner studios whose games integrate as portals. Outreach list, deal templates, technical onboarding spec, revenue share model, exclusivity terms. | Not started | Critical ACT |  | Strategy | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Partner worlds is a defining pillar; this pipeline is unique to Couch Heroes and central to the live service hypothesis ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Partner game target longlist | Identify thirty partner game candidates across indie and mid scale studios whose IP fits the byte punk world: roguelikes, mini RPGs, puzzle games, racing, narrative shorts, retro arcade. | Not started | High |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | First wave should be friendly indie studios with low integration cost; later waves can be bigger names ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Partner game integration tech spec for partners | Public facing technical brief for partner studios: API spec, art constraints, integration cost, certification process, IP rights, marketing commitments. The thing that lets a partner studio say yes without a sales call. | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Head of Tech (Mustafa); turns BD work into a self serve funnel ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Partner game contract template | Standard partner integration agreement: rev share, marketing obligations, certification, IP carve outs, term, termination, dispute resolution. | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Built with legal counsel; expected to evolve over the first ten partner deals ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | First five partner game deals: targeted outreach | Hand picked first five partner game deals chosen for buzz, fit, and case study value. Personal outreach by founders. | Not started | Critical ACT |  | Implementation | Glen, Vardis |  | Partner pipeline, contract template | Studio Business |  |  |  | Agent / Studio Business | The first five partners are a marketing story; pick studios people will write about ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Partner discovery showcase format | Plan for the first partner game showcase event (in game or external) where partner studios are presented to the community. | Not started | Medium |  | Strategy | Glen, Vardis |  | Partner deals | Studio Business |  |  |  | Agent / Studio Business | Partner showcases become ongoing social moments per the vision doc ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Brand and IP partnerships outreach (non game) | Non gaming brand partnerships for crossovers: music labels, streetwear, animation studios, food brands. Targeted at the cosy Explorer audience. | Not started | Low |  | Implementation | Glen, Vardis |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Genshin and FFXIV cross brand activations are the model ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Investor pipeline (BD adjacent) | Maintain investor list for follow on rounds: gaming VCs, family offices, strategic LPs. Updates and check ins. | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Glen has gi skill and investor materials; this is the BD touchpoint not the deck building ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Government grant and tax relief programmes | UK Video Games Tax Relief, UK Games Fund, Innovate UK, Creative Europe (depending on scope), Horizon Europe. Applications and compliance. | Not started | High |  | Research | Glen, Vardis |  | Studio company structure | Studio Business |  |  |  | Agent / Studio Business | UK VGTR is material to the financials; do not miss ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Banking and financial services partnerships | Strategic banking relationships, payment processors (Stripe, Xsolla, Adyen), foreign exchange, transaction cost negotiation. | Not started | Medium |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Operational rather than strategic but adds up at scale ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Localisation vendor selection | Vendor shortlist for localisation: Keywords, Side, Lionbridge Games, Native Prime, Lokalise, plus indie LQA shops. Selection by language coverage, MMO experience, price. | Not started | Medium |  | Research | Glen, Vardis |  | Localisation plan in GTM | Studio Business |  |  |  | Agent / Studio Business | Coordinated with GTM localisation plan ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | QA outsource partner selection | If internal QA is supplemented, vendor shortlist for outsource QA: PTW, Keywords, Testronic, Lionbridge Games. | Not started | Medium |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Live service launch QA spike usually exceeds in house capacity ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Customer service partner selection | Vendor shortlist for player support: Keywords Helpshift, Helpshift direct, 5CA, customer support specialists. Required volume scaling. | Not started | Medium |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Player support is non trivial for an MMO; underbudgeting here is a known live service mistake ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Anti cheat and trust partner selection | Anti cheat vendor decision: Easy Anti Cheat, BattlEye, in house. Plus account fraud, payment fraud, content moderation tooling. | Not started | Medium |  | Research | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Cosy MMO with PvP optional reduces but does not eliminate cheat risk ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Media buy agency relationship | Performance marketing agency relationship for paid acquisition. Shortlist of agencies with games experience. Or in house build. | Not started | Medium |  | Strategy | Glen, Vardis |  | Channel strategy | Studio Business |  |  |  | Agent / Studio Business | In house is cheaper at scale; agency is faster to start ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Convention and trade show booth contracts | Booth contracts and partner negotiations for Gamescom, GDC, PAX, EGX. Includes shared booth opportunities and indie hubs. | Not started | High |  | Implementation | Glen, Vardis |  | PR conference plan | Studio Business |  |  |  | Agent / Studio Business | Coordinated with PR conference plan; this is the contractual layer ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | Contract pipeline tracking | CRM or pipeline tracker for all BD activity: each deal gets stage, value, probability, next action, owner. Reviewed weekly. | Not started | High |  | Implementation | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | BD without a pipeline tracker is an open invitation to drop deals ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / BD | BD KPI definition | Define metrics for BD: deals closed, partners onboarded, partner game integrations live, platform certifications complete, key contract renewals. | Not started | Medium |  | Strategy | Glen, Vardis |  | None | Studio Business |  |  |  | Agent / Studio Business | Without KPIs the BD function is invisible to leadership ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press kit core build | Studio and game press kit: logo pack, key art, screenshots, gif loops, b roll, fact sheet, founder bios, headshots, quote bank, reviewer guide, embed code. Hosted on a press portal. | Not started | Critical ACT |  | Implementation | Glen |  | Visual identity, brand voice | Studio Business |  |  |  | Agent / Studio Business | Press kit absence kills inbound press cycles; must exist before any major announcement ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press kit fact sheet | One pager with all the critical facts: studio location, founding date, team size, platforms, genre, release window, USPs, contact. The thing journalists copy and paste from. | Not started | High |  | Implementation | Glen |  | Press kit core | Studio Business |  |  |  | Agent / Studio Business | Use Couch Heroes Vision doc, vision pillars, batch handoff doc ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Reviewer guide | Document for press explaining what is in the build, what is intentionally absent, what to focus reviews on, known issues, embargo terms. | Not started | High |  | Implementation | Glen |  | Press kit core | Studio Business |  |  |  | Agent / Studio Business | Sets press expectations; reduces unfair review framing ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Story angles document | Living document of pitchable story angles by outlet type: corruption mechanic depth dive, no stat MMO economy, partner worlds as platform, cosy MMO category builders, UK studio profile, founder background. | Not started | High |  | Implementation | Glen |  | Positioning | Studio Business |  |  |  | Agent / Studio Business | Each angle is matched to outlet type; some only fit trade press, some fit consumer press ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press release template and approval flow | Template for press releases with approval flow (Glen, CEO, CMO equivalent). Boilerplate at bottom. Assets attached separately. | Not started | Medium |  | Implementation | Glen |  | Press kit core | Studio Business |  |  |  | Agent / Studio Business | Reuse across announcements ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Studio launch communications plan | If studio has not had a public launch yet (and the vision doc material suggests low public profile), build the announcement plan: founder story, mission, hiring, vision teaser. | Not started | High |  | Strategy | Glen |  | Studio naming, brand voice | Studio Business |  |  |  | Agent / Studio Business | Glen to confirm whether studio has been formally announced; if not this is the first major PR moment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: tier one games trade list | Tier one list with named contacts: GamesIndustry.biz, Edge, Eurogamer, IGN, Polygon, Kotaku, PC Gamer, RPS, Game Developer, GDC press team, Gamesradar. | Not started | High |  | Research | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Tier one tracks studio profile and major beats; relationships not transactions ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: MMO and RPG specialist outlets | Specialist list: MMORPG.com, Massively OP, MMO Fallout, RPG Site, RPGFan, PCGamesN MMO desk, MMO Champion, plus YouTube and podcast equivalents. | Not started | High |  | Research | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | These outlets are where genre fans actually live; conversion to wishlist is high ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: cosy and lifestyle gaming list | Outlets and creators in the cosy gaming space: Cozy Gamer, NookNet for Animal Crossing crossover, lifestyle creators on YouTube, dedicated podcasts. | Not started | High |  | Research | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Cosy MMO is an emerging category; creator friendships in this space are gold ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: regional press (UK and EU) | UK trade and consumer press, plus French, German, Polish, Spanish equivalents. | Not started | Medium |  | Research | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | UK studio means UK trade coverage is structurally easier; do not waste it ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: APAC press | Famitsu, 4Gamer, Inven, Bahamut, IGN Japan, Game Watch. Likely needs partner or local PR support. | Not started | Medium |  | Research | Glen |  | Regional strategy | Studio Business |  |  |  | Agent / Studio Business | Coordinated with localisation plan and regional partner work in BD ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press relationships: streamer press hybrids | YouTube journalists and dedicated commentators: Force Gaming, Asmongold (with care given the pillar tone), Josh Strife Hayes, NoClip, IGN First, Game Maker's Toolkit. | Not started | Medium |  | Research | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Long form video commentary is the high value PR slot for MMO genre ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Embargo policy | Standard embargo terms by content type. Process for handling break embargoes. Outlet specific exclusives policy. | Not started | Medium |  | Implementation | Glen |  | Press relationships | Studio Business |  |  |  | Agent / Studio Business | Without policy embargoes get botched; basic asset ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Exclusive coverage strategy | Pre planned exclusive opportunities by beat: announcement to one outlet, gameplay reveal to another, deep dive to a specialist. Tradeoffs and rules. | Not started | High |  | Strategy | Glen |  | Press relationships, story angles | Studio Business |  |  |  | Agent / Studio Business | Exclusives are how trade press relationships are kept warm ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Spokesperson assignment matrix | Which founder or team lead speaks on which topic. Robin on game design and pillars, Vardis on studio mission, David on art direction, Mustafa on tech and partner integration, Valeria on production, Lorenz on hiring story, Glen on commercial strategy. | Not started | Medium |  | Strategy | Glen |  | Founder media training | Studio Business |  |  |  | Agent / Studio Business | Topic ownership prevents off message comments ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Founder profile pieces strategy | Targeted founder profile pitches to outlets that do them: Edge, GamesIndustry.biz, Game Developer. Pre seeded narrative, photoshoot, anchor topic. | Not started | Medium |  | Strategy | Glen |  | Spokesperson matrix | Studio Business |  |  |  | Agent / Studio Business | Founder profiles drive perception of studio quality and improve hiring funnel ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: GDC | GDC participation: talks submitted, side meetings, networking events, parties, recruiting. | Not started | High |  | Strategy | Glen |  | Founder media training | Studio Business |  |  |  | Agent / Studio Business | GDC is the industry relationship cycle; non negotiable for live service ambition ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: Gamescom | Gamescom strategy across business and consumer halls. Booth, partner meetings, press briefings, livestream slots. | Not started | Critical ACT |  | Strategy | Glen |  | Booth contracts | Studio Business |  |  |  | Agent / Studio Business | Gamescom is the studio's stated next milestone; this is the high stakes external moment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: PAX | PAX (PAX East, West, Aus, Online) participation: Indie Megabooth, panels, signings, fan engagement. | Not started | Medium |  | Strategy | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | PAX is more consumer oriented; great for community moments ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: EGX | EGX UK presence given studio is UK based. Local press flock here. | Not started | Medium |  | Strategy | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | EGX London is a structural advantage for UK studio ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: GDC Europe and Develop Brighton | Develop Brighton, Reboot Develop, Pocket Gamer Connects (if mobile platform component grows). | Not started | Low |  | Strategy | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | UK conferences for trade and recruiting ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry conference plan: TGS, BitSummit | Tokyo Game Show and BitSummit if APAC presence develops. Likely partner needed. | Not started | Low |  | Strategy | Glen |  | APAC strategy | Studio Business |  |  |  | Agent / Studio Business | Coordinated with regional plan ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Award submissions tracker | Schedule of award submissions: BAFTA, GDCA, IGF, IndieCade, Develop, MCV, Mwave, Develop Star, Independent Games Festival, Webby. With deadlines and submission formats. | Not started | Medium |  | Implementation | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Awards drive press cycles even when you do not win ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Trade events and side events plan | Side events at major shows: Day of the Devs, Future Games Show, Future of Play Direct, Wholesome Direct, Guerrilla Collective, MIX, Devolver Direct equivalents. | Not started | High |  | Strategy | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Wholesome Direct is the bullseye event for cosy positioning; do not miss ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Case study programme: feature dev blogs | Long form dev blog series unpacking each pillar: how corruption works, why no stat gear, how partner worlds integrate. Quotable, screenshotable, reblogable. | Not started | High |  | Implementation | Glen |  | Brand voice, content strategy | Studio Business |  |  |  | Agent / Studio Business | Dev blogs serve PR cycles, hiring funnel, and community engagement simultaneously ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Case study programme: postmortems | Public postmortem cadence: closed beta postmortem, Steam Next Fest postmortem, launch postmortem. Builds reputation for professionalism. | Not started | Low |  | Implementation | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Postmortems differentiate at GDC and Game Developer the publication ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Blog cadence (PR sliver) | Editorial calendar for studio blog: weekly cadence target, content slots (dev blog, community spotlight, partner game profile, behind the scenes). | Not started | Medium |  | Strategy | Glen |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Community feature; blog is dual owned ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Podcast appearance plan | Target podcasts for founder appearances: NoClip (NoClip Podcast), GamesIndustry.biz Microcast, IGN Unfiltered, Triple Click, Friends Per Second, Defining Duke, MMOpinions, Game Maker's Notebook. | Not started | Medium |  | Implementation | Glen |  | Spokesperson matrix | Studio Business |  |  |  | Agent / Studio Business | Long form audio reaches the deep audience ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Crisis communications plan (PR layer) | Specific PR plays during crisis: holding statements, escalation contact tree, response time targets, social vs media split. | Not started | High |  | Strategy | Glen |  | GTM crisis comms | Studio Business |  |  |  | Agent / Studio Business | Lives alongside GTM crisis comms but with PR specific tactics ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Reactive PR monitoring | Daily monitoring for press mentions, social mentions, review aggregators. Alert thresholds and triage process. | Not started | Medium |  | Implementation | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Mention.com, Brand24, or similar tooling; coordinated with community sentiment ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Quarterly press briefings rhythm | Off the record quarterly briefings with tier one press once a relationship cadence is established. Maintains presence between announcement beats. | Not started | Low |  | Strategy | Glen |  | Press relationships | Studio Business |  |  |  | Agent / Studio Business | The thing that keeps trade press warm in quiet periods ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Localisation of press materials | Translated press kits for FR, DE, ES, IT, JP, KR, ZH plus regional adaptation. | Not started | Medium |  | Implementation | Glen |  | Localisation, press kit | Studio Business |  |  |  | Agent / Studio Business | Localisation skip is the most common PR mistake at international launch ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Press portal build (web) | The actual web destination for press: press portal page, asset downloads, press kit download, contact form, account requests for embargoed material. | Not started | High |  | Implementation | Glen |  | Website iteration, press kit core | Studio Business |  |  |  | Agent / Studio Business | Coordinated with website feature; this is the press facing surface ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | PR agency assessment and hire (or in house decision) | Decision on whether to retain a PR agency (Plan of Attack, Stride PR, Renaissance PR, Sandbox Strategies, Hooch and Bish, ICO Partners) or build in house. Each path scoped. | Not started | High |  | Strategy | Glen |  | Budget proposal | Studio Business |  |  |  | Agent / Studio Business | Glen and CEO call; PR agency selection drives all the relationship work ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | KPI definition for PR function | Metrics: tier one mentions, share of voice vs competitor set, sentiment, founder speaking slots, press portal traffic, asset downloads. | Not started | Medium |  | Strategy | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Without KPIs PR is invisible to leadership and gets cut first when budgets shrink ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / PR | Industry analyst relationships | Newzoo, Niko Partners, Omdia, DFC, Ampere. Briefings on the studio and category. | Not started | Low |  | Implementation | Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Analyst briefings shape industry conventional wisdom; a long term play ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Discord server architecture | Channel structure design: announcements, general, regional channels, role channels, partner game channels, support, suggestions, lore corner, fan creators, voice rooms. Permission roles. | Not started | Critical ACT |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Discord is the primary community platform for MMO genre; the architecture decision sets a multi year context ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Discord onboarding flow | Welcome flow for new members: role selection, code of conduct accept, channel guide, links to game store and website. Bot configuration. | Not started | High |  | Implementation | Glen, Barb |  | Discord architecture | Studio Business |  |  |  | Agent / Studio Business | Onboarding flow is the difference between active community and ghost server ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Discord moderation policy and tools | Code of conduct, escalation procedure, banned content list, mod team structure (volunteer vs staff), moderation tools (auto mod, MEE6, Carl bot, custom), audit trail. | Not started | High |  | Implementation | Glen, Barb |  | Discord architecture | Studio Business |  |  |  | Agent / Studio Business | Cosy community attracts harassment; tone moderation protects the audience the studio promises ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Discord bots and integrations | Selection and configuration of bots: moderation, roles, levels, partner game widgets, Twitch integration, Twitter or X integration, GitHub or status integration. | Not started | Medium |  | Implementation | Glen, Barb |  | Discord architecture | Studio Business |  |  |  | Agent / Studio Business | Bots multiply moderator productivity; under invest and Barb burns out ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Discord server launch event | Launch event for the Discord with founder Q&A, sneak peek content, server tier rewards. | Not started | Medium |  | Implementation | Glen, Barb |  | Discord architecture | Studio Business |  |  |  | Agent / Studio Business | Soft launch first to test, then external announcement ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community calendar template and rhythm | Annual community calendar template: weekly standing items (developer streams, community spotlight, art Friday), monthly items (Q&A, contest, partner spotlight), seasonal events. | Not started | High |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Calendar is the operating system for Community function ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community Manager onboarding plan: Barb specifically | Specific 30 day plan for Barb (10 hours per week): tools access, brand voice training, escalation paths, content authorisation matrix, schedule template, check in cadence with Glen. | Not started | Critical ACT |  | Implementation | Glen, Barb |  | Brand voice, Discord architecture | Studio Business |  |  |  | Agent / Studio Business | Barb is the only Community headcount; her onboarding determines the whole function's success ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community Manager scope sheet (10 hr/week constraint) | Explicit list of what Barb does and what she does not. With ten hours per week the scope must be ruthlessly bounded; everything else needs an owner or stays undone. | Not started | Critical ACT |  | Implementation | Glen, Barb |  | Barb onboarding | Studio Business |  |  |  | Agent / Studio Business | Without a scope sheet ten hours becomes thirty in chaos; this is a protective document for Barb ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community Manager content authorisation matrix | What Barb can post without approval, what needs Glen sign off, what needs founder sign off. Speed of comms matters. | Not started | High |  | Implementation | Glen, Barb |  | Barb onboarding, brand voice | Studio Business |  |  |  | Agent / Studio Business | Stops the bottleneck of every post needing approval while protecting brand ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community Manager working tools setup | Tooling: Discord access, Twitter or X scheduler (Buffer, Hypefury), Twitch creator account, Reddit account, scheduling tool (Notion or Asana), analytics dashboard. | Not started | High |  | Implementation | Glen, Barb |  | Barb onboarding | Studio Business |  |  |  | Agent / Studio Business | Tools save hours; specifically scoped because Barb has ten of them ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Forum platform decision | Whether to run a forum (Discourse, in house, Reddit reliance only) or stick with Discord plus Reddit only. Each option has scaling implications. | Not started | Medium |  | Strategy | Glen, Barb |  | None | Studio Business |  |  |  | Agent / Studio Business | Forum is heavyweight; Reddit plus Discord is the modern default but loses search SEO benefits ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Reddit subreddit setup and moderation | Set up r/CouchHeroes (or studio renamed equivalent). Reserve username, define rules, recruit volunteer moderators, partnership with subreddit team. | Not started | High |  | Implementation | Glen, Barb |  | Studio naming | Studio Business |  |  |  | Agent / Studio Business | Reserving the subreddit early is critical; if a fan claims it first the dynamics get complicated ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Reddit engagement plan | Editorial plan for the studio's Reddit presence: AMAs, dev posts, response cadence, raid the leaderboard moments, weekly community threads. | Not started | High |  | Strategy | Glen, Barb |  | Reddit setup, brand voice | Studio Business |  |  |  | Agent / Studio Business | Reddit converts harder than Twitter for MMO genre ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Twitter or X engagement plan | Posting cadence, thread strategy, response policy, reply guy cadence, art share programme, partner studio amplification. | Not started | High |  | Strategy | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Despite churn, X remains where games trade press lives; cannot abandon ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Bluesky and Threads presence | Decision and execution on secondary social platforms. Rising audiences but smaller. | Not started | Low |  | Strategy | Glen, Barb |  | None | Studio Business |  |  |  | Agent / Studio Business | Cheap to maintain a presence; early moves can build follow before peers ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | TikTok strategy | Content strategy for TikTok: short clip plan, partner with creators, repurposing of trailer footage, behind the scenes vlogs. | Not started | Medium |  | Strategy | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | TikTok indexes high for cosy gaming audience and is a wishlist driver ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | YouTube channel strategy | Channel content plan: trailer drops, dev diaries, longform interviews, partner game spotlights, lore deep dives, livestream archives. | Not started | Medium |  | Strategy | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | YouTube is the long term content compounding asset ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Instagram presence | Instagram account for art and photo mode community. Lower priority but cheap to maintain. | Not started | Low |  | Strategy | Glen, Barb |  | None | Studio Business |  |  |  | Agent / Studio Business | Photo mode in vision; Instagram is the natural surface ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Player Q&A cadence (text and live) | Monthly text Q&A on Reddit. Quarterly live Q&A on stream. Semi annual founder Q&A. Each format with format brief and prep checklist. | Not started | High |  | Strategy | Glen, Barb |  | Spokesperson matrix | Studio Business |  |  |  | Agent / Studio Business | Q&A is the trust building ritual; consistency matters more than scale ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Beta tester programme: structure | Programme tiers: closed alpha (under 100), playtest (around 100, vision doc says Q1 2026), public alpha (Q4 2026 vision doc), beta. Each with selection criteria, NDA terms, feedback channels, reward for participation. | Not started | Critical ACT |  | Strategy | Glen, Barb |  | Vision doc | Studio Business |  |  |  | Agent / Studio Business | Vision doc has explicit playtest milestones; the community structure for those needs to exist before the milestones ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Beta tester programme: selection process | Application form, scoring criteria, communication cadence with applicants, waitlist management. | Not started | High |  | Implementation | Glen, Barb |  | Beta programme structure | Studio Business |  |  |  | Agent / Studio Business | Applications come in floods; without a process the founders end up answering DMs ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Beta tester NDA and feedback policy | Standard NDA template. Public communication policy. Reward for adherence. Removal policy for breach. | Not started | High |  | Implementation | Glen, Barb |  | Beta programme structure | Studio Business |  |  |  | Agent / Studio Business | Built with legal counsel; reuse across all programme tiers ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Closed alpha logistics | Specific logistics for the first closed alpha: build distribution mechanism, feedback survey, bug report flow, weekly live chats with testers. | Not started | High |  | Implementation | Glen, Barb |  | Beta programme structure | Studio Business |  |  |  | Agent / Studio Business | The first closed alpha is a tone setter for the community's relationship with the dev team ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Developer streams cadence and format | Format design for studio streams: weekly producer update, monthly design deep dive, quarterly all hands stream, ad hoc partner game showcases. | Not started | High |  | Strategy | Glen, Barb |  | Spokesperson matrix | Studio Business |  |  |  | Agent / Studio Business | Vision doc emphasises community visibility; dev streams are how it manifests ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Twitch channel setup | Studio Twitch channel configuration: branding, panels, scheduling, raid programme, mod team. | Not started | Medium |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | The home for live streams; coordinated with YouTube for archival ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Streamer toolkit and assets | Toolkit for partnered streamers: overlays, alerts, sound packs, drops campaign assets. Lowers friction for creators to look on brand. | Not started | Medium |  | Implementation | Glen, Barb |  | Visual identity | Studio Business |  |  |  | Agent / Studio Business | Used in BD influencer outreach; reduces creator effort ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Drops campaign design | Twitch Drops, YouTube Gaming drops, partner game cross drops. Reward design that respects vision pillar of best things found not bought. | Not started | Medium |  | Strategy | Glen, Barb |  | Cosmetic store, BD influencer | Studio Business |  |  |  | Agent / Studio Business | Drops fuel coverage at minimal cost when designed right ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Fan art programme | Structured fan art programme: monthly themes, weekly highlights, official cosmetic inspired by player art, attribution and consent flow. | Not started | Medium |  | Strategy | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Fan art communities create marketing asset surplus; explicit recognition keeps them feeding the brand ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Fan creator support programme (broader than streamers) | Programme for cosplayers, fan fiction writers, machinima makers, content creators outside Twitch and YouTube. Asset access, recognition, occasional sponsorship. | Not started | Low |  | Strategy | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Cosy MMO genre attracts diverse creator types; recognise them or watch them defect ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Player Council programme | A formal player council of around twenty engaged players with regular access to dev team, advance preview of features, structured feedback channel. | Not started | Medium |  | Strategy | Glen, Barb |  | Beta programme | Studio Business |  |  |  | Agent / Studio Business | Ditto Genshin's Honkai survey programme model; converts passion to retention ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community moderation training and resources | Training material for volunteer moderators across Discord, Reddit, forum if applicable. Recognition and rewards for mods. | Not started | Medium |  | Implementation | Glen, Barb |  | Discord moderation policy | Studio Business |  |  |  | Agent / Studio Business | Volunteer moderators do the bulk of community ops; train them or watch the community degrade ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Code of conduct (player facing) | Public player facing code of conduct: harassment, hate speech, cheating, exploit reporting, DMCA. Consistent across game, Discord, Reddit, forums. | Not started | High |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Cosy positioning means the community expects high standards; this document is the floor ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Reporting and ban appeal flow | Player facing reporting of misconduct. Studio facing review process. Appeal flow with documented criteria. | Not started | Medium |  | Implementation | Glen, Barb |  | Code of conduct | Studio Business |  |  |  | Agent / Studio Business | Operational; gets used more than expected at MMO scale ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community sentiment dashboard | Dashboard tracking sentiment across Discord, Reddit, Twitter, Steam reviews, press. Weekly summary to founders. | Not started | Medium |  | Implementation | Glen, Barb |  | Reactive PR monitoring | Studio Business |  |  |  | Agent / Studio Business | Coordinates with PR monitoring tooling ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Partner game cross promo cadence | Calendar of cross promotional moments with partner game studios: their players in our community channels, our players in theirs, joint events. | Not started | High |  | Strategy | Glen, Barb |  | BD partner deals | Studio Business |  |  |  | Agent / Studio Business | Vision doc identifies partner world launches as biggest social moments; this is the operational layer ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Seasonal event playbook | Template for seasonal community events: holiday themes, in game tie ins, social posts, community contests, partner participation. | Not started | Medium |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Reusable templates save Barb's hours ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | New player welcome programme | Programme to welcome new players post launch: in game greeting, Discord welcome, mentor programme connecting new players to veterans. | Not started | Low |  | Strategy | Glen, Barb |  | Discord onboarding | Studio Business |  |  |  | Agent / Studio Business | Vision pillar of voluntary social makes mentor programmes natural fits ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Lapsed player win back programme | Programme to win back lapsed players: communications cadence, return events, comeback rewards, content reintroduction. | Not started | Low |  | Strategy | Glen, Barb |  | Live service forecast | Studio Business |  |  |  | Agent / Studio Business | Costs a fraction of acquisition; high ROI in live service ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community Manager handover document | Document built so that if Barb leaves or is unavailable, another person can step in without everything stopping. | Not started | Medium |  | Implementation | Glen, Barb |  | Barb onboarding | Studio Business |  |  |  | Agent / Studio Business | Bus factor protection; Glen has feedback_verify_work principles relevant here ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community KPI definition | Metrics: Discord MAU, Reddit subscribers, sentiment score, response time, retention proxy via community participation. | Not started | Medium |  | Strategy | Glen, Barb |  | Sentiment dashboard | Studio Business |  |  |  | Agent / Studio Business | Without KPIs the function is invisible at leadership level ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community resource library (player wiki seed) | Seed structured resources to support the inevitable player wiki: character model, location guides, partner studio bios, dev team intros. Often the wiki community organises around these. | Not started | Low |  | Implementation | Glen, Barb |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Wikis form whether the studio supports them or not; better to seed them ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Live ops community calendar (post launch) | Post launch event calendar covering seasonal events, partner showcases, in game contests, community initiated events. | Not started | Medium |  | Strategy | Glen, Barb |  | Community calendar template | Studio Business |  |  |  | Agent / Studio Business | Coordinated with live ops production calendar ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Community | Community manager succession and scaling plan | Plan for when ten hours per week becomes insufficient: triggers for adding hours, hire criteria for second CM, regional CM expansion at international launch. | Not started | Medium |  | Strategy | Glen, Barb |  | Barb onboarding | Studio Business |  |  |  | Agent / Studio Business | Recognise that at launch the function will need more headcount; pre plan ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Audit current website (the one that is being replaced) | Documented audit of current site: pages, content, traffic, SEO state, brand consistency, mobile state, conversion paths, technical debt. Output is a teardown that informs the next iteration. | Not started | High |  | Research | Mustafa, Glen |  | Existing site | Studio Business |  |  |  | Agent / Studio Business | Glen says current site is pretty terrible; the audit document the why so the next iteration does not repeat mistakes ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Status of in flight site rebuild | Document the current state of the three month full stack rebuild. What is shipped, what is broken, what is missing, what was scope cut, what the dev team owner thinks the next iteration needs. | Not started | Critical ACT |  | Research | Mustafa, Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Glen says step up iteration but needs further iteration; this audit lights the path ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Site architecture and information architecture | Full site map: top nav, page hierarchy, URL structure, taxonomy. Includes recruitment portal, press portal, blog, partner portal, investor portal, asset library. | Not started | Critical ACT |  | Strategy | Mustafa, Glen |  | Audit, status of rebuild | Studio Business |  |  |  | Agent / Studio Business | Use site-architecture skill principles; this is the structural decision under all other site work ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Information architecture: hub and spoke decision | Decision on whether the site is a single domain with sub paths or multiple subdomains (press.studio, blog.studio, partners.studio). SEO and operational implications. | Not started | High |  | Strategy | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Single domain is usually better for SEO and brand; multi subdomain is better for operational independence ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | URL structure and slug conventions | Permanent URL structure decisions: trailing slash, capitalisation, locale prefixes, content type prefixes. Hard to change later. | Not started | High |  | Strategy | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Get this right once; URL changes break SEO and bookmarks ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Homepage iteration: hero copy and CTA | Hero copy aligned to message pillars. Single primary CTA (wishlist on Steam) plus supporting paths (community, press, careers). | Not started | Critical ACT |  | Implementation | Mustafa, Glen |  | Message pillars | Studio Business |  |  |  | Agent / Studio Business | The single highest leverage block of copy on the site ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Homepage iteration: visual treatment | Hero visual: animated background, looping b roll, trailer embed. Must convey the byte punk world per vision doc. | Not started | High |  | Implementation | Mustafa, Glen |  | Visual identity | Studio Business |  |  |  | Agent / Studio Business | Vision doc explicitly notes visuals can feel pedestrian; lean exotic ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Game page (the deep dive) | Game page covering features, world, characters, partner worlds concept. The destination for visitors who want more after the homepage. | Not started | High |  | Implementation | Mustafa, Glen |  | Message pillars, brand voice | Studio Business |  |  |  | Agent / Studio Business | Sells the game in detail; supports press deep linking ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | About the studio page | Studio story, founders, mission, location, hiring plug. Distinct from the game itself. | Not started | High |  | Implementation | Mustafa, Glen |  | Studio naming, brand voice | Studio Business |  |  |  | Agent / Studio Business | Coordinated with studio naming decision; cannot be finished until name is settled ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | News and blog section | Blog index and article template. Categories: dev blog, partner spotlight, community, announcements. RSS, share buttons, related posts. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Blog is critical for SEO and community; do not skip on the rebuild ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Recruitment portal | Career page with role listings, application flow, life at studio content, benefits. Integrated with ATS or built standalone. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Studio is hiring; recruitment portal is direct revenue protection (hiring delays cost more than the build) ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Recruitment portal: roles content | Role descriptions for currently open positions plus future openings. Each role with team, location, level, hiring story. | Not started | High |  | Implementation | Mustafa, Glen |  | Recruitment portal build | Studio Business |  |  |  | Agent / Studio Business | Coordinated with HR (Lorenz) and the existing hiring plan documents ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Press portal | Press portal page with kit downloads, asset library, contact form, embargo request flow, latest news. | Not started | High |  | Implementation | Mustafa, Glen |  | Press kit | Studio Business |  |  |  | Agent / Studio Business | Coordinated with PR press kit work ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Press portal asset library | Backend for asset library: logo pack, key art, screenshots, gif loops, b roll, headshots, factsheet PDF. CDN delivered. | Not started | High |  | Implementation | Mustafa, Glen |  | Press kit | Studio Business |  |  |  | Agent / Studio Business | Press will not chase you for assets; if not on the portal, they use the wrong ones ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Partner portal | Page for partner studios explaining the integration opportunity, with API spec download, contact form, partner game gallery. | Not started | High |  | Implementation | Mustafa, Glen |  | BD partner pipeline | Studio Business |  |  |  | Agent / Studio Business | Partner BD funnel needs a self serve top of funnel; this is the page ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Investor portal | Gated page for investor materials: deck, data room access request, investor news. | Not started | Low |  | Implementation | Mustafa, Glen |  | BD investor pipeline | Studio Business |  |  |  | Agent / Studio Business | Lightweight; gate is identity capture ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Asset library (broader than press) | Player facing wallpaper downloads, social profile pictures, fan kit assets, banner kits for community use. | Not started | Low |  | Implementation | Mustafa, Glen |  | Visual identity | Studio Business |  |  |  | Agent / Studio Business | Cosy gaming audience values fan kits highly ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Brand consistency audit | Cross site audit of brand consistency: typography, colour palette, voice, logo usage, image treatment. Finding the gaps. | Not started | Medium |  | Research | Mustafa, Glen |  | Visual identity | Studio Business |  |  |  | Agent / Studio Business | After the audit comes the cleanup; coordinated with Director of Art ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Brand guidelines document | Public brand guidelines covering logo do and do not, colour palette, typography, voice and tone, partner usage rules. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Visual identity | Studio Business |  |  |  | Agent / Studio Business | Required for partner studios using the brand in their materials ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | SEO baseline audit | Technical SEO audit: crawlability, sitemap, robots.txt, structured data, meta tags, canonical URLs, page speed, Core Web Vitals, mobile friendliness, hreflang for localisation. | Not started | Critical ACT |  | Research | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Use seo-audit skill; this surfaces every technical SEO debt that the rebuild has ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | SEO baseline content audit | Audit of content for SEO: title tags, H1s, internal linking, content depth, keyword targeting, image alt text. | Not started | High |  | Research | Mustafa, Glen |  | SEO audit | Studio Business |  |  |  | Agent / Studio Business | Content side of SEO; usually where the most quick wins live ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Keyword strategy and target rankings | Target keyword research: branded (couch heroes), category (cosy MMO, exploration MMO), comparison (palia alternative, light no fire alternative), informational (corruption mechanic). Initial ranking targets. | Not started | High |  | Research | Mustafa, Glen |  | Positioning, competitor map | Studio Business |  |  |  | Agent / Studio Business | Use competitor-alternatives skill methodology; alternative pages are high intent traffic ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Comparison and alternative pages | Alternative pages: Couch Heroes vs Palia, vs Light No Fire, vs FFXIV (cosy comparison), vs Wynncraft. Each page hand built to high standard, not generic vs page. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Keyword strategy, competitor map | Studio Business |  |  |  | Agent / Studio Business | Use competitor-alternatives skill; high commercial intent SEO traffic ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Topic clusters and pillar pages | Pillar pages on big themes: cosy MMO, exploration RPG, corruption mechanic, partner worlds. Each pillar with cluster of supporting articles. | Not started | Medium |  | Strategy | Mustafa, Glen |  | Content strategy | Studio Business |  |  |  | Agent / Studio Business | Use content-strategy skill; topic clusters dominate informational SERPs ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Editorial calendar (website blog) | Calendar of blog post topics aligned to message pillars, SEO targets, marketing milestones. | Not started | Medium |  | Strategy | Mustafa, Glen |  | Keyword strategy, brand voice | Studio Business |  |  |  | Agent / Studio Business | Coordinated with PR blog cadence and Community Reddit plan ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Analytics setup: GA4 plus Plausible or Fathom | Decision on analytics stack. GA4 for depth, Plausible or Fathom for privacy compliant simple metrics. Configuration of events, conversions, audiences. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Without analytics every other GTM and PR claim is unverifiable ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Analytics setup: events and conversions | Custom event mapping: wishlist click, press kit download, role application start, role application submit, demo request, beta sign up, blog read time. | Not started | High |  | Implementation | Mustafa, Glen |  | Analytics setup base | Studio Business |  |  |  | Agent / Studio Business | This is where signal vs noise differentiation happens ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Tag management setup | Google Tag Manager or equivalent for managing tracking pixels: Meta, TikTok, Reddit, X, LinkedIn for hiring, Google Ads. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Analytics setup | Studio Business |  |  |  | Agent / Studio Business | Reduces dev team interruption for marketing changes ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Cookie consent and privacy compliance | GDPR and CCPA compliant consent banner, privacy policy, cookie policy, data subject request flow. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | UK and EU operating; non negotiable from day one ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Newsletter signup and email programme | Email collection on site, ESP selection (Beehiiv, Substack, Customer.io), welcome flow, monthly newsletter template, segmentation. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Email is owned audience; the only thing that does not depend on platform algorithms ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Site search | On site search functionality: Algolia, internal, or none. Decision based on content volume. | Not started | Low |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Likely overkill at current size; revisit as content grows ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Performance optimisation | Page speed, image optimisation, asset bundling, caching strategy, CDN, lazy loading. Core Web Vitals targets. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | SEO and conversion both depend on speed; cosy audience often on lower spec mobile ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Mobile experience | Mobile responsive design pass across all pages. Touch targets, scroll behaviour, performance on mid tier Android. | Not started | High |  | Implementation | Mustafa, Glen |  | Performance optimisation | Studio Business |  |  |  | Agent / Studio Business | Cosy gaming audience indexes higher on mobile browsing than core gamer audiences ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Accessibility compliance | WCAG 2.1 AA pass: keyboard navigation, screen reader, contrast, alt text, ARIA. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Use design accessibility-review skill; vision pillar of accessibility extends beyond the game ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Internationalisation and localisation framework | Site structure to support multiple languages: locale routing, content translation workflow, language selector, hreflang, locale specific assets. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Localisation plan | Studio Business |  |  |  | Agent / Studio Business | Coordinated with GTM localisation plan; site is the second highest priority surface to localise after the game ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Content management workflow | CMS choice and editorial workflow: who can publish what, draft and review process, scheduled posts, version history. | Not started | Medium |  | Strategy | Mustafa, Glen |  | Editorial calendar | Studio Business |  |  |  | Agent / Studio Business | Without workflow the blog dies in week three ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Hosting and infrastructure | Hosting decision (Vercel, Netlify, AWS, Cloudflare Pages), DNS, email, monitoring, uptime SLA. | Not started | High |  | Implementation | Mustafa, Glen |  | Site architecture | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Tech (Mustafa); operational concern ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Security baseline | HTTPS enforcement, security headers (CSP, HSTS, X Frame Options), DDoS protection, dependency scanning, penetration test. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Hosting | Studio Business |  |  |  | Agent / Studio Business | Live service brand cannot afford a defaced website during launch window ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Status page | Public status page for game services. Likely separate domain (status.studio). | Not started | Low |  | Implementation | Mustafa, Glen |  | Hosting | Studio Business |  |  |  | Agent / Studio Business | When servers go down players check this first; absence breeds frustration ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | A/B testing framework | Lightweight A/B testing on hero copy, CTA, layout. Tooling decision: VWO, Optimizely, in house with feature flags. | Not started | Low |  | Implementation | Mustafa, Glen |  | Analytics setup | Studio Business |  |  |  | Agent / Studio Business | Premature optimisation if traffic is low; revisit at scale ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Support and help centre | Help articles, FAQ, contact form. Coordinated with player support partner if used. | Not started | Medium |  | Implementation | Mustafa, Glen |  | BD customer service partner | Studio Business |  |  |  | Agent / Studio Business | Reduces support ticket volume; basic SEO benefit on long tail ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Vision doc and lore wiki seed | Public lore section seeding the world: factions, characters, history. Where the player goes deep on the world before buying. | Not started | Low |  | Implementation | Mustafa, Glen |  | Brand voice | Studio Business |  |  |  | Agent / Studio Business | Vision doc has rich lore; surfacing it on the site differentiates ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Site KPI definition and dashboard | KPIs: organic sessions, wishlist conversions, press kit downloads, role applications, partner enquiries, time on page on key sections. | Not started | Medium |  | Strategy | Mustafa, Glen |  | Analytics setup | Studio Business |  |  |  | Agent / Studio Business | Without KPIs the site is vanity work ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Quarterly site review rhythm | Quarterly review of site analytics, content performance, SEO position, conversion rates. Action item generation. | Not started | Low |  | Implementation | Mustafa, Glen |  | KPI dashboard | Studio Business |  |  |  | Agent / Studio Business | Continuous improvement loop ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Domain portfolio management | Register and renew core domain plus defensive variations (.com, .co.uk, .gg, .games, common typos). Decide which redirect, which sit dormant. | Not started | Medium |  | Implementation | Mustafa, Glen |  | Studio naming | Studio Business |  |  |  | Agent / Studio Business | Coordinated with studio naming decision ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Website | Vendor selection: agency vs in house for next iteration | Decision on whether the next iteration is built by current team, an agency, or hybrid. Each path scoped on cost, speed, control. | Not started | High |  | Strategy | Mustafa, Glen |  | Status of rebuild audit | Studio Business |  |  |  | Agent / Studio Business | Glen and CEO call; impacts every other website item ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Resolve studio name vs game name decision | Single decision: is the studio called Couch Heroes and the game also called Couch Heroes, or do they split. Per Granola Apr 2 discussion this is unsettled. Decision is foundational for every brand artefact downstream. | Not started | Critical ACT |  | Strategy | Vardis, Glen |  | None | Studio Business |  |  |  | Agent / Studio Business | Granola Apr 2 discussion identified this; cannot be deferred indefinitely ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Studio naming workshop facilitation | Facilitated naming workshop with founders. Brief, brainstorm, themes, shortlist, gut check, feedback round. Output a studio name shortlist. | Not started | High |  | Strategy | Vardis, Glen |  | Naming decision | Studio Business |  |  |  | Agent / Studio Business | Use brainstorming skill; structured naming reduces founder bias toward first ideas ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Game name reaffirmation or replacement | Decision on whether the game name remains Couch Heroes or changes. Vision doc consistently uses Couch Heroes; the burden of proof is on a change, not on continuity. | Not started | Critical ACT |  | Strategy | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Glen pointed out the unsettled question; founders to resolve ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Naming criteria and constraints document | Constraints for naming: pronounceability across languages, .com domain availability, social handle availability, trademark clearability, distinctiveness from competitors, founders' personal connection. | Not started | High |  | Implementation | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Without explicit criteria the workshop circles ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Trademark search: studio name shortlist | Trademark availability search across UK IPO, EUIPO, USPTO, WIPO Madrid. Each shortlist candidate scored on clearability. | Not started | High |  | Research | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Cheap to run; expensive to discover after launch ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Trademark search: game name | Same trademark search for the game name (whether Couch Heroes or alternative). | Not started | High |  | Research | Vardis, Glen |  | Game name decision | Studio Business |  |  |  | Agent / Studio Business | Often the game name is the more contested namespace; gaming companies file aggressively ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Domain availability check: studio name shortlist | .com availability, .co.uk, .gg, .games, .studio. Cost of acquiring squatted domains. | Not started | High |  | Research | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Cheap; do this before any external announcement of name ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Domain availability check: game name | Same domain check for game name. | Not started | High |  | Research | Vardis, Glen |  | Game name decision | Studio Business |  |  |  | Agent / Studio Business | Coordinated with studio domain check ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Social handle availability: studio | @StudioName on X, Instagram, TikTok, YouTube, Discord vanity, Reddit subreddit. Each platform with claim cost in time and effort. | Not started | High |  | Research | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Reserve before announcement; once leaked, squatters move fast ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Social handle availability: game | Same social handle check for game. | Not started | High |  | Research | Vardis, Glen |  | Game name decision | Studio Business |  |  |  | Agent / Studio Business | Coordinated with studio handle check ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Steam developer name reservation | Steamworks developer name once chosen. Visible on every store listing. | Not started | Medium |  | Implementation | Vardis, Glen |  | BD Steam onboarding | Studio Business |  |  |  | Agent / Studio Business | Coordinate with Steam onboarding ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Trademark filing: studio name | UK IPO and US filing for studio name. Decision on classes (gaming, software, merchandise, services). | Not started | High |  | Implementation | Vardis, Glen |  | Trademark search | Studio Business |  |  |  | Agent / Studio Business | Built with legal counsel; classes selection is more strategic than it looks ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Trademark filing: game name | Same trademark filing for game name. | Not started | High |  | Implementation | Vardis, Glen |  | Trademark search | Studio Business |  |  |  | Agent / Studio Business | Coordinated with studio trademark filing ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Defensive trademark and domain protection | List of close variants, common typos, malicious lookalikes. Decision on which to defensively register. | Not started | Low |  | Implementation | Vardis, Glen |  | Trademark filings | Studio Business |  |  |  | Agent / Studio Business | Operational hygiene; budget for it ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Brand identity brief: studio | Brief for studio brand identity work covering logo, wordmark, colour palette, typography system, voice anchors. | Not started | High |  | Implementation | Vardis, Glen |  | Naming decision, brand voice | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Director of Art (David); studio brand may differ from game brand ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Brand identity brief: game | Brief for game brand identity work, integrated with the byte punk art direction. | Not started | High |  | Implementation | Vardis, Glen |  | Naming decision, visual identity | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Director of Art (David) ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Logo design: studio | Studio logo design. Wordmark, mark only, lockup variants, colour, mono, reverse. | Not started | High |  | Implementation | Vardis, Glen |  | Brand identity brief studio | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Director of Art; external designer often used ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Logo design: game | Game logo design. Sits adjacent to studio logo, may share or diverge in language. | Not started | High |  | Implementation | Vardis, Glen |  | Brand identity brief game | Studio Business |  |  |  | Agent / Studio Business | Coordinated with Director of Art ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Logo usage guidelines | How the logos are used together and apart: lockup spacing, minimum size, clear space, partner co branding rules. | Not started | Medium |  | Implementation | Vardis, Glen |  | Logo designs | Studio Business |  |  |  | Agent / Studio Business | Required for partner studios using the logos ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Naming announcement plan | Communications plan for revealing the chosen names: order of channels, embargo strategy, founder posts, press release. | Not started | High |  | Strategy | Vardis, Glen |  | Naming decision | Studio Business |  |  |  | Agent / Studio Business | If the names change from current Couch Heroes use, this is a community moment requiring care ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Cultural and linguistic check on candidates | Check candidate names for unintended meanings in target language regions: French, German, Italian, Spanish, Brazilian Portuguese, Japanese, Korean, Mandarin Chinese. | Not started | Medium |  | Research | Vardis, Glen |  | Naming workshop | Studio Business |  |  |  | Agent / Studio Business | Cheap; humour aside, mistakes here become long term tax ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Sound and pronunciation check | Native speaker check on pronunciation across target regions. The thing native English speakers consistently get wrong. | Not started | Low |  | Research | Vardis, Glen |  | Cultural check | Studio Business |  |  |  | Agent / Studio Business | Audio recording for spokesperson reference; reduces internal inconsistency ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Backup name reserves | Hold a few backup names with cleared trademarks and domains in case of legal challenge or change of heart. Cost is small, optionality is meaningful. | Not started | Low |  | Implementation | Vardis, Glen |  | Trademark search | Studio Business |  |  |  | Agent / Studio Business | Cheap insurance ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Studio name vs game name positioning rules | Rules for how the two names appear in marketing: studio always preceded game on first mention vs not, copy phrasing across press releases, social, website. | Not started | Medium |  | Implementation | Vardis, Glen |  | Naming decision, brand voice | Studio Business |  |  |  | Agent / Studio Business | Avoids inconsistency that erodes brand recognition ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Update existing assets with new name(s) | Audit and update all existing studio assets with new name(s) where they differ from current Couch Heroes use: website, decks, social handles, email signatures, contracts. | Not started | High |  | Implementation | Vardis, Glen |  | Naming announcement | Studio Business |  |  |  | Agent / Studio Business | Coordinated rollout to avoid mixed signals during transition ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Email and identity infrastructure update | Email addresses, internal branding, business cards, sign in providers, internal documentation rebranded. | Not started | Medium |  | Implementation | Vardis, Glen |  | Naming announcement | Studio Business |  |  |  | Agent / Studio Business | Operational; sometimes underestimated and slips ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Companies House and corporate name reconciliation | If the legal entity name differs from the trading name, document the relationship clearly. Update Companies House records as needed. | Not started | Medium |  | Implementation | Vardis, Glen |  | Naming decision | Studio Business |  |  |  | Agent / Studio Business | Coordinated with legal; UK corporate rules must align with trading name ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Founder narrative for the name | Story behind the name to use in interviews and pitches. Founders rehearsed on it. | Not started | Low |  | Implementation | Vardis, Glen |  | Naming announcement, founder media training | Studio Business |  |  |  | Agent / Studio Business | The thing journalists ask first when a name is unusual ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Existing community migration plan (if game name changes) | Specific plan for migrating current Couch Heroes community references (Discord, Reddit, social) to a new game name if that path is taken. | Not started | Medium |  | Strategy | Vardis, Glen |  | Naming announcement | Studio Business |  |  |  | Agent / Studio Business | Branch only triggered if game name changes; otherwise no op ¦ Assignee defaulted from feature heuristic - confirm at offsite
Couch Heroes / Studio Business / Studio Naming | Studio name vs game name decision context capture | Document the rationale and tradeoffs of the final decision so future hires understand the context. | Not started | Low |  | Implementation | Vardis, Glen |  | Naming decision | Studio Business |  |  |  | Agent / Studio Business | Institutional memory; avoids relitigating the decision in two years ¦ Assignee defaulted from feature heuristic - confirm at offsite

## Closed-Killed
parent_path | title | description | status | priority | health_state | work_type | assignees | due_date | dependencies | practice_area | type | layer | confidence | source | notes
Couch Heroes / Closed/Killed / Gamescom (Cancelled) | Scope features with the leads | After the walkthrough is set, define the achievable scope for each feature we need to deliver and estimate it | Cancelled | Medium |  |  | Valeria |  |  | Game Studio Operations |  |  |  | CSV row 40 | Killed (Gamescom)
Couch Heroes / Closed/Killed / Gamescom (Cancelled) | Prepare Investor/Partner Narrative | With Vardis Confirm that the walkthrough creates the right impression for partners and investors | Cancelled | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 41 | Killed (Gamescom)
Couch Heroes / Closed/Killed / Gamescom (Cancelled) | Audit Platform readiness | With <@U07K2JSAP9V> Review the current stage of the platform and the connection between the web app and the game and decide on changes/additions | Cancelled | Medium |  |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 42 | Killed (Gamescom)
Couch Heroes / Closed/Killed / Gamescom (Cancelled) | Define the game experience we want to achieve | • Define features and mechanics players use • Define the sequence that feels fun to play • Define how the partner content is blended into this sequence to feel natural | Cancelled | Medium |  |  | Robin |  |  | Game Studio Operations |  |  |  | CSV row 43 | Killed (Gamescom)
Couch Heroes / Closed/Killed / Gamescom (Cancelled) | Shape the player walkthrough | • Set the walkthrough time per person • Outline the narrative arc to follow and places to visit • Assess the features we want to showcase and stages for each of them | Cancelled | Medium |  |  | Valeria |  |  | Game Studio Operations |  |  |  | CSV row 44 | Killed (Gamescom)

## Game
parent_path | title | description | status | priority | health_state | work_type | assignees | due_date | dependencies | practice_area | type | layer | confidence | source | notes
Couch Heroes / Game / Game Vision & Design | Game Vision & Design |  | In progress | Medium | [5 empty] | Game Studio Operations |  |  |  | CSV row 45
Couch Heroes / Game / Game Features / Player Progression System | Player Progression System | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Level Up | [Player Progression] Level Up | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Level Up | [Player Progression] XP gain rules | DoD: XP from kills/quests/events; level curve; caps. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Level Up | [Player Progression] Level-up rewards | DoD: Unlock abilities; stats; notifications; skill points. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Level Up | [Player Progression] Character sheet UI | DoD: Stats breakdown; derived stats; explanations; tooltips. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Level Up | [Player Progression] Level-up configuration | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [CC & Management] Character Stats | [CC & Management] Character Stats | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Player Progression System / [CC & Management] Character Stats | [CC & Management] Character Stats Progression | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [CC & Management] Character Stats | Stats Affect Interactions |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System | Talent/Skill System | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System | [Talent] Skills Trees | DoD: Spend points; prerequisites; respec; loadouts. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System / [Talent] Skills Trees | [Talent] Skill system design | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System / [Talent] Skills Trees | [Talent] Skill system UI | Comments: In progress ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System / [Talent] Skills Trees | [Talent] Skill trees implementation | Comments: In progress ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Achievements/Trophies | [Player Progression] Achievements/Trophies | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Achievements/Trophies | [Player Progression] Achievement system | DoD: Define achievements; tracking; rewards; UI. ¦ Comments: Has basic design ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Achievements/Trophies | [Player Progression] Meta achievements | DoD: Complete sets; track progress; title/mount rewards. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Achievements/Trophies | [Player Progression] Collections | DoD: Mounts/pets/transmog collections; account binding; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Achievements/Trophies | [Player Progression] Achievements Rewards | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Factions | [Player Progression] Factions | Comments: In progress ¦ Owner: Game Design ¦ Integration: Game Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Factions | [Player Progression] Faction Content | Comments: In progress ¦ Owner: Game Design ¦ Integration: Game Design | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Factions / [Player Progression] Faction Content | [Player Progression] Faction NPCs | Comments: In progress ¦ Owner: Game Design ¦ Integration: Char Art | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Factions / [Player Progression] Faction Content | [Player Progression] Faction Quests | Comments: In progress ¦ Owner: Game Design ¦ Integration: Game Design | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] Factions | [Player Progression] Reputation/factions | DoD: Rep gains; ranks; vendor unlocks; hostility; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial | [Player Progression] In-game Tutorial | Comments: Needs Review ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial | [Player Progression] Tutorial & onboarding | DoD: Guided intro; tooltips; training area; skip option. ¦ Comments: Needs Review ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial / [Player Progression] Tutorial & onboarding | [Player Progression] FTUE Configuration | Comments: Needs Review ¦ Owner: Game Design ¦ Integration: Game Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial / [Player Progression] Tutorial & onboarding | [Player Progression] FTUE UI | Comments: Needs Review ¦ Owner: Game Design ¦ Integration: UX/UI | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial | [Player Progression] Help codex | DoD: In-game encyclopedia; searchable; links from UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Game Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Player Progression] In-game Tutorial | [Player Progression] Tooltips | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Fishing | [Professions] Fishing | Comments: In progress ¦ Owner: Game Design ¦ Integration: Game Design | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Gathering | [Professions] Gathering | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Gathering | [Gathering System] Harvest interactions | DoD: Mine/chop/skin; tool requirements; cast time; animations. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Gathering | [Gathering System] Rare proc drops | DoD: Chance for rare mats; luck modifiers; messaging. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Professions] Crafting System | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Recipe system | DoD: Define recipes; inputs/outputs; skill requirements; quality tiers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Item quality/rolls | DoD: Quality affects stats/value; deterministic or RNG; reroll item. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Crafting success/failure (if used) | DoD: Chance-based outcomes; protection; clear UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Crafting UI | DoD: Search/filter; queue; preview; shows missing mats; craft all. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Crafting stations | DoD: Location-based stations; permissions; buffs; tiered stations. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Profession progression | DoD: XP/levels; unlock recipes; specialization. ¦ Comments: In progress, very basic ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Specialization trees | DoD: Choose specialization; locked choices; benefits; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Player Progression System / [Professions] Crafting System | [Crafting System] Player-made item economy hooks | DoD: Bind rules for crafted gear; durability; sinks. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [Core Combat] Magic | [Core Combat] Magic | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [Core Combat] Magic | [Core Combat] Spellcasting System | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [Core Combat] Magic | [Core Combat] Magic Weapons | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management | Character Creation & Management | Comments: In progress ¦ Owner: Game Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management | [CC & Management] Character Management | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management / [CC & Management] Character Management | [CC & Management] Multiple characters per account | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management / [CC & Management] Character Management | [CC & Management] Character rename | DoD: Rename with policy; uniqueness; rename cooldown; logs. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management / [CC & Management] Character Management | [CC & Management] Character transfer (server/shard) | DoD: Paid/free transfer; preserve inventory/mail; cooldown; restrictions. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Appearance customization | [CC & Management] Appearance customization | DoD: Face/body/hair/skin; colors; preview; randomize; save presets. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Appearance customization | [CC & Management] Race/species selection | DoD: Selectable races/species with starting stats/visuals; validates. ¦ Comments: In progress We have races/species in work from the art side, not integrated into the CC yet ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Appearance customization | [CC & Management] Appearance presets/randomizer | Comments: Not started ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Garment System | [CC & Management] Garment System | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Garment System | [CC & Management] Garment Presets | Comments: Not started ¦ Owner: Char Art ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Garment System | [CC & Management] Garment Customization | Comments: Not started ¦ Owner: Char Art ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] CC & Garment UI | [CC & Management] CC & Garment UI | Owner: UX/UI Lead ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] CC & Garment UI | [CC & Management] CC & Garment Menus | Comments: We have something we'll probably completely rework ¦ Owner: UX/UI Lead ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] CC & Garment UI | [CC & Management] CC & Garment UI Access | Comments: We have something we'll probably completely rework ¦ Owner: UX/UI Lead ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems | World Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / World Systems / Corruption | Corruption | Comments: In progress ¦ Owner: Game Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption | [Corruption] Corruption Implementation | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | [Corruption] Corruption VFX | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | [Corruption] Different types support | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | Corrupted environment |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | [Corruption] Corruption SFX | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | [Corruption] Different levels of corruption | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation | [World & Zones] Black Hole R&D | Comments: On pause ¦ Owner: TechArt ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Corruption | [Corruption] Restoration | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Restoration | [Corruption] Restoration Abilities | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Restoration | [Corruption] Restoration Weapons/Tools | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Restoration | [Corruption] Restoration Quests | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System | Movement System | Comments: In Progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Basic character movements | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Basic character movements | Move/turn/strafe/jump/double jump/move midair | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Sprinting/stamina | DoD: Sprint toggle/hold; stamina drain/regen; UI feedback. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Sprinting/stamina | Speedup Archways Animations | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Swimming/breath | DoD: Water volumes; swim movement; breath meter; drowning. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Swimming/breath | Water detection | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Swimming/breath | Swimming water effects |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Swimming/breath | Drowning/damage in the water |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Traversal Mechanics | DoD: Climbable surfaces; vault; fall damage interactions. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Gliding | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Grappling Hooks | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Ziplines | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Launch pads | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Cannons |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics | Climbing | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Mounts/vehicles | DoD: Mount summon/dismiss; speed tiers; restrictions; cosmetics. ¦ Comments: In progress We have a prototype, needs review and proper design ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Mounts/vehicles | Various vehicles types | Comments: Mounts R&D ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Movement System | [Movement System] Teleport items/spells | DoD: Cast time; restrictions; fail handling. (hearthstone, but back to User Space) ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Navigation | Navigation | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] World map UI | DoD: Zoom/pan; filters; player marker; quest markers; fog-of-war. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Minimap / compass | DoD: Optional minimap/compass; markers; rotation modes. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Navigation | Height detection |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Fog-of-war reveal | DoD: Reveal on exploration; persists per character; reset rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Ports/boats/transport network | DoD: Schedules; boarding; travel scenes; reliability. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Fast travel / waypoints | DoD: Unlock points; cost/cooldowns; safe checks. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Collision & navmesh | DoD: Accurate collision; navmesh per zone; regeneration pipeline. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Navigation | [World & Zones] Fall damage | DoD: Thresholds; mitigations; death handling; UI feedback. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Instancing | Instancing | Owner: Level Design | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Instancing | [World & Zones] Instancing | Owner: Server Team ¦ Integration: Server Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Instancing | [World & Zones] Dungeon instances | DoD: Entry/exit; checkpoints; wipes; lockouts; scaling. ¦ Comments: Research ¦ Owner: Server Team ¦ Integration: Server Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Instancing | [World & Zones] Zone/region loading | DoD: Load zones seamlessly or via transitions; handles disconnects. ¦ Comments: Research ¦ Owner: Server Team ¦ Integration: Server Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Instancing | [World & Zones] Instance servers | DoD: Spin up instance servers; matchmaking integration; teardown. ¦ Comments: Not started ¦ Owner: Server Team ¦ Integration: Server Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Instancing | [World & Zones] Shard/realm architecture | DoD: Realms/shards; load balancing; transfers; queueing. ¦ Comments: Not started ¦ Owner: Server Team ¦ Integration: Server Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / World Systems / Day/night cycle | Day/night cycle | DoD: Time progression; lighting; NPC schedules; server time. ¦ Comments: In progress - techart exploration ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Dynamic weather | Dynamic weather | DoD: Weather states; transitions; gameplay hooks optional. ¦ Comments: In progress - techart exploration ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Dynamic weather | [World & Zones] Interactable objects | DoD: Use/pickup/inspect; permissions; cooldowns; sync. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Dynamic weather | Destructibles | Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Dynamic weather | [World & Zones] Resource nodes | DoD: Spawn tables; depletion; respawn; competition rules. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Game Design | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / World Systems / Dynamic weather | [World & Zones] Chests/lootables | DoD: Spawn rules; lock/key; personal vs shared; anti-farm. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Level Design | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic | Combat Epic |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework | [Core Combat] Combat Framework | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework | [Core Combat] Combat state machine | DoD: In/out of combat; regen rules; mount restrictions; logout timer. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework | [Core Combat] Combat encounter reset conditions | DoD: Reset on leash/timeouts; clears debuffs; prevents cheese. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework | [Core Combat] Death & respawn | DoD: Death screen; corpse; respawn points; penalties. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework / [Core Combat] Death & respawn | [Core Combat] Downed state | DoD: Optional downed/bleedout; ally revive; PvP rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework / [Core Combat] Death & respawn | [Core Combat] Revive / resurrection | DoD: Self/ally revive; consumables; restrictions; timers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework / [Core Combat] Death & respawn | [Core Combat] Combat resurrection limits | DoD: Limit battle res per encounter; tracking; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems | [Core Combat] Combat Effect Systems | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems | [Core Combat] Buff/debuff framework | DoD: Timed effects; stacking rules; dispels; persistence rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems | [Core Combat] Rested/bonus XP | DoD: Accumulation rules; display; consumption. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems | [Core Combat] Player Status Effects | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems / [Core Combat] Player Status Effects | Water/fire, water/electricity etc | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Targeting & Validation | [Core Combat] Combat Targeting & Validation | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Targeting & Validation | [Core Combat] Friendly targeting rules | DoD: Heal/assist selection; smart targeting; party priority. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Targeting & Validation | [Core Combat] Targeting system | DoD: Tab target/soft target/action target; line-of-sight; range. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Combat Hit & Damage Processing | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Hit resolution | DoD: Server-authoritative hit checks; latency compensation; anti-cheat. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Damage/healing pipeline | DoD: Mitigation; crit; resist; shields; overheal; logs. ¦ Comments: In progress as a part of combat system ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Diminishing returns framework | DoD: DR categories; reset timers; UI tooltip for immunity. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Cooldown reduction stacking rules | DoD: CDR caps; multiplicative/additive; UI shows effective CD. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Interactions | [Core Combat] Combat Interactions | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Interactions | [Core Combat] Combo/proc system | DoD: Conditional triggers; internal cooldowns; UI proc notification. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Interactions | [Core Combat] Dual Wielding | Comments: In progress ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat | [Core Combat] Ranged Combat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat | Ranged - Firearms |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat | Ranged - Two-handed weapons |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat | Ranged - Ammo |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] AI Combat Behavior | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] Threat/aggro system | DoD: NPC threat tables; taunts; drop rules; leashing. ¦ Comments: In progress as a part of combat system ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] NPC combat AI | DoD: Decision trees/BT; ability use; pathing; kiting protection. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] Elite/boss AI mechanics | DoD: Telegraphs; phases; enrage; target swaps. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] Mob spawning & population | DoD: Spawn points; density; scaling; despawn; roaming. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] Named/rare spawns | DoD: Timers; announcements; loot rules; anti-camp. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior | [Core Combat] Line-of-sight & cover checks | DoD: LOS uses server raycasts; prevents shooting through walls. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] PvP Combat System | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] Battleground arenas | DoD: Matchmaking; teams; scoring; maps; rewards. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] World PvP objectives | DoD: Capture points; resource control; buffs; timers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] MMR / ranking ladder | DoD: Rating calculation; seasons; decay; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] Anti-wintrading detection | DoD: Detect collusion; suspicious patterns; enforcement. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] Spectator mode | DoD: View matches; delay; privacy; anti-stream-snipe. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] PvP gear normalization | DoD: Stat templates; scaling; separate PvP stats. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] Queue types (solo/duo/premade) | DoD: Different queues; matchmaking constraints; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System | [Core Combat] PvP toxicity controls | DoD: Match chat restrictions; report in match; auto penalties. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry | [Core Combat] Combat UX & Telemetry | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry | [Core Combat] Floating combat text | DoD: Damage/heal numbers; filters; crit styling; toggle. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry | [Core Combat] Combat log | DoD: Detailed log; filtering; export; support for addons if allowed. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry | Post-match checks on cheats |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core | [Combat Abilities] Ability Core | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core | [Combat Abilities] Ability data definitions | DoD: Cooldown/cast time/cost/range; tags; scaling; ranks. ¦ Comments: In progress as a part of combat system ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core | [Combat Abilities] Global cooldown rules | DoD: Optional GCD; exceptions; UI indicators. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core | [Combat Abilities] Resource systems (mana/energy/rage) | DoD: Resources regenerate/spend; regen modifiers; UI bars. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core | [Combat Abilities] Ability queueing / buffering | DoD: Queue next ability within window; cancel rules; latency friendly. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics | [Combat Abilities] Casting Mechanics | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics | [Combat Abilities] Channeling abilities | DoD: Interrupt rules; movement rules; tick timing. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics | [Combat Abilities] Interrupts & crowd control | DoD: Stun/root/silence/fear; DR rules; break on damage. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics | [Combat Abilities] Cast bar & interrupt feedback | DoD: Cast bar shows progress; interrupt message; sound cue. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Area & Effect Handling | [Combat Abilities] Area & Effect Handling | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Area & Effect Handling | [Combat Abilities] Area-of-effect | DoD: Circles/cones/lines; ground-targeting; friendly fire rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Area & Effect Handling | [Combat Abilities] Status effects visuals | DoD: Buff/debuff icons; durations; stack count; tooltip. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Combat Epic / Combat UI & HUD | Combat UI & HUD |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space | User Space | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / User Space / [User Space] Server Support | [User Space] Server Support | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Server Support | [User Space] Player housing instance | DoD: Purchase/unlock; enter/exit; persistence; permissions. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Server Support | [User Space] Visitor permissions | DoD: Invite friends/guild/public listing; ban list. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Server Support | [User Space] Mobile front doors | DoD: Place your front door (portal) anywhere. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Decoration | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration / Buildings/parts of buildings placement/design | rooms, windows, etc |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Decoration placement | DoD: Place/move/rotate/scale; grid/snapping; collision; limits. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Crafting stations in housing | DoD: Place stations; buffs; restrictions; economy impacts. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Housing storage | DoD: Extra storage; access rules; anti-dupe. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Blueprints/presets | DoD: Save room layouts; share; import/export. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] World/activities distribution | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / User Space / [User Space] Decoration | [User Space] Lootable themed decorations per zone | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Minigames | Minigames | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / Minigames / [Minigames] Single-player minigames | [Minigames] Single-player minigames | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Minigames / [Minigames] Multiplayer minigames | [Minigames] Multiplayer minigames | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic | Items & Inventory System Epic |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System | Item Core System | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System | [Item System] |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] | [Item System] Initial Item Lists by type |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System | [Item System] Item Data & Rules | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules | [Item System] Item definition schema | DoD: Stats; rarity; binding; stacks; durability; unique limits. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules | [Item System] Item level / power scoring | DoD: Compute ilvl; gates content; display in UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules | [Item System] Item binding rules | DoD: Bind on pickup/equip/use; trade restrictions; UI labels. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules | [Item System] Durability & repair | DoD: Durability loss; repair cost; repair NPC; break rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System | [Item System] Item Lifecycle & Protection | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Lifecycle & Protection | [Item System] Destroy item confirmation | DoD: Prompt for rare/bound; type-to-confirm option. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Lifecycle & Protection | [Item System] Item locking / favorites | DoD: Lock items to prevent delete/sell; favorite marking. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Lifecycle & Protection | [Item System] Loot protection | DoD: Duplicate protection for certain rewards; soulbound rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Lifecycle & Protection | [Item System] Loot lock & corpse ownership | DoD: Prevent looting by others; timeouts; group access. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System | [Item System] Cosmetic & Appearance as Items | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Cosmetic & Appearance as Items | [Item System] Cosmetic transmog/glamour | DoD: Apply appearances independent of stats; unlock collection. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Cosmetic & Appearance as Items | [Item System] Dye system | DoD: Recolor gear/skins; channels; preview; saved palettes. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Cosmetic & Appearance as Items | [Item System] Appearance collection tracking | DoD: Unlock appearances on obtain; UI collection; duplicates handling. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Cosmetic & Appearance as Items | [CC & Management] Titles & vanity | DoD: Earned/equipped titles; vanity slots; preview. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic | [CC & Management] Emotes & gestures | DoD: Emote list; unlocks; chat integration; animations. ¦ Comments: We have something we need to review ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic | [World & Zones] In-game maps | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | Inventory System | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Player-Carried Storage | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Bag/backpack system | DoD: Slot-based; stacking; sorting; auto-loot; overflow handling. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Auto-sort rules | DoD: Sort by type/rarity/ilvl; custom categories. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Split stacks & stack merging | DoD: Split stack UI; partial moves; merge behavior. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Junk tagging & vendor sell-all | DoD: Mark junk; sell all junk; confirm; blacklist. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Long-Term Storage | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Bank/storage system | DoD: Extra storage; tabs; search; sorting; permissions. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Account-wide stash | DoD: Shared across characters; restrictions; currency. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Mail attachments as overflow | DoD: Send items/currency via mail; anti-abuse; return on expiry. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Search in bank/stash | DoD: Search by name/tag; filters; highlight. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Item models |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Item icons |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Buy/Sell (Vendor transfer) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Loot transfer/item drops |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Item editor and tools |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System | [Inventory] Inventory UI | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | Equipment System | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Equipment UI | Comments: In progress ¦ Owner: UX/UI Lead ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Equipment slots | DoD: Equip/unequip; validation; visual swaps; two-hand rules. ¦ Comments: In progress ¦ Owner: UX/UI Lead ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Item comparison tooltips | DoD: Compare to equipped; stat deltas; advanced tooltip toggle. ¦ Comments: Not started ¦ Owner: UX/UI Lead ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Enchanting/augment slots | DoD: Attach augments; remove rules; caps; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Upgrade system | DoD: Upgrade ilvl with materials/currency; caps; UI preview. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Item reforging/rerolling | DoD: Change secondary stats; costs; RNG; limits. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Equipment] Set bonuses | DoD: Track sets; activate bonuses; UI indicators. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Gathering System] Gathering Equipment | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | Equipment] Armour and Kit list |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System | [Gathering System] Tool durability/quality | DoD: Tools affect yield; durability; repairs; sinks. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets | Pets | Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets | [Combat] Combat companions |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets | [CC & Management] Pet/companion system | DoD: Summon pets; cosmetic/combat; commands; persistence. ¦ Comments: In progress, needs review ¦ Owner: Game Design ¦ Integration: Gameplay Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets | [CC & Management] Pets Customization | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets / [CC & Management] Pets Customization | [CC & Management] Pets Naming | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets / [CC & Management] Pets Customization | [CC & Management] Pets Clothes/Accessories | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Forge System | Forge System | Comments: In research ¦ Owner: Game Design, Char Art ¦ Integration: Char & Techart | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Forge System | [Equipment] Forge Crafting system |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Forge System | [Equipment] Forge Item list |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Forge System | [Equipment] Forge models and icons |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | Loot Distribution Systems | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | [Loot Distribution] Loot Drop Generation | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | [Loot Distribution] Loot tables & drops | DoD: Per-NPC loot tables; weighted rolls; guarantees; pity timers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | [Loot Distribution] Personal vs shared loot | DoD: Loot mode selection; group rules; loot lockouts. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | [Loot Distribution] Group Loot Distribution | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Items & Inventory System Epic / Loot Distribution Systems | [Loot Distribution] Need/greed roll | DoD: Group roll UI; timeouts; master looter optional. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy | In-game economy | Comments: In progress, very basic ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / In-game economy / Currency System | Currency System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Currency System | Sources and drains |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Currency System | Crafting Economy |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Currency System | Profession economies / boosts |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Currency System | Reward Economy / Loot Value |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Currency System | [Trading] Multiple currencies | DoD: Gold + premium + tokens; wallet UI; caps; sinks. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Currency System | [Trading] Currency flows | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Currency System | [Trading] Currency transactions ledger | DoD: Server-side ledger; audit trails; rollback support. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | Trading system | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Direct player trade | DoD: Trade window; confirm; prevents scams; distance; locks. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Trading system | COD (cash on delivery) | DoD: Optional COD; safe transaction; escrow; cancel rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Trade restrictions | DoD: Level/region limits; bind rules; rate limits; anti-RMT flags. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Search filters (ilvl, stats) | DoD: Advanced filters; saved searches; controller friendly. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Tax & fee tuning | DoD: Configurable fees; sinks; tooltips show net proceeds. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Buyback tab | DoD: Buyback recently sold items; timer; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] In-game store UI | DoD: Browse items; featured; categories; preview; wishlist. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] NPC vendors | DoD: Buy/sell; limited stock; reputation discounts; restock timers. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Repair & services vendors | DoD: Repair, respec, travel fees; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Token/vendor catch-up gear | DoD: Earn tokens; purchase gear; caps; season rollover rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Suspicious trade detection | DoD: Heuristics for laundering; alerts; thresholds; review queue. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Trading system | [Trading] Listing limits & anti-snipe | DoD: Limit listings; anti-bot; purchase confirmation for high value. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Auction house / market board | Auction house / market board | DoD: List/buy/sell; taxes; duration; search/sort; history. ¦ Comments: Paused ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / In-game economy / Auction house / market board | [Trading Market] Auction building |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Feature | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / In-game economy / Auction house / market board | [Trading] Market price history | DoD: Display last N sales; volume; API rate limits. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Auction house / market board | [Trading] Market tools (retrieval, reversal) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / In-game economy / Auction house / market board | [Trading] Offline sales delivery | DoD: Sales settle offline; proceeds via mail; cancel listing. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System | Quest System | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quests Backend/Tooling | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest definitions & scripting | DoD: Define quests with steps/conditions/rewards; scripting hooks. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest acceptance/turn-in | DoD: NPC/auto acceptance; checks prereqs; reward selection. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest log | DoD: List/track/abandon; sorting; categories; limits. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Objective tracking | DoD: Kill/collect/explore/talk/use; partial credit; reset rules. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Location-based objectives | DoD: Trigger volumes; map pin; completion criteria. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Branching choices | DoD: Mutually exclusive branches; flags; consequences; replay rules. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Dialogue system | DoD: Branching dialogue; localization; VO triggers; skip/cinematics. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Cinematics / cutscenes | DoD: In-engine/Video; skip vote in groups; replay. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest markers & breadcrumbs | DoD: HUD markers; world indicators; distance; toggle. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest exploit prevention | DoD: Detect repeat abuse; reset logic; server-side validation. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quest item delivery | DoD: Auto-grant quest items; reclaim if deleted; prevent softlocks. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | Quest Editor |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Reward framework | DoD: XP/currency/items/rep; choice rewards; mail overflow. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests as Events | [Quest System] Quests as Events | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests as Events | [Quest System] Repeatable quests | DoD: Daily/weekly timers; reset schedule; caps. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests as Events | [Quest System] Bounties/contract board | DoD: Procedural quest offering; expiration; difficulty tiers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quests as Events | [Quest System] World events as quests | DoD: Dynamic objectives with time limit; public participation; scaling. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Multiplayer | [Quest System] Quest Multiplayer | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Multiplayer | [Quest System] Shared/group quest progress | DoD: Rules for party contribution; credit radius; loot sharing. ¦ Comments: In progress, needs review with code and design ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Multiplayer | [Quest System] Quest sharing | DoD: Share quest to party; eligibility checks; cooldown. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | [Quest System] Quest Types | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | [Quest System] Escort AI missions | DoD: Escort NPC path; fail conditions; scaling. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | [Quest System] Timed objectives | DoD: Countdown timers; failure state; UI urgency cues. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Gather Resources |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Collect Unique Item |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Interact with Objects |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Kill Enemies |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Kill & Collect |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Investigate / Track |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Explore Area |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Cleanse Area of corruption |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Challenge / Minigame |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Puzzle |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types | Riddle / Dialogue |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Narrative | [Quest System] Quest Narrative | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Narrative | [Quest System] Lore codex unlocks | DoD: Unlock lore entries from exploration/quests; UI browse/search. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Engineering | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Narrative | Quest Localization |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Player Chat | Comments: In progress ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] General chat channels | DoD: Global/zone/local/party/guild/whisper; moderation hooks. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Backend Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Chat UI & history | DoD: Scrollable chat; tabs; filters; timestamps; copy/paste. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Backend Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Profanity filter | DoD: Locale-aware filter; user toggle; strict mode for minors. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Spam throttling | DoD: Rate limits; mutes; anti-flood; link limits. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Emojis/stickers | DoD: Emoji support; custom stickers; entitlement gating. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Backend Eng | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Block/mute players | DoD: Block whispers/invites; mute chat; persistence. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Voice chat integration | DoD: In-game voice or platform; push-to-talk; mute; reporting. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Player reporting | DoD: Report chat/name/behavior; attach evidence; routing. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Slash commands framework | DoD: Commands (/w,/invite,/ignore,/roll); autocompletion; help. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Chat link items/achievements | DoD: Clickable links to items/quests; safe rendering; spoof prevention. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | [Social Systems] Chat Moderation | Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat / [Social Systems] Chat Moderation | [Social Systems] Chat moderation automation | DoD: Keyword triggers; auto-mute thresholds; escalation. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat / [Social Systems] Chat Moderation | [Social Systems] Language tags / auto-translate (optional) | DoD: Detect language; tag; optional translate; privacy notice. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat / [Social Systems] Chat Moderation | [Social Systems] Chat moderation tools | DoD: Mute, shadowmute, channel bans; audit trail. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat / [Social Systems] Chat Moderation | [Social Systems] Chat logs retrieval tooling | DoD: Secure access for moderators; retention rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat | Tagging/credit rules | DoD: First hit vs contribution; shared credit; anti-ninja. ¦ Comments: ? ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Friends | [Social Systems] Friends | Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Friends | [Social Systems] Friends list | DoD: Add/remove; requests; blocks; notes; presence. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Friends | [Social Systems] Presence/status | DoD: Online/away/busy; current zone/activity; privacy settings. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Friends | [Social Systems] Friend notes/nicknames | DoD: Local nicknames/notes; private; sync optional. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Friends | [Social Systems] Friend suggestions | DoD: Suggest from mutual guild/party; privacy-respecting. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Multiplayer - Co-op | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Party formation | DoD: Invite/accept; role slots; leader; kick; loot rules. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Matchmaking / LFG | DoD: Queue for dungeons/raids; role selection; MMR optional. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Cross-server grouping | DoD: Invite across servers; instancing; chat routing. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Co-op Ready check | DoD: Ready prompt; timeout; kick logic for queues. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Dungeon finder deserter penalty | DoD: Leaving early adds debuff/timeout; exemptions for kicks. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Role enforcement & composition rules | DoD: Tank/healer/DPS validation; flexible rules; warnings. We may not require this. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Instance vote kick | DoD: Vote kick with reasons; cooldowns; abuse prevention. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Player inspect | DoD: Inspect gear/build; privacy toggle; compare. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Player profile card | DoD: Name, titles, achievements, guild; report/block buttons. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Co-op | [Social Systems] Matchmaking service | DoD: Queue management; skill/role matching; timeouts; penalties. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Multiplayer - Raids | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Raid group sizes | DoD: Flexible/fixed sizes; role requirements; scaling. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Raid lockouts & saves | DoD: Weekly lockouts; save states; partial clears; resets. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Dungeon/raid loot distribution | DoD: Personal loot; token systems; currencies; pity timers. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Mythic+/keystone system (if used) | DoD: Scaling difficulty; affixes; timed runs; leaderboards. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Multiplayer - Raids | [Social Systems] Raid finder difficulty (if used) | DoD: Automated raid matching; simplified mechanics; lockouts. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Core Combat] Dueling | [Core Combat] Dueling | DoD: Invite/accept; safe boundaries; rewards none; anti-grief. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Quest System / Guild System | Guild System | Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Identity & Structure | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Identity & Structure | [Guilds] Guild creation | DoD: Name/tag validation; cost; leadership assignment. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Identity & Structure | [Guilds] Guild ranks & permissions | DoD: Configurable roles; bank permissions; invite/kick; logs. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Identity & Structure | [Guilds] Guild emblem/branding | DoD: Create emblem/colors; displays on banners/tabards. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Communication | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Communication | [Guilds] Guild chat & MOTD | DoD: Dedicated chat; announcements; pinned messages. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Membership Visibility | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Membership Visibility | [Guilds] Guild roster & profiles | DoD: Member list; last online; notes; applications. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Membership Visibility | [Guilds] Guild recruitment board | DoD: Post recruitment; applications; auto-accept rules. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Administrative Tools | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Administrative Tools | [Guilds] Guild moderation tools | DoD: Remove offenders; audit logs; reporting; name policy. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Administrative Tools | [Guilds] Guild activity logs | DoD: Logs for invites/kicks/bank transactions; export. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Administrative Tools | [Guilds] Guild ranks & permissions controls | DoD: Configurable roles; bank permissions; invite/kick; logs. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Meta Systems | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Meta Systems | [Guilds] Guild progression/perks | DoD: Guild XP; unlock bonuses; caps; UI. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Meta Systems | [Guilds] Guild perks management UI | DoD: Select perks; show costs; cooldowns; permissions. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Shared Resources | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Shared Resources | [Guilds] Guild bank | DoD: Shared storage; tabs; permissions; logs; withdrawal limits. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Events | Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Events | [Guilds] Guild calendar/events | DoD: Schedule raids; RSVPs; reminders; timezones. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Events | [Guilds] Guild competitions | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System | [Guilds] Guild Physical Presence | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / Guild System / [Guilds] Guild Physical Presence | [Guilds] Guild housing/instances | DoD: Access rules; Bans/kicks; Customisation ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] In-game Mail | Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] In-game mail send/receive | DoD: Send mail to players; delivery delay; inbox UI; unread indicators. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] Mail attachments | DoD: Attach items/currency; limits; return on expiry; anti-dupe checks. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] Mail enhancements |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] mail box models |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] In-game Mail | [Social Systems] Mail expiry & cleanup | DoD: Messages expire; warnings; auto-return attachments; logs. ¦ Comments: In progress ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Notifications | [Social Systems] Notifications | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Notifications | Social notifications |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Quest System / [Social Systems] Notifications | [Social Systems] Red dot system | DoD: Friend online, invite, guild events; settings. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay/Backend | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces | Game Interfaces | Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] HUD & In-Game Interface | Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Health/resource bars | DoD: Player/target frames; buffs/debuffs; cast bars. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Action bars & hotkeys | DoD: Multiple bars; paging; keybind display; cooldown swipe. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Damage direction indicators | DoD: Indicators for incoming hits; toggle; accessibility. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Buff/debuff management UI | DoD: Separate sections; whitelist; enlarge important debuffs. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Quest tracker widget | DoD: Track active objectives; collapse; click-to-navigate. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] Group UI frames | DoD: Party/raid frames; role icons; ready checks; sorting. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] UI Framework & UX Standards | Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Notifications/toasts | DoD: Loot, XP, achievements; rate limiting; accessibility. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Settings menu | DoD: Graphics/audio/controls/gameplay; apply/revert; presets. ¦ Comments: Needs review/overhaul ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] UI scaling | DoD: Scale UI; safe areas; font size; per-platform. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Search within menus | DoD: Search options/collections; highlight results. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Rich tooltips | DoD: Compare, show sources, show requirements; controller friendly. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Localization-ready UI | DoD: No hard-coded text; supports RTL; font fallback; truncation. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] UI mod/addon support (if allowed) | DoD: API sandbox; permissions; versioning; anti-cheat constraints. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Notification center | DoD: History of messages/rewards; clears; filters. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Keybind UI & conflict resolver | DoD: Shows conflicts; reset to default; import/export binds. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] Error handling & messaging | DoD: Human-readable errors; retry prompts; offline handling. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls | Controls | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls | [Controls] General game settings | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Rebindable controls | DoD: Full keybinds; per-device profiles; conflict resolution. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Gamepad support | DoD: UI navigation; aim assist options; prompts; vibration. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Controller glyph switching | DoD: Auto-detect input; display correct glyph set. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Toggle/hold options | DoD: Hold-to-sprint, hold-to-aim, etc. configurable. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] 3rd/1st person camera | DoD: Orbit/zoom; collision; FOV; shoulder swap; sensitivity. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Core | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Loadout switching | DoD: Save/restore gear+skills+UI; restrictions in combat. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings | [Controls] Loadout presets | Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations | UX Optimizations | Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations | [UX] Modern UI/UX Expectations | Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Search everywhere | DoD: Search inventory, bank, auction, codex, settings. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Ping/marker system | DoD: World pings; group visible markers; expiration. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Photo mode | DoD: Free cam; filters; hide UI; poses. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Reconnect & session resume | DoD: Reconnect to same instance; preserve party; grace timers. ¦ Comments: In progress ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] AFK detection | DoD: AFK timers; kick from queues; status display. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Combat readability options | DoD: Reduce clutter; highlight enemy casts; outline allies. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Tooltip explanation mode | DoD: Explain stats/formulas; beginner mode; toggles. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Account-wide unlocks | DoD: Mounts/pets/cosmetics shared; rule exceptions. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Returner experience | DoD: Welcome back rewards; recap; suggestions. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations | [UX] Community safety onboarding | DoD: First-time prompts; reporting tutorial; safe comms. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility | Accessibility | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility | [Accessibility] Visual Accessibility | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Visual Accessibility | [Accessibility] Colorblind modes | DoD: Filter presets; test patterns; applies to UI and telegraphs. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Visual Accessibility | [Accessibility] Reduce motion | DoD: Disable camera shake/motion blur; simplified VFX option. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Visual Accessibility | [Accessibility] High-contrast UI mode | DoD: Contrast theme; outlines; readability. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Visual Accessibility | [Accessibility] Screen reader hints | DoD: UI labels for screen readers where supported; navigation cues. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility | [Accessibility] Audio & Communication Accessibility | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Audio & Communication Accessibility | [Accessibility] Subtitles & captions | DoD: Subtitles for dialogue; speaker labels; size options. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Audio & Communication Accessibility | [Accessibility] Audio cues alternatives | DoD: Visual indicators for important sounds; UI pings. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Audio & Communication Accessibility | [Accessibility] Speech-to-text (STT) for voice | DoD: Optional captions for voice; privacy notices. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Audio & Communication Accessibility | [Accessibility] Text-to-speech (TTS) for chat | DoD: Optional TTS; profanity safe; volume/rate controls. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility | [Accessibility] Input & Control Accessibility | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Input & Control Accessibility | [Accessibility] Remappable UI navigation | DoD: Full remap; controller/KB; one-handed presets optional. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Input & Control Accessibility | [Accessibility] Toggle rapid actions | DoD: Auto-repeat for held inputs; accessibility options. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Input & Control Accessibility | [Accessibility] Input smoothing options | DoD: Adjust dead zones, sensitivity curves; presets. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility | [Accessibility] Learning & Guidance Accessibility | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Accessibility / [Accessibility] Learning & Guidance Accessibility | [Accessibility] Tutorial replay & hints | DoD: Replay tutorial; contextual hints; can disable. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Polish | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion | Presentation & Immersion | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion | [Presentation] Visual Presentation | Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Visual Presentation | [Presentation] Telegraph / readability VFX | DoD: Clear telegraphs; scalable; performance tiers. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Visual Presentation | [Presentation] Ability animation system | DoD: Sync animation to ability timings; cancel windows; blend. ¦ Comments: In progress ¦ Owner: UX/UI Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Visual Presentation | [Presentation] Emote animation library | DoD: Emote playback; loop; cancel; network sync. ¦ Comments: Not started ¦ Owner: UX/UI Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion | [Presentation] Audio Presentation | Owner: Audio Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] 3D positional audio | DoD: Spatial audio; occlusion; distance falloff; mix. (PS5 support in future) ¦ Comments: Not started ¦ Owner: Audio Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] Adaptive music | DoD: Dynamic music by zone/combat; transitions. ¦ Comments: Not started ¦ Owner: Audio Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] UI SFX | Comments: In progress ¦ Owner: Audio Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] Other SFX | Comments: In progress ¦ Owner: Audio Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] Ambience Music | Comments: In progress ¦ Owner: Audio Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] User Space music | Comments: Not started ¦ Owner: Audio Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] Audio Presentation | [Presentation] Zone Music | Comments: In progress ¦ Owner: Audio Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion | [Presentation] VFX | Comments: In progress ¦ Owner: VFX Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion / [Presentation] VFX | Multiple VFX examples | Comments: In progress ¦ Owner: VFX Lead | In progress | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Game Features | Medium confidence: asset-style title in Game Feature List (verify it is not a gameplay feature)
Couch Heroes / Game / Game Features / Platform | Platform | Comments: To be reviewed ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | medium | Features V2 / Game Features | Medium confidence: epic-level row inferred as System; no explicit System keyword
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Account Creation/Deletion | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Account creation / registration | DoD: User can create account; validates email/username/password; handles errors; stores profile. ¦ Comments: Done or partially done. I don't think we're storing profiles atm ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Display name policy & rename | DoD: Unique rules; profanity filter; rename tokens; history. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Ban/suspension state handling | DoD: Account state blocks login appropriately; shows reason codes. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Character delete | DoD: Delete with confirmation; cooldown; prevents deleting last char if needed. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Creation/Deletion | [Platform] Name validation | DoD: Uniqueness rules; reserved words; profanity; unicode handling. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Account Authentification | DoD: Verification email sent; account gated until verified; resend + rate limits. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Email verification | Comments: Done or partially done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Login / authentication | DoD: Secure login; session tokens; remember-me; logout all devices. ¦ Comments: Partially done. We have basic login system ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Password reset | DoD: Self-serve reset via email/SMS; token expiry; audit event. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Multi-factor authentication (MFA) | DoD: Optional/required MFA; recovery codes; device trust. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Sign-in Methods | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with email | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with Google | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with Discord | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Account recovery workflow | DoD: Support-assisted recovery; ownership proof; lockout handling. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | [Platform] Account linking (Steam/PSN/Xbox/Epic/CH) | DoD: Link/unlink external identities; conflict resolution. ¦ Comments: Paused - decided not to link Steam. Needs additional discussion ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | License/ownership check | DoD: Validate game license and DLC/expansions entitlements. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification | Cross-progression entitlements | DoD: Entitlements reconcile across platforms; prevents dupes. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Account Privacy Settings & Legal | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Consent management | DoD: Track and store consent for ToS/Privacy/marketing; versioned. ¦ Comments: Not started though we have a confirmed version of ToU ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Data export (GDPR/CCPA) | DoD: User can request export; generates bundle; authenticated delivery. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Account deletion / erasure | DoD: User can request deletion; cool-off; deletes/anonymizes per policy. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Age gating / parental controls | DoD: Age check; chat restrictions; spending limits; COPPA flows. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal / [Platform] Age gating / parental controls | Age gating restriction flow for the game | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal / [Platform] Age gating / parental controls | Age gating process for 3rd party game partners | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Platform] [Player Dashboard] Player Account Features | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Account Info Display | Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Nickname | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Default profile picture | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Account avatar upload | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Account level | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Log out | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Player Achievements | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] CH currency wallet | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Account Settings | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Support & FAQ | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Platform] [Player Dashboard] Game Dashboard | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Partner Games Display | Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | All games | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Unlocked games | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Quests required to unlock | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Steam key redemption | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Partner Assets (items) display | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Assets (items) display | Inventory section | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Available Quests Tracking | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Launcher Download | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Community Hub | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Featured Games section | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Friends | [Platform] [Player Dashboard] Friends | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Friends | [Player Dashboard] Friend List Management | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Friends | [Player Dashboard] Chat | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Platform] [Player Dashboard] Search & Notifications | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Player Dashboard] Search | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Player Dashboard] Web notifications/red dots | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Marketplace | [Platform] [Player Dashboard] Marketplace | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Marketplace | [Player Dashboard] P2P Marketplace | Comments: Not started, needs discussion ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Platform] [Developer Dashboard] Developer Account | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Account creation/sign in | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Company Info Form | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Manage account | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Platform] [Developer Dashboard] Game Dashboard | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Games management | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Keys management | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Analytics | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Settings & Support | [Platform] [Developer Dashboard] Settings & Support | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Settings & Support | [Developer Dashboard] contact support & FAQ | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Feature | low | Features V2 / Game Features | NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
Couch Heroes / Game / Game Features / Platform / [Platform] Quest Tracking | [Platform] Quest Tracking | DoD: Designers create quests; Translation/Localisation links; Dialogue/Narrative links. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Quest Tracking | [Platform] Quest Input System | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Quest Tracking | [Platform] Partner Quest Integration | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Platform Certification | [Platform] Platform Certification | DoD: PS/Xbox/Nintendo TRCs; submission checklists. Steam also needs this if we decide to go there ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Platform Certification | [Platform] Platform certification requirements | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Payment Processing | [Platform] Payment Processing | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Payment Processing | [Platform] Payment System Integration | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Online Services & Backend | DoD: Transactional emails; throttling; deliverability. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Session concurrency limits | DoD: Limit simultaneous logins; kick/notify; anti-abuse. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Email/SMS service integration | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Patch/manifest CDN | DoD: Serve patches; delta patching; region caches; integrity. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Account-wide settings service | DoD: Store settings server-side; sync; conflict resolution. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Notification/push service | DoD: Send push for events (optional); opt-in; region compliance. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Online Services & Backend | [Platform] Regional routing / shard selection | DoD: User chooses region/shard; can transfer with rules. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Launcher & Distribution | DoD: Self-update; verify files; repair; disk space checks. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Patch/update system | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Launcher integration | DoD: News, login, patch; SSO; crash log upload. ¦ Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Crossplay toggle | DoD: User setting; matchmaking rules; compliance. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Cross-save | DoD: Upload/download save; conflict resolution; offline behavior. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Screenshot/video capture hooks | DoD: Share on platform; privacy; parental settings. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Offline mode behavior | DoD: If offline allowed: restrict features; queue actions; messaging. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Hardware detection & defaults | DoD: Detect hardware; set recommended settings; benchmark optional. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Input method auto-switching | DoD: Instant switch between KB/mouse and controller; UI updates. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Multiple language packs | DoD: Download language packs; switch without reinstall; UI. ¦ Comments: We have something on localization, needs check ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Launcher & Distribution | [Platform] Cross-session settings sync | DoD: Settings stored server-side; per-platform overrides. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Desktop App (?) | [Platform] Desktop App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Features / Platform / [Platform] Mobile App (?) | [Platform] Mobile App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Feature | Foundation | high | Features V2 / Game Features
Couch Heroes / Game / Game Systems / Player Progression | Player Progression |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Player Progression] Level Up | [Player Progression] Level Up |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Player Progression] Achievements | [Player Progression] Achievements |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Player Progression] Factions | [Player Progression] Factions |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Player Progression] In-game Tutorial | [Player Progression] In-game Tutorial |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Professions] Fishing | [Professions] Fishing |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Professions] Gathering | [Professions] Gathering |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [Professions] Crafting System | [Professions] Crafting System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / Character Creation & Management | Character Creation & Management |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [CC & Management] Garment System | [CC & Management] Garment System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [CC & Management] Character Stats | [CC & Management] Character Stats |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [CC & Management] Pets | [CC & Management] Pets |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / [CC & Management] CC & Garment UI | [CC & Management] CC & Garment UI |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Progression / Talent/Skill System | Talent/Skill System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems | World Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Corruption | Corruption |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Movement System | Movement System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Navigation | Navigation |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Instancing | Instancing |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Day/night cycle | Day/night cycle |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / Dynamic weather | Dynamic weather |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / World Systems / World Resources | World Resources |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat | Combat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat Framework | [Core Combat] Combat Framework |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat Effect Systems | [Core Combat] Combat Effect Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat Targeting & Validation | [Core Combat] Combat Targeting & Validation |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Combat Hit & Damage Processing |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat Interactions | [Core Combat] Combat Interactions |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Ranged Combat | [Core Combat] Ranged Combat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Magic | [Core Combat] Magic |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] AI Combat Behavior | [Core Combat] AI Combat Behavior |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] PvP Combat System | [Core Combat] PvP Combat System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Core Combat] Combat UX & Telemetry | [Core Combat] Combat UX & Telemetry |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Combat Abilities] Ability Core | [Combat Abilities] Ability Core |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Combat Abilities] Casting Mechanics | [Combat Abilities] Casting Mechanics |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Combat / [Combat Abilities] Area & Effect Handling | [Combat Abilities] Area & Effect Handling |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / User Space & Minigames | User Space & Minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / User Space & Minigames / [User Space] Server Support | [User Space] Server Support |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / User Space & Minigames / [User Space] Decoration | [User Space] Decoration |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / User Space & Minigames / [Minigames] Single-player minigames | [Minigames] Single-player minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / User Space & Minigames / [Minigames] Multiplayer minigames | [Minigames] Multiplayer minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory | Items & Inventory |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory / Item Core System | Item Core System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory / Inventory System | Inventory System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Core | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory / Equipment System | Equipment System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory / Loot Distribution Systems | Loot Distribution Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Items & Inventory / Trading System | Trading System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System | Quest System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quests Backend/Tooling | [Quest System] Quests Backend/Tooling |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quests as Events | [Quest System] Quests as Events |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quest Multiplayer | [Quest System] Quest Multiplayer |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quest Rewards | [Quest System] Quest Rewards |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quest Types | [Quest System] Quest Types |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Quest System / [Quest System] Quest Narrative | [Quest System] Quest Narrative |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems | Multiplayer Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Chat | Chat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Friends | Friends |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Party (co-op) | Party (co-op) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Multiplayer - raids | Multiplayer - raids |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / In-game mail | In-game mail |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Notifications | Notifications |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Multiplayer Systems / Guild System | Guild System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI | UX/UI |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / [Game Interfaces] HUD & In-Game Interface | [Game Interfaces] HUD & In-Game Interface |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] UI Framework & UX Standards |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Presentation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / Controls | Controls |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / UX Optimizations | UX Optimizations |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / Accessibility | Accessibility |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / UX/UI / Presentation & Immersion | Presentation & Immersion |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform | Platform |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Account Creation/Deletion | [Platform] Account Creation/Deletion |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Account Authentification | [Platform] Account Authentification |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Account Privacy Settings & Legal |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Player Dashboard] Player Account Features | [Platform] [Player Dashboard] Player Account Features |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Player Dashboard] Game Dashboard | [Platform] [Player Dashboard] Game Dashboard |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Player Dashboard] Friends | [Platform] [Player Dashboard] Friends |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Player Dashboard] Search & Notifications | [Platform] [Player Dashboard] Search & Notifications |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Player Dashboard] Marketplace | [Platform] [Player Dashboard] Marketplace |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Developer Dashboard] Developer Account | [Platform] [Developer Dashboard] Developer Account |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Platform] [Developer Dashboard] Game Dashboard |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] [Developer Dashboard] Settings & Support | [Platform] [Developer Dashboard] Settings & Support |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Quest Tracking | [Platform] Quest Tracking |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Platform Certification | [Platform] Platform Certification |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Payment Processing | [Platform] Payment Processing |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Online Services & Backend | [Platform] Online Services & Backend |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Launcher & Distribution | [Platform] Launcher & Distribution |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Desktop App (?) | [Platform] Desktop App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Platform / [Platform] Mobile App (?) | [Platform] Mobile App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend | Online Services & Backend | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] Multiplayer Backend & Simulation Systems | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] Authoritative server simulation | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] Character persistence | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] Inventory persistence | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] Economy ledger | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Online Services & Backend / [Online Services & Backend] Multiplayer Backend & Simulation Systems | [Online Services & Backend] API versioning & schema migrations | Owner: Backend/Server Team ¦ Integration: Network Eng | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System | Player Support System | Comments: Not started ¦ Owner: CS Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Player Support Tools | Comments: Not started ¦ Owner: CS Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] In-game help & ticketing | Comments: Not started ¦ Owner: CS Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Knowledge base integration | Comments: Not started ¦ Owner: CS Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Report triage queue | Comments: Not started ¦ Owner: CS Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Harassment protection | Comments: Not started ¦ Owner: CS Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Appeals workflow | Comments: Not started ¦ Owner: CS Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Player Support System / [CS] Player Support Tools | [CS] Name change enforcement | Comments: Not started ¦ Owner: CS Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System | Analytics System | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Gameplay & Product Analytics | [Analytics] Gameplay & Product Analytics | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Gameplay & Product Analytics | [Analytics] Core gameplay events | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Gameplay & Product Analytics | [Analytics] Onboarding funnel | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Gameplay & Product Analytics | [Analytics] Economy monitoring | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | High |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Gameplay & Product Analytics | [Analytics] Feature flag analytics | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Performance & Technical Telemetry | [Analytics] Performance & Technical Telemetry | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Performance & Technical Telemetry | [Analytics] Client/server perf telemetry | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Performance & Technical Telemetry | [Analytics] Telemetry privacy controls | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Business Intelligence | [Analytics] Business Intelligence | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Business Intelligence | [Analytics] KPI dashboards | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Business Intelligence | [Analytics] Data warehouse & governance | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Alerts System | [Analytics] Alerts System | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Analytics System / [Analytics] Alerts System | [Analytics] Anomaly detection alerts | Comments: Not started ¦ Owner: Analytics Lead/EP | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Feature | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability | Performance & Reliability | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Client Performance | [Performance] Client Performance | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Client Performance | [Performance] Graphics scalability | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Client Performance | [Performance] Memory management | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Client Performance | [Performance] Asset optimization pipeline | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Client Performance | [Performance] Tick rate & scaling | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Network & Simulation Performance | [Performance] Network & Simulation Performance | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Network & Simulation Performance | [Performance] Latency management | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Network & Simulation Performance | [Performance] Network latency indicators | Owner: Backend Team | Not started | High |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Infrastructure Scalability | [Performance] Infrastructure Scalability | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Infrastructure Scalability | [Performance] Data consistency checks | Comments: Not started ¦ Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Infrastructure Scalability | [Performance] Autoscaling policies | Comments: Not started ¦ Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Reliability & Resilience | [Performance] Reliability & Resilience | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Reliability & Resilience | [Performance] Backups & disaster recovery | Comments: Not started ¦ Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Reliability & Resilience | [Performance] Incident response runbooks | Comments: Not started ¦ Owner: Backend Team | Not started | High |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Reliability & Resilience | [Performance] Chaos testing / fault injection | Comments: Not started ¦ Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Service Quality Monitoring | [Performance] Service Quality Monitoring | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / Performance & Reliability / [Performance] Service Quality Monitoring | [Performance] SLOs/SLAs tracking | Comments: Not started ¦ Owner: Backend Team | Not started | High |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering | QA & Release Engineering | Comments: Not started ¦ Owner: QA Lead/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] QA Tools | Comments: Not started ¦ Owner: QA Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Automated tests | Comments: Not started ¦ Owner: QA Lead | Not started | High |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Feature flags | Comments: Not started ¦ Owner: QA Lead | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Test environments | Comments: Not started ¦ Owner: QA Lead | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Crash reporting | Comments: Not started ¦ Owner: QA Lead | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Replay/record system for bugs | Comments: Not started ¦ Owner: QA Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] QA Tools | [QA & Release Engineering] Load testing | Comments: Not started ¦ Owner: QA Lead | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] Release Tools | [QA & Release Engineering] Release Tools | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] Release Tools | [QA & Release Engineering] CI/CD pipeline | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] Release Tools | [QA & Release Engineering] Automated rollback | Comments: Not started ¦ Owner: Backend Team | Not started | High |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] Release Tools | [QA & Release Engineering] Client signing / anti-tamper build steps | Owner: Backend Team | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / QA & Release Engineering / [QA & Release Engineering] Release Tools | [QA & Release Engineering] Stable daily builds provision | Owner: Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools | DevOps & Tools | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Content Creation Tools | [DevOps] Content Creation Tools | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Content Creation Tools | [DevOps] Content editor tooling | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Content Creation Tools | [DevOps] World building tools | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Globalization Pipeline | [DevOps] Globalization Pipeline | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Globalization Pipeline | [DevOps] Localization pipeline | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Globalization Pipeline | [DevOps] Localization QA tooling | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | High |  | Implementation |  |  |  | Game Development | System | Polish | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Data & Observability Platform | [DevOps] Data & Observability Platform | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Data & Observability Platform | [DevOps] Log aggregation | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Data & Observability Platform | [DevOps] Telemetry schema registry | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Build & Content Validation | [DevOps] Build & Content Validation | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Medium |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Game Systems / DevOps & Tools / [DevOps] Build & Content Validation | [DevOps] Asset validation pipeline | Comments: Not started ¦ Owner: DevOps ¦ Integration: DevOps | Not started | Critical ACT |  | Implementation |  |  |  | Game Development | System | Foundation | high | Features V2 / Game Systems
Couch Heroes / Game / Platform Features / Platform, Security & Compliance | Platform, Security & Compliance |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform | Platform | Comments: To be reviewed ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Account Creation/Deletion | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Account creation / registration | DoD: User can create account; validates email/username/password; handles errors; stores profile. ¦ Comments: Done or partially done. I don't think we're storing profiles atm ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Display name policy & rename | DoD: Unique rules; profanity filter; rename tokens; history. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Ban/suspension state handling | DoD: Account state blocks login appropriately; shows reason codes. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Character delete | DoD: Delete with confirmation; cooldown; prevents deleting last char if needed. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Creation/Deletion | [Platform] Name validation | DoD: Uniqueness rules; reserved words; profanity; unicode handling. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Account Authentification | DoD: Verification email sent; account gated until verified; resend + rate limits. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Email verification | Comments: Done or partially done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Login / authentication | DoD: Secure login; session tokens; remember-me; logout all devices. ¦ Comments: Partially done. We have basic login system ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Password reset | DoD: Self-serve reset via email/SMS; token expiry; audit event. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Multi-factor authentication (MFA) | DoD: Optional/required MFA; recovery codes; device trust. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Sign-in Methods | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with email | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with Google | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification / [Platform] Sign-in Methods | [Platform] Sign-in with Discord | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Account recovery workflow | DoD: Support-assisted recovery; ownership proof; lockout handling. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | [Platform] Account linking (Steam/PSN/Xbox/Epic/CH) | DoD: Link/unlink external identities; conflict resolution. ¦ Comments: Paused - decided not to link Steam. Needs additional discussion ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | License/ownership check | DoD: Validate game license and DLC/expansions entitlements. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Authentification | Cross-progression entitlements | DoD: Entitlements reconcile across platforms; prevents dupes. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Account Privacy Settings & Legal | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Consent management | DoD: Track and store consent for ToS/Privacy/marketing; versioned. ¦ Comments: Not started though we have a confirmed version of ToU ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Data export (GDPR/CCPA) | DoD: User can request export; generates bundle; authenticated delivery. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Account deletion / erasure | DoD: User can request deletion; cool-off; deletes/anonymizes per policy. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal | [Platform] Age gating / parental controls | DoD: Age check; chat restrictions; spending limits; COPPA flows. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal / [Platform] Age gating / parental controls | Age gating restriction flow for the game | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Account Privacy Settings & Legal / [Platform] Age gating / parental controls | Age gating process for 3rd party game partners | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Platform] [Player Dashboard] Player Account Features | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Account Info Display | Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Nickname | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Default profile picture | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Account avatar upload | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Account level | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display | Log out | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Player Achievements | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] CH currency wallet | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Account Settings | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Player Account Features | [Player Dashboard] Support & FAQ | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Platform] [Player Dashboard] Game Dashboard | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Partner Games Display | Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | All games | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Unlocked games | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Quests required to unlock | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display | Steam key redemption | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Partner Assets (items) display | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Assets (items) display | Inventory section | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Available Quests Tracking | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Launcher Download | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Community Hub | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Game Dashboard | [Player Dashboard] Featured Games section | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Friends | [Platform] [Player Dashboard] Friends | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Friends | [Player Dashboard] Friend List Management | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Friends | [Player Dashboard] Chat | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Platform] [Player Dashboard] Search & Notifications | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Player Dashboard] Search | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Search & Notifications | [Player Dashboard] Web notifications/red dots | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Marketplace | [Platform] [Player Dashboard] Marketplace | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Player Dashboard] Marketplace | [Player Dashboard] P2P Marketplace | Comments: Not started, needs discussion ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Platform] [Developer Dashboard] Developer Account | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Account creation/sign in | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Company Info Form | Comments: Done ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Developer Account | [Developer Dashboard] Manage account | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Platform] [Developer Dashboard] Game Dashboard | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Games management | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Keys management | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Game Dashboard | [Developer Dashboard] Analytics | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Settings & Support | [Platform] [Developer Dashboard] Settings & Support | Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] [Developer Dashboard] Settings & Support | [Developer Dashboard] contact support & FAQ | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Quest Tracking | [Platform] Quest Tracking | DoD: Designers create quests; Translation/Localisation links; Dialogue/Narrative links. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Quest Tracking | [Platform] Quest Input System | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Quest Tracking | [Platform] Partner Quest Integration | Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | In progress | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Platform Certification | [Platform] Platform Certification | DoD: PS/Xbox/Nintendo TRCs; submission checklists. Steam also needs this if we decide to go there ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Platform Certification | [Platform] Platform certification requirements | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Payment Processing | [Platform] Payment Processing | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Payment Processing | [Platform] Payment System Integration | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: EP/Platform Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Online Services & Backend | DoD: Transactional emails; throttling; deliverability. ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Session concurrency limits | DoD: Limit simultaneous logins; kick/notify; anti-abuse. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Email/SMS service integration | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Patch/manifest CDN | DoD: Serve patches; delta patching; region caches; integrity. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Account-wide settings service | DoD: Store settings server-side; sync; conflict resolution. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Notification/push service | DoD: Send push for events (optional); opt-in; region compliance. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Online Services & Backend | [Platform] Regional routing / shard selection | DoD: User chooses region/shard; can transfer with rules. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Launcher & Distribution | DoD: Self-update; verify files; repair; disk space checks. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Patch/update system | Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Launcher integration | DoD: News, login, patch; SSO; crash log upload. ¦ Comments: In progress ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Done | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Crossplay toggle | DoD: User setting; matchmaking rules; compliance. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Cross-save | DoD: Upload/download save; conflict resolution; offline behavior. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Screenshot/video capture hooks | DoD: Share on platform; privacy; parental settings. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Offline mode behavior | DoD: If offline allowed: restrict features; queue actions; messaging. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Hardware detection & defaults | DoD: Detect hardware; set recommended settings; benchmark optional. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Input method auto-switching | DoD: Instant switch between KB/mouse and controller; UI updates. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Multiple language packs | DoD: Download language packs; switch without reinstall; UI. ¦ Comments: We have something on localization, needs check ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Launcher & Distribution | [Platform] Cross-session settings sync | DoD: Settings stored server-side; per-platform overrides. ¦ Comments: Not started ¦ Owner: Platform/EP ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Desktop App (?) | [Platform] Desktop App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Platform / [Platform] Mobile App (?) | [Platform] Mobile App (?) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance | Compliance | Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Mandatory Legal Docs & Procedures | Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Terms of Service / EULA acceptance | DoD: Must accept before play; versioning; re-consent. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Privacy policy presentation | DoD: Accessible in-game; locale; versioning. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Cookie/consent for web components | DoD: If web views used; region rules. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Loot box odds disclosure | DoD: Display odds where required; logs; audits. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Data retention & deletion policy | DoD: Retention windows; deletion jobs; backup handling. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Vulnerability disclosure process | DoD: Security contact; bug bounty policy optional. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Accessibility compliance checks | DoD: WCAG-inspired checks for UI; console TRCs; docs. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Regional content ratings | DoD: ESRB/PEGI/USK; descriptors; age gating. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention | Security & Abuse Prevention | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Access & Capacity Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Login queue | DoD: Queue when servers full; ETA; priority lanes; disconnect handling. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Rate limiting & abuse protection | DoD: Global per-IP/account rate limits; WAF; alerts. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] DDoS mitigation | DoD: Traffic scrubbing; rate limits; failover. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Anti-Cheat | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Anti-tamper / integrity checks | DoD: Detect modified clients; secure bootstraps; update enforcement. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Server-side cheat detection | DoD: Speed/teleport; impossible actions; DPS anomalies; flags. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Client-side anti-cheat (if used) | DoD: Kernel/user mode as appropriate; privacy notices; compatibility. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Communication & Data Security | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Encryption in transit | DoD: TLS everywhere; cert pinning optional; secure websockets. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Secrets management | DoD: No secrets in client; rotate keys; least privilege. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] Economic & Transaction Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] Fraud & chargeback handling | DoD: Detect suspicious purchases; velocity limits; chargeback workflows. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] RMT mitigation | DoD: Trade caps; detection; escrow; enforcement tooling. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Behavioral Abuse Prevention | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Botting mitigation | DoD: Behavioral detection; captcha in web; in-game friction; bans. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Account takeover prevention | DoD: Suspicious login alerts; device fingerprint; step-up auth. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Compliance & Data Protection | [Security] Compliance & Data Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Platform Features / Security & Abuse Prevention / [Security] Compliance & Data Protection | [Security] Secure logging & PII redaction | DoD: Redact PII in logs; access controls; audit. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Platform Features
Couch Heroes / Game / Live Service Features / LiveOps System | LiveOps System | Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Events | [LiveOps] Events | Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Events | [LiveOps] Public events | DoD: Spawn triggers; participation; scaling; reward distribution. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Events | [LiveOps] Seasonal events | DoD: Timed live events; themed rewards; calendar scheduling. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Events | [LiveOps] World bosses | DoD: Schedule/spawn rules; scaling; loot lockouts. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Seasonal Content | [LiveOps] Seasonal Content | Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Seasonal Content | [LiveOps] Season rollover & rewards | DoD: End-of-season rewards; rank snapshots; soft reset rules. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Seasonal Content | [LiveOps] Battle pass / season track | DoD: XP track; rewards; premium track; catch-up; UI. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Seasonal Content | [Core Combat] PvP rewards & seasons | DoD: Seasonal resets; cosmetics; currency; anti-farm caps. ¦ Comments: Not started ¦ Owner: Game Design ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Retention Activities | [LiveOps] Retention Activities | Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Retention Activities | [LiveOps] Daily/weekly objectives | DoD: Rotating objectives; reset schedule; streaks; UI. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Retention Activities | [LiveOps] Catch-up mechanics | DoD: Boosts for new/returning; cap removals; UI messaging. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Gameplay Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Service Reliability | [LiveOps] Live Service Reliability | Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Service Reliability | [LiveOps] Telemetry pipeline | DoD: Event ingestion; batching; privacy flags; schema versioning. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Service Reliability | [LiveOps] Service health checks | DoD: Heartbeat endpoints; SLO monitoring; dashboards. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Service Reliability | [LiveOps] Graceful degradation | DoD: If service down (e.g., store), game continues with limits. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Live Patching | Comments: Not started ¦ Owner: EP/LiveOps Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Server-side config / tuning | DoD: Hotfix values without client patch; versioned configs. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Content patch pipeline | DoD: Build, validate, publish; rollback; partial rollout. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Event scheduling system | DoD: Schedule start/end; timezones; rewards; announcements. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] In-game announcements | DoD: MOTD, banners, popups; targeting; localization. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Experiment framework | DoD: Randomized assignment; metrics; kill switches; ethics. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Server restart/maintenance mode | DoD: Broadcast; safe shutdown; kick timers; maintenance page. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Network Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Localization hotfixes | DoD: Update text assets without full patch; cache busting. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] Live Patching | [LiveOps] Rollback / restore tooling | DoD: Restore character/inventory from backups; transaction replays. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] LiveOps Tools | Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] GM tools (admin) | DoD: Teleport, spawn, inspect, ban/mute; audit logs. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] Ban waves & enforcement tooling | DoD: Bulk actions; evidence; appeal flags; audit. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] Server-side reward grants | DoD: Grant compensation; targeted cohorts; logs; idempotent. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] Customer messaging for incidents | DoD: Status page integration; in-game banner; localized. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team ¦ Integration: Fullstack Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] Feature configuration UI | DoD: Non-dev tuning UI; permissioned; change tracking. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / LiveOps System / [LiveOps] LiveOps Tools | [LiveOps] Content permissions & approvals | DoD: Role-based approvals; publish gates; audit logs. ¦ Comments: Not started ¦ Owner: EP/LiveOps Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization | Player Monetization | Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Purchases | Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Purchase flow | DoD: Platform payment; confirmations; error handling; receipts. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Entitlement delivery | DoD: Grant items/currency; idempotent; offline delivery; logs. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Refund processing | DoD: Revoke entitlements where possible; currency sinks; logs. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Spending limits & transparency | DoD: Purchase confirmations; spending history; parental controls. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Premium currency wallet | DoD: Purchase/spend; display rates; region pricing. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Regional pricing & taxes | DoD: Price tiers by region; VAT; platform rules. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Purchases | [Monetization] Gift purchases | DoD: Gift items to others; fraud controls; delivery confirmation. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead ¦ Integration: Backend Eng | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Monetization Types | [Monetization] Monetization Types | Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Monetization Types | [Monetization] Subscription benefits | DoD: Monthly perks; renewal; grace period; messaging. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Monetization Types | [Monetization] Loot boxes / random packs (if used) | DoD: Odds disclosure; pity timers; regulation compliance; age gate. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Monetization Types | [Monetization] Cosmetic preview & dressing room | DoD: Try on skins; preview in different lighting; share. ¦ Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Partner Monetization | [Monetization] Partner Monetization | Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Partner Monetization | [Monetization] Subsidized Game Purchase | Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Player Monetization / [Monetization] Partner Monetization | [Monetization] Partner Assets Purchase | Comments: Not started ¦ Owner: EP/Monetization Lead | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance | Compliance | Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Mandatory Legal Docs & Procedures | Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Terms of Service / EULA acceptance | DoD: Must accept before play; versioning; re-consent. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Privacy policy presentation | DoD: Accessible in-game; locale; versioning. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Cookie/consent for web components | DoD: If web views used; region rules. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Loot box odds disclosure | DoD: Display odds where required; logs; audits. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Data retention & deletion policy | DoD: Retention windows; deletion jobs; backup handling. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Vulnerability disclosure process | DoD: Security contact; bug bounty policy optional. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Accessibility compliance checks | DoD: WCAG-inspired checks for UI; console TRCs; docs. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Compliance / [Compliance] Mandatory Legal Docs & Procedures | [Compliance] Regional content ratings | DoD: ESRB/PEGI/USK; descriptors; age gating. ¦ Comments: Not started ¦ Owner: EP/Legal ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention | Security & Abuse Prevention | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Access & Capacity Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Login queue | DoD: Queue when servers full; ETA; priority lanes; disconnect handling. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] Rate limiting & abuse protection | DoD: Global per-IP/account rate limits; WAF; alerts. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Access & Capacity Protection | [Security] DDoS mitigation | DoD: Traffic scrubbing; rate limits; failover. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Anti-Cheat | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Anti-tamper / integrity checks | DoD: Detect modified clients; secure bootstraps; update enforcement. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Server-side cheat detection | DoD: Speed/teleport; impossible actions; DPS anomalies; flags. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Anti-Cheat | [Security] Client-side anti-cheat (if used) | DoD: Kernel/user mode as appropriate; privacy notices; compatibility. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Communication & Data Security | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Encryption in transit | DoD: TLS everywhere; cert pinning optional; secure websockets. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Communication & Data Security | [Security] Secrets management | DoD: No secrets in client; rotate keys; least privilege. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] Economic & Transaction Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] Fraud & chargeback handling | DoD: Detect suspicious purchases; velocity limits; chargeback workflows. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Economic & Transaction Protection | [Security] RMT mitigation | DoD: Trade caps; detection; escrow; enforcement tooling. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Behavioral Abuse Prevention | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Botting mitigation | DoD: Behavioral detection; captcha in web; in-game friction; bans. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Behavioral Abuse Prevention | [Security] Account takeover prevention | DoD: Suspicious login alerts; device fingerprint; step-up auth. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Compliance & Data Protection | [Security] Compliance & Data Protection | Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Live Service Features / Security & Abuse Prevention / [Security] Compliance & Data Protection | [Security] Secure logging & PII redaction | DoD: Redact PII in logs; access controls; audit. ¦ Comments: Not started ¦ Owner: Backend Team ¦ Integration: Web/Backend Team | Not started | Medium |  | Implementation |  |  |  | Game Development | LiveService | Feature | high | Features V2 / Live Service Features
Couch Heroes / Game / Content / Player Progression | Player Progression |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Player Progression] Level Up | [Player Progression] Level Up |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Player Progression] Level Up | Level Up UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Level Up | Level Up VFX | Art team: VFX ¦ Comments: Scale Healing VFX ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Achievements | [Player Progression] Achievements |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Player Progression] Achievements | Achievements UI VFX | Art team: VFX ¦ Comments: Extra SS effects ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Achievements | Achievements UI | Art team: UX/UI, Concept ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Achievements | Achievements Icons | Art team: Concept ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Factions | [Player Progression] Factions |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Player Progression] Factions | Factions NPCs | Art team: Concept, Character, Animations, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Factions | Faction player clothing | Art team: Character, Concept, TechArt, Animations ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Factions | Faction dialogue UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] Factions | Factions Banners/Symbols | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] In-game Tutorial | [Player Progression] In-game Tutorial |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Player Progression] In-game Tutorial | Tutorial Archive UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] In-game Tutorial | Tutorial VFX (arrows) | Art team: VFX ¦ Comments: Mesh + VFX ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Player Progression] In-game Tutorial | Tutorial UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | [Professions] Fishing |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing Animations | Art team: Animations, TechArt ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing Rod Model | Art team: Concept, Character ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fish Models + inventory | Art team: Concept, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing Sign Model/icon | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Aquarium Model | Art team: Concept, Environment, VFX, TechArt ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing shop | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing profession UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Fishing | Fishing VFX | Art team: VFX ¦ Comments: Water material + additional VFX ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gear | [Professions] Gear |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Professions] Gear | Torches, magic crystals, shields and other non-weapon equippables | Art team: Character, TechArt, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | [Professions] Gathering |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering Animations | Art team: Animations, TechArt, VFX ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering VFX | Art team: VFX ¦ Comments: Design and concept art ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering profession UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering inventory items | Art team: Concept ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Gathering | Gathering Tools Models | Art team: Concept, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | [Professions] Crafting System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting Animations | Art team: Animations, VFX, TechArt ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting VFX | Art team: VFX ¦ Comments: Props proposition and concepts ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting profession UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting material icons | Art team: Concept ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [Professions] Crafting System | Crafting Tools Models | Art team: Concept, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Character Creation & Management |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Base face models | Art team: Animations, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Base body models with variations (gender/proportions) | Art team: Animations, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Appearance Elements Sets (eyes, hair, lips etc) | Art team: Animations, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Character UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Character Creation & Management | Races variations | Art team: Animations, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | [CC & Management] Garment System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Basic garment options | Art team: Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Garment variations for slots | Art team: Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Skins | Art team: Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Armour models | Art team: Concept, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Armour UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Armour slot crystals | Art team: Concept, UX/UI, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Garment System | Partner skins | Art team: Concept, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Character Stats | [CC & Management] Character Stats |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [CC & Management] Character Stats | Skill Tree UI icons | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Character Stats | Stats UI Icons + interface | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | [CC & Management] Pets |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Pets Models | Art team: Concept, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Pets Animations | Art team: Concept, Animations, TechArt ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Partner Pets | Art team: Concept, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Pets VFX (trails, summon) | Art team: Concept, Animations, TechArt, VFX ¦ Comments: Characters guidelines ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Pets Appearance Customization Options | Art team: Concept, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] Pets | Pets Garments (collars?) | Art team: Concept, Character, TechArt ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] CC & Garment UI | [CC & Management] CC & Garment UI |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] CC & Garment UI | CC & Garment Menus | Art team: Concept, UX/UI ¦ Comments: Devs implement. ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] CC & Garment UI | CC & Garment Presets | Art team: UX/UI, Character, TechArt ¦ Comments: Tech validation from Char. Art ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / [CC & Management] CC & Garment UI | CC & Garment Randomizer | Art team: UX/UI, Character, TechArt ¦ Comments: Ready to use, DA, Maya scipt ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Talent/Skill System | Talent/Skill System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Player Progression / Talent/Skill System | Talent System UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Player Progression / Talent/Skill System | Talent Upgrade VFX | Art team: VFX ¦ Comments: Design and Chars (?) ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems | World Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / World Ambience | World Ambience |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / World Ambience | Ambient area VFX | Art team: VFX ¦ Comments: Env. ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corruption |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Corruption | Different corruption types support (TechArt) | Art team: Concept, TechArt, VFX ¦ Comments: Mechanics and material visual, VFX support following phase ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corruption cleansing mechanic | Art team: TechArt, VFX ¦ Comments: Ready, optimization pass 1 done ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corruption weapon | Art team: Concept, Character, TechArt, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corrupted enemies | Art team: Concept, Animations, Character, TechArt, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corrupted models | Art team: Concept, Character, TechArt, VFX, Environment ¦ Comments: Volumetric and Painting ready to be implemented, Designers and Env to feedback possible upgrade in shape and underneath material ¦ Owner: Lead Tech Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Corruption | Corruption VFX | Art team: Concept, Character, TechArt, VFX ¦ Comments: Co-dev with TA ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Movement System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Movement System | Basic Movement Animations (walk, run, sprint, jump) | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Gliding Animations | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Gliding Device | Art team: Concept, Character, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Grappling Animations | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Grappling Hook Device | Art team: Concept, Character, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Ziplines Animations | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Grappling Hook Points | Art team: Concept, VFX ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Zipline device | Art team: Concept, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Vaulting animations | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Avoidance anims | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Launch anims | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Dodge anims | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Slide, Crouch, land, strafe | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Movement VFX | Art team: VFX ¦ Comments: Trails + further concepts ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Movement System | Ziplines Model | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Navigation |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Navigation | World Map UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Minimap UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Compass UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Portals | Art team: Concept, VFX, Environment ¦ Comments: Upgrade present with no performance heavy solutions ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Archway race VFX | Art team: VFX, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Navigation | Teleportation scrolls/VFX | Art team: Concept, TechArt, VFX ¦ Comments: Scalable ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Day/night cycle | Day/night cycle |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Day/night cycle | Dynamic day/night cycle | Art team: Environment, TechArt, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Day/night cycle | Town lighting (when dark) | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Day/night cycle | Dynamic lighting | Art team: Environment, TechArt, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Dynamic weather | Dynamic weather |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Dynamic weather | Cloud system | Art team: Environment, TechArt ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Dynamic weather | Define the weather cycle and needs | Art team: Environment, TechArt, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / World Resources | World Resources |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / World Resources | Collectible resources models | Art team: Concept, Environment, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / World Resources | Destructible resources models & VFX | Art team: Concept, Environment, VFX, TechArt ¦ Comments: Explored and planned, start with barrels/crate, expand ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / World Resources | Chests | Art team: Concept, Animations, Environment, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Initial Island Layout | Initial Island Layout | DoD: Digit Isle 1 9 initial zones, 2D map design, layout | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Initial Island Layout | Initial Island Blockouts | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Initial Island Layout | Initial island Biomes Definition | Art team: Concept, Environment ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Initial Island Layout | Initial Island Zones Scope and Sizes | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Points of interest (POIs) | DoD: POI definitions; discovery; map markers; tooltips. | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | List all zones and POIs | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Dungeons layout and set dressing | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Concept all zones and POIs | Art team: Concept, Environment ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | POIs set dressing | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Props | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Vegetation | Art team: Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Points of interest (POIs) | Environmental VFX | Art team: Environment, VFX ¦ Comments: List ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / World Systems / Curved Horizon R&D | Curved Horizon R&D |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / World Systems / Curved Horizon R&D | Decide if we proceed with this idea and how | Art team: Concept, Environment, TechArt ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat | Combat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Framework | Combat Animations (player, AI) | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: Title not in classification file - sheet-based default
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Framework | Combat VFX | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: Title not in classification file - sheet-based default
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Framework | Weapons models (melee, ranged, magic) | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: Title not in classification file - sheet-based default
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Framework | Combat UI | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: Title not in classification file - sheet-based default
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Framework | Combat abilities animations & VFX | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: Title not in classification file - sheet-based default
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Effect Systems | [Core Combat] Combat Effect Systems | Art team: Animations, VFX ¦ Comments: Melee w/o weapons ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Hit & Damage Processing | [Core Combat] Combat Hit & Damage Processing | Art team: Animations, VFX, UX/UI ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Core Combat] Combat Interactions | [Core Combat] Combat Interactions | Art team: Animations, VFX, UX/UI ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Core Combat] Ranged Combat | [Core Combat] Ranged Combat | Art team: Animations, VFX, UX/UI ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Core Combat] Magic | [Core Combat] Magic | Art team: Animations, VFX, UX/UI ¦ Comments: Weapon + Magic spells, coord with Combat Dept ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Core Combat] AI Combat Behavior | [Core Combat] AI Combat Behavior | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Combat Abilities] Skill Tree Abilities for melee weapons | [Combat Abilities] Skill Tree Abilities for melee weapons | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Combat Abilities] Casting Mechanics | [Combat Abilities] Casting Mechanics | Art team: Animations, VFX, UX/UI ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Combat Abilities] Area & Effect Handling | [Combat Abilities] Area & Effect Handling | Art team: Animations, VFX, UX/UI ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / PVP Combat | PVP Combat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Combat / PVP Combat | PvP Arena Layout & Set dressing | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Enemies] Content | [Enemies] Content |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Combat / [Enemies] Content | Enemies types 3D support (define with design) | Art team: Concept, Animations, Character, TechArt, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Enemies] Content | Enemies animations & VFX per type | Art team: Concept, Animations, VFX ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Enemies] Content | Bosses & mini-bosses artwork (models, animations, VFX) | Art team: Concept, Animations, Character, TechArt, VFX ¦ Owner: Art Director | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Combat / [Enemies] Content | Corrupted enemies | Art team: Concept, Animations, Character, TechArt, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames | User Space & Minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | [User Space] Decoration |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | Decoration/furniture sets | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | External balcony doors | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | Partner US objects/trophies | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | Furniture inventory items | Art team: Concept, Environment | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | Object addition VFX | Art team: VFX ¦ Comments: Scalable VFX ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [User Space] Decoration | Interactive US objects & animations/UI | Art team: Concept, UX/UI, Animations ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [Minigames] Single-player minigames | [Minigames] Single-player minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / User Space & Minigames / [Minigames] Single-player minigames | Lockpicking UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [Minigames] Single-player minigames | Arcade cabinet for US (review existing one) | Art team: Environment, Concept ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / User Space & Minigames / [Minigames] Multiplayer minigames | [Minigames] Multiplayer minigames |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / User Space & Minigames / [Minigames] Multiplayer minigames | Speed archway in Downtime (review models, VFX) | Art team: Concept, Environment, VFX ¦ Comments: Design, art concept and upgrade (logic ready) ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory | Items & Inventory |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Items & Inventory / Item Core System | Item Core System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Items & Inventory / Item Core System | Static items (collectibles, crafting items, quest items) | Art team: Concept, Environment, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Item Core System | Interactive items (destructibles) | Art team: Concept, Environment, TechArt, VFX ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Inventory System | Inventory System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Items & Inventory / Inventory System | Inventory UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Equipment System | Equipment System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Equipment System | Equipment UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Trading System | Trading System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Items & Inventory / Trading System | Trading UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Trading System | Vendors NPC | Art team: Concept, Animations, Character ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Trading System | Vendors Animations | Art team: Animations ¦ Owner: Lead Anim Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Items & Inventory / Trading System | Shops Buildings & Props | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Quest System | Quest System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Quest System / [Quest System] Quest UI | [Quest System] Quest UI | Art team: Concept, UX/UI | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Quest System / Quest Tracking (exclamation marks, search area etc) | Quest Tracking (exclamation marks, search area etc) | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Quest System / Quest Special NPCs models | Quest Special NPCs models | Art team: Concept, Animations, Character, VFX ¦ Owner: Lead Character Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems | Multiplayer Systems |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Multiplayer Systems / Chat | Chat |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Multiplayer Systems / Chat | Chat UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Friends | Friends |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Multiplayer Systems / Friends | Friends UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Party (co-op) | Party (co-op) |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Party (co-op) | Party UI/HUD | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / In-game mail | In-game mail |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Multiplayer Systems / In-game mail | Mail UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Notifications | Notifications |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | medium | Features V2 / Content | Medium confidence: no explicit art team or asset keyword; verify it is content not feature
Couch Heroes / Game / Content / Multiplayer Systems / Notifications | Notifications UI | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Guild System | Guild System |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Guild System | Guild UI & chat | Art team: Concept, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Guild System | Guild TV + portals | Art team: Concept, Environment, VFX ¦ Comments: Engineering support and co-dev ¦ Owner: Lead VFX Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / Multiplayer Systems / Guild System | Guild Space (guild house/user space) | Art team: Concept, Environment ¦ Owner: Lead Env Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI | UX/UI |  | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / [Game Interfaces] HUD & In-Game Interface | The current UX/UI throughout the game needs review and decision if we change the style/flows or proceed with the current ones. Each feature needs supporting interfaces | Art team: Concept, VFX, UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / [Game Interfaces] UI Framework & UX Standards | [Game Interfaces] UI Framework & UX Standards | Art team: UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / Controls | Controls | Art team: UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / UX Optimizations | UX Optimizations | Art team: UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Polish | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / Accessibility | Accessibility | Art team: UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Polish | high | Features V2 / Content
Couch Heroes / Game / Content / UX/UI / Presentation & Immersion | Presentation & Immersion | Art team: UX/UI ¦ Owner: Lead UX/UI Artist | Not started | Medium |  | Implementation |  |  |  | Game Development | Content | Presentation | high | Features V2 / Content
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Level Up | V3: Player gains XP from gameplay actions and levels up. Basic UI/VFX. Placeholder progression balance ¦ V4: Final XP rules, sources, pacing, rewards, and polished level-up presentation ¦ V5: Bug fixing, performance improvements, and XP/reward balancing based on playtests or release data | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Character Stats | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define stats definition and behavior, do competitor research, prepare documentation ¦ V2: Implement and playtest basic stats ¦ V3: Implement all desired stats and test out their connection with other sustems in the game (economy, quests, combat etc) ¦ V4: Final stats functionality and balance across all game systems ¦ V5: Bug fixing, performance improvements, and stats balancing based on playtests or release data ¦ V6: Adding new stats, UI improvements, tooltips, presets ¦ V7: Character stats/progression system improvements and tool for designers to work with it | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Talent/Skill System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define talents and skill paths, talent points getting and distribution rules, prepare documentation ¦ V2: One skill path implemented with placeholder UI; skill points gain and distribution implemented ¦ V3: All desired skill paths designed ad implementation started. Connection and affect to other gameplay system in testing ¦ V4: All desired skill paths are implemented in the release quality. Final UI and efefcts. Balance and progression configration is final ¦ V5: Bug fixing, performance improvements, and skills balancing based on playtests or release data ¦ V6: Adding new skill paths, expanding the existing ones, further balance tweaks, UI/UX improvements ¦ V7: Overall skill system optimization and improvement in line with live operations strategy | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Achievements/Trophies | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Achievements conditions and rewards defined, scope confirmed, documentation prepared ¦ V2: Basic achievements functionality implemented (player performs an action - player gets the achievement) ¦ V3: Basic UI and effects implemented. UX tested, if achievements are more than cosmetic - connection with other systems tested ¦ V4: All achievements are implemented with final UX/UI and effects. Achievement getting conditions are tested. Achievements are tracked at the Platform layer ¦ V5: Bug fixes and optimizations ¦ V6: New achievements addition, achievements rarity, special achievements based on community demand ¦ V7: Achievement system improvements across game, web and mobile layers | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Factions | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Factions defined, each faction reputation gain rules are set and designed, faction content and narrative ready, documentation finished ¦ V2: Faction content in production (areas, NPCs, symbols etc), demo faction quests implemented, basic reputation gain fuctionality implemented ¦ V3: All factions visible in game with placeholder dialogues in quests and WIP content. Factions reputation progression finalized and tested with other game systems ¦ V4: Faction content final and implemented, factions reputation progression balanced, all needed quest lines are implemented and tested ¦ V5: Bug fixes and improvements, dialogue/localization tweaks, UX/UI improvements ¦ V6: More faction quests, reputation tree expanded/deepened, new factions, seasonal faction content ¦ V7: Reputation system expanded or applied to other systems in the game that use similar mechanics | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | In-game Tutorial | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: First-time player experience goals defined, player journey described. All systems, features and content participating in FTUE defined, the scope confirmed. Tutotial pop-ups/tooltips described/written. Tutorial segment is included as a part of documentation template for all new features ¦ V2: Basic in-game tutorial implemented, feedback for player implemented, temporary tutorial area exists ¦ V3: Tutorial rules finalized and implemented, design/level design close to final. Player progression through tutorial is in testing. Help codex basic fuctionality is implemented, tooltips across the game implemented ¦ V4: Full tutorial segment is implemented in final quality with all needed UX/UI passes. Tutorial progression is balanced, XP gain set. The player gets access to all needed systems, the progression is not blocked. Each feature the player encounters for the first time has hints. Help codex is full and easily accessible ¦ V5: Bugfix and tweaks bacsed on playtesting/user feedback ¦ V6: Each new feature contains tutorial/tooltips and added to the help codex ¦ V7: Tutorial systems are used during the LiveOps stage for events | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Fishing | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Professions progression and skill points rules are defined and escribed in the documentation. The list of launch-needed professions is finalized ¦ V2: Basic fishing implemented with placeholder UI, animations and content ¦ V3: Fishing skill path implemented with progression rules in place; fishing is a part of trading and in-game economy. Basic aquarium functionality added. Placeholder UI ¦ V4: Fishing minigame and skill progression are final. UX/UI, content and effects are final. Enough content to support the progression. Economy/trading balance finalized. Fishing spot placement in the world is done. US aquarium finalized. Tutorial in place ¦ V5: Bug fixes and improvements based on user feedback ¦ V6: More content (fish types, fishing areas, rods, customization) based on global content expansions and events ¦ V7: Multiplayer fishing systems and competitions | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Gathering | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V2: Gathering mechanic implemented, items are added to the inventory; placeholder animations and effects ¦ V3: Gathering skill path implemented with progression rules in place with placeholder UI. Gathering is a part of trading and in-game economy ¦ V4: Gathering profession is fully implemented with final animations, content and configuration. Gathering nodes placement is finalized. Gathered resources balance is final. Gathering skill path UI is final ¦ V5: Bug fixes and improvements based on user feedback ¦ V6: More content (gathering spots, resource types etc) based on global content expansions and events | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Crafting System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V2: Basic crafting is implemented (items can be combined to get a new item) with placeholder effects and animations ¦ V3: Crafting stations implemented. Crafting skill path implemented with progression rules in place with placeholder UI. Crafting is a part of trading and in-game economy ¦ V4: Crafting profession is fully implemented with final animations, content and configuration. Crafted resources balance is final. Crafting skill path UI is final ¦ V5: Bug fixes and improvements based on user feedback ¦ V6: More content (new crafted items etc) based on global content expansions and events ¦ V7: Crafting nechanic is used as the base for new systems (like Forge), for more UGC content and events | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Magic | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Magic defined, main goals and rules of the mechanic set. Competitor research done. Documentation complete ¦ V2: Basic spell casting implemented with placeholder animations and effects. Placeholder magic configuration ¦ V3: Sufficient number of magic types is implemented and supported by animations and effects. Magic is tested as a part of combat/professions system. Magic profession skill path is implemented with placeholder UI ¦ V4: All types of magic are implemented and balanced, with final animations and effects in place. Skill path UI is final ¦ V5: Bug fixes, optimizations and balance tweaks ¦ V6: New magic types, magic-based puzzles, magic weapons/scrolls ¦ V7: Multiplayer magic usage | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Character Management | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Number of characters per server, char transfer rules, naming rules etc are defined and run through best pratices, competitor research done, documentation completed. Anti-cheat system designed ¦ V2: The game supports at least one character per server that can be renamed, deleted or transffered. Placeholder UI ¦ V3: All decided functionality implemented with temporary UI. UX is close to final. Basic anti-cheat protection implemented ¦ V4: Number of characters, transfer and naming rules etc are fully implemented, with final UX/UI and effects. Anti-cheat system is in place ¦ V5: Bug fixes and optimizations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Appearance customization | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: The limitations of appearance customization defined, with the minimum scope of content needed. Starting appearance defined. Rules of how players can change their appearance in the future explored and set ¦ V2: Basic appearance customization implemented with basic appearance parts to be changed. Placeholder UX/UI, limited customization options ¦ V3: All customization slots implemented with placeholder UI and limited options. Points of appearance customization in the game are implemented. Appearance items are included in the in-game economy with placeholder balance ¦ V4: Final UI and roaster of options. Final economy balance and configuration for tradable appearance items. Appearance presets ¦ V5: Bug fixes and optimizations ¦ V6: More appearance customization options, appearance randomizer ¦ V7: Appearance customization system expanded with more character's parts to alter. Deeper customization. Using the technology to add pets customization | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Garment System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: The limitations of garment choice and garment slots defined, with the minimum scope of content needed. Starting garments defined. Rules of how players can change their garments in the future explored and set ¦ V2: Basic garment system implemented with a limited number of slots to be changed. Placeholder UX/UI, limited customization options ¦ V3: All garment slots are changable with placeholder UI. More customization options added. Garment items are included into the game economy with placeholder balance. UX flow of changing the garments in-game (how do I change the garments - inventory, Barbersmith etc) implemented ¦ V4: Final UI and roaster of options. Final economy balance and configuration for tradable garment items. Garment presets ¦ V5: Bug fixes and optimizations ¦ V6: More garment options, garment sets randomizer, partner and seasonal/event garments ¦ V7: Improve clothing pipelines, performance, compatibility, and tooling to support large wardrobes and long-term live content growth. Support UGC garments | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Corruption | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Corruption types, cleansing mechanic and role in the world designed, documentation completed ¦ V2: Techart R&D completed with one type of corruption implemented. Corruption texture implemented. Corruption cleansing implemented. Corruptions visuals defined ¦ V3: 1-2 types of corruption fully supported with placeholder VFX. Corruption quests added. Corruption cleansing skill path added with placeholder UI and balance. One corrupted enemy supported. Corruption server/client behavior supported ¦ V4: 3-4 corruption types are added and placed around the world in accordance with player progression. Corruption cleansing skill path has final congfiguration with final UI and supported by quests. Final corruption weapon, enemies, animations and VFX in place ¦ V5: Bug fixes and optimizations ¦ V6: New corruption types, new weapons, new corrupted areas and enemies. Black hole as a part of corrupted area. Corruption-based events | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Movement System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define movement style, controls, responsiveness targets, and technical approach ¦ V2: Basic character locomotion with simple input and camera movement ¦ V3: Core movement functional with stable controls and essential traversal actions ¦ V4: Final movement set polished, responsive, and ready for full gameplay use ¦ V5: Improve feel, fix bugs, tune responsiveness, and refine animations/performance ¦ V6: Add advanced traversal options or new movement mechanics ¦ V7: Improve networking, performance, and support for many players or platforms | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Navigation | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define navigation model, world traversal rules, and pathfinding requirements ¦ V2: Basic pathfinding and movement across simple environments ¦ V3: Core navigation functional for standard maps and gameplay scenarios ¦ V4: Reliable navigation across full game content with finalized rules, final map and compass UX/UI ¦ V5: Improve path quality, fix stuck cases, and tune performance ¦ V6: Add advanced navigation features or support for new environment types ¦ V7: Support larger worlds, more agents, and faster content generation workflows | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Instancing | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define instancing goals, player flow, server model, and technical requirements. Documentation finished ¦ V2: Basic creation and joining of isolated test instances ¦ V3: Core instancing functional for key gameplay content and party access ¦ V4: Stable instancing with matchmaking, rules, and production readiness ¦ V5: Improve load times, stability, recovery, and resource efficiency ¦ V6: Add new instance types, rulesets, or player experiences ¦ V7: Support high concurrency, automation, and efficient server capacity growth | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Day/night cycle | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Day/night cycle rules defined, documentation ready ¦ V2: Techart R&D completed to figure out technical limitations. Demo cycle set ¦ V3: Day/night change functional and configurable with placeholder visuals ¦ V4: Final configuration and visuals implemented ¦ V5: Bug fixes and optimizations ¦ V6: Special day/night conditions added ¦ V7: Improve synchronization, performance, tooling, and support for large worlds, zones, and live content systems | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Dynamic weather | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Dynamic weather limitations and rules defined with every season/weather type specifics set and change rules/restrictions ¦ V2: Techart R&D completed to figure out technical limitations. Demo weather set with switch between two states ¦ V3: 1-2 weather types functional and configurable with placeholder visuals ¦ V4: All weather types and seasons implemented with cycle rules configured ¦ V5: Bug fixes and optimizations ¦ V6: New weather types and seasons added, special conditions for new zones and events ¦ V7: Support large worlds, zone-specific weather, synchronization, live events, and efficient content control | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Combat unified | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define combat vision, pacing, depth, skill ceiling, target audience ¦ V2: Basic melee combo / attack chain Basic shooting/projectile One enemy AI that attacks/chases Damage numbers / HP loss Placeholder animations/VFX PvP prototyped Test arena only ¦ V3: Core melee + ranged both functional Several enemy archetypes Basic abilities / cooldowns Hit reactions / dodge / interrupt basics Core stats affecting combat PvE encounters playable PvP arena playable ¦ V4: Final weapon/class kits Good responsiveness / animation quality Full enemy combat behavior set Balanced TTK / progression UI clarity / FX readability Stable multiplayer sync Combo systems Status effects ¦ V5: Balance classes/builds Fix frustrating AI Improve hit feel Reduce ability spam/ clunkiness Meta adjustments ¦ V6: New weapon archetypes New enemy mechanics Advanced builds ¦ V7: Large raids with many entities Server authority improvements Ability scripting tools Combat telemetry dashboards Faster content creation pipeline | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | User Space | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Competitor research and user space functionality defined; technical research on the system support ¦ V2: Basic user space instance functionality with furniture placement; placeholder objects, VFX and UI ¦ V3: Users can create and decorate their user space (added quest to get a user space); refined UX/UI and camera position; connection between user spaces explored ¦ V4: User space obtain, decorate and visit final functionality; a roaster of user space items; user space crafting stations; stable server support; conencted user spaces ¦ V5: Bugfix and stabilization ¦ V6: More user spaces items and trophies added; user space expansion (room -> several rooms -> house -> garden etc) ¦ V7: Reuse housing systems, permissions, and content pipelines to support guild houses and future shared spaces | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Minigames | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define the minigames mechanics we need, single-player/multiplayer and plan out minigames accessibility through the game. Prepare all needed documentation ¦ V2: 1-2 minigames core implemented on temporary assets ¦ V3: 1-2 minigames are fully functional with final assets and content. Server/client support and syncronization ¦ V4: All required minigames are implemented with final assets and content. Stable server/client support, progress save, multiplayer etc ¦ V5: Bugfix and stabilization ¦ V6: New minigames added, seasonal content and rewards ¦ V7: Expanding minigames mechanics into fully functional features/events | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Items & Inventory General Feature | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Combines R&D stages of item core, inventory, equipment and loot systems ¦ V2: Basic item creation, storage, equip, and drop loop works ¦ V3: Players can obtain, store, equip, and use items in core gameplay ¦ V4: Stable, polished, scalable item ecosystem ready for live players ¦ V5: QoL, balance, exploits, performance, UX improvement ¦ V6: Crafting hooks, rarity depth, loadouts, advanced loot rules, new item types ¦ V7: Shared backend/tools supporting large content volume and future systems | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Item Core System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define item architecture, data model, types, rarity, ownership, and technical foundations ¦ V2: Basic item definitions created and recognized by the game ¦ V3: Core item properties, usage rules, stacking, and persistence functional ¦ V4: Finalized item framework supporting all planned item categories and gameplay systems ¦ V5: Fix issues, improve data workflows, and tune item logic/performance ¦ V6: Add new item categories, advanced properties, and deeper system integrations ¦ V7: Data-driven architecture and tooling supporting large item libraries and future systems | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Inventory System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define inventory rules, capacity, UX flows, storage logic, and technical requirements ¦ V2: Basic item storage with add, remove, and move actions ¦ V3: Core inventory management functional with slots, stacking, and persistence ¦ V4: Final inventory UX, sorting, rules, and stable gameplay integration ready for release ¦ V5: Improve usability, fix bugs, and optimize performance/load times ¦ V6: Add filters, presets, extra storage types, and advanced management features ¦ V7: Support high item counts, shared storage, and efficient backend/content operations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Equipment System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define equipment slots, stat impact, restrictions, and progression goals ¦ V2: Basic equip/unequip actions with simple slot support ¦ V3: Core equipment slots, stat application, and visual updates functional ¦ V4: Final equipment rules, polished UX, full item support, and stable gameplay integration ¦ V5: Balance gear progression, fix issues, and improve usability/performance ¦ V6: Add loadouts, set bonuses, cosmetic slots, and advanced gear systems ¦ V7: Support many item types, reusable slot systems, and efficient content growth pipelines | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Loot Distribution Systems | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define loot sources, ownership rules, fairness model, and reward goals ¦ V2: Basic item drops from enemies or containers ¦ V3: Core loot drops and player acquisition rules functional for gameplay loops ¦ V4: Final loot tables, party rules, rarity balance, and polished reward presentation ¦ V5: Tune drop rates, fix exploits, and improve reward pacing ¦ V6: Add smart loot, group modes, event loot, and advanced reward systems ¦ V7: Support large content libraries, automated loot pipelines, and high concurrency gameplay | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Player Economy | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define player economy pillars, currency sources and sinks, main currency flows and rules. Perform competitor research and prepare documentation ¦ V2: Basic currencies, earning/spending flows, vendor transactions, and simple player trading tested to validate core value loops ¦ V3: Core economy functional with currencies, rewards, sinks, item pricing, vendors, and basic player exchange supporting regular gameplay progression ¦ V4: Final economy functionality with antii-cheat protection, server validation etc. Platform transactions are a part of the economy. LiveOps economy is included into overall balance. Tracking and BI in place ¦ V5: Bug fixes and improvements, UX/UI optimizations, balance tweaks ¦ V6: New currency sources/sinks, new currency types, LiveOps economy expansion ¦ V7: Advanced tools, analytics, automation, and balancing systems supporting large player populations, live operations, multiple markets, and long-term economic stability | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Trading System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define player-to-player and player-to-NPC trading rules, restrictions, pricing, and security needs ¦ V2: Basic item or currency exchange with players and NPC vendors functional ¦ V3: Core player trade and NPC buy/sell flows working reliably with item and currency transfer ¦ V4: Final trading UX, pricing rules, restrictions, safeguards, and stable gameplay integration ready for release ¦ V5: Improve usability, balance prices, prevent exploits, and refine speed/stability ¦ V6: Add gifting, barter, COD mail, reputation vendors, or advanced trading features ¦ V7: Support high trade volume, many vendors, cross-server systems, automation tools, and long-term live operations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Currency System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define currencies, sources, sinks, progression role, and balancing goals ¦ V2: Basic earning and spending of core currency functional ¦ V3: Core currencies integrated with rewards, vendors, and progression loops ¦ V4: Final currency balance, sinks, UI clarity, and stable economy integration ready for release ¦ V5: Tune inflation, rewards, sinks, and fix economy issues ¦ V6: Add premium, seasonal, faction, or specialized currencies ¦ V7: Advanced balancing tools, analytics, and support for multiple currencies across live operations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Auction House | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define marketplace goals, pricing model, taxes, and anti-abuse requirements ¦ V2: Basic item listing, browsing, and purchasing functional ¦ V3: Core marketplace flow with listings, purchases, expiration, and simple search/filter tools ¦ V4: Final marketplace UX, taxes/fees, safeguards, and stable production readiness ¦ V5: Improve search, pricing clarity, performance, and abuse prevention ¦ V6: Add bidding, advanced filters, history, smart pricing, or regional markets ¦ V7: Support high listing volume, cross-server markets, automation tools, and long-term economy management | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Pets | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Pets functionality defined and described; division between functional and cosmetic pets set; pets obtain flow defined ¦ V2: Player can get a cosmetic pet and equip/summon it; placeholder model/animations/effects ¦ V3: Player can get one cosmetic and one functional pet. Pet functionality works as intended with stats/ combat/ economy/ game interactions affect tested ¦ V4: Roaster of cosmetic and functional pets with final content is ready. Final economy/combat balance and defined pets sources ¦ V5: Bug fixes, optimizations and improvements ¦ V6: New pet types, themed and partner pets, new pet functionality introduced ¦ V7: Pet customization & garments shared pets, pet upgrade and development | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Forge System | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Quest System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define quest structure, content goals, progression role, tooling needs, and technical approach ¦ V2: Basic quest creation, acceptance, objective tracking, completion, and reward flow functional ¦ V3: Core quest types, progression integration, rewards, and essential UI fully playable ¦ V4: Final quest content framework, polished UX, reliable scripting, and stable gameplay integration ready for release ¦ V5: Improve pacing, fix bugs, refine rewards, readability, and content flow based on testing ¦ V6: Add advanced quest types, branching paths, dynamic events, chains, and richer narrative systems ¦ V7: Support large content volumes, designer-friendly tools, localization pipelines, live updates, and long-term content operations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Player Chat | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Prepare GDD and TDD on chat functionality, techology and limits ¦ V2: Basic chat with placeholder UX/UI with send-receive functionality ¦ V3: Send-receive functions, slash commands, more concurrent players support. Personal/party chat ¦ V4: Final UX/UI, emoji/colored text support, expanded functionality: block/report, add to friends, LFG. Profanity filters and chat moderation tools ¦ V5: Bug fixes and optimization ¦ V6: Voice chat support, more commands added ¦ V7: Chat technology used as the basis for guild functionality and friends. Overall chat system stability and load improvements and optimizations | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Friends | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Prepare GDD and TDD on friends functionality, techology and limits ¦ V2: Basic Friend list with add/remove functionality, placeholder UI ¦ V3: Players can add, remove and block friends, open chat with them, check friends profiles, party. Adding to friends is available from different places of the game ¦ V4: Polished functionality and UX/UI implemented. Server support and syncronization across game and platform ¦ V5: Bug fixes and stability improvements ¦ V6: New friend features (gifts, etc), seasonal events for friends ¦ V7: Support large social graphs, cross-platform/cross-server connections, high concurrency, and efficient tools for managing long-term social features | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Multiplayer (Co-op, raids and dueling) | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define multiplayer architecture, modes, and rules ¦ V2: Basic co-op + simple duel + dummy raid instance ¦ V3: Functional co-op, duels, and basic raid loop ¦ V4: Polished multiplayer modes with full rulesets ¦ V5: Balance, latency fixes, UX improvements ¦ V6: New raid types, ranked duels, modifiers ¦ V7: Large-scale encounters, server optimization, tooling | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Guild System | V0: The feature is in the backlog, no one has started working on any aspect of it yet ¦ V1: Define guild goals and functionality, prepare all needed documentation and best practices/competitor research ¦ V2: Basic create and join guild functionality with placeholder UI ¦ V3: Players can create, join, leave the guild, see the list of members, chat. Guild menu exists and players can check guild info. Placeholder UI ¦ V4: Fully functional guilds with menus, guild halls, shared bank and chats. Server stability ¦ V5: Bug fixes, server stability and syncronization improvements, UX/UI optimizations ¦ V6: Guild wars/events, guild halls expansions, guild cosmetics ¦ V7: Larger guilds support and overall system improvements | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | In-game Mail | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Notifications | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | HUD & In-Game Interface | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | UI Framework & UX Standards | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Controls | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | UX Optimizations | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Accessibility | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | Presentation & Immersion | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Maturity | Feature | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Account Creation/Deletion | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Account Authentification | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Account Privacy Settings & Legal | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Player Dashboard] Player Account Features | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Player Dashboard] Game Dashboard | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Player Dashboard] Friends | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Player Dashboard] Search & Notifications | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Player Dashboard] Marketplace | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Developer Dashboard] Developer Account | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Developer Dashboard] Game Dashboard | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] [Developer Dashboard] Settings & Support | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Quest Tracking | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Platform Certification | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Payment Processing | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Online Services & Backend | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions
Couch Heroes / Game / Feature Versions / Feature Versions Maturity Map | [Platform] Launcher & Distribution | V0: The feature is in the backlog, no one has started working on any aspect of it yet | Not started | Medium |  | Implementation |  |  |  | Game Development | Platform | Foundation | high | Features V2 / Feature Versions

## AI
parent_path | title | description | status | priority | health_state | work_type | assignees | due_date | dependencies | practice_area | type | layer | confidence | source | notes
Couch Heroes / AI / Usage Policy & Governance | AI Policy: verify final presentation item | develop a clear AI policy to safeguard CH AI usage and IP | Not started | High | Red |  | Glen |  |  | Game Studio Operations |  |  |  | CSV row 46
Couch Heroes / AI / Usage Policy and Governance | Draft v1 of the studio AI Acceptable Use Policy | Single source-of-truth policy document covering scope, definitions, principles, allowed use, prohibited use, exceptions process, and review cadence. Must distinguish generative AI, predictive AI, and AI-assisted features inside the game. Owned by the Producer with Legal sign-off. | Not started | Critical ACT | Red | Implementation | Producer; Legal |  | None | AI Governance |  |  |  | Agent / AI Project | Foundation document. Needs Glen input on whether to use NBI's draft policy as a template.
Couch Heroes / AI / Usage Policy and Governance | Define what counts as "AI" within the policy | Scope definition: which tools and techniques fall under the policy (LLMs, image generators, voice synthesis, code copilots, upscalers, animation tools, automated QA bots, telemetry-driven tooling). Avoids the typical loophole of staff arguing a tool "isn't really AI". | Not started | High | Red | Implementation | Producer; Tech Lead |  | AI policy v1 draft | AI Governance |  |  |  | Agent / AI Project | Be explicit: Adobe Firefly, Photoshop generative fill, Premiere AI features, etc. all count.
Couch Heroes / AI / Usage Policy and Governance | Define acceptable internal-use cases | List the use cases the studio actively endorses: ideation, summarisation, internal documentation, code completion under review, asset reference research, internal mockups, internal localisation drafts. Must specify "internal only" boundary. | Not started | High | Yellow | Implementation | Producer; Department Heads |  | AI scope definition | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on which cases the studio leadership wants to actively encourage.
Couch Heroes / AI / Usage Policy and Governance | Define prohibited use cases | Hard prohibitions: shipping unreviewed AI output as final asset, training third-party models on Couch Heroes IP, replacing voice actors with cloned voices, using AI for any narrative on minors, using AI to generate likenesses of real people without contract. | Not started | Critical ACT | Red | Implementation | Producer; Legal |  | AI scope definition | AI Governance |  |  |  | Agent / AI Project | Voice cloning prohibition is non-negotiable post-2024 SAG-AFTRA strike.
Couch Heroes / AI / Usage Policy and Governance | Define IP safeguards in the policy | Policy clauses preventing studio confidential information, GDD content, source code, art assets, and partner IP from being submitted to public AI tools. Explicit ban on prompting with proprietary text from the GDD outside approved enterprise tools. | Not started | Critical ACT | Red | Implementation | Producer; Legal; Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Critical because partner IP exposure could breach existing licensing deals.
Couch Heroes / AI / Usage Policy and Governance | Define output ownership clarification | Per-tool clarity on who owns AI outputs (studio, individual contributor, tool vendor, no one). Reference each tool's ToS. Default position: outputs created in the course of work belong to Couch Heroes; staff may not retain personal rights. | Not started | High | Yellow | Implementation | Legal; Producer |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | Some tools (Midjourney standard tier) grant non-exclusive licences; flag those.
Couch Heroes / AI / Usage Policy and Governance | Define mandatory human review requirements | Specify which output types require human review before use: all art assets, all narrative copy, all code committed to main, all marketing copy, all communications sent to partners or platforms. Reviewer cannot be the same person who generated the output. | Not started | High | Red | Implementation | Producer; Department Heads |  | None | AI Governance |  |  |  | Agent / AI Project | This is the structural enforcement of "AI-assisted, not AI-authored".
Couch Heroes / AI / Usage Policy and Governance | Define platform-specific AI disclosure rules | Per-platform disclosure matrix: Steam (mandatory pre-recorded vs live-generated AI disclosure since Jan 2024), PlayStation, Nintendo, Xbox, Epic. Maps studio obligations to each storefront. Updated every quarter as platforms revise terms. | Not started | Critical ACT | Red | Ongoing Mgmt | Producer; Publishing Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Steam disclosure form is mandatory; non-disclosure is grounds for store removal.
Couch Heroes / AI / Usage Policy and Governance | Define vendor security review process | Security questionnaire any new AI tool must pass before use: data residency, retention, training-data opt-out, SSO support, breach history, indemnification, sub-processor list. Bound to ICO/GDPR requirements. | Not started | High | Red | Ongoing Mgmt | Tech Lead; Legal |  | None | AI Governance |  |  |  | Agent / AI Project | UK studio = ICO jurisdiction. Needs DPIA for any tool processing employee or player data.
Couch Heroes / AI / Usage Policy and Governance | Define renewal and audit cadence | Quarterly review of approved tool list, annual policy review, ad-hoc review on any platform-rules change or breach incident. Documented in a governance calendar with named owners. | Not started | Medium | Yellow | Ongoing Mgmt | Producer |  | AI policy v1 draft | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Usage Policy and Governance | Define breach response playbook | Playbook for what happens when AI policy is breached (e.g., proprietary code leaked into a public LLM, unreviewed AI asset shipped, voice cloning incident). Roles, communication tree, legal escalation, partner notification, ICO notification thresholds. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer; Tech Lead |  | AI policy v1 draft | AI Governance |  |  |  | Agent / AI Project | Mirror existing data-breach playbook structure.
Couch Heroes / AI / Usage Policy and Governance | Legal review of full policy | External legal counsel sign-off on the complete policy before staff rollout. Cover IP, employment law, GDPR, contract risk with partners, platform compliance. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; External Counsel |  | All policy items | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on whether Couch Heroes has standing legal counsel or needs introduction.
Couch Heroes / AI / Usage Policy and Governance | Staff communications and rollout plan | All-hands briefing, written FAQ, manager talking points, signed acknowledgement from every staff member that they have read and understood the policy. Acknowledgement stored in HR system. | Not started | High | Yellow | Implementation | People Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Signed acknowledgement is the audit trail when something goes wrong.
Couch Heroes / AI / Usage Policy and Governance | Establish AI Governance Committee | Standing committee meeting monthly to review tool requests, exceptions, incidents, and policy updates. Composition: Producer, Tech Lead, Legal, an Art rep, a Narrative rep, an Engineering rep. | Not started | High | Yellow | Ongoing Mgmt | Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Cross-discipline reps prevent the policy being captured by any one department.
Couch Heroes / AI / Usage Policy and Governance | Define exceptions and waivers process | Formal request form for staff who want to use a tool not on the approved list or for a use case the policy restricts. Time-bound waivers with sunset dates and named approver. | Not started | Medium | Yellow | Ongoing Mgmt | Producer |  | AI Governance Committee | AI Governance |  |  |  | Agent / AI Project | Without a clean exceptions path, staff route around the policy entirely.
Couch Heroes / AI / Usage Policy and Governance | Whistleblower channel for AI policy violations | Anonymous reporting route for staff to flag misuse without fear of retaliation. Integrate with existing HR whistleblower process if one exists, otherwise create. | Not started | Medium | Yellow | Ongoing Mgmt | People Lead; Legal |  | AI policy v1 draft | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on existing whistleblower infrastructure at Couch Heroes.
Couch Heroes / AI / Usage Policy and Governance | Map policy obligations to publisher contracts | Cross-reference the AI policy against active publisher and platform contracts. Identify clauses where the policy must be more restrictive than internal preference because a contract demands it. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Publishing Lead |  | AI policy v1 draft; Contract inventory | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on which publisher contracts are active or in negotiation.
Couch Heroes / AI / Usage Policy and Governance | Investor disclosure position on AI | Standard answer pack for the question "what is your AI usage and exposure?" used in investor calls, due diligence packs, and pitch decks. One narrative, consistent across spokespeople. | Not started | High | Yellow | Implementation | Producer; Finance |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Investors are increasingly listing AI governance in due diligence checklists.
Couch Heroes / AI / Usage Policy and Governance | Press and community position on AI | Public-facing statement on how the studio uses AI, ready for community questions. Non-defensive, specific, and refreshed when the policy changes. | Not started | High | Yellow | Implementation | Marketing; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Concept artist communities will Google this; vague answers are worse than honest ones.
Couch Heroes / AI / Usage Policy and Governance | Subcontractor and contractor AI clause | Standard clause inserted into all freelancer and outsource contracts: confirms whether the contractor is permitted to use AI in their deliverable, requires disclosure if they do, and confirms IP transfer covers AI-derived elements. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Outsource art studios are the largest single source of unattributed AI content risk.
Couch Heroes / AI / Usage Policy and Governance | Insurance review for AI-related risks | Review existing studio insurance (E&O, cyber, IP infringement) for AI-related exclusions and coverage gaps. Engage broker on AI-specific endorsements. | Not started | Medium | Yellow | Ongoing Mgmt | Finance; Legal |  | None | AI Governance |  |  |  | Agent / AI Project | Insurers are starting to add AI-output exclusions; check the small print.
Couch Heroes / AI / Usage Policy and Governance | DPIA for AI tools processing personal data | Data Protection Impact Assessment for any AI tool that touches employee or player personal data. ICO-aligned template. | Not started | High | Red | Ongoing Mgmt | Legal; Tech Lead |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | Mandatory under UK GDPR for high-risk processing.
Couch Heroes / AI / Usage Policy and Governance | Records retention rule for AI prompts and outputs | Define how long AI prompt/output logs are retained, where, and who can access. Balance audit needs against data minimisation. | Not started | Medium | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | AI policy v1 draft | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Usage Policy and Governance | Annual policy effectiveness review | Yearly retrospective on whether the policy is achieving its objectives: incidents avoided, exceptions granted, staff confidence, platform compliance status. | Not started | Low | Green | Ongoing Mgmt | Producer |  | One year of policy operation | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Usage Policy and Governance | Cross-reference NBI's AI policy as starting point | Pull NBI Analytics' existing AI usage policy as a structural template (NBI is itself a heavy AI user). Adapt for game-studio-specific risks. | Not started | Low | Green | Research | Producer |  | None | AI Governance |  |  |  | Agent / AI Project | Glen has internal NBI policy; can be supplied as a starter.
Couch Heroes / AI / Usage Policy and Governance | "AI Policy: verify final presentation item" | Existing CSV item rolled into this backlog. Confirms the AI policy is the single deliverable Couch Heroes presents externally and that the Gamescom-track build is not contingent on AI assistance that breaches the policy. | Not started | High | Red | Assessment | Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | This is the original item from the Couch Heroes CSV.
Couch Heroes / AI / Tool Selection and Licensing | Inventory current AI tools across the studio | Department-by-department survey of every AI tool currently in use, including personal accounts being used for work. Survey covers tool name, vendor, use case, who uses it, paid/free, account ownership (studio vs personal). | Not started | Critical ACT | Red | Research | Producer; Department Heads |  | None | AI Governance |  |  |  | Agent / AI Project | This is the foundation. Without this you cannot govern what you don't know about. Needs Glen input on whether the studio has done any prior audit.
Couch Heroes / AI / Tool Selection and Licensing | Licence terms review for each tool in inventory | For every tool in the inventory, capture: commercial-use rights, training-data opt-out availability, data residency, output ownership, indemnification, termination clauses. Tabulated and red/amber/green rated. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | Most consumer-tier AI tools forbid commercial use or claim a licence to outputs.
Couch Heroes / AI / Tool Selection and Licensing | Identify tools using studio data for model training | Flag any tool whose default ToS allows the vendor to train future models on studio inputs. Force-migrate to enterprise tier with training opt-out, or remove the tool. | Not started | Critical ACT | Red | Ongoing Mgmt | Tech Lead; Legal |  | Tool inventory; Licence review | AI Governance |  |  |  | Agent / AI Project | OpenAI ChatGPT free/Plus, default Midjourney, default Anthropic Claude consumer tier all need attention.
Couch Heroes / AI / Tool Selection and Licensing | Establish approved tool list (positive list) | Curated list of tools that staff are permitted to use for studio work, by department and use case. Anything not on the list requires a waiver. | Not started | Critical ACT | Red | Ongoing Mgmt | AI Governance Committee |  | Tool inventory; Licence review | AI Governance |  |  |  | Agent / AI Project | Positive list is more defensible than a blocked list.
Couch Heroes / AI / Tool Selection and Licensing | Establish blocked tool list with rationale | Explicit list of tools that are not permitted, with a one-line reason. Includes consumer-tier versions of tools whose enterprise tier is allowed. | Not started | High | Yellow | Ongoing Mgmt | AI Governance Committee |  | Tool inventory; Licence review | AI Governance |  |  |  | Agent / AI Project | Spell out the rationale; staff need to understand why, not just what.
Couch Heroes / AI / Tool Selection and Licensing | Annual licence and pricing review | Yearly review of every active subscription: usage, ROI, alternatives, price changes, ToS updates. Decision per tool: renew, downgrade, replace, retire. | Not started | Medium | Yellow | Ongoing Mgmt | Producer; Finance |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Tool Selection and Licensing | Centralised cost tracking for AI tools | Single line of sight on monthly spend across all AI tools, by department. Catches the "twelve teams each pay for their own ChatGPT" problem. | Not started | High | Yellow | Ongoing Mgmt | Finance; Producer |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | Often reveals 2-3x savings by consolidating to studio enterprise plans.
Couch Heroes / AI / Tool Selection and Licensing | Tool retirement and data egress process | When a tool is retired, define: how staff are notified, how outputs are exported and stored, how accounts are closed, how the vendor confirms deletion. | Not started | Medium | Yellow | Ongoing Mgmt | Tech Lead; Producer |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | Often skipped; leaves stale accounts with studio data sitting in vendor systems.
Couch Heroes / AI / Tool Selection and Licensing | Evaluation criteria for new AI tools | Standardised scorecard for any proposed new tool: licensing, security, ROI estimate, integration overhead, staff training cost, alternative consideration. Required input before AI Governance Committee approval. | Not started | High | Red | Ongoing Mgmt | AI Governance Committee |  | None | AI Governance |  |  |  | Agent / AI Project | Forces consistent decision-making. Otherwise it's whoever shouts loudest in the room.
Couch Heroes / AI / Tool Selection and Licensing | Proof-of-concept and pilot framework | Structured pilot process: limited user group, defined success metrics, time-boxed evaluation, exit criteria. Prevents "we've been piloting this for nine months" drift. | Not started | Medium | Yellow | Ongoing Mgmt | Tech Lead |  | Evaluation criteria | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Tool Selection and Licensing | Enterprise vs consumer tier decision matrix | Decision rules for when a tool must be on enterprise tier (any studio data, any partner IP, any code) versus when a consumer tier is acceptable (purely personal learning). | Not started | High | Yellow | Ongoing Mgmt | Tech Lead; Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Default position: studio work requires enterprise tier.
Couch Heroes / AI / Tool Selection and Licensing | SSO and identity integration for approved tools | Wherever supported, route AI tool access through studio SSO so accounts can be revoked on offboarding. No personal-email accounts for studio work. | Not started | High | Yellow | Implementation | Tech Lead; IT |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Critical for offboarding. Personal accounts cannot be revoked.
Couch Heroes / AI / Tool Selection and Licensing | Data residency mapping per tool | For each approved tool, document where data is processed (UK, EU, US, elsewhere) and whether that meets contractual obligations to partners and platforms. | Not started | High | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | UK studios increasingly need data-residency answers from publishers.
Couch Heroes / AI / Tool Selection and Licensing | Sub-processor disclosure tracking | Many AI vendors use sub-processors (OpenAI on Azure, Anthropic on AWS, etc.). Track this chain for each approved tool so studio knows the full data path. | Not started | Medium | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Required for GDPR Article 28 compliance.
Couch Heroes / AI / Tool Selection and Licensing | Training-data provenance check per tool | For each tool, document what is publicly known about its training data sources. Flag tools trained on scraped artwork without consent (mid-2024 lawsuits ongoing). | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Art Director |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Stable Diffusion, Midjourney, several open-source models have known provenance issues.
Couch Heroes / AI / Tool Selection and Licensing | Vendor financial stability check | Quick financial-health check on AI vendors holding studio data. Many are early-stage and may close. Plan for vendor failure. | Not started | Low | Green | Ongoing Mgmt | Finance; Tech Lead |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Tool Selection and Licensing | API key and credential management | All API keys and tokens stored in studio secrets manager, rotated quarterly, attributed to a named owner. No keys in source code or shared documents. | Not started | High | Red | Implementation | Tech Lead; IT |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Standard security hygiene; often missed for AI tools because they feel "small".
Couch Heroes / AI / Tool Selection and Licensing | Local-only AI tool option for sensitive work | Maintain at least one locally-run model (Ollama, LM Studio, or equivalent) for use cases where no data may leave the building. Especially relevant for unreleased GDD content and partner IP. | Not started | Medium | Yellow | Implementation | Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Slower and weaker but eliminates external data exposure.
Couch Heroes / AI / Tool Selection and Licensing | Plugin and extension governance | Many AI tools (Claude, ChatGPT, Cursor, Copilot) accept third-party plugins or extensions. Define which plugins are approved and how new ones are reviewed. | Not started | Medium | Yellow | Ongoing Mgmt | Tech Lead |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Plugins effectively bypass the tool's own security model.
Couch Heroes / AI / Tool Selection and Licensing | Browser-based AI assistant policy | Browser extensions with AI assistants (Sider, Monica, Copilot for Edge, etc.) read everything on every page. Default position: not permitted on studio devices. | Not started | High | Red | Ongoing Mgmt | Tech Lead; IT |  | Blocked tool list | AI Governance |  |  |  | Agent / AI Project | Massive data-leak vector. Often invisible to IT.
Couch Heroes / AI / Tool Selection and Licensing | Mobile device AI app policy | Define which AI apps are permitted on studio-issued or BYOD devices accessing studio data. Voice assistants are a particular risk. | Not started | Medium | Yellow | Ongoing Mgmt | Tech Lead; IT |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Tool Selection and Licensing | Open-source AI tool licence review | Open-source models often carry licences with commercial-use restrictions (e.g., LLaMA 2 community licence, Stable Diffusion RAIL). Review per use case. | Not started | High | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | LLaMA 2 has user-count thresholds; some "free" models become paid above 700M MAU.
Couch Heroes / AI / Tool Selection and Licensing | Cost-per-output benchmarking | Where multiple tools serve the same use case (e.g., concept ideation), benchmark cost per useful output. Inform consolidation decisions. | Not started | Low | Green | Research | Producer; Finance |  | Cost tracking | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Tool Selection and Licensing | Cross-reference tool list against publisher allow-lists | Some publishers maintain lists of approved or banned AI tools for licensed projects. Cross-check the studio's approved list against any partner's list. | Not started | High | Yellow | Ongoing Mgmt | Publishing Lead; Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on which publishers are involved and whether they have published lists.
Couch Heroes / AI / Tool Selection and Licensing | Tool category gap analysis | Identify use cases where staff need an AI tool but no approved option exists, leading to shadow IT. Active gap-filling reduces policy circumvention. | Not started | Medium | Yellow | Research | AI Governance Committee |  | Approved tool list; Tool inventory | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Foundational AI literacy programme for all staff | One-hour module covering: what generative AI is, what it cannot do, how it can fail, why it matters for a games studio, how the studio's policy works. Mandatory for all staff including non-technical roles. | Not started | Critical ACT | Red | Implementation | People Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Without baseline literacy, the policy cannot be enforced because staff cannot interpret it.
Couch Heroes / AI / Training and Education | Designer-specific AI training module | Module for designers covering: ideation use cases, prohibited use cases, how to brief AI tools to get useful output, how to keep iteration loops with the team, why AI is not a substitute for design judgement. | Not started | High | Yellow | Implementation | Design Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Programmer-specific AI training module | Module for engineers covering: code copilot use, security risks of pasting code into LLMs, licence-aware prompting, mandatory review process for AI-suggested code, prohibited repos and codebases for AI tools. | Not started | High | Yellow | Implementation | Tech Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Heavily test-coupled; should reference the studio's CI gating rules.
Couch Heroes / AI / Training and Education | Artist-specific AI training module | Module for artists covering: when AI is acceptable for reference and ideation, when it is prohibited (final asset, character likeness, style transfer of named artists), platform disclosure obligations, community-perception risks. | Not started | Critical ACT | Red | Implementation | Art Director; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Highest reputational risk department. Must be precise.
Couch Heroes / AI / Training and Education | Producer-specific AI training module | Module for producers covering: how to estimate work that involves AI, how to review schedules for AI-related risk, how to enforce policy in sprint planning, how to escalate breaches. | Not started | Medium | Yellow | Implementation | Producer; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | QA-specific AI training module | Module for QA covering: AI-assisted test case generation, AI-assisted bug triage, what AI cannot reliably test, how to validate that AI testing tools haven't missed anything. | Not started | Medium | Yellow | Implementation | QA Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Gaming QA has been an early adopter of AI tooling; needs structure.
Couch Heroes / AI / Training and Education | Writer-specific AI training module | Module for narrative team covering: ideation use, prohibition on shipped narrative copy without rewrite, voice consistency risks, partner-IP narrative safeguards, lore continuity risks from generated text. | Not started | High | Yellow | Implementation | Narrative Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Narrative is a high-disclosure category on Steam.
Couch Heroes / AI / Training and Education | Marketing and community team AI training | Module for marketing covering: AI use in copy and imagery, disclosure requirements, community perception of AI marketing assets, social listening tools that use AI. | Not started | High | Yellow | Implementation | Marketing Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Community can detect AI marketing imagery quickly; sensitivity is high.
Couch Heroes / AI / Training and Education | Voice and audio team AI training | Module covering voice cloning prohibitions, music model licensing risks, sound effect generation, union obligations in voice work, mixing AI-assisted and human-recorded audio. | Not started | Critical ACT | Red | Implementation | Audio Director; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Post-2024 SAG-AFTRA strike; this is one of the highest-risk areas.
Couch Heroes / AI / Training and Education | Onboarding AI module for new starters | AI literacy and policy module added to standard onboarding, completed before new staff get access to AI tools. Acknowledgement signed during onboarding. | Not started | High | Yellow | Implementation | People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | External speaker series on AI in games | Quarterly or bi-annual session bringing in external speakers (academic, legal, industry, union reps) to broaden internal thinking. Open to whole studio. | Not started | Low | Green | Implementation | People Lead |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Internal AI working group | Standing cross-discipline group meeting monthly to share experiments, surface new tools, raise risks. Pipeline into the AI Governance Committee for formal decisions. | Not started | High | Yellow | Ongoing Mgmt | Producer |  | None | AI Governance |  |  |  | Agent / AI Project | Where the actual learning happens; the policy alone won't drive adoption.
Couch Heroes / AI / Training and Education | Best-practice prompt library | Internal library of vetted prompts and prompt patterns by use case: concept ideation, code review, narrative draft, summarisation. Reduces the "everyone reinvents prompting" problem. | Not started | Medium | Yellow | Implementation | AI Working Group |  | Internal AI working group | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Prompt engineering training course | Hands-on course covering structured prompting, chain-of-thought, few-shot, output formatting, evaluation. Open to any staff member. | Not started | Medium | Yellow | Implementation | Tech Lead; People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Internal AI failure case library | Curated library of real failure modes: hallucinated lore, wrong citations, plausible-but-wrong code, copyright collisions, biased outputs. Used in training to build healthy scepticism. | Not started | High | Yellow | Implementation | AI Working Group |  | None | AI Governance |  |  |  | Agent / AI Project | Most effective single training intervention. Concrete examples beat abstract warnings.
Couch Heroes / AI / Training and Education | Refresher training cadence | Annual refresher for all staff, triggered earlier if policy changes or major industry incident occurs. | Not started | Medium | Yellow | Implementation | People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Manager training on AI policy enforcement | Module specifically for managers and leads on how to spot policy breaches, how to handle conversations about AI use, how to escalate, how to approve exceptions. | Not started | High | Yellow | Implementation | People Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | The policy lives or dies at the manager-direct-report layer.
Couch Heroes / AI / Training and Education | Contractor and freelancer briefing pack | Short document and acknowledgement form given to every contractor at engagement, covering studio AI rules and disclosure obligations. | Not started | High | Yellow | Implementation | Producer; Legal |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Contractors are typically the weakest compliance link.
Couch Heroes / AI / Training and Education | Knowledge base of approved tool how-tos | Per-tool how-to guides for the approved tool list. Lowers friction so staff stay on approved tools rather than going off-piste. | Not started | Medium | Yellow | Implementation | AI Working Group |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Tabletop exercise on AI incidents | Quarterly tabletop run-throughs of AI incident scenarios (leaked code, voice cloning complaint, platform-disclosure failure). Tests the breach playbook. | Not started | Medium | Yellow | Ongoing Mgmt | Producer; Legal |  | Breach response playbook | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Cross-training with NBI or external AI consultancy | Bring in external expertise (NBI Analytics or equivalent) for advanced topics where in-house knowledge is thin. Avoid the "AI literacy gap = AI policy gap" trap. | Not started | Low | Green | Implementation | Producer |  | None | AI Governance |  |  |  | Agent / AI Project | Glen's NBI infrastructure is a candidate provider.
Couch Heroes / AI / Training and Education | Department lead AI champion programme | Named AI champion in each department who attends working group, fields department questions, surfaces emerging needs. | Not started | Medium | Yellow | Ongoing Mgmt | Producer |  | Internal AI working group | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Critical-thinking module on AI bias and limits | Module on the limits of LLMs, image models, and predictive systems: hallucination, bias, training-data cutoff, brittleness. Important for staff who haven't worked with these tools deeply. | Not started | High | Yellow | Implementation | People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | Most underrated training topic.
Couch Heroes / AI / Training and Education | Q&A session series with Legal and Producer | Recurring open Q&A where staff can ask anonymous questions about AI policy and use without risk. Surfaces real concerns the policy misses. | Not started | Medium | Green | Implementation | Producer; Legal |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Training completion tracking and reporting | Dashboard showing completion rates of mandatory AI training by team. Reported quarterly to leadership. | Not started | Medium | Yellow | Ongoing Mgmt | People Lead |  | Foundational literacy module | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Industry-event attendance for AI topics | Budget and approvals process for staff to attend AI-relevant industry events (GDC AI track, Develop, AIAS, IGN Fan Fest panels, regional games AI summits). | Not started | Low | Green | Ongoing Mgmt | Producer; Finance |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Training and Education | Internal Wiki section on AI governance | Single discoverable home for the policy, approved tools, training materials, FAQ, and contact points. Linked from staff onboarding and from every department's page. | Not started | High | Yellow | Implementation | People Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Discoverability is the difference between a policy used and a policy ignored.
Couch Heroes / AI / Production Integration | AI-assisted concept art guidelines | Department guideline document: when concept artists may use AI for ideation and reference, when they may not, mandatory human-redraw step before any output enters the asset pipeline, attribution rules. Includes good and bad examples. | Not started | Critical ACT | Red | Implementation | Art Director; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | The single highest community-perception risk. Must be specific, not aspirational.
Couch Heroes / AI / Production Integration | AI-assisted code generation guidelines | Engineering guideline: which repos and codebases AI tools may see, mandatory human review for any AI-suggested code, licence-aware prompting, prohibition on AI-generated commits without review tags, exclusions for security-sensitive code. | Not started | Critical ACT | Red | Implementation | Tech Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Code generation is the highest-volume AI use case in most studios.
Couch Heroes / AI / Production Integration | AI-assisted narrative writing guidelines | Narrative guideline: AI for brainstorming and structural exploration, prohibition on shipped quest text without full rewrite by human writer, lore consistency check, character-voice preservation rules. | Not started | High | Yellow | Implementation | Narrative Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Couch Heroes' "no disposable photo-copied quests" pillar makes this especially important.
Couch Heroes / AI / Production Integration | AI-assisted asset pipeline assessment | Map every step in the art pipeline (concept, modelling, texturing, rigging, animation, VFX) and identify where AI could legitimately accelerate work, where it cannot, and where the risk outweighs the benefit. | Not started | High | Yellow | Research | Art Director; Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Required before any pipeline tool decision. Otherwise the studio is buying tools without a target use case.
Couch Heroes / AI / Production Integration | Quality gates for AI-generated content | Define gating criteria any AI-influenced asset must pass before integration: human review, IP check, style consistency check, technical spec check, test coverage where applicable. | Not started | Critical ACT | Red | Ongoing Mgmt | Producer; Department Heads |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Quality gate is the structural enforcement layer.
Couch Heroes / AI / Production Integration | Per-discipline review and sign-off workflow | Sign-off matrix: who must approve AI-influenced output before it enters main builds. Different rules per asset category. Documented in JIRA/Hansoft templates. | Not started | High | Yellow | Ongoing Mgmt | Producer; Department Heads |  | Quality gates | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Asset attribution metadata standard | Every asset in the pipeline carries metadata indicating: human-authored / AI-assisted / AI-derived, tools used, prompts used, reviewer. Required for audit, platform disclosure, and IP defence. | Not started | Critical ACT | Red | Implementation | Tech Lead; Producer |  | None | AI Governance |  |  |  | Agent / AI Project | This is the audit trail. Without it, no defensible disclosure is possible.
Couch Heroes / AI / Production Integration | Audit trail requirements per asset category | Define what counts as a sufficient audit trail per asset category (concept, model, texture, animation, VFX, audio, code, text). Some need full prompt history, some need only flag. | Not started | High | Yellow | Ongoing Mgmt | Producer; Tech Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | AI-assisted upscaling and texture enhancement guidelines | Specific rules for upscaling tools (ESRGAN, Topaz, etc.) used on textures and reference imagery. These are widely used and often forgotten in policy. | Not started | Medium | Yellow | Implementation | Art Director; Tech Lead |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Upscaling tools are used quietly across most studios; surface them.
Couch Heroes / AI / Production Integration | AI-assisted animation assistance guidelines | Rules for tools that retarget, clean, or generate animation (Cascadeur, DeepMotion, RADiCAL, Move.ai). Particularly fraught with motion-capture actor likeness issues. | Not started | High | Yellow | Implementation | Animation Lead; Legal |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Mocap actor likeness rights are an emerging litigation area.
Couch Heroes / AI / Production Integration | AI-assisted voice and audio guidelines | Rules for voice synthesis, voice cloning prohibition, AI-generated SFX, AI-assisted music, mastering tools. Includes union-obligation flagging and mandatory contract clauses for voice actors. | Not started | Critical ACT | Red | Implementation | Audio Director; Legal |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Voice cloning prohibition must be unambiguous and contract-enforced.
Couch Heroes / AI / Production Integration | AI-assisted localisation guidelines | Rules for using AI in localisation: machine translation as draft only, human linguist review mandatory for all shipped strings, cultural review unchanged, partner-IP language preservation. | Not started | High | Yellow | Implementation | Localisation Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Common cost-cutting target; usually goes wrong.
Couch Heroes / AI / Production Integration | AI-assisted QA tooling guidelines | Rules for AI-assisted test generation, automated bug triage, automated regression analysis, AI-driven smoke tests. What can be automated vs what must remain human-driven. | Not started | Medium | Yellow | Implementation | QA Lead; Tech Lead |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | AI in marketing asset creation guidelines | Rules for marketing imagery, social copy, trailer assistance, B-roll generation. Public-facing means highest scrutiny. | Not started | High | Yellow | Implementation | Marketing Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Public AI marketing imagery has triggered review-bombing in 2024-2026.
Couch Heroes / AI / Production Integration | Steam AI disclosure form workflow | Operational workflow for completing and updating the Steam AI disclosure form: who fills it, who reviews, when it must be updated, what happens if disclosure changes mid-development. | Not started | Critical ACT | Red | Ongoing Mgmt | Producer; Publishing Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | Mandatory for every Steam release; cannot be left to launch week.
Couch Heroes / AI / Production Integration | PlayStation, Xbox, Nintendo, Epic disclosure workflow | Equivalent workflow for each non-Steam platform with AI disclosure obligations. Tracked separately because requirements differ. | Not started | Critical ACT | Red | Ongoing Mgmt | Producer; Publishing Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | Console platforms are catching up to Steam; expect tightening.
Couch Heroes / AI / Production Integration | AI-assisted UI/UX design guidelines | Rules for AI in UI mockup generation, layout exploration, copywriting on UI strings, accessibility checks. | Not started | Medium | Yellow | Implementation | UX Lead; Producer |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | AI-generated content removal procedure | Defined procedure for pulling AI-generated content from a build if a problem is discovered: which assets, how to identify them via metadata, fallback assets, time-to-replace estimate. | Not started | High | Yellow | Ongoing Mgmt | Tech Lead; Producer |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | If a model later turns out to be tainted, the studio needs to act fast.
Couch Heroes / AI / Production Integration | Partner-IP firewall in AI workflows | Hard rule: assets, copy, or code derived from partner IP cannot be passed through public AI tools. Enforcement via tooling restrictions, not just policy. | Not started | Critical ACT | Red | Implementation | Tech Lead; Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Couch Heroes' partner integration model means this is a contractual obligation.
Couch Heroes / AI / Production Integration | Pipeline integration testing for AI tools | Before any AI tool enters the production pipeline, run integration testing: file format compatibility, source-control implications, build-time impact, asset-bake impact. | Not started | Medium | Yellow | Implementation | Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Often missed; AI tools land in pipelines without testing the pipeline.
Couch Heroes / AI / Production Integration | Reviewer training for AI-output review | Reviewers signing off on AI output need specific training on what to look for: hallucination, plausibility traps, copyright collision, style drift, security flaws. | Not started | High | Yellow | Implementation | Producer; Department Heads |  | Quality gates | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Sprint-planning AI-impact tag | New JIRA/Hansoft tag for sprint items that involve AI assistance, so sprint reviews can track AI usage in completed work. | Not started | Medium | Green | Ongoing Mgmt | Producer |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Outsource studio AI disclosure requirement | Any outsource partner delivering assets must disclose what AI was used and provide audit trail. Backed by contractual clause. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer |  | Subcontractor and contractor AI clause | AI Governance |  |  |  | Agent / AI Project | Largest unknown surface area in most studios.
Couch Heroes / AI / Production Integration | AI-generated asset rejection criteria | Defined criteria for refusing to integrate an AI-generated asset: provenance unclear, IP risk, quality below bar, style inconsistent. Reviewer's right to reject is explicit. | Not started | High | Yellow | Ongoing Mgmt | Producer; Department Heads |  | Quality gates | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Concept artist red-line process | Specifically for the concept art workflow: every AI-influenced concept goes through a named human concept artist who redraws, modifies, or rejects. Output credited to the human artist, not the AI tool. | Not started | Critical ACT | Red | Ongoing Mgmt | Art Director |  | AI-assisted concept art guidelines | AI Governance |  |  |  | Agent / AI Project | This is how the studio defends against the concept artist boycott concerns.
Couch Heroes / AI / Production Integration | AI-assisted prototyping guidelines | Distinct rules for AI use in prototyping (lower bar, throwaway code) versus production code (full review). Allows velocity in prototyping without leaking into production. | Not started | Medium | Yellow | Implementation | Tech Lead |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Generated content tagging in source control | Source-control hooks or pre-commit checks that prompt the committer to flag AI-derived content. Provides automated audit trail. | Not started | Medium | Yellow | Implementation | Tech Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Build-pipeline AI usage report | Automated report at every build showing aggregate count of AI-tagged assets and code, by category. Visible in producer dashboards. | Not started | Low | Green | Implementation | Tech Lead; Producer |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / Production Integration | Discipline-specific FAQ on AI integration | Living FAQ per discipline answering "can I use AI for X" questions surfaced by staff. Maintained by the AI Working Group. | Not started | Medium | Yellow | Implementation | AI Working Group |  | Internal AI working group | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Audit AI clauses in active publisher contracts | Read every active publisher and platform contract for AI-related clauses: warranty of human authorship, indemnification, audit rights, termination triggers. Build a clause matrix. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Publishing Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on which contracts are in scope. Some 2024-2026 publisher contracts include AI warranties that the studio may already be tripping.
Couch Heroes / AI / IP Safeguards | Audit AI clauses in partner-IP licensing agreements | Couch Heroes' partner-game integration model brings external IP into the world. Each licensing contract needs an AI-clause review: can partner IP be processed by AI tools, are derivatives owned by partner or studio, are AI-generated promotional images permitted. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Publishing Lead |  | None | AI Governance |  |  |  | Agent / AI Project | This is a structural risk because the partner-integration model is a Couch Heroes pillar.
Couch Heroes / AI / IP Safeguards | Confirm training data sources are clean for each tool | For each approved tool, document the vendor's published position on training data and any active litigation. Flag tools whose training-data position is unsettled. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Tech Lead |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Stable Diffusion, Midjourney, Suno, several others have unresolved litigation as of 2026.
Couch Heroes / AI / IP Safeguards | Output ownership clarification per tool | For each approved tool, capture in writing: who owns outputs, what licence the studio holds, can the studio commercialise, does the vendor retain rights. Stored in tool inventory. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Many vendors grant non-exclusive licences; this is not the same as ownership.
Couch Heroes / AI / IP Safeguards | Trademark and copyright check process for AI assets | Workflow: any AI-generated asset entering production gets a reverse-image search and trademark database check before sign-off. Automated where possible. | Not started | High | Yellow | Ongoing Mgmt | Legal; Art Director |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | Catches accidental brand or character collisions before they become a takedown notice.
Couch Heroes / AI / IP Safeguards | Open-source AI tool licensing review | Specific deep-dive on open-source AI models in use: licence type, commercial-use permission, attribution requirements, derivative-work obligations, MAU thresholds. | Not started | High | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | Tool inventory | AI Governance |  |  |  | Agent / AI Project | LLaMA, Stable Diffusion, Mistral, Whisper all have nuanced terms.
Couch Heroes / AI / IP Safeguards | Takedown and removal process for AI-derived assets | Defined process for receiving an IP claim against an AI-derived asset, investigating, removing if warranted, replacing with clean asset, communicating with claimant. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Tech Lead; Producer |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | Speed matters; most platforms expect response within days.
Couch Heroes / AI / IP Safeguards | Source-control flagging of AI-generated content | Required tag in commit messages or asset metadata identifying AI-derived content. Enables fast filtering during incident response. | Not started | High | Yellow | Implementation | Tech Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | Same control listed in Production Integration; cross-listed because IP-incident response depends on it.
Couch Heroes / AI / IP Safeguards | Legal indemnification position for AI tools | For each approved tool, document the vendor's IP indemnification: do they cover the studio if outputs infringe, what are the conditions, what is the cap. | Not started | High | Yellow | Ongoing Mgmt | Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | OpenAI Enterprise, Microsoft Copilot, Adobe Firefly offer indemnification with conditions. Worth pursuing.
Couch Heroes / AI / IP Safeguards | Establish IP defensibility narrative | Public-facing narrative the studio can stand behind on AI and IP: "human-authored core, AI-assisted only where disclosed, no shipped voice or likeness cloning, full audit trail." Used in press, investor, and partner contexts. | Not started | High | Yellow | Implementation | Producer; Marketing |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Coherent narrative > defensive scrambling at incident time.
Couch Heroes / AI / IP Safeguards | Voice actor likeness and consent contract clause | Standard clause in voice actor contracts: explicit rights granted, prohibition on AI training use, prohibition on voice cloning beyond contract scope, residuals for AI re-use. SAG-AFTRA-aligned where applicable. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Audio Director |  | None | AI Governance |  |  |  | Agent / AI Project | Post-2024 SAG-AFTRA strike standard. UK Equity has parallel demands.
Couch Heroes / AI / IP Safeguards | Mocap and performance capture AI clause | Clause in performance capture contracts addressing AI use of captured data, retraining prohibitions, likeness protection, and re-use scope. | Not started | High | Yellow | Ongoing Mgmt | Legal; Animation Lead |  | None | AI Governance |  |  |  | Agent / AI Project | Performance capture is a related but distinct risk to voice.
Couch Heroes / AI / IP Safeguards | Concept artist contract AI clause | Clause in concept artist contracts confirming output is human-authored or, if AI-assisted, disclosed and approved. Protects studio against post-hoc claims. | Not started | High | Yellow | Ongoing Mgmt | Legal; Art Director |  | None | AI Governance |  |  |  | Agent / AI Project | Cuts both ways: also confirms artist hasn't trained models on studio-supplied references.
Couch Heroes / AI / IP Safeguards | Player UGC and AI policy interface | If players can submit user-generated content (community art, mods, screenshots), define how AI-generated submissions are handled and whether disclosure is required. | Not started | Medium | Yellow | Implementation | Community; Legal |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Trademark portfolio review for AI risk | Review studio's own trademarks and IP for AI-related dilution risk: are bots scraping in-game brand names, are AI tools generating outputs that resemble studio IP, monitor accordingly. | Not started | Medium | Yellow | Ongoing Mgmt | Legal; Marketing |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Monitor active AI-IP litigation | Standing watch on the AI-IP litigation landscape (NYT v OpenAI, Getty v Stability, Concord Music v Anthropic, ongoing concept artist class actions). Quarterly summary to AI Governance Committee. | Not started | High | Yellow | Ongoing Mgmt | Legal |  | None | AI Governance |  |  |  | Agent / AI Project | Settlements and rulings will reshape vendor liability and tool eligibility.
Couch Heroes / AI / IP Safeguards | Insurance position on AI-IP claims | Confirm whether E&O and IP infringement insurance covers AI-derived assets. Push broker for explicit coverage or accept exclusion in writing. | Not started | High | Yellow | Ongoing Mgmt | Finance; Legal |  | Insurance review | AI Governance |  |  |  | Agent / AI Project | Often a hidden exclusion; surface it.
Couch Heroes / AI / IP Safeguards | Platform takedown response playbook | Playbook for handling a platform-issued takedown of AI-derived content: triage, replacement, comms, post-mortem. Distinct from a third-party DMCA. | Not started | High | Yellow | Ongoing Mgmt | Producer; Legal |  | Takedown and removal process | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | DMCA response playbook for AI-derived content | DMCA-specific response process: counter-notice criteria, evidence requirements (audit trail), deadlines, escalation. | Not started | High | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Partner notification process for AI-derived partner content | If AI is used in producing partner-related content (promo art for a partner game's quest line, partner-themed cosmetic), notify partner with audit trail before publication. | Not started | Critical ACT | Red | Ongoing Mgmt | Producer; Publishing Lead |  | Approved final policy | AI Governance |  |  |  | Agent / AI Project | Partner contracts may require pre-approval; default to disclosing.
Couch Heroes / AI / IP Safeguards | Voice actor union liaison plan | Identify which actor unions (Equity UK, SAG-AFTRA for US talent) Couch Heroes will work with and document their AI position. Maintain a liaison contact. | Not started | High | Yellow | Ongoing Mgmt | Audio Director; Producer |  | None | AI Governance |  |  |  | Agent / AI Project | Needs Glen input on whether the studio is using union or non-union talent.
Couch Heroes / AI / IP Safeguards | Fan community communication position | Pre-drafted messaging on AI use ready for community manager, addressing common community concerns: "are you using AI to replace artists" "is the lore AI-generated" "are voice actors being cloned". Honest, specific, refreshed quarterly. | Not started | High | Yellow | Implementation | Community; Marketing |  | IP defensibility narrative | AI Governance |  |  |  | Agent / AI Project | Communities will detect evasion faster than they detect AI.
Couch Heroes / AI / IP Safeguards | Pre-launch IP audit | Before any external release (Gamescom build, alpha, beta, launch), full audit of all AI-derived content in the build against IP register, audit trail, and disclosure obligations. Sign-off by Legal. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer |  | Asset attribution metadata standard | AI Governance |  |  |  | Agent / AI Project | The single highest-leverage gate. Catches everything before it ships.
Couch Heroes / AI / IP Safeguards | Investor due diligence pack on AI/IP | Standard pack for investor due diligence covering tool list, policy, audit process, indemnification position, contract clauses, current incidents. Refreshed quarterly. | Not started | High | Yellow | Implementation | Producer; Finance |  | All IP safeguard items | AI Governance |  |  |  | Agent / AI Project | Investors are starting to score this in due diligence.
Couch Heroes / AI / IP Safeguards | Vendor breach notification clause | Contractual requirement for AI vendors to notify the studio within a defined window if their tool's training data, ToS, or ownership terms change in a way that affects studio outputs. | Not started | Medium | Yellow | Ongoing Mgmt | Legal |  | Approved tool list | AI Governance |  |  |  | Agent / AI Project | Ahead of the curve, but worth attempting in negotiation.
Couch Heroes / AI / IP Safeguards | Cross-check Gamescom build for AI-derived content | Specific pre-Gamescom audit on the demo build: every asset, every line of code, every audio clip, every UI string. Disclosure-ready before show floor. | Not started | Critical ACT | Red | Ongoing Mgmt | Legal; Producer; Department Heads |  | Pre-launch IP audit | AI Governance |  |  |  | Agent / AI Project | Demo builds get more scrutiny than retail because press are watching for stories.
Couch Heroes / AI / IP Safeguards | Maintain "human-only" reference build | Maintain at least one full content category (e.g., main character art, principal voice) with documented zero AI involvement, as a defensibility anchor. | Not started | Medium | Yellow | Ongoing Mgmt | Producer; Department Heads |  | None | AI Governance |  |  |  | Agent / AI Project | Useful both for marketing and for legal defence.
Couch Heroes / AI / IP Safeguards | Reverse-image search service for asset checks | Operational tooling: subscription to a reverse-image-search service or pipeline integration so any AI-generated asset can be checked against a corpus before release. | Not started | Medium | Yellow | Implementation | Tech Lead; Art Director |  | Trademark and copyright check process | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Retention and disposal of AI prompts and outputs | Define retention periods for AI prompt logs, outputs, and intermediate assets in a way that supports IP defence without retaining unnecessary risk. Aligns with records retention rule. | Not started | Medium | Yellow | Ongoing Mgmt | Legal; Tech Lead |  | None | AI Governance |  |  |  | Agent / AI Project | None
Couch Heroes / AI / IP Safeguards | Quarterly IP-and-AI risk review | Standing quarterly review by the AI Governance Committee covering: new litigation, new platform rules, new vendor terms, new partner contracts, incidents, near-misses. Output: action items for the next quarter. | Not started | High | Yellow | Ongoing Mgmt | AI Governance Committee |  | AI Governance Committee | AI Governance |  |  |  | Agent / AI Project | The cadence ensures the work keeps up with the field.

## _VALIDATION
Severity | Issue | Detail
REVIEW | Missing or TBD assignee | Couch Heroes / Studio Business / BD ¦ Player target Segments
REVIEW | Missing or TBD assignee | Couch Heroes / Studio Business / BD ¦ Go To Market Strategy
REVIEW | Missing or TBD assignee | Couch Heroes / HR / 1:1s - Weekly Programme ¦ Establish and maintain one-on-ones with Dino
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - QA ¦ Set up one with Hannah
REVIEW | Missing or TBD assignee | Couch Heroes / Studio Operations / IT & Systems ¦ Review and assess primary tool set, specifically test rail and purchase tool set
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - QA ¦ Align with Hannah on overall team size at phases of development
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Coaching Programme ¦ Coaching Programme
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Art ¦ Hire: TECHNICAL ANIMATOR (HIRED)
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Engineering ¦ Hire: CTO
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Production & Design ¦ Hire: EXECUTIVE PRODUCER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Production & Design ¦ Hire: LEVEL DESIGN LEAD
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Art ¦ Hire: SR CHARACTER MODELER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Engineering ¦ Hire: JIRA ADMIN CONTRACTOR
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: HR OPERATIONS
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Art ¦ Hire: LEAD ANIMATOR (HIRED)
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Engineering ¦ Hire: LEAD FULL STACK DEVELOPER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Engineering ¦ Hire: LEAD GAMEPLAY DEVELOPER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Engineering ¦ Hire: SNR NETWORK ENGINEER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: HEAD OF FINANCE
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Production & Design ¦ Hire: GAME DESIGN LEAD
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Production & Design ¦ Hire: ART PRODUCER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - QA ¦ Hire: MID QA TESTER (CONTRACT)
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Production & Design ¦ Hire: UI/UX LEAD (NEW)
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: IT LEAD
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Engineering ¦ Hire: TOOLS ENGINEER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Production & Design ¦ Hire: TECH PRODUCER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Art ¦ Hire: SNR TECHNICAL ARTIST
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Production & Design ¦ Hire: SENIOR LEVEL DESIGNER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Art ¦ Hire: SNR ENVIRO ARTIST
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - QA ¦ Hire: MID QA TESTER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Art ¦ Hire: SR VFX ARTIST
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Production & Design ¦ Hire: MID GENERAL DESIGNER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Audio ¦ Hire: AUDIO MENTOR (3-MONTH CONTRACT)
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Production & Design ¦ Hire: ASSOC PRODUCER
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Art ¦ Hire: SNR LIGHTING ARTIST
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Art ¦ Hire: LEAD CONCEPT ARTIST
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Audio ¦ Hire: AUDIO LEAD
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Headcount Totals
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: COGS Headcount
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: S&M Headcount
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: R&D Headcount
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: G&A Headcount
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Total Headcount
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Salary Totals
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Basic Salary Subtotals
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Basic COGS Salaries
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Basic S&M Salaries
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Basic R&D Salaries
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Basic G&A Salaries
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Basic Salary Subtotal
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Loaded Salary Subtotals
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: (Incl. benefits, employer taxes, + annual raises)
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Loaded COGS Salaries
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Loaded S&M Salaries
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Loaded R&D Salaries
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Loaded G&A Salaries
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Total Salaries (Loaded)
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Recruiting Fees
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Loaded Salaries + Recruiting
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Salary Assumptions
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Payroll Load (Benefits & Taxes)
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Annual Salary Increase %
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Operations ¦ Hire: Recruiting Fee %
REVIEW | Missing or TBD assignee | Couch Heroes / HR / Hiring Pipeline - Art ¦ Hire: Recruiting Start Month
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Player Progression System / [CC & Management] Character Stats ¦ [CC & Management] Character Stats ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Player Progression System / [CC & Management] Character Stats ¦ Stats Affect Interactions ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System ¦ [Talent] Skills Trees ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Player Progression System / Talent/Skill System / [Talent] Skills Trees ¦ [Talent] Skill system design ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management ¦ Character Creation & Management ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management ¦ [CC & Management] Character Management ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / maybe will go under professions / Character Creation & Management / [CC & Management] Character Management ¦ [CC & Management] Character rename ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Appearance customization ¦ [CC & Management] Appearance customization ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Appearance customization ¦ [CC & Management] Race/species selection ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Appearance customization ¦ [CC & Management] Appearance presets/randomizer ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Garment System ¦ [CC & Management] Garment Presets ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] Garment System ¦ [CC & Management] Garment Customization ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / maybe will go under professions / [CC & Management] CC & Garment UI ¦ [CC & Management] CC & Garment Menus ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Corruption / [Corruption] Corruption Implementation ¦ [World & Zones] Black Hole R&D ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Sprinting/stamina ¦ Speedup Archways Animations ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Swimming/breath ¦ Water detection ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Swimming/breath ¦ Swimming water effects ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Swimming/breath ¦ Drowning/damage in the water ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics ¦ Gliding ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics ¦ Grappling Hooks ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics ¦ Ziplines ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics ¦ Launch pads ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics ¦ Cannons ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Traversal Mechanics ¦ Climbing ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Movement System / [Movement System] Mounts/vehicles ¦ Various vehicles types ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Navigation ¦ Navigation ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Navigation ¦ Height detection ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Navigation ¦ [World & Zones] Fog-of-war reveal ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Navigation ¦ [World & Zones] Fast travel / waypoints ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Navigation ¦ [World & Zones] Fall damage ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Instancing ¦ Instancing ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Instancing ¦ [World & Zones] Instancing ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Instancing ¦ [World & Zones] Dungeon instances ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Day/night cycle ¦ Day/night cycle ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Dynamic weather ¦ Dynamic weather ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Dynamic weather ¦ [World & Zones] Interactable objects ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Dynamic weather ¦ Destructibles ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / World Systems / Dynamic weather ¦ [World & Zones] Resource nodes ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework ¦ [Core Combat] Combat encounter reset conditions ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework ¦ [Core Combat] Death & respawn ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework / [Core Combat] Death & respawn ¦ [Core Combat] Downed state ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework / [Core Combat] Death & respawn ¦ [Core Combat] Revive / resurrection ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Framework / [Core Combat] Death & respawn ¦ [Core Combat] Combat resurrection limits ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems ¦ [Core Combat] Combat Effect Systems ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems ¦ [Core Combat] Rested/bonus XP ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems ¦ [Core Combat] Player Status Effects ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Effect Systems / [Core Combat] Player Status Effects ¦ Water/fire, water/electricity etc ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing ¦ [Core Combat] Combat Hit & Damage Processing ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing ¦ [Core Combat] Hit resolution ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Hit & Damage Processing ¦ [Core Combat] Cooldown reduction stacking rules ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Interactions ¦ [Core Combat] Combat Interactions ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat Interactions ¦ [Core Combat] Dual Wielding ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat ¦ [Core Combat] Ranged Combat ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat ¦ Ranged - Firearms ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat ¦ Ranged - Two-handed weapons ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Ranged Combat ¦ Ranged - Ammo ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior ¦ [Core Combat] Mob spawning & population ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior ¦ [Core Combat] Named/rare spawns ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] AI Combat Behavior ¦ [Core Combat] Line-of-sight & cover checks ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System ¦ [Core Combat] Battleground arenas ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System ¦ [Core Combat] World PvP objectives ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System ¦ [Core Combat] MMR / ranking ladder ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System ¦ [Core Combat] Anti-wintrading detection ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System ¦ [Core Combat] Spectator mode ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System ¦ [Core Combat] PvP gear normalization ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System ¦ [Core Combat] Queue types (solo/duo/premade) ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] PvP Combat System ¦ [Core Combat] PvP toxicity controls ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry ¦ [Core Combat] Floating combat text ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry ¦ [Core Combat] Combat log ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Core Combat] Combat UX & Telemetry ¦ Post-match checks on cheats ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core ¦ [Combat Abilities] Global cooldown rules ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Ability Core ¦ [Combat Abilities] Resource systems (mana/energy/rage) ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics ¦ [Combat Abilities] Casting Mechanics ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics ¦ [Combat Abilities] Channeling abilities ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics ¦ [Combat Abilities] Interrupts & crowd control ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Casting Mechanics ¦ [Combat Abilities] Cast bar & interrupt feedback ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Area & Effect Handling ¦ [Combat Abilities] Area & Effect Handling ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Area & Effect Handling ¦ [Combat Abilities] Area-of-effect ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Combat Epic / [Combat Abilities] Area & Effect Handling ¦ [Combat Abilities] Status effects visuals ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / User Space / [User Space] Decoration / Buildings/parts of buildings placement/design ¦ rooms, windows, etc ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Minigames / [Minigames] Single-player minigames ¦ [Minigames] Single-player minigames ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Minigames / [Minigames] Multiplayer minigames ¦ [Minigames] Multiplayer minigames ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] ¦ [Item System] Initial Item Lists by type ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System ¦ [Item System] Item Data & Rules ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules ¦ [Item System] Item definition schema ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules ¦ [Item System] Item level / power scoring ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Data & Rules ¦ [Item System] Item binding rules ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System ¦ [Item System] Item Lifecycle & Protection ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Lifecycle & Protection ¦ [Item System] Destroy item confirmation ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Item Lifecycle & Protection ¦ [Item System] Item locking / favorites ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Cosmetic & Appearance as Items ¦ [Item System] Appearance collection tracking ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Item Core System / [Item System] Cosmetic & Appearance as Items ¦ [CC & Management] Titles & vanity ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic ¦ [CC & Management] Emotes & gestures ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic ¦ [World & Zones] In-game maps ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System ¦ [Inventory] Player-Carried Storage ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System ¦ [Inventory] Auto-sort rules ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System ¦ [Inventory] Split stacks & stack merging ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System ¦ [Inventory] Junk tagging & vendor sell-all ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System ¦ [Inventory] Long-Term Storage ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System ¦ [Inventory] Search in bank/stash ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System ¦ [Inventory] Item models ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System ¦ [Inventory] Item icons ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System ¦ [Inventory] Buy/Sell (Vendor transfer) ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Inventory System ¦ [Inventory] Item editor and tools ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System ¦ [Equipment] Equipment slots ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System ¦ [Equipment] Item comparison tooltips ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System ¦ [Equipment] Item reforging/rerolling ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System ¦ [Equipment] Set bonuses ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Equipment System ¦ Equipment] Armour and Kit list ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets ¦ Pets ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets ¦ [CC & Management] Pets Customization ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets / [CC & Management] Pets Customization ¦ [CC & Management] Pets Naming ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Pets / [CC & Management] Pets Customization ¦ [CC & Management] Pets Clothes/Accessories ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Forge System ¦ [Equipment] Forge Item list ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Items & Inventory System Epic / Forge System ¦ [Equipment] Forge models and icons ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Currency System ¦ Sources and drains ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Currency System ¦ [Trading] Multiple currencies ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Currency System ¦ [Trading] Currency flows ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Currency System ¦ [Trading] Currency transactions ledger ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Trading system ¦ COD (cash on delivery) ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Trading system ¦ [Trading] Search filters (ilvl, stats) ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Trading system ¦ [Trading] Tax & fee tuning ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Trading system ¦ [Trading] Buyback tab ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Trading system ¦ [Trading] NPC vendors ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Trading system ¦ [Trading] Repair & services vendors ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Trading system ¦ [Trading] Token/vendor catch-up gear ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Trading system ¦ [Trading] Listing limits & anti-snipe ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Auction house / market board ¦ [Trading] Market price history ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Auction house / market board ¦ [Trading] Market tools (retrieval, reversal) ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / In-game economy / Auction house / market board ¦ [Trading] Offline sales delivery ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types ¦ Gather Resources ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types ¦ Collect Unique Item ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types ¦ Interact with Objects ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types ¦ Kill Enemies ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types ¦ Kill & Collect ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types ¦ Investigate / Track ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Quest System / [Quest System] Quest Types ¦ Challenge / Minigame ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Quest System / [Social Systems] Player Chat ¦ Tagging/credit rules ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Quest System / [Core Combat] Dueling ¦ [Core Combat] Dueling ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface ¦ [Game Interfaces] Health/resource bars ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface ¦ [Game Interfaces] Action bars & hotkeys ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] HUD & In-Game Interface ¦ [Game Interfaces] Damage direction indicators ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards ¦ [Game Interfaces] Notifications/toasts ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards ¦ [Game Interfaces] Search within menus ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards ¦ [Game Interfaces] Rich tooltips ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / [Game Interfaces] UI Framework & UX Standards ¦ [Game Interfaces] Error handling & messaging ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / Controls ¦ Controls ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / Controls ¦ [Controls] General game settings ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings ¦ [Controls] Rebindable controls ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings ¦ [Controls] Gamepad support ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / Controls / [Controls] General game settings ¦ [Controls] Toggle/hold options ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations ¦ [UX] Search everywhere ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations ¦ [UX] Photo mode ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations ¦ [UX] AFK detection ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations ¦ [UX] Returner experience ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / UX Optimizations / [UX] Modern UI/UX Expectations ¦ [UX] Community safety onboarding ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion ¦ Presentation & Immersion ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Game Interfaces / Presentation & Immersion ¦ [Presentation] Visual Presentation ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] Account Authentification ¦ License/ownership check ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] Account Privacy Settings & Legal / [Platform] Age gating / parental controls ¦ Age gating restriction flow for the game ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display ¦ Nickname ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display ¦ Default profile picture ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features / [Player Dashboard] Account Info Display ¦ Log out ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features ¦ [Player Dashboard] CH currency wallet ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Player Account Features ¦ [Player Dashboard] Support & FAQ ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard ¦ [Player Dashboard] Partner Games Display ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display ¦ All games ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display ¦ Unlocked games ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Games Display ¦ Steam key redemption ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard ¦ [Player Dashboard] Partner Assets (items) display ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard / [Player Dashboard] Partner Assets (items) display ¦ Inventory section ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard ¦ [Player Dashboard] Community Hub ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Game Dashboard ¦ [Player Dashboard] Featured Games section ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Search & Notifications ¦ [Player Dashboard] Search ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Player Dashboard] Search & Notifications ¦ [Player Dashboard] Web notifications/red dots ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Developer Account ¦ [Developer Dashboard] Company Info Form ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard ¦ [Developer Dashboard] Games management ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard ¦ [Developer Dashboard] Keys management ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Game Dashboard ¦ [Developer Dashboard] Analytics ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Game item: low classification confidence | Couch Heroes / Game / Game Features / Platform / [Platform] [Developer Dashboard] Settings & Support ¦ [Developer Dashboard] contact support & FAQ ¦ reason: NEEDS OFFSITE REVIEW: no clear layer keyword matched; defaulted to Feature/Feature
REVIEW | Studio Operations possible UK duplicate | Register for Corporation Tax ¦ POSSIBLE DUPLICATE OF UK 5.4 Corporation Tax Registration - confirm at offsite. Per CH_Guidance section 5.
REVIEW | Studio Operations possible UK duplicate | VAT registration assessment ¦ POSSIBLE DUPLICATE OF UK 5.5 VAT Registration - confirm at offsite. Decision before first invoice.
REVIEW | Studio Operations possible UK duplicate | Auto-enrolment pension scheme ¦ POSSIBLE DUPLICATE OF UK 1.6 Pension Auto-Enrolment Letter - confirm at offsite. Per CH_Guidance section 2. £6,240-£50,2
REVIEW | Studio Operations possible UK duplicate | Employers' Liability Insurance ¦ POSSIBLE DUPLICATE OF UK 1.7 EL Insurance Certificate - confirm at offsite. £250-£800/year per CH_Guidance 1.1.
REVIEW | Studio Operations possible UK duplicate | Confirmation statement filing ¦ POSSIBLE DUPLICATE OF UK 5.x Companies House Filings - confirm at offsite.
REVIEW | Studio Operations possible UK duplicate | Director Identity Verification ¦ POSSIBLE DUPLICATE OF UK 5.3 Director Identity Verification - confirm at offsite. Per CH_Guidance Priority 5.
REVIEW | Studio Operations possible UK duplicate | EMI option scheme design ¦ POSSIBLE DUPLICATE OF UK 4.12 EMI Share Scheme - confirm at offsite. Per CH_Guidance Priority 4 (optional but high-value
REVIEW | Missing or TBD assignee | Couch Heroes / Studio Operations / IT and Systems ¦ DCC tool licences - audio
REVIEW | Studio Operations possible UK duplicate | Contract template - employment ¦ POSSIBLE DUPLICATE OF UK 1.1 Employment Contract - confirm at offsite. Riley owns drafting; CH approves.
REVIEW | Studio Operations possible UK duplicate | Contract template - mutual NDA ¦ POSSIBLE DUPLICATE OF UK 2.3 Confidentiality / NDA - confirm at offsite.
REVIEW | Studio Operations possible UK duplicate | Sponsor Licence application ¦ POSSIBLE DUPLICATE OF UK 3.x Sponsor Licence - confirm at offsite. Per CH_Guidance section 3. Patrice can act as L1 User
REVIEW | Studio Operations possible UK duplicate | Sponsor Licence HR Compliance Pack ¦ POSSIBLE DUPLICATE OF UK 3.1 HR Compliance Pack - confirm at offsite. Per CH_Guidance Priority 3.
REVIEW | Studio Operations possible UK duplicate | Sponsored worker file standard ¦ POSSIBLE DUPLICATE OF UK 3.2 Sponsored Worker File Template - confirm at offsite.
REVIEW | Studio Operations possible UK duplicate | Right to Work check process ¦ POSSIBLE DUPLICATE OF UK 1.4 Right to Work Checks - confirm at offsite. Per CH_Guidance Priority 1.
REVIEW | Studio Operations possible UK duplicate | DPIA process and templates ¦ POSSIBLE DUPLICATE OF UK 2.5 DPIA Template - confirm at offsite. Per CH_Guidance Priority 2.
REVIEW | Studio Operations possible UK duplicate | Cross-border data transfer agreement ¦ POSSIBLE DUPLICATE OF UK 2.6 Cross-Border Data Transfer Agreement - confirm at offsite. Per CH_Guidance Priority 2.
REVIEW | Studio Operations possible UK duplicate | Health and Safety policy ¦ POSSIBLE DUPLICATE OF UK 1.5 Health and Safety Policy - confirm at offsite. Per CH_Guidance Priority 1.
REVIEW | Studio Operations possible UK duplicate | Employee handbook - full set ¦ POSSIBLE DUPLICATE OF UK 2.1 Employee Handbook - confirm at offsite. Per CH_Guidance Priority 2. Full list.
REVIEW | Studio Operations possible UK duplicate | Bribery Act 2010 procedures ¦ POSSIBLE DUPLICATE OF UK 4.9 Bribery Act Policy - confirm at offsite. Per CH_Guidance Priority 4.
REVIEW | Studio Operations possible UK duplicate | Modern Slavery Statement (deferred) ¦ POSSIBLE DUPLICATE OF UK 4.10 Modern Slavery Statement - confirm at offsite. Per CH_Guidance Priority 4.