## Plan
WORK STREAMS |  |  |  |  | CONCEPT | [38 empty] | PRE-PRODUCTION | [38 empty] | PRODUCTION | [116 empty] | RELEASE | [155 empty] | LIVE SERVICE
[5 empty] | GATE 0 | CONCEPT ~2 months Target: T0 Ideation | [37 empty] | GATE 1 | PRE-PRODUCTION Target: T1-T2 R&D / GDD-TDD-Brief | [37 empty] | GATE 2 | EARLY PROD Target: T3 Prototype | [37 empty] | GATE 3 | MID PRO Target: T4 MVP | [37 empty] | GATE 4 | END PROD Target: T5 Feature Complete | [37 empty] | GATE 5 | ALPHA Target: T6 Player Tested | [37 empty] | GATE 6 | BETA Target: T6 Player Tested | [37 empty] | GATE 7 | LAUNCH Target: T6 Player Ready | [37 empty] | GATE 8 | FIRST RELEASE ~1.5 months Target: T6-T7 Player Ready / Expand | [37 empty] | GATE 9 | LS 1 Live Target: T7 Expand | [37 empty] | GATE 10 | LS 2 Live Target: T8 Scale
Epic | Feature | Size | Current Tier | Notes |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team
Player Build
| Player Progression | L | T1: R&D
| Skill System | L | T1: R&D
| Achievements & Trophies | M | T1: R&D
| Factions / Reputation | M | T1: R&D
| FTUE | M | T2: GDD/TDD/Brief
| Professions | L | T1: R&D
| Character Management | M | T0: Ideation
| Character Creation & Customization | L | T1: R&D
| Garment System | M | T0: Ideation
| Persona System | M | T1: R&D
| Emote System | S | T0: Ideation
World Systems
| Foam Corruption | M | T2: GDD/TDD/Brief
| Miasma Corruption | M | T0: Ideation
| Water Corruption | M | T0: Ideation
| Crystal Corruption | M | T0: Ideation
| Time Corruption | M | T0: Ideation
| Enemy Corruption | M | T0: Ideation
| Oil Corruption | M | T0: Ideation
| Texture Corruption | M | T0: Ideation
| Environmental Elemental Effects (combination states) | L | T2: GDD/TDD/Brief
| Basic Movement System | L | T1: R&D
| Advanced Traversal | L | T1: R&D
| Navigation | M | T0: Ideation
| Day/Night Cycle | M | T1: R&D
| Dynamic Weather | M | T1: R&D
| Instancing | L | T0: Ideation
| Dungeon Mechanics | L | T0: Ideation
| The Dungeon | L | T0: Ideation
| Partner Portal | M | T1: R&D
| World Bosses | L | T0: Ideation
| Corruption Heatmap | M | T1: R&D
| Biome - Portal Peak | M | T4: MVP
| Biome - Hidden Hills | M | T0: Ideation
| Biome - Farmlands | M | T0: Ideation
| Biome - Mistrun Shore | M | T0: Ideation
| Biome - Whispering Woods | M | T0: Ideation
| Biome - Tranquil Sands | M | T0: Ideation
| Biome - Torrential Vale | M | T0: Ideation
| Biome - Clockwork | M | T0: Ideation
| Biome - Downtime | M | T4: MVP
Combat
| Combat Framework | L | T2: GDD/TDD/Brief
| Ranged Combat | M | T0: Ideation
| Combat AI Behavior | L | T0: Ideation
| Enemies Art | M | T0: Ideation
| PvP Combat | L | T0: Ideation
| Combat Balance & Telemetry | M | T2: GDD/TDD/Brief
| Combat Abilities | L | T1: R&D
| Magic | L | T0: Ideation
| Full Motion Video (FMV) | M | T1: R&D
User Space
| User Space Server & Instance | L | T2: GDD/TDD/Brief
| User Space Decoration | M | T0: Ideation
| P2P / P2G User Space Connection | M | T2: GDD/TDD/Brief
| Building Houses | L | T1: R&D
| Saving House Layouts | M | T0: Ideation
| Partner Portal System (player house) | M | T0: Ideation
| Arcade Cabinet | M | T1: R&D
| Anywhere Door Placement | S | T0: Ideation
Items & Inventory
| Item Core System | L | T2: GDD/TDD/Brief
| Inventory System | M | T2: GDD/TDD/Brief
| Equipment System | M | T0: Ideation
| Loot Distribution | M | T2: GDD/TDD/Brief
| Mounts / Pets | L | T1: R&D
| Banks | M | T0: Ideation
| P2P Item Transfer | M | T0: Ideation
| Consumables | S | T2: GDD/TDD/Brief
| Durable Items | S | T0: Ideation
Player Economy
| Trading System | L | T0: Ideation
| Currency System | M | T0: Ideation
| Auction House | L | T0: Ideation
| In-game Store | M | T0: Ideation
| In-game Economy | L | T0: Ideation
| RMT Game Economy | L | T0: Ideation
| IG / RMT Monitoring System | M | T0: Ideation
Quest System
| Quests Backend / Tooling | L | T2: GDD/TDD/Brief
| Quests as Events | M | T1: R&D
| Quest Multiplayer | L | T1: R&D
| Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | L | T2: GDD/TDD/Brief
| Quest Reward System | M | T0: Ideation
| Quest Log | M | T0: Ideation
| Quest Dialog GUI | M | T0: Ideation
| Quest Narrative Content | L | T2: GDD/TDD/Brief
| In Game Cinematic (IGC) | L | T2: GDD/TDD/Brief
| Meta Quest System | M | T0: Ideation
| Quest Generator System | L | T0: Ideation
| Targeted VO | M | T2: GDD/TDD/Brief
Social & Multiplayer
| Game Chat System | M | T1: R&D
| Friends | M | T1: R&D
| Guilds | L | T1: R&D
| Co-op / Party | M | T1: R&D
| Co-op / Raids | L | T1: R&D
| Dueling | M | T1: R&D
| In-game Mail | S | T2: GDD/TDD/Brief
| Notifications | S | T1: R&D
| Player Config PvP Server | M | T0: Ideation
| LFG / Pick-up Groups | M | T0: Ideation
Game Bibles
| UX/UI Bible | M | T0: Ideation
| Accessibility Guidelines | M | T0: Ideation
| Brand Bible | M | T2: GDD/TDD/Brief
| Art Bible | L | T3: Prototype
| Monetization Bible | M | T0: Ideation
| Red Books (Live Service emergency guidelines) | M | T0: Ideation
Platform
| Player Account Creation / Deletion | M | T2: GDD/TDD/Brief
| Player Account Authentication | M | T2: GDD/TDD/Brief
| Player Account Privacy Settings & Legal | M | T1: R&D
| Player Dashboard - Account Features | M | T1: R&D
| Player Dashboard - Game Dashboard | M | T1: R&D
| Player Dashboard - Friends | M | T1: R&D
| Player Dashboard - Search & Notifications | M | T1: R&D
| Player Dashboard - Marketplace | L | T1: R&D
| Developer Dashboard - Developer Account | M | T1: R&D
| Developer Dashboard - Game Dashboard | M | T1: R&D
| Developer Dashboard - Settings & Support | M | T1: R&D
| Quest Tracking | M | T1: R&D
| Payment Processing (incl. Refunds) | L | T0: Ideation
| Online Services & Backend | L | T0: Ideation
| Launcher & Distribution | L | T2: GDD/TDD/Brief
| Partner Loop | M | T1: R&D
| Game Tool Integration (incl. Game Key Generation) | M | T1: R&D
| Account Level Settings | S | T0: Ideation
| Social Media Support | M | T0: Ideation
Live Game
| Live GDD | M | T0: Ideation
| Content | L | T0: Ideation
| Forecast | M | T0: Ideation
| Analytics & BI | L | T0: Ideation
| Sales Dashboard | M | T0: Ideation
| Telemetry | L | T0: Ideation
| Live Service Event Plan | L | T0: Ideation
Partner Build
| Partner = Feature definition | S | T0: Ideation
| Sign Partner | S | T0: Ideation
| Partner Brief | M | T0: Ideation
| Partner Design Doc | M | T0: Ideation
| Partner TDD | M | T0: Ideation
| Partner Art Brief | M | T0: Ideation
| Partner Build | L | T0: Ideation
| Partner Integration | M | T0: Ideation
Product Publishing
| Web Presence | M | T0: Ideation
| Website | M | T0: Ideation
| Community Persona | M | T0: Ideation
| Title Identity | M | T0: Ideation
| Player Support | M | T0: Ideation
| Go-To-Market Strategy & Implementation | L | T0: Ideation
| 3rd-party Store Publishing | M | T0: Ideation
| Total PW (man-days) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Headcount @ 20 wd/mo (per gate duration) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Headcount per Gate (sum) |  |  |  |  | 0 | [38 empty] | 0 | [38 empty] | 0 | [38 empty] | 0 | [38 empty] | 0 | [38 empty] | 0 | [38 empty] | 0 | [38 empty] | 0 | [38 empty] | 0 | [38 empty] | 0 | [38 empty] | 0
TIER LEGEND (matches the Miro 'Tiers of Completion' cards)
T0 | Ideation | Idea captured, no commitment yet
T1 | R&D | Research, prototyping intent, technical feasibility
T2 | GDD/TDD/Brief | GDD done, TDD done, art brief done
T3 | Prototype | Functional with no skins, can be bugged
T4 | MVP | Limited quality, but full-featured
T5 | Feature Complete | Final assets, polished, no scope cuts left
T6 | Player Tested | Playtest, alpha, beta, telemetry feedback applied
T7 | Expand | Add to feature / content
T8 | Scale | Productional optimization post-load

## Sheet1
WORK STREAMS | [6 empty] | CONCEPT | [38 empty] | PRE-PRODUCTION | [38 empty] | PRODUCTION | [116 empty] | RELEASE | [155 empty] | LIVE SERVICE
[7 empty] | GATE 0 | CONCEPT ~2 months Target: T0 Ideation | [37 empty] | GATE 1 | PRE-PRODUCTION Target: T1-T2 R&D / GDD-TDD-Brief | [37 empty] | GATE 2 | EARLY PROD Target: T3 Prototype | [37 empty] | GATE 3 | MID PRO Target: T4 MVP | [37 empty] | GATE 4 | END PROD Target: T5 Feature Complete | [37 empty] | GATE 5 | ALPHA Target: T6 Player Tested | [37 empty] | GATE 6 | BETA Target: T6 Player Tested | [37 empty] | GATE 7 | LAUNCH Target: T6 Player Ready | [37 empty] | GATE 8 | FIRST RELEASE ~1.5 months Target: T6-T7 Player Ready / Expand | [37 empty] | GATE 9 | LS 1 Live Target: T7 Expand | [37 empty] | GATE 10 | LS 2 Live Target: T8 Scale
Epic | Feature | Story | Team | Size | Current Tier | Notes |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  | This is the role |  |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team
This is the epic
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| This is the feature name |  | This is the department ¦ This is the team | S | T2: GDD/TDD/Brief | [80 empty] | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6 | 3 | 6
|  | This is the story name | This is the department ¦ This is the team | M | T1: R&D | [80 empty] | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 12 | 20
|  | This is the story name | This is the department ¦ This is the team | L | T4: MVP | [80 empty] | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15 | 11 | 15
|  | This is the story name | This is the department ¦ This is the team | [82 empty] | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7 | 5 | 7
| This is the feature name |  | This is the department ¦ This is the team | [82 empty] | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14 | 7 | 14
|  | This is the story name | This is the department ¦ This is the team | [82 empty] | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11 | 9 | 11
| This is the feature name |  | This is the department ¦ This is the team | [82 empty] | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4
|  | This is the story name | This is the department ¦ This is the team | [82 empty] | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286 | 5.1429 | 7.4286
| This is the feature name |  | This is the department ¦ This is the team | [82 empty] | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357 | 4.6786 | 6.5357
|  | This is the story name | This is the department ¦ This is the team | [82 empty] | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429 | 4.2143 | 5.6429
| This is the feature name |  | This is the department ¦ This is the team | [82 empty] | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75 | 3.75 | 4.75
|  | This is the story name | This is the department ¦ This is the team | [82 empty] | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571 | 3.2857 | 3.8571
|  |  | This is the department ¦ This is the team | [82 empty] | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643 | 2.8214 | 2.9643

## Summary
Epic | Features | Concept ~2 months T0 | Pre-production ~4 months T1-T2 | Early Prod ~4 months T3 | Mid Prod ~6 months T4 | End Prod ~4 months T5 | Alpha ~2 months T6 | Beta ~1.5 months T6 | Launch ~1 month T6 | First Release ~1.5 months T6-T7 | LS 1 Live T7 | LS 2 Live T8 | Total PW
Player Build | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
World Systems | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Combat | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Space | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Items & Inventory | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Player Economy | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quest System | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Social & Multiplayer | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Game Bibles | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Live Game | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Partner Build | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Product Publishing | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GRAND TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Epics & Features
Epic | Feature | Sizing | Current Tier
Player Build | Player Progression | L | T1: R&D
Player Build | Skill System | L | T1: R&D
Player Build | Achievements & Trophies | M | T1: R&D
Player Build | Factions / Reputation | M | T1: R&D
Player Build | FTUE | M | T2: GDD/TDD/Brief
Player Build | Professions | L | T1: R&D
Player Build | Character Management | M | T0: Ideation
Player Build | Character Creation & Customization | L | T1: R&D
Player Build | Garment System | M | T0: Ideation
Player Build | Persona System | M | T1: R&D
Player Build | Emote System | S | T0: Ideation
World Systems | Foam Corruption | M | T2: GDD/TDD/Brief
World Systems | Miasma Corruption | M | T0: Ideation
World Systems | Water Corruption | M | T0: Ideation
World Systems | Crystal Corruption | M | T0: Ideation
World Systems | Time Corruption | M | T0: Ideation
World Systems | Enemy Corruption | M | T0: Ideation
World Systems | Oil Corruption | M | T0: Ideation
World Systems | Texture Corruption | M | T0: Ideation
World Systems | Environmental Elemental Effects (combination states) | L | T2: GDD/TDD/Brief
World Systems | Basic Movement System | L | T1: R&D
World Systems | Advanced Traversal | L | T1: R&D
World Systems | Navigation | M | T0: Ideation
World Systems | Day/Night Cycle | M | T1: R&D
World Systems | Dynamic Weather | M | T1: R&D
World Systems | Instancing | L | T0: Ideation
World Systems | Dungeon Mechanics | L | T0: Ideation
World Systems | The Dungeon | L | T0: Ideation
World Systems | Partner Portal | M | T1: R&D
World Systems | World Bosses | L | T0: Ideation
World Systems | Corruption Heatmap | M | T1: R&D
World Systems | Biome - Portal Peak | M | T4: MVP
World Systems | Biome - Hidden Hills | M | T0: Ideation
World Systems | Biome - Farmlands | M | T0: Ideation
World Systems | Biome - Mistrun Shore | M | T0: Ideation
World Systems | Biome - Whispering Woods | M | T0: Ideation
World Systems | Biome - Tranquil Sands | M | T0: Ideation
World Systems | Biome - Torrential Vale | M | T0: Ideation
World Systems | Biome - Clockwork | M | T0: Ideation
World Systems | Biome - Downtime | M | T4: MVP
Combat | Combat Framework | L | T2: GDD/TDD/Brief
Combat | Ranged Combat | M | T0: Ideation
Combat | Combat AI Behavior | L | T0: Ideation
Combat | Enemies Art | M | T0: Ideation
Combat | PvP Combat | L | T0: Ideation
Combat | Combat Balance & Telemetry | M | T2: GDD/TDD/Brief
Combat | Combat Abilities | L | T1: R&D
Combat | Magic | L | T0: Ideation
Combat | Full Motion Video (FMV) | M | T1: R&D
User Space | User Space Server & Instance | L | T2: GDD/TDD/Brief
User Space | User Space Decoration | M | T0: Ideation
User Space | P2P / P2G User Space Connection | M | T2: GDD/TDD/Brief
User Space | Building Houses | L | T1: R&D
User Space | Saving House Layouts | M | T0: Ideation
User Space | Partner Portal System (player house) | M | T0: Ideation
User Space | Arcade Cabinet | M | T1: R&D
User Space | Anywhere Door Placement | S | T0: Ideation
Items & Inventory | Item Core System | L | T2: GDD/TDD/Brief
Items & Inventory | Inventory System | M | T2: GDD/TDD/Brief
Items & Inventory | Equipment System | M | T0: Ideation
Items & Inventory | Loot Distribution | M | T2: GDD/TDD/Brief
Items & Inventory | Mounts / Pets | L | T1: R&D
Items & Inventory | Banks | M | T0: Ideation
Items & Inventory | P2P Item Transfer | M | T0: Ideation
Items & Inventory | Consumables | S | T2: GDD/TDD/Brief
Items & Inventory | Durable Items | S | T0: Ideation
Player Economy | Trading System | L | T0: Ideation
Player Economy | Currency System | M | T0: Ideation
Player Economy | Auction House | L | T0: Ideation
Player Economy | In-game Store | M | T0: Ideation
Player Economy | In-game Economy | L | T0: Ideation
Player Economy | RMT Game Economy | L | T0: Ideation
Player Economy | IG / RMT Monitoring System | M | T0: Ideation
Quest System | Quests Backend / Tooling | L | T2: GDD/TDD/Brief
Quest System | Quests as Events | M | T1: R&D
Quest System | Quest Multiplayer | L | T1: R&D
Quest System | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | L | T2: GDD/TDD/Brief
Quest System | Quest Reward System | M | T0: Ideation
Quest System | Quest Log | M | T0: Ideation
Quest System | Quest Dialog GUI | M | T0: Ideation
Quest System | Quest Narrative Content | L | T2: GDD/TDD/Brief
Quest System | In Game Cinematic (IGC) | L | T2: GDD/TDD/Brief
Quest System | Meta Quest System | M | T0: Ideation
Quest System | Quest Generator System | L | T0: Ideation
Quest System | Targeted VO | M | T2: GDD/TDD/Brief
Social & Multiplayer | Game Chat System | M | T1: R&D
Social & Multiplayer | Friends | M | T1: R&D
Social & Multiplayer | Guilds | L | T1: R&D
Social & Multiplayer | Co-op / Party | M | T1: R&D
Social & Multiplayer | Co-op / Raids | L | T1: R&D
Social & Multiplayer | Dueling | M | T1: R&D
Social & Multiplayer | In-game Mail | S | T2: GDD/TDD/Brief
Social & Multiplayer | Notifications | S | T1: R&D
Social & Multiplayer | Player Config PvP Server | M | T0: Ideation
Social & Multiplayer | LFG / Pick-up Groups | M | T0: Ideation
Game Bibles | UX/UI Bible | M | T0: Ideation
Game Bibles | Accessibility Guidelines | M | T0: Ideation
Game Bibles | Brand Bible | M | T2: GDD/TDD/Brief
Game Bibles | Art Bible | L | T3: Prototype
Game Bibles | Monetization Bible | M | T0: Ideation
Game Bibles | Red Books (Live Service emergency guidelines) | M | T0: Ideation
Platform | Player Account Creation / Deletion | M | T2: GDD/TDD/Brief
Platform | Player Account Authentication | M | T2: GDD/TDD/Brief
Platform | Player Account Privacy Settings & Legal | M | T1: R&D
Platform | Player Dashboard - Account Features | M | T1: R&D
Platform | Player Dashboard - Game Dashboard | M | T1: R&D
Platform | Player Dashboard - Friends | M | T1: R&D
Platform | Player Dashboard - Search & Notifications | M | T1: R&D
Platform | Player Dashboard - Marketplace | L | T1: R&D
Platform | Developer Dashboard - Developer Account | M | T1: R&D
Platform | Developer Dashboard - Game Dashboard | M | T1: R&D
Platform | Developer Dashboard - Settings & Support | M | T1: R&D
Platform | Quest Tracking | M | T1: R&D
Platform | Payment Processing (incl. Refunds) | L | T0: Ideation
Platform | Online Services & Backend | L | T0: Ideation
Platform | Launcher & Distribution | L | T2: GDD/TDD/Brief
Platform | Partner Loop | M | T1: R&D
Platform | Game Tool Integration (incl. Game Key Generation) | M | T1: R&D
Platform | Account Level Settings | S | T0: Ideation
Platform | Social Media Support | M | T0: Ideation
Live Game | Live GDD | M | T0: Ideation
Live Game | Content | L | T0: Ideation
Live Game | Forecast | M | T0: Ideation
Live Game | Analytics & BI | L | T0: Ideation
Live Game | Sales Dashboard | M | T0: Ideation
Live Game | Telemetry | L | T0: Ideation
Live Game | Live Service Event Plan | L | T0: Ideation
Partner Build | Partner = Feature definition | S | T0: Ideation
Partner Build | Sign Partner | S | T0: Ideation
Partner Build | Partner Brief | M | T0: Ideation
Partner Build | Partner Design Doc | M | T0: Ideation
Partner Build | Partner TDD | M | T0: Ideation
Partner Build | Partner Art Brief | M | T0: Ideation
Partner Build | Partner Build | L | T0: Ideation
Partner Build | Partner Integration | M | T0: Ideation
Product Publishing | Web Presence | M | T0: Ideation
Product Publishing | Website | M | T0: Ideation
Product Publishing | Community Persona | M | T0: Ideation
Product Publishing | Title Identity | M | T0: Ideation
Product Publishing | Player Support | M | T0: Ideation
Product Publishing | Go-To-Market Strategy & Implementation | L | T0: Ideation
Product Publishing | 3rd-party Store Publishing | M | T0: Ideation

## Roles
Role | Discipline | Notes
CEO | Leadership
Creative Director | Leadership
Head of Legal | Leadership
COO | Leadership
HR Manager | Leadership
Executive Producer | Production
Producer | Production
Game Producer | Production
Tech Producer | Production
Art Producer | Production
Game Director | Design
Game Design Lead | Design
Level Design Lead | Design
Game Designer | Design
Combat Designer | Design
Level Designer | Design
Technical Designer | Design
Writer | Design
Art Director | Art
Concept Artist | Art
UI/UX Designer | Art
Graphic Designer | Art
Character Artist | Art
Environment Artist | Art
Prop Artist | Art
Animator | Art
Character Rigger | Art
VFX Artist | Art
Technical Artist | Art
CTO | Engineering
Tech Lead | Engineering
Gameplay Developer | Engineering
Full Stack Developer | Engineering
Backend Developer | Engineering
Network Engineer | Engineering
QA | QA
Sound Designer | Audio
Platform Team | Platform

## Gates
Gate | Phase | Target Tier | Tier Name | Notes
0 | Concept | T0 | Ideation | Y-doc, pitch, vision lock; all features captured at T0
1 | Pre-production | T1-T2 | R&D / GDD-TDD-Brief | GDD/TDD/Art briefs for all greenlit features (T2)
2 | Early Prod | T3 | Prototype | Prototype every feature; many bugs allowed (T3)
3 | Mid Prod | T4 | MVP | Full MVP scope - heaviest production gate (T4)
4 | End Prod | T5 | Feature Complete | Feature complete, polish to ship quality (T5)
5 | Alpha | T6 | Player Tested | Playtest, telemetry, balance pass; gating bugs only
6 | Beta | T6 | Player Tested | External player feedback, cert prep, content lock
7 | Launch | T6 | Player Ready | Day-0 readiness, marketing, store, support
8 | First Release | T6-T7 | Player Ready / Expand | Live monitoring, hotfixes, day-1/7/30 patches
9 | LS 1 | T7 | Expand | Expansions, new content drops, season cadence (T7)
10 | LS 2 | T8 | Scale | Optimize / scale post-load, sustain plan (T8)

## Tiers
Tier | Name | Definition
T0 | Ideation | Idea captured, no commitment
T1 | R&D | Research, prototyping intent, technical feasibility
T2 | GDD / TDD / Brief ready | GDD done, TDD done, art brief done
T3 | Prototype | Functional with no skins, can be bugged
T4 | MVP | Limited quality, but full-featured
T5 | Feature Complete (at quality) | Final assets, polished, no scope cuts left
T6 | Player Ready / Tested | Playtest, alpha, beta, telemetry feedback applied
T7 | Expand | Add to feature / content
T8 | Scale | Productional optimization post-load

## Legend
Cell Color / Section | Meaning
Phase super-headers (row 1 of Plan)
Concept | Concept gate (T0 Ideation)
Pre-production | Pre-production gate (T1-T2)
Production | Early / Mid / End Prod gates (T3-T5)
Release | Alpha / Beta / Launch / First Release
Live Service | LS 1 / LS 2
Discipline | Role group color (row 3 of Plan)
Leadership | CEO, Head of Legal, Head of Finance & Ops, HR Manager
Production | Executive / Producer / Game / Tech / Art Producer
Design | Game Director, Design Leads, Designers, Writer
Art | Art Director, Concept, UI/UX, Character/Env/Prop, Anim, Rig, VFX, TA
Engineering | CTO, Tech Lead, Gameplay/Full Stack/Backend/Network
QA | QA
Audio | Sound Designer
Platform | Platform Team
Sizing key (col C)
S | Small feature
M | Medium feature
L | Large feature
How to use
Plan sheet | Fill in man-days per (feature, gate, role). Cells are blank by default.
Totals row | Bottom of Plan: SUMs each role column per gate.
Headcount row | Total PW / (gate months * 20 working days). Edit GATE_MONTHS in the script if your durations change.
Summary sheet | Auto-rolls up Plan totals per epic per gate.
Adding rows | Insert rows inside an epic block on Plan. Update Total PW SUM ranges if you extend past the current last data row.