## Plan
WORK STREAMS | [6 empty] | CONCEPT | [38 empty] | PRE-PRODUCTION | [38 empty] | PRODUCTION | [154 empty] | RELEASE | [155 empty] | LIVE SERVICE
[7 empty] | GATE 0 | CONCEPT | [37 empty] | GATE 1 | PRE-PRODUCTION Target: T1-T2 R&D / GDD-TDD-Brief | [37 empty] | GATE 2 | EARLY PROD | [75 empty] | GATE 3 | MID PRO Target: T4 MVP | [37 empty] | GATE 4 | END PRO Target: T5 Feature Complete | [37 empty] | GATE 5 | ALPHA Target: T6 Playtest | [37 empty] | GATE 6 | BETA Target: T6 Playtest | [37 empty] | GATE 7 | LAUNCH Target: T6 | [37 empty] | GATE 8 | FIRST RELEASE Target: T6-T7 | [37 empty] | GATE 9 | LS 1 Live T7 | [37 empty] | GATE 10 | LS 2 Live T8
Epic | Feature | Story | Team | Size | Current Tier | Notes |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO |  | Creative Director |  | Head of Legal |  | COO |  | HR Manager |  | Executive Producer |  | Producer |  | Game Producer |  | Tech Producer |  | Art Producer |  | Game Director |  | Game Design Lead |  | Level Design Lead |  | Game Designer |  | Combat Designer |  | Level Designer |  | Technical Designer |  | Writer |  | Art Director |  | Concept Artist |  | UI/UX Designer |  | Graphic Designer |  | Character Artist |  | Environment Artist |  | Prop Artist |  | Animator |  | Character Rigger |  | VFX Artist |  | Technical Artist |  | CTO |  | Tech Lead |  | Gameplay Developer |  | Full Stack Developer |  | Backend Developer |  | Network Engineer |  | QA |  | Sound Designer |  | Platform Team |  |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team
Player Build
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Player Progression |  |  | L | T1: R&D | [107 empty] | 7 | [13 empty] | 3 | [13 empty] | 2 | [7 empty] | 20 | [9 empty] | 2
|  | Player level up documentation | Design ¦ Game design | [108 empty] | 1 | 14
|  | Player level up configuration | Design ¦ Game design | [108 empty] | 0.5 | 15
|  | player level up integration | Engineering ¦ Gameplay Engineering
|  | Player level up UI | Art ¦ UX/UI | [122 empty] | 2 | 3
|  | Character stats documentation | Design ¦ Game design | [108 empty] | 5 | 5
|  | Character stats implementation | Engineering ¦ Gameplay Engineering
|  | Character stats configuration in connection with other systems | Design ¦ Game design | [108 empty] | 1 | 10
|  | Character stats UI | Art ¦ UX/UI | [123 empty] | 15
|  | Level up & Stats QA | QA ¦ QA
|  | Earn different types of EXP depending on objective | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Update player level and exp with (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Fetch player level and exp from (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Fetch and update UI for player level and exp | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Increase stat when player level up | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Update stats UI | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Update player stats in backend (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | fetch player stats from backend service (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Integrate stat system with other systems | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 20
|  | Items give u stats | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
| Skill System |  |  | L | T1: R&D | [107 empty] | 20 | [13 empty] | 15 | [13 empty] | 5 | [7 empty] | 35 | [9 empty] | 7
|  | Skill Tree UI Audio | Audio ¦ Audio | [154 empty] | 7 | 8
|  | Skills in-game audio | Audio ¦ Audio | [154 empty] | 7 | 8
|  | Skill System Documentation | Design ¦ Game design | [108 empty] | 4 | 15
|  | Skill System Implementation | Engineering ¦ Gameplay Engineering
|  | Skill System Configuration | Design ¦ Game design | [108 empty] | 4 | 5
|  | Skill System UI | Art ¦ UX/UI
|  | Skill system QA | QA ¦ QA
|  | Connect skill tree to UI | Engineering ¦ Gameplay Engineering | [144 empty] | 4 | 6
|  | Add new abilities to skill tree | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | Add new weapons to skill tree | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Fetech all skill trees from backend | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Update all skill trees from backend | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Sync all skill trees to backend, tool | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Create weapon skill tree / nodes in (internal dashboard service) | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Remove weapon skill tree / nodes in (internal dashboard service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update weapon skill tree / nodes in (internal dashboard service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Fetch weapon skill tree / nodes in (internal dashboard service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create new collection for weapon skill tree (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Update player skill tree per weapon (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Fetch player skill tree per weapon (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | endpoint to reset skill tree for weapons | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create frontend for skill tree in internal dashboard | Engineering ¦ Backend Engineering | [148 empty] | 5 | 7
| Achievements & Trophies |  |  | M | T1: R&D | [107 empty] | 7 | [13 empty] | 5 | [7 empty] | 5 | [5 empty] | 3 | [7 empty] | 35 | [9 empty] | 2
| Factions / Reputation |  |  | M | T1: R&D
| FTUE |  |  | M | T2: GDD/TDD/Brief | [107 empty] | 16 | [11 empty] | 5 |  | 5 | [5 empty] | 15 |  |  |  | 5 |  |  |  | 12 |  | 10 | [5 empty] | 15 | [9 empty] | 2
|  | Tutorial Cave Layout Fixes | Design ¦ Level design | [112 empty] | 7 | 10
|  | Tutorial cave set dressing fixes | Art ¦ Environment Art
|  | Tutorial Cave lighting | Art ¦ Environment Art
|  | Tutorial cave Ambience & SFX | Audio ¦ Audio | [154 empty] | 5 | 7
|  | Tutorial Configuration/set up/texts | Design ¦ Game design | [108 empty] | 2 | 3
|  | Tutorial UI | Art ¦ UX/UI | [122 empty] | 4 | 6
|  | Tutorial VFX | Art ¦ VFX
|  | Controls UI | Art ¦ UX/UI | [122 empty] | 2 | 4
|  | Tutorial cave contents | Design ¦ Game design | [108 empty] | 1 | 2
|  | Narrative | Design ¦ Narrative | [116 empty] | 0.5 | 1
|  | Tutorial QA check | QA ¦ QA
|  | Controls UI | Art ¦ VFX
| Professions |  |  | L | T1: R&D
|  | Component System Design | Design ¦ Game design | [108 empty] | 2 | 5
|  | Crafted Weapon Parts in-game Audio | Audio ¦ Audio | [154 empty] | 5 | 5
|  | Forge Crafting Audio | Audio ¦ Audio | [154 empty] | 3 | 5
|  | Forge Documentation | Design ¦ Game design | [108 empty] | 3 | 5
|  | Forge Concepts | Art ¦ Concept Art
|  | Forge Integration | Engineering ¦ Gameplay Engineering
|  | Forge UI | Art ¦ UX/UI | [122 empty] | 5 | 10
|  | Forge VFX | Art ¦ VFX
|  | DA combination setup | Art ¦ TechArt
|  | Crafting Desk | Art ¦ Environment Art
|  | Forge Props | Art ¦ Character Art
|  | Forge QA | QA ¦ QA
|  | Fishing Integration | Design ¦ Game design | [108 empty] | 3 | 3
|  | Fishing Rod model | Art ¦ Environment Art
|  | Fish model | Art ¦ Environment Art
|  | Fishing spot sign model | Art ¦ Environment Art
|  | Fishing UI | Art ¦ UX/UI | [123 empty] | 3
|  | Fishing Spot SFX | Audio ¦ Audio | [154 empty] | 0 | 0
|  | Fishing VFX | Art ¦ VFX
|  | Fishing QA | QA ¦ QA
|  | Review fishing code | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Fishing Spot VFX | Audio ¦ Audio
| Character Management |  |  | M | T0: Ideation
| Character Creation & Customization |  |  | L | T1: R&D | [107 empty] | 5 | [13 empty] | 20 | [15 empty] | 10 | [5 empty] | 5
| Garment System |  |  | M | T0: Ideation | [107 empty] | 20 | [13 empty] | 20 | [15 empty] | 10 | [5 empty] | 60
|  | Garment System GDD/TDD | Design ¦ Game design | [108 empty] | 4 | 7
|  | Vertical Slice garments | Design ¦ Game design | [108 empty] | 5 | 5
|  | Garment System Integration | Engineering ¦ Gameplay Engineering
|  | Garment System UI | Art ¦ UX/UI | [122 empty] | 10 | 14
|  | Equipment Concepts | Art ¦ Concept Art
|  | Equipment Models | Art ¦ Character Art
|  | Garment Type SFX | Audio ¦ Audio | [154 empty] | 2 | 3
|  | Equipment Stats integrated with character stats | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Garment System QA | QA ¦ QA
|  | Equipment QA | QA ¦ QA
|  | Equip and unequped based on garment system | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Equiment Concepts | Art ¦ Concept Art
|  | Cull occluded body parts | Art ¦ TechArt
|  | Setup budget for skining and cloth sim | Art ¦ Animation & Rigging | [132 empty] | 5 | 7
|  | Freeze cloth sim | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Maya tool to represent cloth sim like unreal | Art ¦ Animation & Rigging | [132 empty] | 10 | 15
|  | Move socket based on clothing type | Art ¦ Animation & Rigging | [132 empty] | 5 | 10
|  | Setup capsules for cloth collision on character | Art ¦ Animation & Rigging | [132 empty] | 1 | 2
| Persona System |  |  | M | T1: R&D
| Emote System |  |  | S | T0: Ideation
World Systems
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Foam Corruption |  |  | M | T2: GDD/TDD/Brief
|  | Corrupted Vines | Design ¦ Game design | [108 empty] | 0.5 | 1
|  | Corrupted texture | Art ¦ TechArt
|  | Vine NPC Narrative | Design ¦ Narrative | [117 empty] | 1
|  | Vines Foliage | Art ¦ Environment Art
|  | Corrupted VFX | Art ¦ VFX
|  | Corrupted vines behavior & visual QA | QA ¦ QA
|  | Foam Corruption | Design ¦ Game design
|  | Foam Corruption Techart | Art ¦ TechArt
|  | Foam Corruption integration | Engineering ¦ Gameplay Engineering | [144 empty] | 4 | 5
|  | Foam Corruption VFX | Art ¦ VFX
|  | Foam Corruption cleansing animations | Art ¦ Animation & Rigging | [132 empty] | 2 | 3
|  | Foam Corruption cleansing weapon | Art ¦ Character Art
|  | Foam Corruption SFX, VFX design | Design ¦ Game design | [108 empty] | 3 | 3
|  | Foam Corruption SFX | Audio ¦ Audio | [154 empty] | 2 | 2
|  | Foam Corruption QA | QA ¦ QA
|  | Timed Corruption | Design ¦ Game design | [108 empty] | 10 | 40
|  | Timed Corruption Design | Design ¦ Game design | [108 empty] | 2 | 10
|  | Timed Corruption TechArt | Art ¦ TechArt
|  | Timed Corruption Integration | Engineering ¦ Gameplay Engineering
|  | Timed Corruption Server & Multiplayer | Engineering ¦ Backend Engineering
|  | Timed Corruption 3D Assets | Art ¦ Environment Art
|  | Timed Corruption VFX | Art ¦ VFX
|  | Timed Corruption SFX | Audio ¦ Audio | [154 empty] | 3 | 5
|  | Timed Corruption QA | QA ¦ QA
|  | Trigger objective when clean is done | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Quest tracking system | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Make corruption come back after a set time | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Link with corruption gun | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | Replicate animation | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Trigger building the bridge | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Trigger VFX when effect is completed | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Timer to revert bridge to broken state | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Toggle path once puzzle is completed to allow or disallow player from crossing the bridge by replicating collision | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
| Miasma Corruption |  |  | M | T0: Ideation
| Water Corruption |  |  | M | T0: Ideation
| Crystal Corruption |  |  | M | T0: Ideation
| Time Corruption |  |  | M | T0: Ideation
| Enemy Corruption |  |  | M | T0: Ideation
| Oil Corruption |  |  | M | T0: Ideation
| Texture Corruption |  |  | M | T0: Ideation
| Environmental Elemental Effects (combination states) |  |  | L | T2: GDD/TDD/Brief
| Basic Movement System |  |  | L | T1: R&D
|  | Locomotion Integration | Engineering ¦ Gameplay Engineering
|  | Walk | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Run | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Sprint | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Jump | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Double Jump | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Iteration | Design ¦ Game design | [109 empty] | 5
|  | Locomotion QA check | QA ¦ QA
| Advanced Traversal |  |  | L | T1: R&D
|  | Glider Stamina UI | Art ¦ UX/UI | [122 empty] | 2 | 2
|  | Gliding Concepts | Art ¦ Concept Art
|  | Gliding Integration | Engineering ¦ Gameplay Engineering
|  | Gliding Animations | Art ¦ Animation & Rigging | [132 empty] | 1 | 1
|  | Gliding SFX | Audio ¦ Audio | [154 empty] | 1 | 2
|  | Gliding VFX | Art ¦ VFX
|  | Gliding Device | Art ¦ Character Art
|  | Gliding QA | QA ¦ QA
|  | Portals spawning & Xyron moving through portals | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | Narrative for Xyron quests | Design ¦ Narrative | [116 empty] | 1 | 2
|  | Spawning portals SFX | Audio ¦ Audio | [154 empty] | 2 | 4
|  | 5 or 6 mini quests | Design ¦ Game design | [108 empty] | 5 | 8
|  | Xyron voiceover narrative | Design ¦ Narrative | [116 empty] | 0.5 | 2
|  | Xyron voiceover | Audio ¦ Audio | [154 empty] | 7 | 8
|  | Xyron/portals spawning QA | QA ¦ QA
|  | Safety System | Design ¦ Game design | [108 empty] | 3 | 3
|  | Archway race design | Design ¦ Game design | [109 empty] | 3
|  | Persistent leaderboards | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Archway Placement | Design ¦ Game design | [108 empty] | 1 | 7
|  | Archway Models | Art ¦ Environment Art
|  | Archway VFX | Art ¦ VFX
|  | Win Fanfare VFX | Art ¦ VFX
|  | Archway SFX | Audio ¦ Audio | [154 empty] | 0 | 0
|  | Archway QA | QA ¦ QA
|  | Convert gliding to blend space | Art ¦ Animation & Rigging | [132 empty] | 1 | 1
|  | Spawn gliding actor | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Check if ability is unlock to glide | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
| Navigation |  |  | M | T0: Ideation
|  | World Map | Design ¦ Game design | [108 empty] | 10 | 10
|  | Map markers sfx | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | World Map background asset | Art ¦ Concept Art
|  | World Map asset integration | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | World Map UI | Art ¦ UX/UI | [123 empty] | 10
|  | Quest markers support | Engineering ¦ Gameplay Engineering
|  | Map QA check | QA ¦ QA
|  | Fog-of-war | Engineering ¦ Gameplay Engineering
|  | Fog of war QA check | QA ¦ QA
|  | Minimap | Engineering ¦ Gameplay Engineering
|  | Minimap Levels | Design ¦ Game design | [108 empty] | 5 | 5
|  | Minimap UI | Art ¦ UX/UI | [123 empty] | 10
|  | Minimap assets | Art ¦ Concept Art
|  | Minimap quest navigation support | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Minimap QA check | QA ¦ QA
|  | Compass | Engineering ¦ Gameplay Engineering
|  | Compass UI | Art ¦ UX/UI | [122 empty] | 2 | 10
|  | Compass Integration | Engineering ¦ Gameplay Engineering
|  | Compass QA check | QA ¦ QA
|  | Indoor Map | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 7
|  | Special NPCs positions | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Zoom out/in | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | Party player position | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | POI names | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | Quest markers and objectives support | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Fog of war shader | Art ¦ TechArt
|  | Create fog of war grid | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Hide/Unhide markers that are in fog of war | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Fog of war changes based on player visited locations | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | fetch fog of war and update it from unreal side | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Sync fog of war to backend | Engineering ¦ Backend Engineering | [148 empty] | 5 | 5
|  | Show distance to objective | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Party player distance | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show POI distance | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Special NPCs distance | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show quest distance | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show or hide compass from options menu | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Rotate compass with camera | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
| Day/Night Cycle |  |  | M | T1: R&D | [107 empty] | 10 | [13 empty] | 3 | [7 empty] | 11 |  | 15
| Dynamic Weather |  |  | M | T1: R&D | [107 empty] | 17 | [13 empty] | 20 | [7 empty] | 10 | [5 empty] | 5 |  | 90 | [5 empty] | 60
| Instancing |  |  | L | T0: Ideation | [107 empty] | 5 | [29 empty] | 10 | [5 empty] | 120
|  | GDD Documentation | Design ¦ Game design | [108 empty] | 3 | 2
|  | Instancing Documentation | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | User Space Instancing support | Engineering ¦ Backend Engineering
|  | Guild House instancing support | Engineering ¦ Backend Engineering
|  | Dungeon Instancing | Engineering ¦ Backend Engineering
|  | Zones Instancing | Engineering ¦ Backend Engineering
|  | Instancing QA | QA ¦ QA
|  | Research phasing system | Engineering ¦ Backend Engineering
|  | Research phasing system | Engineering ¦ Gameplay Engineering
|  | Document phasing system | Engineering ¦ Backend Engineering
|  | Create phasing system | Engineering ¦ Gameplay Engineering
|  | Create phasing system | Engineering ¦ Backend Engineering
|  | Manage player session | Engineering ¦ Backend Engineering
|  | Record if player is online in redis | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create a session service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Custom HPA for Kubernetes | Engineering ¦ Backend Engineering
|  | Create Nodejs service | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Integrate Kubernetes API | Engineering ¦ Backend Engineering | [148 empty] | 3 | 5
|  | Create metrics to scale up and down | Engineering ¦ Backend Engineering | [148 empty] | 4 | 6
|  | Create rules when to merge instances | Engineering ¦ Backend Engineering | [148 empty] | 4 | 6
|  | Setup Kubernetes on Azure | Engineering ¦ Backend Engineering
|  | Setup azure | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Custom service to handle dungeons | Engineering ¦ Backend Engineering
|  | Create a service in nodejs | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a list of all dungeons that are currently running in redis | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Search for dungeon by id | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch dungeon ip by id | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Delete dungeon instance | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create dungeon instance | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Call backend to figure out which dungeon to connect to | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Player general stat before disconnecting service | Engineering ¦ Backend Engineering
|  | Create a way to save player stat (which server they were connected to last, which party were they connected to, etc..) before disconnecting | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Custom service for overworld zones | Engineering ¦ Backend Engineering
|  | Create a list of all overworld zones that are currently running in redis | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Search for overworld zones by id | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch overworld zones ip by id | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Delete overworld zones instance | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create overworld zones instance | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Call backend to figure out which overworld zones to connect to | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Inform UE server that a player is getting migrated to another UE server | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Inform UE server that a player is getting migrated to another UE server | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create a queue service | Engineering ¦ Backend Engineering
| Dungeon Mechanics |  |  | L | T0: Ideation | [143 empty] | 20
|  | Dungeons documentation | Design ¦ Game design | [108 empty] | 2 | 5
|  | Narrative | Design ¦ Narrative | [116 empty] | 0.5 | 1
|  | Multiplayer enviromental puzzle design | Design ¦ Game design | [108 empty] | 5 | 12
|  | Multiplayer enviromental puzzle layout | Design ¦ Level design | [112 empty] | 4 | 10
|  | Multiplayer enviromental puzzle integration | Engineering ¦ Gameplay Engineering
|  | Puzzles QA | QA ¦ QA
|  | BD Quest design | Design ¦ Game design | [108 empty] | 2 | 5
|  | BD Quest narrative design | Design ¦ Game design | [108 empty] | 3 | 8
|  | Partner Shop Blockout | Design ¦ Level design | [112 empty] | 3 | 4
|  | BD Quest integration | Engineering ¦ Backend Engineering | [148 empty] | 5 | 10
|  | Partner themed shop concept | Art ¦ Concept Art
|  | Partner themed shop model | Art ¦ Environment Art
|  | Partner themed shop props | Art ¦ Environment Art
|  | Used Partner Portals | Art ¦ Environment Art
|  | Assets & Portals Models | Art ¦ Environment Art
|  | Portals Placement in the shop | Art ¦ Environment Art
|  | BD Quest themed reward model | Art ¦ Character Art
|  | BD quest special macguffin reward | Design ¦ Game design
|  | Special item design | Design ¦ Game design | [108 empty] | 1 | 1
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Environment Art
|  | Tech art | Art ¦ TechArt
|  | Behavior implementation | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Audio | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | UI | Art ¦ UX/UI | [123 empty] | 5
|  | VFX | Art ¦ VFX
|  | QA | QA ¦ QA
|  | Join dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Dungeon UI | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Transition to dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Dungeon gameplay loop | Engineering ¦ Gameplay Engineering | [144 empty] | 10 | 20
|  | Dungeon character | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Dungeon end reward and condition | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | dungeon character respawn | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | dungeon transition to out of dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Make puzzle | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
| The Dungeon |  |  | L | T0: Ideation | [107 empty] | 35 |  | 10 |  | 15 | [15 empty] | 30 | [15 empty] | 10
| Partner Portal |  |  | M | T1: R&D | [127 empty] | 5 | [7 empty] | 17 | [7 empty] | 20
|  | Partner shop portal placement | Design ¦ Game design | [109 empty] | 1
|  | Portals design | Design ¦ Game design | [109 empty] | 1
|  | Partner Portal Integration | Engineering ¦ Backend Engineering | [148 empty] | 10 | 15
|  | Partner Portal VFX | Art ¦ VFX
|  | Partner Portal Enviro Art | Art ¦ Environment Art
|  | Partner Portal Integration | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
| World Bosses |  |  | L | T0: Ideation
| Corruption Heatmap |  |  | M | T1: R&D
| Biome - Portal Peak |  |  | M | T4: MVP
|  | PP Design | Design ¦ Game design | [108 empty] | 3 | 5
|  | PP Blockout | Design ¦ Level design | [112 empty] | 10 | 20
|  | PP Concept | Art ¦ Concept Art
|  | PP Foliage | Art ¦ Environment Art
|  | PP Props Build | Art ¦ Environment Art
|  | PP layout | Art ¦ Environment Art
|  | PP Audio | Audio ¦ Audio | [154 empty] | 14 | 15
|  | Portal Peak QA | QA ¦ QA
|  | Portal Dimension Design | Design ¦ Game design | [108 empty] | 1 | 1
|  | Portal Dimension Blockout | Design ¦ Level design | [112 empty] | 1 | 15
|  | Portal Dimension Concept | Art ¦ Concept Art
|  | Portal Dimension Foliage | Art ¦ Environment Art
|  | Portal Dimension Props Build | Art ¦ Environment Art
|  | Portal Dimension layout | Art ¦ Environment Art
|  | Portal Dimension Audio | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | Portal Dimension QA | QA ¦ QA
|  | Final Tower Design | Design ¦ Game design | [108 empty] | 1 | 1
|  | Final Tower Blockout | Design ¦ Level design | [112 empty] | 1 | 5
|  | Final Tower Concept | Art ¦ Concept Art
|  | Final Tower Foliage | Art ¦ Environment Art
|  | Final Tower Props Build | Art ¦ Environment Art
|  | Final Tower layout | Art ¦ Environment Art
|  | Final Tower Audio | Audio ¦ Audio | [154 empty] | 3 | 2
| Biome - Hidden Hills |  |  | M | T0: Ideation
|  | The Two Hills Design | Design ¦ Game design | [108 empty] | 4 | 5
|  | The Two Hills Blockout | Design ¦ Level design | [112 empty] | 3 | 15
|  | The Two Hills Concept | Art ¦ Concept Art
|  | The Two Hills Foliage | Art ¦ Environment Art
|  | The Two Hills Props Build | Art ¦ Environment Art
|  | The Two Hills layout | Art ¦ Environment Art
|  | The Two Hills Audio | Audio ¦ Audio | [154 empty] | 4 | 4
|  | The Two Hills QA | QA ¦ QA
| Biome - Farmlands |  |  | M | T0: Ideation
| Biome - Mistrun Shore |  |  | M | T0: Ideation
| Biome - Whispering Woods |  |  | M | T0: Ideation
|  | Waterfall Beauty Spot Concept | Art ¦ Concept Art
|  | Waterfall Beauty Spot Design | Design ¦ Game design | [108 empty] | 2 | 2
|  | Waterfall Beauty Spot Blockout | Design ¦ Level design | [112 empty] | 1 | 4
|  | Waterfall Beauty Spot Foliage | Art ¦ Environment Art
|  | Waterfall Beauty Spot Props Build | Art ¦ Environment Art
|  | Waterfall Beauty Spot layout | Art ¦ Environment Art
|  | Waterfall Beauty Spot Audio | Audio ¦ Audio | [154 empty] | 4 | 3
|  | Waterfall Spot QA | QA ¦ QA
| Biome - Tranquil Sands |  |  | M | T0: Ideation
| Biome - Torrential Vale |  |  | M | T0: Ideation
| Biome - Clockwork |  |  | M | T0: Ideation
| Biome - Downtime |  |  | M | T4: MVP
|  | Multiplayer interactions (toasts) | Design ¦ Game design | [108 empty] | 2 | 2
|  | Downtime Shops closed area | Design ¦ Game design | [108 empty] | 2 | 2
|  | Downtime Social Hub Area Blockout | Design ¦ Level design | [112 empty] | 6 | 6
|  | Downtime Tavern Blockout | Design ¦ Level design | [112 empty] | 3 | 7
|  | Downtime Tavern Concept | Art ¦ Concept Art
|  | Downtime Tavern Model | Art ¦ Environment Art
|  | Downtime Tavern Props | Art ¦ Environment Art
|  | NPC behaviour document | Design ¦ Game design | [109 empty] | 2
|  | Downtime NPC placement | Design ¦ Game design | [108 empty] | 4 | 5
|  | Downtime shops storefronts models | Art ¦ Environment Art
|  | Downtime Auction House storefront model | Art ¦ Environment Art
|  | Downtime Bank storefront model | Art ¦ Environment Art
|  | Downtime Barbersmith storefront model | Art ¦ Environment Art
|  | Downtime QA | QA ¦ QA
Combat
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Combat Framework |  |  | L | T2: GDD/TDD/Brief | [107 empty] | 24 | [13 empty] | 9 | [13 empty] | 30 |  | 60 | [5 empty] | 36 | [9 empty] | 6
|  | Combat Design | Design ¦ Game design | [108 empty] | 15 | 15
|  | Attacks Design Doc - per weapon (Combo + off-hand attacks) | Design ¦ Game design | [108 empty] | 3 | 4
|  | Weapon Attributes (per weapon) | Design ¦ Game design | [108 empty] | 1 | 1
|  | Combat Animations | Art ¦ Animation & Rigging
|  | Combat Montages | Art ¦ Animation & Rigging
|  | Combat Tech anim? | Art ¦ Animation & Rigging | [132 empty] | 10 | 20
|  | Combat integration | Engineering ¦ Gameplay Engineering
|  | Weapons models | Art ¦ Character Art
|  | Combat VFX | Art ¦ VFX
|  | Melee Combat QA | QA ¦ QA
|  | Weapon spesific hand poses | Art ¦ Animation & Rigging | [132 empty] | 2 | 2
|  | Aim offset implementation | Art ¦ Animation & Rigging | [132 empty] | 2 | 4
|  | Review the combat with networking engineer | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 5
|  | Death sequance system | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Pressure based agro | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 8
|  | Distance based agro | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Health based agro | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Utility managment | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Scaling | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | AI vs AI | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Player feedback | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Safety check | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Reflex check | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Survival check | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Social check | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Execution check | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | different types of movements | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | decision tick | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | utility abilities (healthing etc...) | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | attack abilities (attack etc...) | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
| Ranged Combat |  |  | M | T0: Ideation | [131 empty] | 30 |  | 10 | [9 empty] | 20
|  | Dual Wielding Ranged | Design ¦ Game design | [108 empty] | 2 | 4
|  | Ranged Attributes | Design ¦ Game design | [108 empty] | 5 | 5
|  | Aimed offsets | Art ¦ Animation & Rigging
| Combat AI Behavior |  |  | L | T0: Ideation | [107 empty] | 14 | [13 empty] | 6 | [9 empty] | 15 |  | 5 |  | 25 |  | 20 | [5 empty] | 6 | [9 empty] | 10
| Enemies Art |  |  | M | T0: Ideation | [107 empty] | 13 | [11 empty] | 10 |  | 30 |  |  |  | 15 | [5 empty] | 35 |  | 10 |  | 15 |  | 10 | [5 empty] | 20 | [9 empty] | 17
|  | Wolf montages | Art ¦ Animation & Rigging
|  | Wolf AI behaviour | Design ¦ Game design | [109 empty] | 2
|  | Design | Design ¦ Game design | [108 empty] | 2 | 5
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging | [132 empty] | 10 | 10
|  | Animation | Art ¦ Animation & Rigging
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | VFX | Art ¦ VFX
|  | Wolfy noises | Audio ¦ Audio | [154 empty] | 0 | 0
|  | Wolves QA | QA ¦ QA
|  | Goblin montages | Art ¦ Animation & Rigging
|  | Goblin AI behaviour | Design ¦ Game design | [109 empty] | 4
|  | SFX | Audio ¦ Audio | [154 empty] | 5 | 7
|  | Goblins QA | QA ¦ QA
|  | Skeleton montages | Art ¦ Animation & Rigging
|  | Skeleton AI behaviour | Design ¦ Game design | [109 empty] | 4
|  | Skeletons QA | QA ¦ QA
|  | Slimes AI behaviour | Design ¦ Game design | [109 empty] | 2
|  | Slimes QA | QA ¦ QA
|  | Narrative | Design ¦ Game design | [108 empty] | 2 | 1
|  | Quest structure | Design ¦ Game design | [108 empty] | 1 | 4
|  | Corrupted Enemies QA | QA ¦ QA
|  | Carapax AI design | Design ¦ Game design | [109 empty] | 4
|  | Carapax QA | QA ¦ QA
|  | Create animation graph | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Create control rig | Art ¦ Animation & Rigging | [132 empty] | 1 | 2
|  | Make combat moves | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | RBF setup | Art ¦ Animation & Rigging | [132 empty] | 2 | 4
|  | Seperate clothing from body | Art ¦ Animation & Rigging | [132 empty] | 2 | 2
|  | Custom death sequance | Art ¦ Animation & Rigging | [132 empty] | 1 | 2
| PvP Combat |  |  | L | T0: Ideation | [107 empty] | 16 | [13 empty] | 3 | [21 empty] | 3 | [9 empty] | 2
|  | PVP Combat design | Design ¦ Game design | [108 empty] | 5 | 12
|  | PVP Combat support | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | PVP only available in Arena | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | PVP Arena Design | Design ¦ Game design | [108 empty] | 6 | 7
|  | PVP Combat Setup | Design ¦ Game design | [109 empty] | 6
|  | PVP Arena concept | Art ¦ Concept Art
|  | PVP Arena blockout | Design ¦ Level design | [112 empty] | 3 | 10
|  | PVP Arena Foliage | Art ¦ Environment Art
|  | PVP Arena set dressing | Art ¦ Environment Art
|  | PVP Arena props | Art ¦ Environment Art
|  | PVP Arena Audio | Audio ¦ Audio | [154 empty] | 7 | 5
|  | PVP combat QA | QA ¦ QA
|  | Show damage numbers between players on hit | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 3
|  | Implement player prediction algorithm for networking | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Show other player HP in area fight | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | declare player who is connected as winner | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create fight timer and declare draw | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Reward player who won and display a message to the loser | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Sign up for arena fight actor | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Kick players that are in the area who are not fighting when you and someone else decide to start a fight | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | PVP area blocks player from entering and leaving | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create UI/UX | Art ¦ UX/UI
|  | Ensure combat system works | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
| Combat Balance & Telemetry |  |  | M | T2: GDD/TDD/Brief | [143 empty] | 40
|  | Create leaderboard collection | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create a leaderboard in dashboard (internal dashboard) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 4
|  | Delete a leaderboard from dashboard (internal dashboard) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Delete an entry from the leaderboard from dashboard (internal dashboard) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create UI for leaderboard in (internal dashboard) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch all leaderboards (internal dashboard) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update leaderboard from (social service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch leaderboard from (social service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Fetch leaderboard in unreal | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Update leaderboard in unreal | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
| Combat Abilities |  |  | L | T1: R&D | [107 empty] | 20 | [11 empty] | 2 |  | 10 | [9 empty] | 25 |  | 10 |  | 20 | [7 empty] | 30 | [9 empty] | 20
|  | Abilities Design | Design ¦ Game design | [108 empty] | 8 | 9
|  | 4 Abilities designed (2 weapons) | Design ¦ Game design | [108 empty] | 5 | 20
|  | Weapon attribute system | Design ¦ Game design | [108 empty] | 3 | 5
|  | Combat Abilities UI | Art ¦ UX/UI | [122 empty] | 8 | 15
|  | HUD Combat Abilities UI | Art ¦ UX/UI | [122 empty] | 8 | 5
|  | HUD design | Art ¦ UX/UI | [122 empty] | 5 | 7
|  | Combat Abilities integrated with skill path | Engineering ¦ Gameplay Engineering
|  | Combat abilities casting animations | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Combat Abilities QA | QA ¦ QA
|  | Combat Abilities SFX | Audio ¦ Audio | [154 empty] | 7 | 7
|  | Integrate abilities with skill path | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Make the abilities | Engineering ¦ Gameplay Engineering | [144 empty] | 10 | 12
|  | Combat SFX | Audio ¦ Audio
| Magic |  |  | L | T0: Ideation | [101 empty] | 5 | [5 empty] | 30 |  | 5 | [11 empty] | 10 | [9 empty] | 30 |  | 10 |  | 20 | [7 empty] | 30
|  | Magic Weapon (e.g. wand) | Design ¦ Game design | [108 empty] | 3 | 5
|  | Weapon | Art ¦ Environment Art
|  | Magic system design (5 spells) | Design ¦ Game design | [108 empty] | 5 | 10
|  | Magic implementation | Engineering ¦ Gameplay Engineering
|  | Magic UI (1 skill tree mapped out) | Art ¦ UX/UI | [122 empty] | 5 | 7
|  | Magic casting animations | Art ¦ Animation & Rigging
|  | Magic SFX | Audio ¦ Audio | [154 empty] | 7 | 5
|  | Magic VFX | Art ¦ VFX
|  | Magic QA | QA ¦ QA
|  | Magic system design (3-4 spells) | Design ¦ Game design
|  | make wand abilities 4 | Engineering ¦ Gameplay Engineering | [144 empty] | 10 | 15
|  | wand skill tree | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | make wand an item type | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | equipd wand | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
| Full Motion Video (FMV) |  |  | M | T1: R&D
|  | Intro supports FMV | Engineering ¦ Backend Engineering
|  | Create placeholder FMV playback flow | Engineering ¦ Backend Engineering
|  | Implement FMV skip behavior | Engineering ¦ Backend Engineering
|  | Implement transition after FMV | Engineering ¦ Backend Engineering
|  | FMV Production | Art ¦ Environment Art
|  | Integrate final/near-final FMV asset | Engineering ¦ Backend Engineering
|  | QA playback across target builds | QA ¦ QA
|  | Fix FMV blocker bugs | Engineering ¦ Backend Engineering
|  | Narrative - Cinematic scripting | Design ¦ Narrative | [116 empty] | 1 | 1
|  | Intro sequence plays 3 slides with voiceover | Engineering ¦ Backend Engineering
|  | Create intro sequence controller | Engineering ¦ Backend Engineering
|  | Display static slides full-screen | Engineering ¦ Backend Engineering
|  | Play voiceover synced to sequence | Engineering ¦ Backend Engineering
|  | Display subtitles synced to VO | Engineering ¦ Backend Engineering
|  | Implement skip behavior | Engineering ¦ Backend Engineering
|  | Implement transition to gameplay/menu | Engineering ¦ Backend Engineering
|  | Final art production | Art ¦ Concept Art
|  | VO production | Audio ¦ Audio | [154 empty] | 6 | 3
|  | Subtitles production | Design ¦ Game design | [108 empty] | 0.5 | 1
|  | Integrate final art + VO assets | Engineering ¦ Backend Engineering
|  | QA + fix blockers | QA ¦ QA
|  | Intro supports FMV | Engineering ¦ Gameplay Engineering
|  | Create placeholder FMV playback flow and allow designers to set the FMV easily | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | Create a system to disallow the player from moving while in FMV | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Implement FMV skip behavior | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Implement transition after FMV - Fade in/Fade out system | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Integrate final/near-final FMV asset | Engineering ¦ Gameplay Engineering
|  | Intro sequence plays 3 slides with voiceover | Engineering ¦ Gameplay Engineering
|  | Create intro sequence controller | Engineering ¦ Gameplay Engineering
|  | Allow this to be triggered from quest | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Display static slides full-screen | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Tool for designers | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | UI Design | Art ¦ UX/UI
|  | Play voiceover synced to sequence | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Display subtitles synced to VO | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Implement skip behavior | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Implement transition to gameplay/menu | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | VO production | Design ¦ Game design
|  | Integrate final art + VO assets | Design ¦ Game design
User Space
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| User Space Server & Instance |  |  | L | T2: GDD/TDD/Brief | [143 empty] | 60
|  | FTUE Design | Design ¦ Game design | [108 empty] | 3 | 5
|  | FTUE UI | Art ¦ UX/UI | [123 empty] | 5
|  | User Space Editor audio | Audio ¦ Audio | [154 empty] | 2 | 2
|  | Mutual Activity Design | Design ¦ Game design | [108 empty] | 2 | 4
|  | Mutual Activity UI | Art ¦ UX/UI | [123 empty] | 5
|  | Drinking design | Design ¦ Game design | [109 empty] | 1
|  | Drunken UI | Art ¦ UX/UI | [123 empty] | 4
|  | User Space is a separate instance | Engineering ¦ Backend Engineering
|  | User Space editor & UI | Engineering ¦ Gameplay Engineering
|  | User Space Ambience | Audio ¦ Audio | [154 empty] | 1 | 1
|  | Item SFX | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | Island ambient audio | Audio ¦ Audio | [154 empty] | 1 | 1
|  | User Space editor VFX | Art ¦ VFX
|  | User Space functionality QA | QA ¦ QA
|  | User Space GDD VS page | Design ¦ Game design | [109 empty] | 1
|  | User Space location concepts | Art ¦ Concept Art
|  | User Space location blockout | Design ¦ Level design | [112 empty] | 5 | 7
|  | User Space location set dressing | Art ¦ Environment Art
|  | User Space location props | Art ¦ Environment Art
|  | User Space location foliage | Art ¦ Environment Art
|  | User Space visuals QA | QA ¦ QA
|  | DevOps | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | IP address list service | Engineering ¦ Backend Engineering | [148 empty] | 5 | 6
|  | Multiple players join one server and only show what is relevent to current player | Engineering ¦ Gameplay Engineering | [144 empty] | 10 | 20
|  | Figure out friend ip address to join his server when invited | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Host permissions | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Edit mode improvmeents | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Save userspace furniture location in userspace | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Fetch userspace furniture from backend | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Update userspace furniture and tell that to all players | Engineering ¦ Gameplay Engineering | [144 empty] | 4 | 5
|  | Player joining friends userspace | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Enable fishing in userspace | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Load userspace from save data | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 7
|  | Setup animation for userspace editing tool | Art ¦ Animation & Rigging | [132 empty] | 1 | 1
|  | Implement interaction animation with userspace items (snap) | Art ¦ Animation & Rigging | [132 empty] | 1 | 5
| User Space Decoration |  |  | M | T0: Ideation | [107 empty] | 14 | [11 empty] | 20 | [9 empty] | 15 | [13 empty] | 30 | [9 empty] | 2
|  | User Space House concept | Art ¦ Concept Art
|  | User Space House model | Art ¦ Environment Art
|  | User Space furniture props | Art ¦ Environment Art
| P2P / P2G User Space Connection |  |  | M | T2: GDD/TDD/Brief | [107 empty] | 1 | [35 empty] | 30
| Building Houses |  |  | L | T1: R&D | [121 empty] | 3 | [21 empty] | 60 | [9 empty] | 2
| Saving House Layouts |  |  | M | T0: Ideation | [143 empty] | 30
| Partner Portal System (player house) |  |  | M | T0: Ideation
| Arcade Cabinet |  |  | M | T1: R&D
| Anywhere Door Placement |  |  | S | T0: Ideation | [119 empty] | 5 | [15 empty] | 15 | [7 empty] | 5
|  | User space door can be placed at predefined spots | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Anywhere Door QA | QA ¦ QA
|  | Create endpoint to update the position, rotation and zone name of MULTIPLE anywhere door in backend (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create fetech anywhere door endpoint (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update anywhere door position, rotation, zone name after fethcing anywhere door info from (player data serivce) | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create an ability to place anywhere door in the world | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create anywhere door as item in backend service. | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create anywhere door as item. | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Show if the anywhere door is placed or not placed to remove it if needed | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show anywhere door on map | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show anywhere door on minimap | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show anywhere door on compass | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Make anywhere door as an actor | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Remove anywhere door | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | fetch anywhere door info from backend service and place it in the world | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Make spesific regions where anywhere door can be placed | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
Items & Inventory
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Item Core System |  |  | L | T2: GDD/TDD/Brief | [143 empty] | 30
|  | Starting Chest | Design ¦ Game design | [108 empty] | 0.5 | 5
|  | Chest concept | Art ¦ Concept Art
|  | Chest model | Art ¦ Environment Art
|  | Chest animation | Art ¦ Animation & Rigging | [132 empty] | 1 | 1
|  | Chest VFX | Art ¦ VFX
|  | QA check | QA ¦ QA
|  | Shield | Design ¦ Game design | [108 empty] | 2 | 4
|  | Shield animations | Art ¦ Animation & Rigging
|  | Shield Asset | Art ¦ Environment Art
|  | Starting Sword | Design ¦ Game design | [108 empty] | 0.5 | 4
|  | Sword concept | Art ¦ Concept Art
|  | Sword model | Art ¦ Character Art
|  | Sword animations | Art ¦ Animation & Rigging | [132 empty] | 5 | 10
|  | Sword VFX | Art ¦ VFX
|  | Equipment Stats integrated with character stats | Design ¦ Game design | [108 empty] | 5 | 5
|  | Equipment Stats integrated with character stats | Engineering ¦ Gameplay Engineering
| Inventory System |  |  | M | T2: GDD/TDD/Brief | [119 empty] | 10 |  | 30 | [13 empty] | 20 | [7 empty] | 20 | [9 empty] | 2
| Equipment System |  |  | M | T0: Ideation | [107 empty] | 10 | [11 empty] | 10 |  | 40 | [15 empty] | 10 | [5 empty] | 20
|  | an endpoint to all items equiped (batch requests only send what changed) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create an endpoint to store abilities in internal dashboard | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to fetch abilities internal dashboard | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to remove ability internal dashboard | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to fetch equiped items | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to euip items | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | an endpoint to update all item and abilities position in the hotbar (batch requests only send what changed) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create endpoint to fetch hotbar items and abilities | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create unit test for updating, fetching | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Send an HTTP reuqest only after 2 seconds after not moving any items or abilities in hotbar | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Get hotbar item and abiltitie positions and set them | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 3
|  | Fetch and set equiped items | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
| Loot Distribution |  |  | M | T2: GDD/TDD/Brief | [107 empty] | 3 | [13 empty] | 10 | [13 empty] | 30 | [7 empty] | 30
|  | Loot distribution design | Design ¦ Game design | [109 empty] | 3
|  | Loot is distributed after the raid | Engineering ¦ Gameplay Engineering
|  | Loot distribution QA | QA ¦ QA
|  | Create loot distribution collection ( internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Update loot distribution collection ( internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch loot distribution collection (internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create loot distribution system which lets Actors inherit from multiple templates | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Refreance loot table in enemy/actor in tool | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create a new loot table in tool | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Save temp loot table in tool | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Edit loot table in CH tool | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Delete loot table in CH tool | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Fetch current loot tables in CH tool | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Release loot table in CH tool | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create a system for actors to referance loot table | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Enemies drop item when they are killed | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | distrubute loot according to dungeon rules | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
| Mounts / Pets |  |  | L | T1: R&D | [107 empty] | 5 |  | 2 | [21 empty] | 13 |  | 3 |  | 5 |  | 2 | [5 empty] | 20
|  | Pet system design | Design ¦ Game design | [109 empty] | 4
|  | Pet concepts | Art ¦ Concept Art
|  | Pet model | Art ¦ Character Art
|  | Pet animations | Art ¦ Animation & Rigging
|  | Pet VFX | Art ¦ VFX
|  | Pet behavior | Engineering ¦ Gameplay Engineering
|  | Pet integration | Engineering ¦ Gameplay Engineering
|  | Pet QA | QA ¦ QA
|  | Teleport pet to player when pet is stuck | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Review pet system code | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Pet maya rig setup | Art ¦ Animation & Rigging | [132 empty] | 2 | 2
|  | Pet animation grpah setup | Art ¦ Animation & Rigging | [132 empty] | 2 | 2
| Banks |  |  | M | T0: Ideation | [107 empty] | 1 | [11 empty] | 5 | [23 empty] | 20 | [9 empty] | 1
| P2P Item Transfer |  |  | M | T0: Ideation | [143 empty] | 30
| Consumables |  |  | S | T2: GDD/TDD/Brief | [121 empty] | 2 | [9 empty] | 5 | [21 empty] | 2
|  | Check the health potion usage | QA ¦ QA
|  | Implement drinking animation | Art ¦ Animation & Rigging | [132 empty] | 1 | 1
| Durable Items |  |  | S | T0: Ideation
Player Economy
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Trading System |  |  | L | T0: Ideation | [107 empty] | 10 | [13 empty] | 30 | [21 empty] | 40 | [9 empty] | 3
|  | Shop Fake Fascia Design | Design ¦ Game design | [108 empty] | 5 | 1
|  | Clothing Shop Basic Contents | Design ¦ Game design | [108 empty] | 2 | 3
|  | Shops Concepts | Art ¦ Concept Art
|  | Shops Models & Set dressing | Art ¦ Environment Art
|  | Shop props | Art ¦ Environment Art
|  | Vendors Concepts | Art ¦ Concept Art
|  | Vendors Models | Art ¦ Character Art
|  | Vendors animation | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Trading UX/UI | Art ¦ UX/UI | [122 empty] | 15 | 15
|  | Currency Integration | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Soft Currency (gold) icon | Art ¦ Concept Art
|  | Premium currency icon | Art ¦ Concept Art
|  | P2G Transactions Support | Engineering ¦ Backend Engineering
|  | Trading System QA | QA ¦ QA
|  | Create vendor collection ( internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update vendor collection ( internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch vendor collection (internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create fresh cron job to refresh item stacks for vendors (internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | delete items and vendor (internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Update NPC tool to match vendor in unreal engine | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Release vendor in game from tempate to release | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | fetch last 20 items sold, buyback item, Create buyback functionality | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Create a list of sold items (redis / server) ??? fetch, create buyback endpoint, update endpoint, pipeline | Engineering ¦ Backend Engineering | [148 empty] | 5 | 7
|  | Fetch a list of sold items | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create buy endpoint | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create sell endpoint | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Use buy endpoint | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Use sell endpoint | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Update UI | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
| Currency System |  |  | M | T0: Ideation | [107 empty] | 10 |  | 2 | [9 empty] | 2 |  | 30 | [21 empty] | 20
| Auction House |  |  | L | T0: Ideation | [143 empty] | 120
|  | P2G Transactions Support | Engineering ¦ Backend Engineering
|  | Trading System QA | QA ¦ QA
| In-game Store |  |  | M | T0: Ideation | [143 empty] | 60
|  | Virtual currency balance and items | Design ¦ Game design | [109 empty] | 2
|  | RMT subscription design | Art ¦ UX/UI | [122 empty] | 8 | 3
|  | RNT partner store | Art ¦ UX/UI | [123 empty] | 3
|  | RMT virtual currency page | Art ¦ UX/UI | [123 empty] | 3
|  | RMT store integration | Engineering ¦ Backend Engineering
|  | RMT Store SFX | Audio ¦ Audio | [154 empty] | 7 | 7
|  | RMT Store QA | QA ¦ QA
|  | RMT store design | Design ¦ Game design
|  | Fetch total owned virtual currancy | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create an endpoint to fetch total owned virtual currancy from store service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Call purchase virtual currnacy endpoint from Unreal | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create a purchase virtual currancy endpoint in store service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to fetch all store items, prices, images, titles from store service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update in-game store when fetching store items | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create purcahse item endpoint in store service | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Call purchase item endpoint in unreal and sned item to player mailbox when item is purchased | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create an endpoint to add items to in-game store in dashboard management service | Engineering ¦ Backend Engineering | [148 empty] | 4 | 5
|  | Create an endpoint to update items to in-game store in dashboard management service | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create an endpoint to remove items from in-game store in dashboard management service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to pause the purcahsing of an item from in-game store in dashboard managment serivce | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Display paused banner on paused items with a tooltip explaining why the item is paused | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Set a limit on items. example gun only 100 people can buy it. first come first serve | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Connect UI with code | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | RMT Store UI | Art ¦ UX/UI
|  | Basic RMT balance config | Design ¦ Game design
| In-game Economy |  |  | L | T0: Ideation | [107 empty] | 90 | [13 empty] | 30
|  | Basic Economy configuration | Design ¦ Game design | [108 empty] | 10 | 5
|  | In-game economy QA check | QA ¦ QA
| RMT Game Economy |  |  | L | T0: Ideation | [143 empty] | 60
| IG / RMT Monitoring System |  |  | M | T0: Ideation
Quest System
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Quests Backend / Tooling |  |  | L | T2: GDD/TDD/Brief | [143 empty] | 60
|  | Tutorial Quest Chain Configuration & Setup | Design ¦ Game design | [108 empty] | 7 | 10
|  | QA check | QA ¦ QA
|  | Green Faction NPC Concepts | Art ¦ Concept Art
|  | Green Faction NPC Models | Art ¦ Character Art
|  | Green Faction NPC animations | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Green Faction NPC dialogue setup | Design ¦ Narrative | [116 empty] | 1 | 2
|  | Green Faction NPCs placement | Design ¦ Game design | [108 empty] | 2 | 2
|  | Quest Editor | Design ¦ Game design | [108 empty] | 5 | 2
|  | Dialogue System Design | Design ¦ Game design | [108 empty] | 3 | 3
|  | Dialogue System | Engineering ¦ Backend Engineering
|  | Dialogue UI | Art ¦ UX/UI | [123 empty] | 10
|  | Quest Log | Engineering ¦ Backend Engineering
|  | Quest Log QA | QA ¦ QA
|  | Xyron narrative | Design ¦ Game design | [108 empty] | 2 | 2
|  | Green Faction NPC dialogue setup | Design ¦ Game design
|  | Dialogue System | Engineering ¦ Gameplay Engineering | [144 empty] | 0 | 0
|  | Quest Log | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
| Quests as Events |  |  | M | T1: R&D | [121 empty] | 30 | [21 empty] | 30
| Quest Multiplayer |  |  | L | T1: R&D | [107 empty] | 5 | [13 empty] | 30 | [21 empty] | 30
| Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking |  |  | L | T2: GDD/TDD/Brief | [101 empty] | 2 | [5 empty] | 3 | [35 empty] | 30
|  | Lockpicking | Design ¦ Game design | [108 empty] | 7 | 2
|  | Lockpicking Concept | Art ¦ Concept Art
|  | Lockpicking UI | Art ¦ UX/UI | [122 empty] | 8 | 6
|  | Lockpicking Integration | Engineering ¦ Gameplay Engineering
|  | Lockpicking Techart | Art ¦ TechArt
|  | Lockpicking QA check | QA ¦ QA
|  | Design interface for quest types | Design ¦ Game design | [108 empty] | 2 | 5
|  | Other quest types support? | Engineering ¦ Gameplay Engineering
|  | Check if lockpicking solution is correct | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create an actor with a grid for all tiles | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create data asset | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | Create pipe entity actor | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create magnatic enitity actor | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create ball entity actor to compelete the game | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | Start and end condition | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 0.5
|  | Create a system to modify ball proaprties while traveling | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | VFX | Art ¦ VFX
|  | SFX | Audio ¦ Audio
|  | Implement VFX and SFX | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create quest tool | Engineering ¦ Gameplay Engineering | [144 empty] | 20 | 20
|  | Create quest system backend service | Engineering ¦ Backend Engineering | [148 empty] | 20 | 20
| Quest Reward System |  |  | M | T0: Ideation | [121 empty] | 10 | [21 empty] | 20
|  | Quest UI Audio | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | Quest Reward UI | Art ¦ UX/UI | [123 empty] | 5
|  | Quest Reward System design doc | Design ¦ Game design | [109 empty] | 2
|  | Quest Reward List | Design ¦ Game design | [108 empty] | 2 | 2
|  | Rewards Choice | Engineering ¦ Gameplay Engineering
|  | Quest Rewards QA | QA ¦ QA
| Quest Log |  |  | M | T0: Ideation | [121 empty] | 10 | [21 empty] | 20
| Quest Dialog GUI |  |  | M | T0: Ideation | [107 empty] | 4 |  | 2 | [5 empty] | 4 | [5 empty] | 30
| Quest Narrative Content |  |  | L | T2: GDD/TDD/Brief | [101 empty] | 3 | [5 empty] | 4 | [7 empty] | 7 | [5 empty] | 20
|  | Quest Flow Design & Narrative Overview | Design ¦ Game design | [108 empty] | 2 | 3
|  | Cave Intro Quest | Design ¦ Game design
|  | Quest Narrative Doc | Design ¦ Narrative | [116 empty] | 0.5 | 1
|  | Quest Design Doc | Design ¦ Game design | [108 empty] | 3 | 3
|  | Quest Implementation | Design ¦ Game design | [108 empty] | 3 | 3
|  | Quest Playtesting & Revision | Design ¦ Game design | [108 empty] | 2 | 5
|  | Docs, Implement, Revise | Design ¦ Game design | [108 empty] | 7 | 7
| In Game Cinematic (IGC) |  |  | L | T2: GDD/TDD/Brief
|  | The game supports cutscenes | Engineering ¦ Gameplay Engineering
|  | Cutscene trigger system | Engineering ¦ Gameplay Engineering
|  | Camera control during cutscene | Engineering ¦ Gameplay Engineering
|  | Player control lock/unlock | Engineering ¦ Gameplay Engineering
|  | NPC/character sequencing | Engineering ¦ Gameplay Engineering
|  | Dialogue playback (in-cutscene) | Engineering ¦ Gameplay Engineering
|  | Cutscene skip functionality | Engineering ¦ Gameplay Engineering
|  | Transition in/out of cutscene | Engineering ¦ Gameplay Engineering
|  | Basic cutscene sequencing (timeline) | Engineering ¦ Gameplay Engineering
|  | Cutscene stability (QA & fixes) | QA ¦ QA
|  | Cutscene content | Design ¦ Game design | [108 empty] | 5 | 5
|  | Narrative | Design ¦ Narrative | [116 empty] | 0.5 | 1
|  | Camera behavior implementation/fixes | Engineering ¦ Gameplay Engineering
|  | Combat Camera | Design ¦ Game design | [108 empty] | 4 | 9
|  | Camera QA | QA ¦ QA
|  | Custom camera position and rotation | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Custom camera animations | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Stream camera position (world partition) | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Implement camera according to design | Engineering ¦ Gameplay Engineering | [144 empty] | 6 | 7
| Meta Quest System |  |  | M | T0: Ideation
| Quest Generator System |  |  | L | T0: Ideation
| Targeted VO |  |  | M | T2: GDD/TDD/Brief | [109 empty] | 2 | [5 empty] | 20 | [37 empty] | 10
Social & Multiplayer
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Game Chat System |  |  | M | T1: R&D | [101 empty] | 1 | [5 empty] | 12 | [13 empty] | 20 | [21 empty] | 60
|  | General systems | Engineering ¦ Backend Engineering
|  | Create pipeline and deploy | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create chat service in go | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a serialization/deserialization system | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create a list of users info such as server ip and usernames | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create a multithreaded system | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create a custom protocol using TCP | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create a heartbeat system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a packet system | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Connect to redis | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Proximity chat | Engineering ¦ Backend Engineering
|  | Send chat message only to people near you | Engineering ¦ Backend Engineering | [148 empty] | 4 | 5
|  | Zone channel | Engineering ¦ Backend Engineering
|  | Create a way to send a chat to entire zone | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Private message | Engineering ¦ Backend Engineering
|  | Send a private message to user | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Party chat | Engineering ¦ Backend Engineering
|  | Send a party message to your party | Engineering ¦ Backend Engineering | [148 empty] | 4 | 5
|  | Guild chat | Engineering ¦ Backend Engineering
|  | Send a message to your guild | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | System chat | Engineering ¦ Backend Engineering
|  | Create a system chat which will warn you on if the server is shutting down or if Show invites, kicks, bans in chat | Engineering ¦ Backend Engineering | [148 empty] | 4 | 5
|  | Chat text limit | Engineering ¦ Backend Engineering
|  | Create a system to limit the amount of text sent | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Chat spam filter | Engineering ¦ Backend Engineering
|  | Create a system to rate limit messages | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Profanity filter | Engineering ¦ Backend Engineering
|  | Create a system to filter a set of words | Engineering ¦ Backend Engineering | [148 empty] | 3 | 5
|  | Chat UI | Art ¦ UX/UI
|  | Auto scroll incomming chat messages | Art ¦ UX/UI
|  | Different colours for different type of message | Art ¦ UX/UI
|  | integraet chat service in unreal using websockets | Engineering ¦ Gameplay Engineering
|  | Create a websocket connection | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Create a way to receive messages on unreal server and pass that to client | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Create a way to send a message from unreal server to chat server | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
| Friends |  |  | M | T1: R&D | [121 empty] | 30 | [21 empty] | 20
| Guilds |  |  | L | T1: R&D | [101 empty] | 1 | [5 empty] | 20 | [13 empty] | 10 | [21 empty] | 40
|  | Guilds system design | Design ¦ Game design | [109 empty] | 15
|  | Guild house is an instance | Engineering ¦ Backend Engineering
|  | Guild house concept | Art ¦ Concept Art
|  | Guild house model | Art ¦ Environment Art
|  | Guild house props | Art ¦ Environment Art
|  | Guild house TV + video | Art ¦ Environment Art
|  | Guild NPCs | Art ¦ Character Art
|  | Guild house blockout | Design ¦ Level design | [112 empty] | 4 | 10
|  | Sitting NPCs | Art ¦ Animation & Rigging
|  | Guild UI | Art ¦ UX/UI | [123 empty] | 3
|  | Guild chat | Engineering ¦ Gameplay Engineering
|  | Guild Chat design | Design ¦ Game design | [108 empty] | 3 | 1
|  | Guild QA | QA ¦ QA
|  | Guild house | Engineering ¦ Gameplay Engineering
|  | Guild house entry | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Guild house leave | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Guild house server | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Connect Guild UI | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
| Co-op / Party |  |  | M | T1: R&D | [101 empty] | 2 | [5 empty] | 5 |  | 2 | [11 empty] | 6 | [21 empty] | 60
|  | Party formation | Engineering ¦ Backend Engineering | [148 empty] | 3 | 8
|  | Party system design | Design ¦ Game design | [109 empty] | 5
|  | Party chat | Design ¦ Game design
|  | Party supports real players and bots | Engineering ¦ Backend Engineering
|  | Party UI | Art ¦ UX/UI | [123 empty] | 2
|  | Party chat | Engineering ¦ Gameplay Engineering
|  | Party QA | QA ¦ QA
|  | Create party puzzle | Engineering ¦ Gameplay Engineering
|  | Make a puzzle | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 5
|  | Create pipeline and deploy | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create party service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a serialization/deserialization system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a list of users info such as server ip and usernames | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a multithreaded system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a custom protocol using TCP | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a heartbeat system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a packet system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Connect to redis | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Invite someone to party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Kick someone from party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Roll check in party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Leave party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Disband party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Change leadership | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update party player position on map, mana, health | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create a party | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Invite someone to party | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Kick someone from party | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Roll check in party | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Leave party | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Disband party | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Change leadership | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Update party player position on map, mana, health | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
| Co-op / Raids |  |  | L | T1: R&D | [143 empty] | 40
| Dueling |  |  | M | T1: R&D
| In-game Mail |  |  | S | T2: GDD/TDD/Brief | [101 empty] | 1 | [5 empty] | 3 | [7 empty] | 2 |  |  |  | 1 |  | 10 | [21 empty] | 20
|  | In-game Mail backend | Engineering ¦ Backend Engineering
|  | In-game UI | Art ¦ UX/UI | [123 empty] | 10
|  | In-game Mail frontend/UI | Engineering ¦ Gameplay Engineering
|  | Mail UI Audio | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | Mail QA | QA ¦ QA
|  | Postbox Concept | Art ¦ Concept Art
|  | Postbox VFX | Art ¦ VFX
|  | Postbox SFX | Audio ¦ Audio | [154 empty] | 1 | 1
|  | Postbox Model | Art ¦ Environment Art
|  | Restore trash mail | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Mark mail as read | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Delete mail | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Claim items from mail | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Send mail from one player to another with items | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Restore trash mail | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Mark mail as read | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Delete mail | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Claim items from mail | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Claim currancy and increase ingame gold | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Send mail from one player to another with items | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create mail UI/UX | Art ¦ UX/UI
|  | Create mail SFX | Audio ¦ Audio
|  | Create new mail model | Art ¦ Environment Art
| Notifications |  |  | S | T1: R&D | [143 empty] | 30
| Player Config PvP Server |  |  | M | T0: Ideation
| LFG / Pick-up Groups |  |  | M | T0: Ideation | [143 empty] | 40
|  | Create Dungeon finder UI/UX | Art ¦ UX/UI
|  | Connect dungeons to UI | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 8
|  | Create pipeline and deploy | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create dungeon finder service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Add player to dungeon finder list | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch a list of players queued up for dungeon by dungon id | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Remove player from dungeon queue | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Connect to redis | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Invite player to party | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Queue group for dungeon | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Send request to add player to dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Send request to remove player from dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Send request to fetch player from dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Remove party from queue after party is full | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Remove party from queue after party is full | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Send player status in dungeon finder | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Get player status in dungeon finder | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
Game Bibles
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| UX/UI Bible |  |  | M | T0: Ideation
| Accessibility Guidelines |  |  | M | T0: Ideation
| Brand Bible |  |  | M | T2: GDD/TDD/Brief
| Art Bible |  |  | L | T3: Prototype
| Monetization Bible |  |  | M | T0: Ideation | [107 empty] | 40
| Red Books (Live Service emergency guidelines) |  |  | M | T0: Ideation | [143 empty] | 30
Platform
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Player Account Creation / Deletion |  |  | M | T2: GDD/TDD/Brief | [143 empty] | 10
| Player Account Authentication |  |  | M | T2: GDD/TDD/Brief | [143 empty] | 15
| Player Account Privacy Settings & Legal |  |  | M | T1: R&D | [143 empty] | 10
| Player Dashboard - Account Features |  |  | M | T1: R&D | [143 empty] | 30
| Player Dashboard - Game Dashboard |  |  | M | T1: R&D | [143 empty] | 30
| Player Dashboard - Friends |  |  | M | T1: R&D | [143 empty] | 30
| Player Dashboard - Search & Notifications |  |  | M | T1: R&D | [143 empty] | 30
| Player Dashboard - Marketplace |  |  | L | T1: R&D | [143 empty] | 30
| Developer Dashboard - Developer Account |  |  | M | T1: R&D
| Developer Dashboard - Game Dashboard |  |  | M | T1: R&D
| Developer Dashboard - Settings & Support |  |  | M | T1: R&D
| Quest Tracking |  |  | M | T1: R&D | [143 empty] | 20
| Payment Processing (incl. Refunds) |  |  | L | T0: Ideation
| Online Services & Backend |  |  | L | T0: Ideation
|  | List of servers and their ip address | Engineering ¦ Backend Engineering | [148 empty] | 4 | 5
|  | Create an endpoint to store player X, Y, Z corrdinates and rotation and server ip address | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create an endpoint to fetch player position, rotation and IP address | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create unit test for update and fetch endpoint | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Set player position, rotation, when spawning player | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Conect to last server player left from | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Save player position and rotation and ip every X seconds on server, so if the server crashes we can retrieve this information later | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | For network engineer to figure out | Engineering ¦ Gameplay Engineering
|  | Pass entrance parameters from one server to another | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Set entrace points on map | Design ¦ Game design
|  | Set spawn position according to entrance paramters | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
| Launcher & Distribution |  |  | L | T2: GDD/TDD/Brief
| Partner Loop |  |  | M | T1: R&D
|  | Full partner loop definition/design | Design ¦ Game design | [108 empty] | 3 | 5
|  | Create Partner Store | Engineering ¦ Backend Engineering | [148 empty] | 10 | 20
|  | Integrate partner loop | Engineering ¦ Backend Engineering | [148 empty] | 5 | 10
|  | Buy game subscription time from website and/or from game | Engineering ¦ Backend Engineering
|  | Buy CH virtual currency | Engineering ¦ Backend Engineering
|  | Complete partner quest | Engineering ¦ Backend Engineering
|  | Purchase partner game from in-game store | Engineering ¦ Backend Engineering
|  | Redeem Partner Steam key | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Download Partner game | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Run partner game from same exe as CH | Engineering ¦ Backend Engineering
|  | Unlock partner item in CH by playing partner game | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Claim partner item from CH mailbox | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Partner functionality QA | QA ¦ QA
|  | Claim partner item from CH mailbox | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Run partner game from same exe as CH | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Create IPC between exe launcher and unreal and partner game | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create exe launcher | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Run CH in exe launcher | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Run partner in exe launcher | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Transition to lightweight map before launching partner game from exe launcher | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
| Game Tool Integration (incl. Game Key Generation) |  |  | M | T1: R&D
| Account Level Settings |  |  | S | T0: Ideation
| Social Media Support |  |  | M | T0: Ideation | [143 empty] | 20
Live Game
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Live GDD |  |  | M | T0: Ideation
| Content |  |  | L | T0: Ideation
| Forecast |  |  | M | T0: Ideation
| Analytics & BI |  |  | L | T0: Ideation
| Sales Dashboard |  |  | M | T0: Ideation
| Telemetry |  |  | L | T0: Ideation
| Live Service Event Plan |  |  | L | T0: Ideation
Partner Build
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Partner = Feature definition |  |  | S | T0: Ideation
| Sign Partner |  |  | S | T0: Ideation
| Partner Brief |  |  | M | T0: Ideation
| Partner Design Doc |  |  | M | T0: Ideation
| Partner TDD |  |  | M | T0: Ideation
| Partner Art Brief |  |  | M | T0: Ideation
| Partner Build |  |  | L | T0: Ideation
| Partner Integration |  |  | M | T0: Ideation
Product Publishing
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Web Presence |  |  | M | T0: Ideation
| Website |  |  | M | T0: Ideation
|  | Create UI to display web browser inside the game launcher | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Pass data between in-launcher browswer and launcher | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Change play button from subscribe to play when a subscription is active | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Fetch subscription information from backend service | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | New UI/UX for game launcher to support web browser | Art ¦ UX/UI
|  | Create subscription endpoint in store service with tier rewards / different time lengths (30 , 90 , 180 , 360 ) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create an endpoint to cancel subsciption | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to fetch current subscription information from account managment service | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create a subscription page in the store | Engineering ¦ Backend Engineering | [148 empty] | 3 | 5
| Community Persona |  |  | M | T0: Ideation
| Title Identity |  |  | M | T0: Ideation
| Player Support |  |  | M | T0: Ideation
| Go-To-Market Strategy & Implementation |  |  | L | T0: Ideation
| 3rd-party Store Publishing |  |  | M | T0: Ideation