## Plan
METADATA | [10 empty] | DESIGN ESTIMATES (Robin Jubber — Game Director) | [18 empty] | ENGINEERING ESTIMATES (Mustafa Sibai — Head of Engineering) | [20 empty] | MIRO BID TOTALS — Agreed Days per Role (feature level)
[11 empty] | Yorgos Dritsas (Jr Game Designer) |  | Nadir Latif (Combat Designer) |  | Kieron Naylor (Technical Designer) |  | Panos Andriopoulos (Jr Level Designer) |  | Nikolas Tziotis (Jr Level Designer) |  | Seth Dahl (Jr Level Designer) |  | Maria Cibej (Jr Writer) |  | Hannah Pickard (QA) |  | Aggeliki Peroutsea (Jr Sound Designer) |  | Design Final | Samer Balushi (Backend Developer) |  | Nikos Gerontakis (Sr Full Stack Developer) |  | Daniel Negri (Sr Full Stack Developer) |  | Ilya Achmetov (Gameplay Developer) |  | Raynor D'Souza (Sr Gameplay Developer) |  | Leon Huang (Gameplay Developer) |  | Ignasi Ezpeleta (Jr Gameplay Developer) |  | Roberto (Gameplay Developer) |  | Matt (Technical Animation Engineer) |  | Mustafa Sibai (Head of Eng — Adjusted) |  | Eng Notes | Animator | Character Artist | Character Rigger | Combat Designer | Concept Artist | Environment Artist | Game Designer | Game Director | Gameplay Developer | Level Designer | Prop Artist | Sound Designer | Technical Artist | UI/UX Designer | VFX Artist | Writer | Bid Total
Epic | Feature | Story | Task | Department | Team | Description | Definition of Success | Size | Current Tier | Notes | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Final | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Adj Min | Adj Max | Notes | Days | Days | Days | Days | Days | Days | Days | Days | Days | Days | Days | Days | Days | Days | Days | Days | Days
Player Build | Garment System |  |  | Design | Game design | Classic garment system with equipment slots for different pieces of clothing/gear. Needs finalized documentation, sufficient number of equipment parts and UI. Also should be integrated with character stats if equipment affects them |  | M | T0: Ideation |  |  |  | 7 | 10 | [42 empty] | 20 |  | 60 |  |  |  | 10 | 20 |  |  | 110
|  | Equiment Concepts |  | Art | Concept Art
|  | Equipment Concepts |  | Art | Concept Art
|  | Equipment Models |  | Art | Character Art
|  | Equipment Models | Garment Type SFX | Audio | Audio | (on buy,sell, wear, unequip) | [20 empty] | 2 | 4 | 3
|  | Equipment Stats integrated with character stats |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 5 | 7 | 3 | 5 | 7 | 9 |  |  | 2 | 3
|  | Equipment Stats integrated with character stats | Equipment QA | QA | QA
|  | Equipment Stats integrated with character stats | Garment System QA | QA | QA
|  | Garment System GDD/TDD |  | Design | Game design | [5 empty] | 6 | 10 | 4 | 8 | 5 | 10 | 6 | 10 |  |  | 7 | 10 | 5 | 6 |  |  |  |  | 7
|  | Garment System GDD/TDD | Vertical Slice garments | Design | Game design | [5 empty] | 5 | 7 | [16 empty] | 5
|  | Garment System Integration |  | Engineering | Gameplay Engineering
|  | Garment System Integration | Equip and unequped based on garment system | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 5 | 15 | 3 | 5 | 5 | 7 |  |  | 2 | 3 | dispolve, unequipe and equipe, replicate,
|  | Garment System UI |  | Art | UX/UI | [7 empty] | 10 | 15 | [14 empty] | 14
Player equips clothing
|  | Player equips clothing | Cull occluded body parts | Art | TechArt
|  | Player equips clothing | Equipment QA | QA | QA
|  | Player equips clothing | Freeze cloth sim | Art | Animation & Rigging | This happenes when you teleport the player so shit doesnt expload | [39 empty] | 5 | 7 | 3 | 5 | reset cloth sim
|  | Player equips clothing | Garment System QA | QA | QA
|  | Player equips clothing | Maya tool to represent cloth sim like unreal | Art | Animation & Rigging | [40 empty] | 10 | 15 | 10 | 15 | reasearch
|  | Player equips clothing | Move socket based on clothing type | Art | Animation & Rigging | [40 empty] | 5 | 10 | 5 | 10 | reasearch
|  | Player equips clothing | Setup budget for skining and cloth sim | Art | Animation & Rigging | [40 empty] | 5 | 7 | 5 | 7 | profile, and create performance budget, step down in quality when reaching budget
|  | Player equips clothing | Setup capsules for cloth collision on character | Art | Animation & Rigging | [40 empty] | 1 | 3 | 1 | 2
| In-game Tutorial |  |  | Design | Game design | Finalized in-game tutorial explaining basic mechanics to the player, set in the starting location | The tutorial is clear and straightforward UX/UI pass Players can't die during the tutorial sequence No major visual or functional bugs | [43 empty] | 5 |  |  |  | 5 | 15 | 16 |  | 15 |  |  | 2 | 10 | 5 | 12 |  | 85
|  | Controls UI |  | Art | UX/UI | Clear controls UI and convenient keyboard layout | [6 empty] | 2 | 4 | [14 empty] | 4
|  | Controls UI |  | Art | VFX
|  | Controls UI | Narrative | Design | Narrative | [17 empty] | 0.5 | 1 |  |  |  |  | 1
|  | Controls UI | Tutorial QA check | QA | QA
|  | Controls UI | Tutorial cave contents | Design | Game design | [11 empty] | 2 | 5 |  |  | 1 | ~ | [6 empty] | 2
|  | Tutorial Cave Layout Fixes |  | Design | Level design | Shorter and easier to complete cave blockout | Reduced completion time No spots where the player can die |  |  |  | 8 | 12 |  |  |  |  | 7 | 14 |  |  | 10 | 15 | [6 empty] | 10
|  | Tutorial Cave lighting |  | Art | Environment Art
|  | Tutorial Configuration/set up/texts |  | Design | Game design | Place the tutorial hints so player understands the basic game mechanics (movement, navigation, interaction with objects) | Hints are clear and understandable Hints go over all main in-game mechanics the player needs to start the game |  |  |  | 2 | 3 | 2 | 3 | 10 | 20 | 3 | 8 | [10 empty] | 3
|  | Tutorial UI |  | Art | UX/UI | Make sure the UI in the tutorial cave is well visible and aligned with the tutorial cave art style | [6 empty] | 4 | 10 | [14 empty] | 6
|  | Tutorial VFX |  | Art | VFX
|  | Tutorial cave Ambience & SFX |  | Audio | Audio | [21 empty] | 5 | 10 | 7
|  | Tutorial cave set dressing fixes |  | Art | Environment Art | Adapt the set dressing of the cave to the updated blockout | No major art changes or new content produced, no change of the art style
| Player Progression |  |  | Design | Game design | Players can gain XP for in-game actions (combat, quests, etc) and level up. Level up affects chararcter stats and skills. Character stats are defined and configured and connected with other in-game systems (combat, skills, etc) |  | L | T1: R&D | [47 empty] | 7 |  | 20 |  |  | 2 |  | 3 | 2 |  | 34
|  | Character stats UI |  | Art | UX/UI | [23 empty] | 15
|  | Character stats UI | Level up & Stats QA | QA | QA
|  | Character stats configuration in connection with other systems |  | Design | Game design | [7 empty] | 5 | 10 | 15 | 25 |  |  |  |  | 1 | ~ | [6 empty] | 10
|  | Character stats documentation |  | Design | Game design | [5 empty] | 7 | 12 | 5 | 8 | 5 | 10 | 6 | 10 | [10 empty] | 5
|  | Character stats implementation |  | Engineering | Gameplay Engineering
|  | Character stats implementation | Increase stat when player level up | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 3 | 5 | 2 | 3 | 4 | 5 |  |  | 3 | 4
|  | Character stats implementation | Integrate stat system with other systems | Engineering | Gameplay Engineering | [30 empty] | 6 | 15 | 5 | 10 | 5 | 15 | 3 | 5 | 7 | 10 |  |  | 1 | 20 | depends on system. uknown
|  | Character stats implementation | Items give u stats | Engineering | Gameplay Engineering | [30 empty] | 7 | 14 | 3 | 5 | 5 | 8 | 2 | 3 | 7 | 9 |  |  | 3 | 5
|  | Character stats implementation | Update player stats in backend (player data service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 5 | 10 | [12 empty] | 1 | 2
|  | Character stats implementation | Update stats UI | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 5 | 10 | 2 | 3 | 1 | 2 |  |  | 3 | 5 | UI wireframe and make it work with state system
|  | Character stats implementation | fetch player stats from backend service (player data service) | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 3 | 5 | [12 empty] | 1 | 2
|  | Player level up UI |  | Art | UX/UI | [7 empty] | 2 | 5 | [6 empty] | 5 | 10 | [6 empty] | 3
|  | Player level up configuration |  | Design | Game design | [5 empty] | 10 | 15 | 5 | 7 | 10 | 20 |  |  |  |  | 0.5 | ~ | [6 empty] | 15
|  | Player level up documentation |  | Design | Game design | [5 empty] | 10 | 18 | 10 | 15 | 5 | 10 | 6 | 10 |  |  | 1 | 4 | [6 empty] | 14
|  | player level up integration |  | Engineering | Gameplay Engineering
|  | player level up integration | Earn different types of EXP depending on objective | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 3 |  |  | 2 | 3
|  | player level up integration | Fetch and update UI for player level and exp | Engineering | Gameplay Engineering | [30 empty] | 1 | 3 | 1 | 3 | 2 | 5 | 2 | 4 | 1 | 2 |  |  | 1 | 2
|  | player level up integration | Fetch player level and exp from (player data service) | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 2 | 4 | [12 empty] | 1 | 2
|  | player level up integration | Update player level and exp with (player data service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 0.5 | 2 | 5 | [12 empty] | 1 | 2
| Skill System (1 skill tree active) |  |  | Design | Game design | Basic skill system supported with one skill tree active and interactive. 2 more skill trees shown but not active. Skill progression is integrated with other game systems (stats etc) | [50 empty] | 20 |  | 35 |  |  | 7 |  | 15 | 5 |  | 82
|  | Skill System Configuration |  | Design | Game design | [7 empty] | 4 | 5 | 15 | 25 | [12 empty] | 5
|  | Skill System Documentation |  | Design | Game design | [5 empty] | 8 | 12 | 10 | 13 | 5 | 10 | 6 | 10 |  |  | 4 | 8 | [6 empty] | 15
|  | Skill System Implementation |  | Engineering | Gameplay Engineering
|  | Skill System Implementation | Add new abilities to skill tree | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 3 | 2 | 5 | 1 | 5 | 3 | 4 |  |  | 2 | 4
|  | Skill System Implementation | Add new weapons to skill tree | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 5 | 1 | 5 | 3 | 4 |  |  | 1 | 2
|  | Skill System Implementation | Connect skill tree to UI | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 4 | 5 | 15 | 2 | 3 | 5 | 6 |  |  | 4 | 6 | with existing system
|  | Skill System Implementation | Create frontend for skill tree in internal dashboard | Engineering | Backend Engineering | [24 empty] | 10 | 25 | 0.5 | 0.5 | 5 | 20 | [12 empty] | 5 | 7
|  | Skill System Implementation | Create new collection for weapon skill tree (player data service) | Engineering | Backend Engineering | properties of new collection: playerId, weaponType, jsonB with all skills available, assigned ones, level of each tier | [23 empty] | 4 | 10 | 1 | 2 | 5 | 8 | [12 empty] | 3 | 4
|  | Skill System Implementation | Create weapon skill tree / nodes in (internal dashboard service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 3 | 5 | [12 empty] | 3 | 4
|  | Skill System Implementation | Fetch player skill tree per weapon (player data service) | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 1 | 3 | [12 empty] | 1 | 2
|  | Skill System Implementation | Fetch weapon skill tree / nodes in (internal dashboard service) | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 1 | 3 | [12 empty] | 1 | 2
|  | Skill System Implementation | Fetech all skill trees from backend | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 5 | 3 | 5 | 3 | 4 |  |  | 1 | 2
|  | Skill System Implementation | Remove weapon skill tree / nodes in (internal dashboard service) | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 1 | 3 | [12 empty] | 1 | 2
|  | Skill System Implementation | Sync all skill trees to backend, tool | Engineering | Gameplay Engineering | [42 empty] | 5 | 10
|  | Skill System Implementation | Update all skill trees from backend | Engineering | Gameplay Engineering | [30 empty] | 2 | 3 | 1 | 2 | 2 | 5 | 2 | 4 | 3 | 4 |  |  | 1 | 2
|  | Skill System Implementation | Update player skill tree per weapon (player data service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 0.5 | 3 | 5 | [12 empty] | 1 | 2
|  | Skill System Implementation | Update weapon skill tree / nodes in (internal dashboard service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 2 | 4 | [12 empty] | 1 | 2
|  | Skill System Implementation | endpoint to reset skill tree for weapons | Engineering | Backend Engineering | [42 empty] | 2 | 3
|  | Skill System UI |  | Art | UX/UI
|  | Skill System UI | Skill system QA | QA | QA
|  | Skill Tree UI Audio |  | Audio | Audio | [21 empty] | 7 | 14 | 8
|  | Skills in-game audio |  | Audio | Audio | [21 empty] | 7 | 14 | 8
World Systems | Advanced Traversal |  |  | Design | Game design | Only gliding for now. Gliding is an airborne locomotion state, not a flight simulation. While gliding, the player retains directional movement control similar to ground traversal, but with reduced acceleration, limited top speed, and continuous stamina drain. |  | L | T1: R&D |  |  |  | 15 | 25 | 5 | 10 | [12 empty] | 2 | [21 empty] | 60 |  | 20 | [13 empty] | 80
|  | Glider Stamina UI |  | Art | UX/UI | [7 empty] | 2 | 3 | [14 empty] | 2
|  | Gliding Animations |  | Art | Animation & Rigging | [40 empty] | 1 | 1 | 1 | 1
|  | Gliding Concepts |  | Art | Concept Art
|  | Gliding Concepts | Check if ability is unlock to glide | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 2 | 3 | 2 | 3 | 1 | 2 | 1 | 2 |  |  | 1 | 1 | give designed ability to know when to unlock gliding
|  | Gliding Concepts | Convert gliding to blend space | Art | Animation & Rigging | [40 empty] | 1 | 1 | 1 | 1
|  | Gliding Concepts | Spawn gliding actor | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 3 | 5 | 1 | 2 | 0.5 | 1 |  |  | 2 | 3
|  | Gliding Device |  | Art | Character Art
|  | Gliding Device | Gliding QA | QA | QA
|  | Gliding Integration |  | Engineering | Gameplay Engineering
|  | Gliding SFX |  | Audio | Audio | [21 empty] | 1 | 2 | 2
|  | Gliding VFX |  | Art | VFX
|  | Portals spawning & Xyron moving through portals |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 4 | 5 |  |  | 2 | 3 |  |  | 2 | 4 | this is only for Xyron - hard coded
|  | Portals spawning & Xyron moving through portals | 5 or 6 mini quests | Design | Game design | [5 empty] | 6 | 8 | 7 | 12 | 10 | 20 | 5-6d | 10-12d |  |  | 5 | 8 | [6 empty] | 8
|  | Portals spawning & Xyron moving through portals | Narrative for Xyron quests | Design | Narrative | [5 empty] | 2 | 3 | 4 | 6 | 5 | 10 |  |  |  |  | 1 | 2 | 1 | 3 |  |  |  |  | 2
|  | Portals spawning & Xyron moving through portals | Spawning portals SFX | Audio | Audio | [21 empty] | 2 | 4 | 4
|  | Portals spawning & Xyron moving through portals | Xyron voiceover narrative | Design | Narrative | [5 empty] | 3 | 5 |  |  | 1 | 3 | [6 empty] | 0.5 | 1 |  |  |  |  | 2
|  | Portals spawning & Xyron moving through portals | Xyron/portals spawning QA | QA | QA
|  | Xyron voiceover |  | Audio | Audio | [21 empty] | 7 | 14 | 8
|  | Xyron voiceover | Xyron/portals spawning QA | QA | QA
| Basic movement system |  |  | Design | Game design | [9 empty] | no idea | no idea | [34 empty] | 60 |  | 20 | [13 empty] | 80
|  | Locomotion Integration |  | Engineering | Gameplay Engineering | Player can access all main movement mechanics | No major bugs with functionality or visuals All needed animations implemented
|  | Locomotion Integration | Double Jump | Engineering | Gameplay Engineering | [30 empty] | 0.5 | 2 | 0.5 | 1 | 1 | 2 | 1 | 2 | 0.5 | 0.5 |  |  | 0.5 | 1
|  | Locomotion Integration | Iteration | Design | Game design | [23 empty] | 5
|  | Locomotion Integration | Jump | Engineering | Gameplay Engineering | [30 empty] | 0.5 | 2 | 0.5 | 1 | 1 | 2 | 1 | 2 | 0.5 | 0.5 |  |  | 0.5 | 1
|  | Locomotion Integration | Locomotion QA check | QA | QA
|  | Locomotion Integration | Run | Engineering | Gameplay Engineering | [30 empty] | 0.5 | 2 | 0.5 | 1 | 1 | 2 | 1 | 2 | 0.5 | 0.5 |  |  | 0.5 | 1
|  | Locomotion Integration | Sprint | Engineering | Gameplay Engineering | [30 empty] | 0.5 | 2 | 0.5 | 1 | 1 | 2 | 1 | 2 | 0.5 | 0.5 |  |  | 0.5 | 1
|  | Locomotion Integration | Walk | Engineering | Gameplay Engineering | [30 empty] | 0.5 | 2 | 0.5 | 1 | 1 | 2 | 1 | 2 | 0.5 | 0.5 |  |  | 0.5 | 1
| Camera behavior |  |  | Design | Game design | Camera behavior designed for different game situations and actions |  |  |  |  | 2 | 4 | 8 | 14 | 5 | 5 | [12 empty] | 5 | [27 empty] | 17 |  | 60 |  | 10 |  | 90 | 20 | 5 |  | 202
|  | Camera behavior implementation/fixes |  | Engineering | Gameplay Engineering | Camera behavior is implemented according to the design | Camera acts according to the design without major/blocking bugs
|  | Camera behavior implementation/fixes | Camera QA | QA | QA
|  | Camera behavior implementation/fixes | Implement camera according to design | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 5 | 15 | 4 | 8 | 2 | 3 |  |  | 6 | 7
|  | Combat Camera |  | Design | Game design | [5 empty] | 4 | 6 | 6 | 9 | 5 | 10 | [12 empty] | 9
|  | Combat Camera | Camera QA | QA | QA
| Carapax (Hero, but one type) |  |  | Design | Game design | [45 empty] | 35 | 15 | 10 |  | 10 |  | 13 |  | 20 |  |  | 17 | 10 | 30 | 15 |  | 175
|  | Animation |  | Art | Animation & Rigging
|  | Animation | Create animation graph | Art | Animation & Rigging | [40 empty] | 3 | 5 | 3 | 5
|  | Animation | Create control rig | Art | Animation & Rigging | [40 empty] | 1 | 2 | 1 | 2
|  | Animation | Custom death sequance | Art | Animation & Rigging | [40 empty] | 1 | 2 | 1 | 2
|  | Animation | Seperate clothing from body | Art | Animation & Rigging | [40 empty] | 2 | 2 | 2 | 2
|  | Carapax AI design |  | Design | Game design | [23 empty] | 4
|  | Combat Behavior |  | Engineering | Gameplay Engineering
|  | Combat Behavior | Make combat moves | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 3 | 10 | 3 | 5 | 5 | 7 |  |  | 5 | 10 | design vfx animation
|  | Concept |  | Art | Concept Art
|  | Design |  | Design | Game design | [5 empty] | 2 | 3 |  |  | 3 | 5 | [12 empty] | 5
|  | Implementation | Asset Validation | Art | TechArt
|  | Model |  | Art | Character Art
|  | Rigging |  | Art | Animation & Rigging | [40 empty] | 10 | 10 | 10 | 10
|  | SFX |  | Audio | Audio | [21 empty] | 5 | 8 | 7
|  | SFX | Carapax QA | QA | QA
|  | VFX |  | Art | VFX
|  | VFX | Carapax QA | QA | QA
| Corrupted Guardian |  |  | Design | Game design | Corrupted Enemies are not required for the Vertical Slice - except for one reanimated robot, who technically falls under this category. He wakes up, looks menacing, then is destroyed by the crystal found in the partner game. | [44 empty] | 35 | 15 | 10 |  | 10 |  | 13 |  | 20 |  |  | 17 | 10 | 30 | 15 |  | 175
|  | Animation |  | Art | Animation & Rigging
|  | Concept |  | Art | Concept Art
|  | Design |  | Design | Game design | Includes the quest structure |  |  |  |  | 2 | 4 | 5 | 10 | 5 | 10 | [12 empty] | 2
|  | Design | Quest structure | Design | Game design | [5 empty] | 1 | 3 | [16 empty] | 4
|  | Implementation | Asset Validation | Art | TechArt
|  | Model |  | Art | Character Art
|  | Narrative |  | Design | Game design | [5 empty] | 2 | 3 |  |  | 2 | 5 | [12 empty] | 1
|  | Rigging |  | Art | Animation & Rigging
|  | SFX |  | Audio | Audio | [21 empty] | 3 | 7 | 3
|  | SFX | Corrupted Enemies QA | QA | QA
|  | VFX |  | Art | VFX
| Corrupted enemies |  |  | Design | Game design | These are not required for the Vertical Slice - except for one reanimated robot, who technically falls under this category. He is wakes up, looks menacing, then is destroyed by the crystal found in the partner game. | [44 empty] | 35 | 15 | 10 |  | 10 |  | 13 |  | 20 |  |  | 17 | 10 | 30 | 15 |  | 175
|  | Animation |  | Art | Animation & Rigging
|  | Combat Behavior |  | Engineering | Gameplay Engineering
|  | Combat Behavior | Make combat moves | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 |  |  | 3 | 5 | 5 | 7 |  |  | 5 | 10 | design vfx animation
|  | Concept |  | Art | Concept Art
|  | Design |  | Design | Game design
|  | Implementation | Asset Validation | Art | TechArt
|  | Model |  | Art | Character Art
|  | Rigging |  | Art | Animation & Rigging | [40 empty] | 5 | 15 | 5 | 15 | Depends if we are having these morph in to the corrupted enemies like there has been some discussion
|  | VFX |  | Art | VFX | [34 empty] | 3 | 10
|  | VFX | Corrupted Enemies QA | QA | QA
| Corruption |  |  | Design | Game design | [45 empty] | 35 | 15 | 10 |  | 10 |  | 13 |  | 20 |  |  | 17 | 10 | 30 | 15 |  | 175
|  | Corrupted Vines |  | Design | Game design | The texture on the vines that implies they are corrupted. No functionality, just visual |  |  |  |  | 2 | 3 |  |  | 3 | 5 |  |  |  |  | 0.5 | 0.5 | [6 empty] | 1
|  | Corrupted Vines | Corrupted VFX | Art | VFX | Upgrade features form TA material
|  | Corrupted Vines | Corrupted texture | Art | TechArt | Material suitable to communicate cleaning mechanics and hazard | Match Art Direction, tested and working for different size and elements
|  | Corrupted Vines | Corrupted vines behavior & visual QA | QA | QA
|  | Corrupted Vines | Vine NPC Narrative | Design | Narrative | [23 empty] | 1
|  | Corrupted Vines | Vines Foliage | Art | Environment Art
|  | Foam Corruption |  | Design | Game design | Another clean up system that could be investigated is a physical model that is removed in parts. This would need a destruction system like Red Faction, or a voxel system to represent a poisonous foam that covers the environment and can be cleaned up by multiple players simultaneously. This is the alternative to Environmental Corruption, which may prove easier to implement in multiplayer.
|  | Foam Corruption | Foam Corruption QA | QA | QA
|  | Foam Corruption | Foam Corruption SFX | Audio | Audio | [21 empty] | 2 | 3 | 2
|  | Foam Corruption | Foam Corruption SFX, VFX design | Design | Game design | [5 empty] | 3 | 5 |  |  | 5 | 10 | [12 empty] | 3
|  | Foam Corruption | Foam Corruption Techart | Art | TechArt | Volumetric Corruption dependancy with additional specific elements | Readable as same mechanics, adaptable to assets and areas, performant
|  | Foam Corruption | Foam Corruption VFX | Art | VFX | Upgrade features form TA material
|  | Foam Corruption | Foam Corruption cleansing animations | Art | Animation & Rigging | [42 empty] | 2 | 3
|  | Foam Corruption | Foam Corruption cleansing weapon | Art | Character Art
|  | Foam Corruption | Foam Corruption integration | Engineering | Gameplay Engineering | [32 empty] | 5 | 8 |  |  | 1 | 5 |  |  |  |  | 4 | 5
|  | Foam Corruption | Link with corruption gun | Engineering | Gameplay Engineering | When shoot gun make corruptoin go away | [29 empty] | 2 | 4 | 2 | 4 |  |  | 1 | 3 | 3 | 4 |  |  | 2 | 4
|  | Foam Corruption | Make corruption come back after a set time | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 |  |  | 1 | 5 | 2 | 3 |  |  | 1 | 2
|  | Foam Corruption | Quest tracking system | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 3 |  |  | 1 | 5 | 2 | 3 |  |  | 1 | 2
|  | Foam Corruption | Trigger objective when clean is done | Engineering | Gameplay Engineering | [30 empty] | 2 | 3 | 1 | 2 |  |  | 1 | 5 | 1 | 2 |  |  | 1 | 2
|  | Timed Corruption |  | Design | Game design | A simple mechanic to implement using animation curves. An object such as a door or bridge has been broken into multiple parts, and the player has to use magic to rebuild it, visually reversing time. There will be puzzle and multiplayer opportunities. For instance one player may need to restore a bridge while another player crosses it to reach a switch. There can also be a multi-stage set of things that have collapsed or prematurely rusted. The player has to work out which ones to reverse, in which order, to recreate the original setting (all pieces lock into place once this has been achieved, for a short time). | [6 empty] | 10 | 15 | 20 | 40
|  | Timed Corruption | Replicate animation | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 |  |  | 3 | 5 | 1 | 2 |  |  | 1 | 2
|  | Timed Corruption | Timed Corruption 3D Assets | Art | Environment Art
|  | Timed Corruption | Timed Corruption Design | Design | Game design | [5 empty] | 3 | 5 | 5 | 9 | 5 | 10 | 10 | 15 |  |  | 2 | 3 | [6 empty] | 10
|  | Timed Corruption | Timed Corruption Integration | Engineering | Gameplay Engineering
|  | Timed Corruption | Timed Corruption QA | QA | QA
|  | Timed Corruption | Timed Corruption SFX | Audio | Audio | [21 empty] | 3 | 6 | 5
|  | Timed Corruption | Timed Corruption Server & Multiplayer | Engineering | Backend Engineering
|  | Timed Corruption | Timed Corruption TechArt | Art | TechArt
|  | Timed Corruption | Timed Corruption VFX | Art | VFX | Upgrade features form TA material
|  | Timed Corruption | Timer to revert bridge to broken state | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 |  |  | 1 | 2 | 0.5 | 1 |  |  | 1 | 2
|  | Timed Corruption | Toggle path once puzzle is completed to allow or disallow player from crossing the bridge by replicating collision | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 |  |  | 1 | 2 | 2 | 3 |  |  | 1 | 1
|  | Timed Corruption | Trigger VFX when effect is completed | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 |  |  | 1 | 2 | 0.5 | 1 |  |  | 1 | 2
|  | Timed Corruption | Trigger building the bridge | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 |  |  | 1 | 3 | 1 | 2 |  |  | 2 | 3
Create a system to allow a player to interact with the world and have event only happen for that player in a multiplayer setting
|  |  | Create phasing system | Engineering | Gameplay Engineering | [34 empty] | 7 | 20 | 10 | 15
|  |  | Create phasing system | Engineering | Backend Engineering | [26 empty] | 3 | 5 | 20 | 50
|  |  | Document phasing system | Engineering | Backend Engineering | [34 empty] | 2 | 3 | 4 | 5
|  |  | Document phasing system | Engineering | Backend Engineering | [24 empty] | 2 | 5 | 1 | 2 | 4 | 7
|  |  | Research phasing system | Engineering | Backend Engineering | [24 empty] | 2 | 5 | 1 | 2 | 3 | 5
|  |  | Research phasing system | Engineering | Gameplay Engineering | [34 empty] | 3 | 5 | 4 | 5
| Downtime Final set dressing (L) |  |  | Art | Environment Art | Finalized Downtime (MVP quality). No blockouts. Focus on the social area (tavern) + several shop fronts that are not accessible inside | [48 empty] | 20 |  | 14 |  | 30 |  | 15 | 2 |  |  |  |  | 81
|  | Downtime Auction House storefront model |  | Art | Environment Art
|  | Downtime Bank storefront model |  | Art | Environment Art
|  | Downtime Barbersmith storefront model |  | Art | Environment Art
|  | Downtime Barbersmith storefront model | Downtime QA | QA | QA
|  | Downtime NPC placement |  | Design | Game design | [5 empty] | 5 | 7 |  |  | 5 | 8 | 4 | 10 | [10 empty] | 5
|  | Downtime Shops closed area |  | Design | Game design | [5 empty] | 2 | 3 |  |  | 3 | 5 | [12 empty] | 2
|  | Downtime Social Hub Area Blockout |  | Design | Level design | [9 empty] | blockouts are LD? | yes | 6 | 10 | 7 | 12 | 7 | 15 | [6 empty] | 6
|  | Downtime Tavern Blockout |  | Design | Level design | [11 empty] | 6 | 10 | 3 | 7 | 7 | 15 | [6 empty] | 7
|  | Downtime Tavern Concept |  | Art | Concept Art
|  | Downtime Tavern Model |  | Art | Environment Art
|  | Downtime Tavern Props |  | Art | Environment Art
|  | Downtime shops storefronts models |  | Art | Environment Art
|  | Multiplayer interactions (toasts) |  | Design | Game design | [5 empty] | 2 | 3 |  |  | 3 | 15 | [12 empty] | 2
|  | NPC behaviour document |  | Design | Game design | [23 empty] | 2
| Dungeons mechanics |  |  | Design | Game design | Design different mechanics that can be used in dungeons. Only design stage for the vertical slice | [6 empty] | 7 | 10 | 5 | 15 | [42 empty] | 20 | [7 empty] | 20
Dungeon impelmenation
|  | Dungeon impelmenation | Dungeon UI | Engineering | Gameplay Engineering | [30 empty] | 15 | 20 | 10 | 20 | 5 | 10 | 3 | 5 | 7 | 9 |  |  | 3 | 5
|  | Dungeon impelmenation | Dungeon character | Engineering | Gameplay Engineering | [30 empty] | 5 | 8 | 3 | 5 | 3 | 5 | 1 | 2 | 5 | 6 |  |  | 3 | 4
|  | Dungeon impelmenation | Dungeon end reward and condition | Engineering | Gameplay Engineering | [30 empty] | 5 | 8 | 3 | 5 | 4 | 7 | 2 | 4 | 2 | 3 |  |  | 3 | 5
|  | Dungeon impelmenation | Dungeon gameplay loop | Engineering | Gameplay Engineering | [30 empty] | 15 | 20 | 10 | 20 | 8 | 15 | 3 | 5 | 7 | 8 |  |  | 10 | 20
|  | Dungeon impelmenation | Join dungeon | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 3 | 5 | 10 | 2 | 4 | 3 | 4 |  |  | 1 | 2
|  | Dungeon impelmenation | Transition to dungeon | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 3 | 3 | 5 | 1 | 3 | 2 | 3 |  |  | 1 | 2
|  | Dungeon impelmenation | dungeon character respawn | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 3 | 5 | 1 | 2 | 2 | 3 |  |  | 2 | 3 | not outside dungeon. in dungeon
|  | Dungeon impelmenation | dungeon transition to out of dungeon | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 3 | 3 | 5 | 2 | 3 | 3 | 4 |  |  | 1 | 2
|  | Dungeons documentation |  | Design | Game design | [5 empty] | 2 | 4 | 2 | 4 | 3 | 5 | 6 | 15 | [10 empty] | 5
|  | Dungeons documentation | Narrative | Design | Narrative | [17 empty] | 0.5 | 2 |  |  |  |  | 1
| Forge |  |  | Design | Game design | Weapon crafting mechanic that allows to combine different parts of the weapon to get a new one | recipe based crafting system | [5 empty] | 12 | 18 | 5 | 20 | [12 empty] | 12 | [25 empty] | 10 |  | 10 |  | 20 |  |  |  | 10 | 40 |  |  | 90
|  | Component System Design |  | Design | Game design | [5 empty] | 2 | 4 | 9 | 12 | 3 | 5 |  |  |  |  | 5 | 10 | [6 empty] | 5
|  | Crafted Weapon Parts in-game Audio |  | Audio | Audio | [21 empty] | 5 | 10 | 5
|  | Crafting Desk |  | Art | Environment Art
|  | DA combination setup |  | Art | TechArt | Weapon color customization parallel to garments plus pieces and parts assembly
|  | Forge Concepts |  | Art | Concept Art
|  | Forge Crafting Audio |  | Audio | Audio | [21 empty] | 3 | 7 | 5
|  | Forge Documentation |  | Design | Game design | [5 empty] | 4 | 6 | 5 | 7 | 3 | 5 | 6 | 10 | [10 empty] | 5
|  | Forge Integration |  | Engineering | Gameplay Engineering
|  | Forge Props |  | Art | Character Art
|  | Forge Props | Forge QA | QA | QA
|  | Forge Techart | DA combination setup | Art | TechArt | Weapon color customization parallel to garments plus pieces and parts assembly
|  | Forge UI |  | Art | UX/UI | [7 empty] | 7 | 10 | 5 | 15 | [12 empty] | 10
|  | Forge VFX |  | Art | VFX
| Full Motion Video (FMV) |  |  | Design | Game design | [9 empty] | no idea | no idea | [12 empty] | 1 | [21 empty] | 5 |  |  |  | 5 | 15 | 16 |  | 15 |  |  | 2 | 10 | 5 | 12 |  | 85
|  | Intro supports FMV |  | Engineering | Backend Engineering | The game supports full motion videos integration and playback | FMV triggers correctly Playback completes or skips No crashes or black screens Transitions to next state
|  | Intro supports FMV |  | Engineering | Gameplay Engineering | The game supports full motion videos integration and playback | FMV triggers correctly Playback completes or skips No crashes or black screens Transitions to next state
|  | Intro supports FMV | Create a system to disallow the player from moving while in FMV | Engineering | Gameplay Engineering | [30 empty] | 0.5 | 1 | 2 | 3 | 2 | 4 | 1 | 2 | 1 | 2 |  |  | 0.5 | 1 | it takes 30 min to not make the character not move
|  | Intro supports FMV | Create placeholder FMV playback flow | Engineering | Backend Engineering | System to trigger fmv from within a quest, or at startup
|  | Intro supports FMV | Create placeholder FMV playback flow and allow designers to set the FMV easily | Engineering | Gameplay Engineering | System to trigger fmv from within a quest, or at startup | [29 empty] | 1 | 2 | 3 | 4 | 2 | 4 | 2 | 4 | 0.5 | 1 |  |  | 2 | 4 | Playing FMV at the start of game is easy. 1 hour. But need to create a system for designers to play an FMV in quest and load FMV if it is too big
|  | Intro supports FMV | FMV Production | Art | Environment Art | To determine possible scopes with GD and AD
|  | Intro supports FMV | Fix FMV blocker bugs | Engineering | Backend Engineering
|  | Intro supports FMV | Implement FMV skip behavior | Engineering | Backend Engineering | Skip should not be accidental (e.g. hold down skip button) - and there should also be a way to pause playback
|  | Intro supports FMV | Implement FMV skip behavior | Engineering | Gameplay Engineering | Skip should not be accidental (e.g. hold down skip button) - and there should also be a way to pause playback | [29 empty] | 0.5 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 0.5 | 1 |  |  | 1 | 2 | Taking into consideration meeting with UI designer and bug fixing
|  | Intro supports FMV | Implement transition after FMV | Engineering | Backend Engineering | Transition to explicit camera rotation and location
|  | Intro supports FMV | Implement transition after FMV - Fade in/Fade out system | Engineering | Gameplay Engineering | Transition to explicit camera rotation and location | [29 empty] | 0.5 | 1 | 2 | 3 | 2 | 4 | 1 | 2 | 1 | 2 |  |  | 1 | 2 | talk with tech art to get material and shader, time fade in and fade out on video, disable controls until fade in/out is done
|  | Intro supports FMV | Integrate final/near-final FMV asset | Engineering | Backend Engineering | Create an editable system so that anybody can make a change here
|  | Intro supports FMV | Integrate final/near-final FMV asset | Engineering | Gameplay Engineering | Create an editable system so that anybody can make a change here
|  | Intro supports FMV | Narrative - Cinematic scripting | Design | Narrative | [17 empty] | 1 | 3 |  |  |  |  | 1
|  | Intro supports FMV | QA playback across target builds | QA | QA
| Goblins |  |  | Design | Game design | [45 empty] | 35 | 15 | 10 |  | 10 |  | 13 |  | 20 |  |  | 17 | 10 | 30 | 15 |  | 175
|  | Animation |  | Art | Animation & Rigging
|  | Animation | Create animation graph | Art | Animation & Rigging | [40 empty] | 3 | 5 | 3 | 5
|  | Animation | Create control rig | Art | Animation & Rigging | [40 empty] | 1 | 2 | 1 | 2
|  | Animation | RBF setup | Art | Animation & Rigging | [40 empty] | 2 | 4 | 2 | 4
|  | Combat Behavior |  | Engineering | Gameplay Engineering
|  | Combat Behavior | Make combat moves | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 3 | 10 | 3 | 5 | 5 | 7 |  |  | 5 | 10 | design vfx animation
|  | Concept |  | Art | Concept Art
|  | Design |  | Design | Game design | [7 empty] | 7 | 10 | 3 | 10 | [12 empty] | 9
|  | Goblin AI behaviour |  | Design | Game design | [23 empty] | 4
|  | Goblin montages |  | Art | Animation & Rigging
|  | Implementation | Asset Validation | Art | TechArt
|  | Model |  | Art | Character Art
|  | Rigging |  | Art | Animation & Rigging | [40 empty] | 10 | 10 | 10 | 10
|  | SFX |  | Audio | Audio | [21 empty] | 7 | 14 | 7
|  | SFX | Goblins QA | QA | QA
|  | VFX |  | Art | VFX
|  | VFX | Goblins QA | QA | QA
| In-game cutscenes |  |  | Engineering | Gameplay Engineering | [45 empty] | 5 |  |  |  | 5 | 15 | 16 |  | 15 |  |  | 2 | 10 | 5 | 12 |  | 85
|  | Cutscene content |  | Design | Game design | Define all required content and direct the cutscenes; make sure all required assets exist | Basic cutscenes directed, MVP quality |  |  |  | 15 | 20 | 10 | 20 | 5 | 10 | [12 empty] | 5
|  | Cutscene content | Narrative | Design | Narrative | [17 empty] | 0.5 | 1 |  |  |  |  | 1
|  | The game supports cutscenes |  | Engineering | Gameplay Engineering | In-engine cutscene mechanism is implemented, designers can set the necessary scenes in defined places of the game. Documentation exists for proposed system (talk to GD). Basically this uses Unreal's Sequencer, or a simplified version, so that designers can trigger a basic movie from a dialogue box or quest intro. | Cutscenes are triggered and played correctly Camera behavior is correct Skip mechanism implemented No major bugs or blockers
|  | The game supports cutscenes | Basic cutscene sequencing (timeline) | Engineering | Gameplay Engineering
|  | The game supports cutscenes | Camera control during cutscene | Engineering | Gameplay Engineering
|  | The game supports cutscenes | Custom camera animations | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 5 | 2 | 3 |  |  | 1 | 2
|  | The game supports cutscenes | Custom camera position and rotation | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 3 |  |  | 1 | 2
|  | The game supports cutscenes | Cutscene skip functionality | Engineering | Gameplay Engineering
|  | The game supports cutscenes | Cutscene stability (QA & fixes) | QA | QA
|  | The game supports cutscenes | Cutscene trigger system | Engineering | Gameplay Engineering
|  | The game supports cutscenes | Dialogue playback (in-cutscene) | Engineering | Gameplay Engineering
|  | The game supports cutscenes | NPC/character sequencing | Engineering | Gameplay Engineering
|  | The game supports cutscenes | Player control lock/unlock | Engineering | Gameplay Engineering
|  | The game supports cutscenes | Stream camera position (world partition) | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 5 | 3 | 5 | 2 | 5 | 2 | 3 |  |  | 3 | 5
|  | The game supports cutscenes | Transition in/out of cutscene | Engineering | Gameplay Engineering
| Instancing |  |  | Engineering | Backend Engineering | Allow players or parties to enter private versions of locations with isolated gameplay state. |  | L | T0: Ideation | [47 empty] | 5 |  | 120 |  |  |  | 10 |  |  |  | 135
|  | Create a queue service |  | Engineering | Backend Engineering | when you login into the game to let you into the game
|  | Create a queue service | Create Nodejs service | Engineering | Backend Engineering | Player initially connect to this service first and sit in a queue until they connect to the real server instance. this is used when there is a high demand on a server | [23 empty] | 5 | 15 | 1 | 2 | 5 | 14 | [12 empty] | 3 | 4
|  | Create a queue service | Instancing QA | QA | QA
|  | Custom HPA for Kubernetes |  | Engineering | Backend Engineering | Scales pods according to player count and any custom metrics
|  | Custom HPA for Kubernetes | Create Nodejs service | Engineering | Backend Engineering | [24 empty] | 10 | 25 | 1 | 3 | 6 | 15 | [12 empty] | 1 | 2
|  | Custom HPA for Kubernetes | Create metrics to scale up and down | Engineering | Backend Engineering | [24 empty] | 10 | 25 | 1 | 3 | 6 | 10 | [12 empty] | 4 | 6
|  | Custom HPA for Kubernetes | Create rules when to merge instances | Engineering | Backend Engineering | [24 empty] | 15 | 35 | 0.5 | 2 | 5 | 12 | [12 empty] | 4 | 6
|  | Custom HPA for Kubernetes | Integrate Kubernetes API | Engineering | Backend Engineering | [24 empty] | 10 | 25 | 1 | 3 | 4 | 8 | [12 empty] | 3 | 5
|  | Custom service for overworld zones |  | Engineering | Backend Engineering
|  | Custom service for overworld zones | Call backend to figure out which overworld zones to connect to | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 3 | 2 | 4 | 1 | 2 | 5 | 6 |  |  | 2 | 3
|  | Custom service for overworld zones | Create overworld zones instance | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 1 | 3 | [12 empty] | 2 | 3
|  | Custom service for overworld zones | Create a list of all overworld zones that are currently running in redis | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 3 | 7 | [12 empty] | 3 | 4
|  | Custom service for overworld zones | Create a service in nodejs | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 5 | 8 | [12 empty] | 1 | 2
|  | Custom service for overworld zones | Delete overworld zones instance | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 1 | 3 | [12 empty] | 2 | 3
|  | Custom service for overworld zones | Fetch overworld zones ip by id | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 1 | 2 | [12 empty] | 2 | 3
|  | Custom service for overworld zones | Inform UE server that a player is getting migrated to another UE server | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 3 | 2 | 10 | 1 | 2 | 2 | 3 |  |  | 2 | 3
|  | Custom service for overworld zones | Inform UE server that a player is getting migrated to another UE server | Engineering | Backend Engineering | [24 empty] | 7 | 18 | 1 | 2 | 3 | 7 | [12 empty] | 3 | 4
|  | Custom service for overworld zones | Search for overworld zones by id | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 1 | 2 | [12 empty] | 2 | 3
|  | Custom service to handle dungeons |  | Engineering | Backend Engineering | This service creates new instances for dungeons when needed
|  | Custom service to handle dungeons | Call backend to figure out which dungeon to connect to | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 3 |  |  | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Custom service to handle dungeons | Create a list of all dungeons that are currently running in redis | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 3 | 5 | 10 | [12 empty] | 3 | 4
|  | Custom service to handle dungeons | Create a service in nodejs | Engineering | Backend Engineering | [24 empty] | 10 | 25 | 1 | 3 | 5 | 10 | [12 empty] | 1 | 2
|  | Custom service to handle dungeons | Create dungeon instance | Engineering | Backend Engineering | [24 empty] | 7 | 18 | 0.5 | 2 | 1 | 3 | [12 empty] | 1 | 2
|  | Custom service to handle dungeons | Delete dungeon instance | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 0.5 | 1 | 3 | [12 empty] | 2 | 3
|  | Custom service to handle dungeons | Fetch dungeon ip by id | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 2 | 1 | 2 | [12 empty] | 2 | 3
|  | Custom service to handle dungeons | Search for dungeon by id | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 2 | 1 | 2 | [12 empty] | 2 | 3
|  | Dungeon Instancing |  | Engineering | Backend Engineering
|  | GDD Documentation |  | Design | Game design | [5 empty] | 4 | 6 |  |  | 3 | 5 | 15 | 20 | [10 empty] | 2
|  | Guild House instancing support |  | Engineering | Backend Engineering
|  | Instancing Documentation |  | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 3 | 7 | [12 empty] | 2 | 3
|  | Player general stat before disconnecting service |  | Engineering | Backend Engineering
|  | Player general stat before disconnecting service | Create a service in nodejs | Engineering | Backend Engineering | [24 empty] | 7 | 18 | 1 | 3 | 10 | 20 | [12 empty] | 1 | 2
|  | Player general stat before disconnecting service | Create a way to save player stat (which server they were connected to last, which party were they connected to, etc..) before disconnecting | Engineering | Backend Engineering | [24 empty] | 7 | 18 | 1 | 2 | 3 | 7 | [12 empty] | 3 | 4
|  | Setup Kubernetes on Azure |  | Engineering | Backend Engineering
|  | Setup Kubernetes on Azure | Setup azure | Engineering | Backend Engineering | [24 empty] | 14 | 35 | 1 | 3 | 6 | 12 | [12 empty] | 2 | 3
|  | User Space Instancing support |  | Engineering | Backend Engineering
|  | Zones Instancing |  | Engineering | Backend Engineering
|  | Zones Instancing | Instancing QA | QA | QA
| Navigation |  |  | Design | Game design |  |  | M | T0: Ideation | [47 empty] | 5 |  | 120 |  |  |  | 10 |  |  |  | 135
|  | Compass |  | Engineering | Gameplay Engineering | Basic navigation tool that shown direction to the selected marker/quest (or north) at the top of the screen
|  | Compass | Compass Integration | Engineering | Gameplay Engineering
|  | Compass | Compass QA check | QA | QA
|  | Compass | Compass UI | Art | UX/UI | [7 empty] | 2 | 5 | [14 empty] | 10
|  | Compass | Party player distance | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 3 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Compass | Rotate compass with camera | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 5 | 7 |  |  | 3 | 5
|  | Compass | Show POI distance | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 3 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Compass | Show distance to objective | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 5 | 10 | 1 | 2 | 1 | 2 |  |  | 3 | 5 | need to show distance from one zone to another if the quest of POI is in a different zone. So distance is first calculated to entrance of exist of the zone then to POI
|  | Compass | Show or hide compass from options menu | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Compass | Show quest distance | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 3 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Compass | Special NPCs distance | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 3 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Fog-of-war |  | Engineering | Gameplay Engineering | Parts of the map are hidden until the player reaches them or gets information about them | The hide/reveal functionality works without major bugs
|  | Fog-of-war | Create fog of war grid | Engineering | Gameplay Engineering | [42 empty] | 2 | 3 | This is based on a simple grid layout made by code team. if cell visited show icon and unhide fog of war
|  | Fog-of-war | Fog of war QA check | QA | QA
|  | Fog-of-war | Fog of war changes based on player visited locations | Engineering | Gameplay Engineering | [30 empty] | 8 | 12 | 3 | 5 | 4 | 8 | 4 | 6 | 5 | 7 |  |  | 2 | 3
|  | Fog-of-war | Fog of war shader | Art | TechArt
|  | Fog-of-war | Hide/Unhide markers that are in fog of war | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 3 | 5 | 5 | 10 | 1 | 3 | 1 | 2 |  |  | 2 | 3
|  | Fog-of-war | Sync fog of war to backend | Engineering | Backend Engineering | [42 empty] | 5 | 5 | Create service, fetch, update, unit test, doc, pipeline
|  | Fog-of-war | fetch fog of war and update it from unreal side | Engineering | Gameplay Engineering | [42 empty] | 1 | 2
|  | Minimap |  | Engineering | Gameplay Engineering
|  | Minimap | Minimap Levels | Design | Game design | [5 empty] | 5 | 8 | I personally endorse this |  | 10 | 20 | [12 empty] | 5
|  | Minimap | Minimap QA check | QA | QA
|  | Minimap | Minimap UI | Art | UX/UI | Minimap is constantly present on the screen to help players navigate; it supports quest tracking | [22 empty] | 10
|  | Minimap | Minimap assets | Art | Concept Art
|  | Minimap | Minimap quest navigation support | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 5 | 5 | 15 | 2 | 4 | 4 | 6 |  |  | 3 | 4 | dot on map for quest
|  | Minimap | Party player position | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 4 |  |  | 1 | 2
|  | Minimap | Special NPCs positions | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 5 | 2 | 5 | 2 | 3 | 2 | 4 |  |  | 2 | 3 | figure out if npc is needed to be show, static vs dynamic marker, npc icon, indoor vs outdoor
|  | Minimap | Zoom out/in | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 5 | 1 | 2 | 1 | 1.5 |  |  | 1 | 1
|  | World Map |  | Design | Game design | World map integrated with accessible areas visible and major points of interest placed + quality of life features to be designed | Player can access and navigate the world map Map has correct assets and quest tracking functionality |  |  |  | 10 | 14 | 15 | 25 | 10 | 20 | 10 | 20 | [10 empty] | 10
|  | World Map | Indoor Map | Engineering | Gameplay Engineering | A way to show indoor map | [29 empty] | 4 | 6 | 3 | 8 | 5 | 10 | 2 | 4 | 2 | 3 |  |  | 5 | 7 | if big map not much work needs to be done, if small map sync player position and make it adapt for indoor map
|  | World Map | Map QA check | QA | QA
|  | World Map | Map markers sfx | Audio | Audio | [21 empty] | 0.5 | 1 | 1
|  | World Map | POI names | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 3 |  |  | 1 | 1
|  | World Map | Party player position | Engineering | Gameplay Engineering | A way to show players position | [29 empty] | 4 | 6 | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 3 |  |  | 1 | 2 | display it on UI
|  | World Map | Quest markers and objectives support | Engineering | Gameplay Engineering | [32 empty] | 3 | 8 | 2 | 10 | 1 | 3 | 2 | 3 |  |  | 3 | 4 | Quest location, objectives location related to quest, radius, update icon depending on quest status
|  | World Map | Quest markers support | Engineering | Gameplay Engineering
|  | World Map | Special NPCs positions | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 5 | 2 | 3 | 2 | 3 | 2 | 3 |  |  | 2 | 3 | figure out if npc is needed to be show, static vs dynamic marker, npc icon, indoor vs outdoor
|  | World Map | World Map UI | Art | UX/UI | [23 empty] | 10
|  | World Map | World Map asset integration | Engineering | Gameplay Engineering | [32 empty] | 1 | 3 | 2 | 3 | 2 | 4 | 1 | 2 |  |  | 1 | 2
|  | World Map | World Map background asset | Art | Concept Art
|  | World Map | Zoom out/in | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 3 | 1 | 2 | 0.5 | 1 |  |  | 1 | 2 | its already done in outdoor, need to be impelemented indoor
| POI: Final Tower |  |  | Design | Game design | Intermediate layer before loading into the partner game | [44 empty] | 15 | [5 empty] | 10 |  |  |  | 11 |  |  | 3 |  |  | 39
|  | Final Tower Audio |  | Audio | Audio | [21 empty] | 3 | 5 | 2
|  | Final Tower Audio | Portal Dimension QA | QA | QA
|  | Final Tower Blockout |  | Design | Level design | [11 empty] | 4 | 8 | 4 | 15 | 1 | 5 | 2 | [5 empty] | 5
|  | Final Tower Concept |  | Art | Concept Art
|  | Final Tower Design |  | Design | Game design | Nikolas is desperate to call it Obsidian Tower | [10 empty] | 3 | 4 |  |  |  |  | 1 | [5 empty] | 1
|  | Final Tower Foliage |  | Art | Environment Art
|  | Final Tower Props Build |  | Art | Environment Art
|  | Final Tower layout |  | Art | Environment Art
| POI: Portal Dimension (XS) |  |  | Design | Game design | Intermediate layer before loading into the partner game | [44 empty] | 15 | [5 empty] | 10 |  |  |  | 11 |  |  | 3 |  |  | 39
|  | Portal Dimension Audio |  | Audio | Audio | [21 empty] | 0.5 | 1 | 1
|  | Portal Dimension Audio | Portal Dimension QA | QA | QA
|  | Portal Dimension Blockout |  | Design | Level design | [11 empty] | 4 | 8 | 4 | 15 | 1 | 5 | 2
|  | Portal Dimension Concept |  | Art | Concept Art
|  | Portal Dimension Design |  | Design | Game design | [11 empty] | 3 | 4 |  |  |  |  | 1 | [5 empty] | 1
|  | Portal Dimension Foliage |  | Art | Environment Art
|  | Portal Dimension Props Build |  | Art | Environment Art
|  | Portal Dimension layout |  | Art | Environment Art
| POI: The Two Hills (S) |  |  | Design | Game design | Two towers sequence with traversal and stuff. Player returns here after Downtime for the final scene | [44 empty] | 15 | [5 empty] | 10 |  |  |  | 11 |  |  | 3 |  |  | 39
|  | The Two Hills Audio |  | Audio | Audio | [21 empty] | 4 | 6 | 4
|  | The Two Hills Audio | The Two Hills QA | QA | QA
|  | The Two Hills Blockout |  | Design | Level design | approx. 15 min of gameplay. Content of Platforming and Scattered Enemies | [10 empty] | 6 | 15 | 3 | 7 | 7 | 15 | [6 empty] | 15
|  | The Two Hills Concept |  | Art | Concept Art
|  | The Two Hills Design |  | Design | Game design | [5 empty] | 4 | 6 |  |  |  |  | 4 | 10 | [10 empty] | 5
|  | The Two Hills Foliage |  | Art | Environment Art
|  | The Two Hills Props Build |  | Art | Environment Art
|  | The Two Hills layout |  | Art | Environment Art
| POI: Waterfall Beauty Spot (S) |  |  | Design | Game design | Shattered Pools can be used? user Space door placement here | [44 empty] | 15 | [5 empty] | 10 |  |  |  | 11 |  |  | 3 |  |  | 39
|  | Waterfall Beauty Spot Audio |  | Audio | Audio | [21 empty] | 4 | 6 | 3
|  | Waterfall Beauty Spot Audio | Waterfall Spot QA | QA | QA
|  | Waterfall Beauty Spot Blockout |  | Design | Level design | [11 empty] | 4 | 6 | 2 | 5 | 1 | 3 | [6 empty] | 4
|  | Waterfall Beauty Spot Concept |  | Art | Concept Art
|  | Waterfall Beauty Spot Design |  | Design | Game design | [5 empty] | 2 | 4 |  |  |  |  | 2 | 5 | [10 empty] | 2
|  | Waterfall Beauty Spot Foliage |  | Art | Environment Art
|  | Waterfall Beauty Spot Props Build |  | Art | Environment Art
|  | Waterfall Beauty Spot layout |  | Art | Environment Art
| Portal Dimension (XS) |  |  | Design | Game design | [45 empty] | 15 | [5 empty] | 10 |  |  |  | 11 |  |  | 3 |  |  | 39
|  | Portal Dimension Audio |  | Audio | Audio
|  | Portal Dimension Audio | Portal Dimension QA | QA | QA
|  | Portal Dimension Blockout |  | Design | Level design
|  | Portal Dimension Concept |  | Art | Concept Art
|  | Portal Dimension Design |  | Design | Game design
|  | Portal Dimension Foliage |  | Art | Environment Art
|  | Portal Dimension Props Build |  | Art | Environment Art
|  | Portal Dimension layout |  | Art | Environment Art
| Portal Peak (Medium) |  |  | Design | Game design | Just making sure that there are no blockouts/unfinished parts in PP player can see - probably mainly for enviro artists | [44 empty] | 15 | [5 empty] | 10 |  |  |  | 11 |  |  | 3 |  |  | 39
|  | PP Audio |  | Audio | Audio | [21 empty] | 14 | 18 | 15
|  | PP Audio | Portal Peak QA | QA | QA
|  | PP Blockout |  | Design | Level design | [11 empty] | 10 | 20 | 20 | 25 | 15 | 30 | [6 empty] | 20
|  | PP Concept |  | Art | Concept Art
|  | PP Design |  | Design | Game design | [5 empty] | 3 | 5 |  |  |  |  | 6 | 10 | [10 empty] | 5
|  | PP Foliage |  | Art | Environment Art
|  | PP Props Build |  | Art | Environment Art
|  | PP layout |  | Art | Environment Art
| Puzzles |  |  | Design | Game design | Implement a puzzle that requires multiple players to interact with environment elements to progress. | [6 empty] | 12 | 15 | 10 | 15 | [12 empty] | 5 | [29 empty] | 20 | [7 empty] | 20
|  | Multiplayer enviromental puzzle design |  | Design | Game design | Time Corruption puzzle (bridge + switch - 2 players) |  |  |  |  | 5 | 8 | 5 | 9 | 10 | 20 | 6 | 10 | [10 empty] | 12
|  | Multiplayer enviromental puzzle integration |  | Engineering | Gameplay Engineering
|  | Multiplayer enviromental puzzle integration | Make puzzle | Engineering | Gameplay Engineering | [30 empty] | 10 | 15 | 5 | 10 | 5 | 40 | 5 | 10 |  |  |  |  | 5 | 10 | dont know what puzzle is
|  | Multiplayer enviromental puzzle integration | Puzzles QA | QA | QA
|  | Multiplayer enviromental puzzle layout |  | Design | Level design | [11 empty] | 6 | 10 | 10 | 20 | 4 | 7 | [6 empty] | 10
| Session |  |  | Engineering | Backend Engineering | [51 empty] | 5 |  | 120 |  |  |  | 10 |  |  |  | 135
|  | Manage player session |  | Engineering | Backend Engineering
|  | Manage player session | Create a session service | Engineering | Backend Engineering | [24 empty] | 7 | 18 | 2 | 3 | 10 | 30 | [12 empty] | 1 | 2
|  | Manage player session | Record if player is online in redis | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 5 | 10 | [12 empty] | 3 | 4
| Skeletons |  |  | Design | Game design | [45 empty] | 35 | 15 | 10 |  | 10 |  | 13 |  | 20 |  |  | 17 | 10 | 30 | 15 |  | 175
|  | Animation |  | Art | Animation & Rigging
|  | Animation | Create animation graph | Art | Animation & Rigging | [40 empty] | 3 | 5 | 3 | 5
|  | Animation | Create control rig | Art | Animation & Rigging | [40 empty] | 1 | 2 | 1 | 2
|  | Animation | Custom death sequance | Art | Animation & Rigging | [40 empty] | 5 | 7 | 5 | 7
|  | Animation | Seperate clothing from body | Art | Animation & Rigging | [40 empty] | 5 | 7 | 5 | 7
|  | Combat Behavior |  | Engineering | Gameplay Engineering
|  | Combat Behavior | Make combat moves | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 3 | 10 | 3 | 5 | 5 | 7 |  |  | 5 | 10 | design vfx animation
|  | Concept |  | Art | Concept Art
|  | Design |  | Design | Game design | [7 empty] | 7 | 10 | 3 | 5 | [12 empty] | 9
|  | Implementation | Asset Validation | Art | TechArt
|  | Model |  | Art | Character Art
|  | Rigging |  | Art | Animation & Rigging | [40 empty] | 10 | 10 | 10 | 10
|  | SFX |  | Audio | Audio | [21 empty] | 0 | 0 | 0
|  | SFX | Skeletons QA | QA | QA
|  | Skeleton AI behaviour |  | Design | Game design | [23 empty] | 4
|  | Skeleton montages |  | Art | Animation & Rigging
|  | VFX |  | Art | VFX
|  | VFX | Skeletons QA | QA | QA
| Slimes |  |  | Design | Game design | [45 empty] | 35 | 15 | 10 |  | 10 |  | 13 |  | 20 |  |  | 17 | 10 | 30 | 15 |  | 175
|  | Animation |  | Art | Animation & Rigging
|  | Animation | Create animation graph | Art | Animation & Rigging | [40 empty] | 2 | 2 | 2 | 2
|  | Combat Behavior |  | Engineering | Gameplay Engineering
|  | Combat Behavior | Make combat moves | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 3 | 10 | 3 | 5 | 5 | 7 |  |  | 5 | 10 | design vfx animation
|  | Concept |  | Art | Concept Art
|  | Design |  | Design | Game design | [5 empty] | 4 | 6 | 7 | 10 | 3 | 5 | [12 empty] | 5
|  | Implementation | Asset Validation | Art | TechArt
|  | Model |  | Art | Character Art
|  | Rigging |  | Art | Animation & Rigging | [40 empty] | 2 | 2 | 2 | 2
|  | SFX |  | Audio | Audio | [21 empty] | 0 | 0 | 0
|  | SFX | Slimes QA | QA | QA
|  | Slimes AI behaviour |  | Design | Game design | [23 empty] | 2
|  | VFX |  | Art | VFX
|  | VFX | Slimes QA | QA | QA
| Speedup Archway |  |  | Design | Game design | The archway through Downtime going through the entire town. The goal is to show the player the town without making them actually walking around it. The main function is the competition between player for who completes it faster. Should have persistent leaderboards. | [6 empty] | 4 | 10 | 3 | 5 | [39 empty] | 5 |  |  | 20 | [5 empty] | 17 |  | 42
|  | Archway Models |  | Art | Environment Art
|  | Archway Placement |  | Design | Game design | [5 empty] | 2 | 4 | 2 | 4 | 2 | 5 | 4 | 7 |  |  | 1 | 2
|  | Archway SFX |  | Audio | Audio | [21 empty] | 0 | 0 | 0
|  | Archway SFX | Archway QA | QA | QA
|  | Archway VFX |  | Art | VFX
|  | Archway VFX | Win Fanfare VFX | Art | VFX
|  | Archway race design |  | Design | Game design | Downtime specifically | [22 empty] | 3
|  | Persistent leaderboards |  | Engineering | Backend Engineering | [24 empty] | 10 | 25 |  |  | 12 | 20 | [12 empty] | 1 | 2
|  | Safety System |  | Design | Game design | [7 empty] | -- | -- | 3 | 5 | [12 empty] | 3
| Static pictures intro + voiceover |  |  | Design | Game design | This is the proposed backup if an FMV cannot be produced within budget. |  |  |  |  | 8 | 10 | 15 | 20 | 10 | 30 | [12 empty] | 10 | [21 empty] | 5 |  |  |  | 5 | 15 | 16 |  | 15 |  |  | 2 | 10 | 5 | 12 |  | 85
|  | Intro sequence plays 3 slides with voiceover |  | Engineering | Backend Engineering | Intro sequence supports static pictures playback with voiceover and subtitles | The pictures are played correctly Voiceover and subtitles are synced to the scene Skip functionality works No major bugs or blockers
|  | Intro sequence plays 3 slides with voiceover |  | Engineering | Gameplay Engineering | Intro sequence supports static pictures playback with voiceover and subtitles | The pictures are played correctly Voiceover and subtitles are synced to the scene Skip functionality works No major bugs or blockers
|  | Intro sequence plays 3 slides with voiceover | Allow this to be triggered from quest | Engineering | Gameplay Engineering | [30 empty] | 0.5 | 1 | 2 | 3 | 3 | 5 | 1 | 2 | 1 | 2 |  |  | 2 | 3
|  | Intro sequence plays 3 slides with voiceover | Create a system to disallow the player from moving while in FMV | Engineering | Gameplay Engineering | [30 empty] | 0.5 | 1 | 2 | 3 | 2 | 3 | 1 | 2 | 1 | 2 |  |  | 0.5 | 1 | it takes 30 min to not make the character not move
|  | Intro sequence plays 3 slides with voiceover | Create intro sequence controller | Engineering | Backend Engineering
|  | Intro sequence plays 3 slides with voiceover | Create intro sequence controller | Engineering | Gameplay Engineering | ?????????????
|  | Intro sequence plays 3 slides with voiceover | Display static slides full-screen | Engineering | Backend Engineering
|  | Intro sequence plays 3 slides with voiceover | Display static slides full-screen | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 3 | 5 | 3 | 5 | 1 | 2 | 0.5 | 1 |  |  | 3 | 5 | Scale for wide screen and all resolutions, transition, zoom,
|  | Intro sequence plays 3 slides with voiceover | Display subtitles synced to VO | Engineering | Backend Engineering
|  | Intro sequence plays 3 slides with voiceover | Display subtitles synced to VO | Engineering | Gameplay Engineering | [30 empty] | 2 | 3 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 2 |  |  | 2 | 3 | Make subtitle typewriter effect, background
|  | Intro sequence plays 3 slides with voiceover | Final art production | Art | Concept Art
|  | Intro sequence plays 3 slides with voiceover | Implement skip behavior | Engineering | Backend Engineering
|  | Intro sequence plays 3 slides with voiceover | Implement skip behavior | Engineering | Gameplay Engineering | [30 empty] | 0.5 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 0.5 | 1 |  |  | 1 | 2 | Taking into consideration meeting with UI designer and bug fixing
|  | Intro sequence plays 3 slides with voiceover | Implement transition to gameplay/menu | Engineering | Backend Engineering
|  | Intro sequence plays 3 slides with voiceover | Implement transition to gameplay/menu | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Intro sequence plays 3 slides with voiceover | Integrate final art + VO assets | Engineering | Backend Engineering
|  | Intro sequence plays 3 slides with voiceover | Integrate final art + VO assets | Design | Game design | This was engineering, should be design
|  | Intro sequence plays 3 slides with voiceover | Play voiceover synced to sequence | Engineering | Backend Engineering
|  | Intro sequence plays 3 slides with voiceover | Play voiceover synced to sequence | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 2 |  |  | 1 | 2 | Play wav files in FMOD
|  | Intro sequence plays 3 slides with voiceover | QA + fix blockers | QA | QA
|  | Intro sequence plays 3 slides with voiceover | Subtitles production | Design | Game design | [7 empty] | 2 | 4 | 2 | 5 | [6 empty] | 0.5 | 2 |  |  |  |  | 1
|  | Intro sequence plays 3 slides with voiceover | Tool for designers | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 2 | 5 | 2 | 5 | 2 | 4 |  |  | 5 | 10 | Syncing subtitles, voice overs, images, delay/speed up on subtitles, voice overs and images, localization if needed, show list of existing data assets, remove data assets
|  | Intro sequence plays 3 slides with voiceover | UI Design | Art | UX/UI
|  | Intro sequence plays 3 slides with voiceover | VO production | Audio | Audio | [7 empty] | 6 | 10 | no idea | no idea | [12 empty] | 3
|  | Intro sequence plays 3 slides with voiceover | VO production | Design | Game design
| Sync last known player position | [55 empty] | 7 |  | 20 |  |  | 2 |  | 3 | 2 |  | 34
Player can server travel between zones semlessly
|  | Player can server travel between zones semlessly | For network engineer to figure out | Engineering | Gameplay Engineering
Player can server travel between zones with loading screen
|  | Player can server travel between zones with loading screen | Pass entrance parameters from one server to another | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 3 | 3 | 4 | 3 | 4 | 1 | 2 |  |  | 3 | 5
|  | Player can server travel between zones with loading screen | Set entrace points on map | Design | Game design
|  | Player can server travel between zones with loading screen | Set spawn position according to entrance paramters | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 3 |  |  | 1 | 2 | 1 | 2 |  |  | 3 | 5
When the player login he should be in the same last spot he logged out (player data service)
|  | When the player login he should be in the same last spot he logged out (player data service) | Conect to last server player left from | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 2 | 3 | 1 | 2 | 2 | 3 |  |  | 1 | 2
|  | When the player login he should be in the same last spot he logged out (player data service) | Create an endpoint to fetch player position, rotation and IP address | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 2 | 1 | 2 | [12 empty] | 1 | 2
|  | When the player login he should be in the same last spot he logged out (player data service) | Create an endpoint to store player X, Y, Z corrdinates and rotation and server ip address | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 1 | 3 | [12 empty] | 2 | 3
|  | When the player login he should be in the same last spot he logged out (player data service) | Create unit test for update and fetch endpoint | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 0.5 | 1 | 2 | [12 empty] | 1 | 2
|  | When the player login he should be in the same last spot he logged out (player data service) | List of servers and their ip address | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 2 | 4 | [12 empty] | 4 | 5
|  | When the player login he should be in the same last spot he logged out (player data service) | Save player position and rotation and ip every X seconds on server, so if the server crashes we can retrieve this information later | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 3 | 3 | 5 | 1 | 2 | 1 | 2 |  |  | 3 | 4
|  | When the player login he should be in the same last spot he logged out (player data service) | Set player position, rotation, when spawning player | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 3 | 3 | 5 | 1 | 2 | 1 | 2 |  |  | 1 | 2
| Wolves |  |  | Design | Game design | [45 empty] | 35 | 15 | 10 |  | 10 |  | 13 |  | 20 |  |  | 17 | 10 | 30 | 15 |  | 175
|  | Animation |  | Art | Animation & Rigging
|  | Animation | Create animation graph | Art | Animation & Rigging | [40 empty] | 3 | 5 | 3 | 5
|  | Animation | Create control rig | Art | Animation & Rigging | [40 empty] | 1 | 2 | 1 | 2
|  | Combat Behavior |  | Engineering | Gameplay Engineering
|  | Combat Behavior | Make combat moves | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 3 | 10 | 3 | 5 | 5 | 7 |  |  | 5 | 10 | design vfx animation
|  | Concept |  | Art | Concept Art
|  | Design |  | Design | Game design | [5 empty] | 4 | 6 | 7 | 10 | 3 | 5 | [12 empty] | 5
|  | Implementation | Asset Validation | Art | TechArt | Geo topology, UVs space optim., textures compliant to D/NRM/ORME/Mask rules, LOD0/1/2 decimation 100%/50%/25%
|  | Model |  | Art | Character Art
|  | Rigging |  | Art | Animation & Rigging | [40 empty] | 10 | 10 | 10 | 10
|  | VFX |  | Art | VFX
|  | VFX | Wolves QA | QA | QA
|  | Wolf AI behaviour |  | Design | Game design | [23 empty] | 2
|  | Wolf montages |  | Art | Animation & Rigging
|  | Wolfy noises |  | Audio | Audio | [21 empty] | 0 | 0 | 0
|  | Wolfy noises | Wolves QA | QA | QA
| World Resources |  |  | Design | Game design | [49 empty] | 10 |  | 10 |  | 20 |  |  |  | 10 | 40 |  |  | 90
|  | Equipment Stats integrated with character stats |  | Design | Game design | Reliant on character design (do stats change) |  |  |  |  | 5 | 10 | 5 | 8 | 5 | 10 | [12 empty] | 5
|  | Equipment Stats integrated with character stats | Equipment Stats integrated with character stats | Engineering | Gameplay Engineering
|  | Equipment Stats integrated with character stats | QA check | QA | QA
|  | Shield |  | Design | Game design | NOTE: Should be in combat section |  |  |  |  | 4 | 6 | 2 | 4 | 3 | 5 | [12 empty] | 4
|  | Shield | Shield Asset | Art | Environment Art
|  | Shield | Shield animations | Art | Animation & Rigging
|  | Starting Chest |  | Design | Game design | NOTE: This entire story may be redundant. We already have chests. There is already a task for adding one to the initial cave. Player can find a chest in the tutorial cave that has the sword inside | The chest should be located on the player's way. The player should be incentivised to interact with the chest. Progress should rely on opening the chest. |  |  |  | 1 | 2 | 1 | 2 | 3 | 5 | 0.5 | 1 |  |  | 0.5 | 1
|  | Starting Chest | Chest VFX | Art | VFX | Open "sparkle" and rewarding feedback, Ballista minigame
|  | Starting Chest | Chest animation | Art | Animation & Rigging | [40 empty] | 1 | 1 | 1 | 1
|  | Starting Chest | Chest concept | Art | Concept Art
|  | Starting Chest | Chest model | Art | Environment Art
|  | Starting Chest | QA check | QA | QA
|  | Starting Sword |  | Design | Game design | NOTE: Should be in combat section Starting player weapon. Should be good enough to fight starting enemies and not get easily killed | [6 empty] | 2 | 4 | 3 | 5 |  |  |  |  | 0.5 | 0.5 | [6 empty] | 4
|  | Starting Sword | Equipment Stats integrated with character stats | Engineering | Gameplay Engineering
|  | Starting Sword | QA check | QA | QA
|  | Starting Sword | Sword VFX | Art | VFX | Swing sword trail (visual: color, opacity) | Readable and underline weapon movement and area of damage plus distinction with standard/enchanted/poisoned
|  | Starting Sword | Sword animations | Art | Animation & Rigging | [40 empty] | 5 | 10 | 5 | 10 | design unkown yet, so 5 - 10 days. setup belnds, motion warping, ensure sword animation layers with locamotion, jumping, etc..
|  | Starting Sword | Sword concept | Art | Concept Art
|  | Starting Sword | Sword model | Art | Character Art
| World/buiding scale design |  |  | Design | Game design | World scale and building scale :defined and accepted throughout the game. | Scales definition are locked in documentation Parts of the game that are out of scale are fixed | [11 empty] | 1 month | 6 months | [8 empty] | 21 | [27 empty] | 17 |  | 60 |  | 10 |  | 90 | 20 | 5 |  | 202
Combat | Basic Magic system |  |  | Design | Game design | Basic magic systems with 3-4 different spells (attack & heal). The player won't have access to spells but the bots/other players (pre-configured builds) should be able to use it during the coop segment | [6 empty] | 20 | 25 | 5 | 15 | [12 empty] | 25 | [21 empty] | 30 |  | 10 | 5 |  |  | 30 | 5 | 30 |  |  |  |  | 10 | 20 |  | 140
|  | Magic SFX |  | Audio | Audio | [21 empty] | 7 | 10 | 5
|  | Magic UI (1 skill tree mapped out) |  | Art | UX/UI | [7 empty] | 5 | 9 | [14 empty] | 7
|  | Magic VFX |  | Art | VFX | Elemental x4 (Fire, Ice, Lighting, Earth) | Visibility, AOE, distinction
|  | Magic VFX | Magic QA | QA | QA
|  | Magic Weapon (e.g. wand) |  | Design | Game design | [7 empty] | 5 | 10 | 3 | 10 | [12 empty] | 5
|  | Magic Weapon (e.g. wand) | Weapon | Art | Environment Art
|  | Magic casting animations |  | Art | Animation & Rigging
|  | Magic implementation |  | Engineering | Gameplay Engineering
|  | Magic system design (3-4 spells) |  | Design | Game design
|  | Magic system design (5 spells) |  | Design | Game design | [7 empty] | 10 | 15 | 5 | 15 | [12 empty] | 10
|  | equipd wand |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 2 | 3 | 1 | 3 | 1 | 2 |  |  | 1 | 1
|  | make wand abilities 4 |  | Engineering | Gameplay Engineering | [30 empty] | 10 | 15 | 10 | 15 | 10 | 15 | 5 | 10 | 12 | 16 |  |  | 10 | 15 | VFx, animation, ability, gameplay effect, gameplay cue
|  | make wand an item type |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 2 | 3 | 2 | 4 | 1 | 2 |  |  | 1 | 1
|  | wand skill tree |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 5 | 5 | 7 | 2 | 4 | 3 | 4 |  |  | 2 | 3 | 4 abilities
| Combat abilities |  |  | Design | Game design | A set of abilities to use during combat (powerful hits, special moves, etc). Can be gained through the skill system. Equipped in the abilities bar | [44 empty] | 25 |  | 10 |  | 2 |  | 20 |  | 30 |  |  | 20 |  | 10 | 20 |  | 137
|  | Abilities Design |  | Design | Game design | Define the set of abilities available for the vertical slice (1-2 available from the beginning plus 1-2 unlocked through progression) | [6 empty] | 8 | 10 | [14 empty] | 9
|  | Abilities Design | 4 Abilities designed (2 weapons) | Design | Game design | [7 empty] | 16 | 22 | 5 | 10 | [12 empty] | 20
|  | Abilities Design | Weapon attribute system | Design | Game design | [7 empty] | 3 | 7 | 3 | 8 | [12 empty] | 5
|  | Combat Abilities SFX |  | Audio | Audio | These are for special moves, not base combat | [20 empty] | 7 | 14 | 7
|  | Combat Abilities UI |  | Art | UX/UI | [7 empty] | 8 | 15 | [14 empty] | 15
|  | Combat Abilities integrated with skill path |  | Engineering | Gameplay Engineering
|  | Combat SFX |  | Audio | Audio
|  | Combat abilities casting animations |  | Art | Animation & Rigging | [40 empty] | 5 | 7 | 3 | 5 | depends on the complexity of the task
|  | Combat abilities casting animations | Combat Abilities QA | QA | QA
|  | HUD Combat Abilities UI |  | Art | UX/UI | [7 empty] | 8 | 15 | [14 empty] | 5
|  | HUD Combat Abilities UI | HUD design | Art | UX/UI | [7 empty] | 5 | 7 | 5 | 10 | [12 empty] | 7
|  | Integrate abilities with skill path |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 3 | 5 | 10 | 5 | 10 | 3 | 4 |  |  | 2 | 3 | Current design
|  | Make the abilities |  | Engineering | Gameplay Engineering | [30 empty] | 15 | 20 | 10 | 15 | 20 | 40 | 5 | 10 | 12 | 15 |  |  | 10 | 12 | 4 abilties for sword, 2 abilities for heal, 4 abilties for shield
| Combat component | [55 empty] | 24 |  | 36 |  |  | 6 | 60 | 9 | 30 |  | 165
Impelment all ai decision
|  | Impelment all ai decision | Execution check | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 3 | 5 | 2 | 3 | 2 | 3 |  |  | 2 | 4
|  | Impelment all ai decision | Reflex check | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 3 | 5 | 2 | 3 | 2 | 3 |  |  | 5 | 10
|  | Impelment all ai decision | Safety check | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 3 | 5 | 2 | 3 | 2 | 3 |  |  | 5 | 10
|  | Impelment all ai decision | Social check | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 3 | 5 | 2 | 3 | 2 | 3 |  |  | 5 | 10
|  | Impelment all ai decision | Survival check | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 3 | 5 | 2 | 3 | 2 | 3 |  |  | 5 | 10
|  | Impelment all ai decision | attack abilities (attack etc...) | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 5 | 10 | 2 | 4 | 4 | 5 |  |  | 2 | 4
|  | Impelment all ai decision | decision tick | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 5 | 8 | 2 | 3 | 2 | 3 |  |  | 2 | 4
|  | Impelment all ai decision | different types of movements | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 5 | 10 | 3 | 4 | 3 | 4 |  |  | 5 | 10
|  | Impelment all ai decision | utility abilities (healthing etc...) | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 5 | 10 | 2 | 3 | 4 | 5 |  |  | 2 | 4
| Combat director | [55 empty] | 24 |  | 36 |  |  | 6 | 60 | 9 | 30 |  | 165
Impelment all ai decision
|  | Impelment all ai decision | AI vs AI | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 5 | 10 | 1 | 2 | 3 | 4 |  |  | 3 | 5 | depends on design
|  | Impelment all ai decision | Distance based agro | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 3 | 5 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Impelment all ai decision | Health based agro | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 3 | 5 | 2 | 3 | 1 | 2 |  |  | 1 | 2
|  | Impelment all ai decision | Player feedback | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 3 | 5 |  |  | 3 | 5 | 2 | 3 |  |  | 3 | 5
|  | Impelment all ai decision | Pressure based agro | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 3 | 5 | 1 | 2 | 1 | 2 |  |  | 5 | 8
|  | Impelment all ai decision | Scaling | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 5 | 10 | 3 | 5 | 3 | 4 |  |  | 1 | 2
|  | Impelment all ai decision | Utility managment | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 5 | 8 | 3 | 5 | 1 | 2 |  |  | 5 | 10
| Consumables | [49 empty] | 5 | [10 empty] | 2 |  | 2 |  |  | 9
|  | Check the health potion usage |  | QA | QA | We only use the heal potion for the vertical slice - the functionality, props and VFX should be implemented and working but need check if everyhting is okay
Player should be able to drink a potion
|  | Player should be able to drink a potion | Implement drinking animation | Art | Animation & Rigging | [40 empty] | 1 | 1 | 1 | 1
| Melee Combat Framework |  |  | Design | Game design | Player can engage in melee combat with various enemies throughout the game. Combat has all needed movements and animation and supports sword + shield for the player and heavy weapon and magic for bots (party). | [50 empty] | 24 |  | 36 |  |  | 6 | 60 | 9 | 30 |  | 165
|  | Aim offset implementation |  | Art | Animation & Rigging | [40 empty] | 2 | 4 | 2 | 4
|  | Attacks Design Doc - per weapon (Combo + off-hand attacks) |  | Design | Game design | [7 empty] | 3 | 4 | 3 | 5 | [12 empty] | 4
|  | Combat Animations |  | Art | Animation & Rigging
|  | Combat Design |  | Design | Game design | [7 empty] | 15 | 20 | 15 | 20 | [12 empty] | 15
|  | Combat Montages |  | Art | Animation & Rigging
|  | Combat Tech anim? |  | Art | Animation & Rigging | [40 empty] | 10 | 20 | 10 | 20
|  | Combat VFX |  | Art | VFX
|  | Combat VFX | Melee Combat QA | QA | QA
|  | Combat integration |  | Engineering | Gameplay Engineering
|  | Death sequance system |  | Engineering | Gameplay Engineering | [30 empty] | 4 | 6 | 3 | 5 | 5 | 10 | 2 | 4 | 3 | 4 |  |  | 1 | 2
|  | Review the combat with networking engineer |  | Engineering | Gameplay Engineering | [30 empty] | 8 | 12 | 5 | 10 | 5 | 10 | 10 | 15 | 5 | 7 |  |  | 5 | 5
|  | Weapon Attributes (per weapon) |  | Design | Game design | [7 empty] | 1 | 2 | 3 | 5 | [12 empty] | 1
|  | Weapon spesific hand poses |  | Art | Animation & Rigging | [40 empty] | 2 | 2 | 2 | 2
|  | Weapons models |  | Art | Character Art
| PVP Combat |  |  | Design | Game design | Basic PVP combat support, no special PVP moves or animations. Should only be active in the Arena, no free PVP interactions in the world | [6 empty] | 20 | 30 | [42 empty] | 16 |  | 3 |  |  | 2 |  | 3 |  |  | 24
Area implementation
|  | Area implementation | Create UI/UX | Art | UX/UI
|  | Area implementation | Create fight timer and declare draw | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 |  |  | 1 | 2
|  | Area implementation | Implement player prediction algorithm for networking | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 10 | 20 | 5 | 10 | 10 | 15 |  |  | 5 | 10
|  | Area implementation | Kick players that are in the area who are not fighting when you and someone else decide to start a fight | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 4 | 1 | 2 | 2 | 3 |  |  | 2 | 4
|  | Area implementation | PVP Combat support | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 1 | 5 | 3 | 6 | 4 | 5 |  |  | 3 | 5
|  | Area implementation | PVP area blocks player from entering and leaving | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Area implementation | PVP only available in Arena | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Area implementation | Reward player who won and display a message to the loser | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 3 |  |  | 1 | 2
|  | Area implementation | Show damage numbers between players on hit | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 3 | 5 | 3 | 4 | 2 | 3 |  |  | 1 | 3 | current system
|  | Area implementation | Show other player HP in area fight | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 4 | 1 | 3 | 2 | 3 |  |  | 2 | 4
|  | Area implementation | Sign up for arena fight actor | Engineering | Gameplay Engineering | [30 empty] | 2 | 3 | 1 | 2 | 3 | 5 | 2 | 3 | 3 | 4 |  |  | 1 | 2
|  | Area implementation | declare player who is connected as winner | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 3 |  |  | 1 | 2
|  | Ensure combat system works |  | Engineering | Gameplay Engineering | [34 empty] | 5 | 10 | 5 | 10 | 4 | 5 |  |  | 2 | 3
|  | PVP Arena Audio |  | Audio | Audio | [21 empty] | 7 | 14 | 5
|  | PVP Arena Audio | PVP combat QA | QA | QA
|  | PVP Arena Design |  | Design | Game design | [11 empty] | 6 | 10 | [10 empty] | 7
|  | PVP Arena Foliage |  | Art | Environment Art
|  | PVP Arena blockout |  | Design | Level design | [11 empty] | 6 | 15 | 3 | 7 | 10 | 15 | [6 empty] | 10
|  | PVP Arena concept |  | Art | Concept Art
|  | PVP Arena props |  | Art | Environment Art
|  | PVP Arena set dressing |  | Art | Environment Art
|  | PVP Combat Setup |  | Design | Game design | [23 empty] | 6
|  | PVP Combat design |  | Design | Game design | [7 empty] | 10 | 18 | 10 | 20 |  |  |  |  | 5 | 10 | [6 empty] | 12
|  | PVP Combat support |  | Engineering | Gameplay Engineering
|  | PVP only available in Arena |  | Engineering | Gameplay Engineering
| Ranged (Corruption Gun) |  |  | Design | Game design | [7 empty] | 4 | 8 | [14 empty] | 4 | [21 empty] | 30 |  | 10 | [5 empty] | 20 | [7 empty] | 60
|  | Aimed offsets |  | Art | Animation & Rigging
|  | Dual Wielding Ranged |  | Design | Game design | [7 empty] | 4 | 6 | 2 | 5 | [12 empty] | 4
|  | Ranged Attributes |  | Design | Game design | [7 empty] | 5 | 8 | 5 | 10 | [12 empty] | 5
User Space | Anywhere door placement |  |  | Engineering | Gameplay Engineering | [49 empty] | 5 |  |  |  | 5 | [5 empty] | 15 |  | 25
|  | Create an ability to place anywhere door in the world |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 3 | 5 | 1 | 2 | 4 | 6 |  |  | 1 | 2
|  | Create anywhere door as item in backend service. |  | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 0.5 | 0.5 | 3 | 4 | [12 empty] | 1 | 2
|  | Create anywhere door as item. |  | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 2 |  |  | 2 | 3
|  | Create endpoint to update the position, rotation and zone name of MULTIPLE anywhere door in backend (player data service) |  | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 0.5 | 1 | 3 | 5 | [12 empty] | 1 | 2
|  | Create fetech anywhere door endpoint (player data service) |  | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 2 | 4 | [12 empty] | 1 | 2
|  | Make anywhere door as an actor |  | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 5 | 1 | 3 | 2 | 4 |  |  | 1 | 2
|  | Make spesific regions where anywhere door can be placed |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 2 | 7 | 1 | 3 | 2 | 3 |  |  | 1 | 2
|  | Make spesific regions where anywhere door can be placed | Anywhere Door QA | QA | QA
|  | Remove anywhere door |  | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 5 | 1 | 2 | 3 | 4 |  |  | 1 | 2
|  | Show anywhere door on compass |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 1 | 5 | 1 | 2 | 1 | 2 |  |  | 3 | 4
|  | Show anywhere door on map |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 1 | 5 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Show anywhere door on minimap |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 1 | 5 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Show if the anywhere door is placed or not placed to remove it if needed |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 1 | 5 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Update anywhere door position, rotation, zone name after fethcing anywhere door info from (player data serivce) |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 3 | 2 | 3 | 2 | 3 | 1 | 3 | 1 | 2 |  |  | 1 | 2
|  | User space door can be placed at predefined spots |  | Engineering | Gameplay Engineering | We choose predefined spots in Portal peak (flat surface) where player can place their door. The door stays there and serves as a permanent user Space entrance | [29 empty] | 2 | 3 | 2 | 4 | 2 | 4 | 2 | 4 | 5 | 7 |  |  | 2 | 3
|  | User space door can be placed at predefined spots | Anywhere Door QA | QA | QA
|  | fetch anywhere door info from backend service and place it in the world |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 3 | 1 | 2 | 2 | 5 | 1 | 3 | 2 | 3 |  |  | 1 | 2
| Fishing |  |  | Design | Game design | Fishing minigame/profession. Quite self-explanatory. Basically ready but needs final assets, animations and QA | [48 empty] | 20 |  | 14 |  | 30 |  | 15 | 2 |  |  |  |  | 81
|  | Fish model |  | Art | Environment Art
|  | Fishing Integration |  | Design | Game design | [9 empty] | 3 | 10 | [12 empty] | 3
|  | Fishing Rod model |  | Art | Environment Art
|  | Fishing Spot SFX |  | Audio | Audio | [21 empty] | 0 | 0 | 0
|  | Fishing Spot VFX |  | Audio | Audio
|  | Fishing Spot VFX | Fishing QA | QA | QA
|  | Fishing UI |  | Art | UX/UI | [23 empty] | 3
|  | Fishing VFX |  | Art | VFX
|  | Fishing VFX | Fishing QA | QA | QA
|  | Fishing spot sign model |  | Art | Environment Art
|  | Review fishing code |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 2 | 4 | 2 | 3 | 2 | 3 |  |  | 2 | 3
| Pets (mechanical parrot reuse) |  |  | Design | Game design | Demo of the pets functionality. Pure cosmetic for the time being. Should be already supported. Decided to proceed with the parrot that was modelled for the pirates enemies |  |  |  |  | 3 | 5 |  |  | 8 | 15 | [34 empty] | 13 |  | 3 | 2 |  |  | 5 |  | 20 |  |  |  | 2 |  | 5 |  | 50
|  | Pet VFX |  | Art | VFX
|  | Pet animation grpah setup |  | Art | Animation & Rigging | [40 empty] | 2 | 2 | 2 | 2
|  | Pet animation grpah setup | Pet QA | QA | QA
|  | Pet animations |  | Art | Animation & Rigging
|  | Pet behavior |  | Engineering | Gameplay Engineering
|  | Pet concepts |  | Art | Concept Art
|  | Pet integration |  | Engineering | Gameplay Engineering
|  | Pet integration | Pet QA | QA | QA
|  | Pet maya rig setup |  | Art | Animation & Rigging | [40 empty] | 2 | 2 | 2 | 2
|  | Pet model |  | Art | Character Art
|  | Pet system design |  | Design | Game design | [23 empty] | 4
|  | Review pet system code |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 2 | 4 | 2 | 3 | 3 | 4 |  |  | 1 | 2
|  | Teleport pet to player when pet is stuck |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 1 | 3 | 2 | 4 | 1 | 2 |  |  | 1 | 2
| User Space Decoration |  |  | Art | Environment Art | The model of the house and sufficient furniture pieces that can be placed in the User Space |  | M | T0: Ideation | [45 empty] | 20 |  | 14 |  | 30 |  | 15 | 2 |  |  |  |  | 81
|  | User Space House concept |  | Art | Concept Art
|  | User Space House model |  | Art | Environment Art
|  | User Space furniture props |  | Art | Environment Art
| User Space Island (S) |  |  | Design | Game design | A separate location that serves as a player home. Inclides a half-build house, pets, a pond/river and fishing spots | [52 empty] | 60 |  |  | 2 |  | 3 |  |  | 65
|  | User Space GDD VS page |  | Design | Game design | [23 empty] | 1
|  | User Space location blockout |  | Design | Level design | [11 empty] | 6 | 10 | 7 | 15 | 5 | 10 | [6 empty] | 7
|  | User Space location concepts |  | Art | Concept Art
|  | User Space location foliage |  | Art | Environment Art
|  | User Space location foliage | User Space visuals QA | QA | QA
|  | User Space location props |  | Art | Environment Art
|  | User Space location set dressing |  | Art | Environment Art
| User Space Server & Instance |  |  | Engineering | Backend Engineering | User Space is a separate instance and a player's home. Players place the door to access it. For the vertical slice, the door is placed in a POI in Portal Peak and the player is loaded into a separate location with a half-build house. |  | L | T2: GDD/TDD/Brief | [49 empty] | 60 | [7 empty] | 60
|  |  | Drinking design | Design | Game design | [23 empty] | 1
|  |  | Drunken UI | Art | UX/UI | [23 empty] | 4
|  |  | FTUE Design | Design | Game design | [5 empty] | 4 | 6 |  |  | 3 | 8 |  |  |  |  | 4 | 7 | [6 empty] | 5
|  |  | FTUE UI | Art | UX/UI | [23 empty] | 5
|  |  | Mutual Activity Design | Design | Game design | [5 empty] | 4 | 6 |  |  | 5 | 10 |  |  |  |  | 2 | 5 | [6 empty] | 4
|  |  | Mutual Activity UI | Art | UX/UI | [23 empty] | 5
|  |  | User Space Editor audio | Audio | Audio | [21 empty] | 2 | 3 | 2
|  | User Space Ambience |  | Audio | Audio | [21 empty] | 1 | 2 | 1
|  | User Space Ambience | Island ambient audio | Audio | Audio | [21 empty] | 1 | 2 | 1
|  | User Space Ambience | Item SFX | Audio | Audio | [21 empty] | 0.5 | 1 | 1
|  | User Space editor & UI |  | Engineering | Gameplay Engineering
|  | User Space editor & UI | Implement interaction animation with userspace items (snap) | Art | Animation & Rigging | [40 empty] | 2 | 5 | 1 | 5 | if chair table it will be 1 day, if more need more time
|  | User Space editor & UI | Setup animation for userspace editing tool | Art | Animation & Rigging | [40 empty] | 1 | 1 | 1 | 1
|  | User Space editor VFX |  | Art | VFX
|  | User Space editor VFX | User Space functionality QA | QA | QA
|  | User Space is a separate instance |  | Engineering | Backend Engineering
|  | User Space is a separate instance | DevOps | Engineering | Backend Engineering | [24 empty] | 5 | 18 | 3 | 4 | 5 | 15 | [12 empty] | 2 | 3 | pipeline
|  | User Space is a separate instance | Edit mode improvmeents | Engineering | Gameplay Engineering | [30 empty] | 4 | 5 | 3 | 5 | 4 | 8 | 5 | 10 | 3 | 4 |  |  | 5 | 10 | UI, build house etc..
|  | User Space is a separate instance | Enable fishing in userspace | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 5 | 15 | 1 | 3 | 2 | 3 |  |  | 2 | 3
|  | User Space is a separate instance | Fetch userspace furniture from backend | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 5 | 3 | 5 | 6 | 7 |  |  | 1 | 2
|  | User Space is a separate instance | Figure out friend ip address to join his server when invited | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 4 | 7 | [12 empty] | 3 | 4
|  | User Space is a separate instance | Host permissions | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 5 | 8 | 5 | 15 | 5 | 7 |  |  | 5 | 10 | kick, invite, make sure only host does X things and who joins doesnt do X things
|  | User Space is a separate instance | IP address list service | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 3 | 5 | [12 empty] | 5 | 6
|  | User Space is a separate instance | Load userspace from save data | Engineering | Gameplay Engineering | [30 empty] | 2 | 3 | 1 | 2 | 2 | 3 | 2 | 5 | 3 | 4 |  |  | 5 | 7
|  | User Space is a separate instance | Multiple players join one server and only show what is relevent to current player | Engineering | Gameplay Engineering | [30 empty] | 15 | 20 | 10 | 20 | 10 | 20 | 10 | 20 | 15 | 20 |  |  | 10 | 20
|  | User Space is a separate instance | Player joining friends userspace | Engineering | Gameplay Engineering | [30 empty] | 4 | 6 | 3 | 5 | 2 | 3 | 5 | 10 | 3 | 6 |  |  | 5 | 10 | user space invites, join with ip, ui
|  | User Space is a separate instance | Save userspace furniture location in userspace | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 4 | 6 | [12 empty] | 3 | 4
|  | User Space is a separate instance | Update userspace furniture and tell that to all players | Engineering | Gameplay Engineering | [30 empty] | 4 | 6 | 3 | 5 | 2 | 5 | 3 | 5 | 5 | 6 |  |  | 4 | 5
Items & Inventory | Sync hotbar to db | [57 empty] | 30 | [7 empty] | 30
The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | Create an endpoint to euip items | Engineering | Backend Engineering | [42 empty] | 2 | 3
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | Create an endpoint to fetch abilities internal dashboard | Engineering | Backend Engineering | [42 empty] | 1 | 2
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | Create an endpoint to fetch equiped items | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 1 | 3 | [12 empty] | 1 | 2
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | Create an endpoint to remove ability internal dashboard | Engineering | Backend Engineering | [42 empty] | 1 | 2
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | Create an endpoint to store abilities in internal dashboard | Engineering | Backend Engineering | [42 empty] | 1 | 2
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | Create endpoint to fetch hotbar items and abilities | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 2 | 4 | [12 empty] | 1 | 2
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | Create unit test for updating, fetching | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 1 | 3 | [12 empty] | 1 | 2
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | Fetch and set equiped items | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 3 | 3 | 10 | 1 | 2 | 2 | 3 |  |  | 2 | 3
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | Get hotbar item and abiltitie positions and set them | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 3 | 3 | 10 | 1 | 2 | 1 | 2 |  |  | 1 | 3 | based on current system
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | Send an HTTP reuqest only after 2 seconds after not moving any items or abilities in hotbar | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 3 | 3 | 5 | 1 | 2 | 2 | 3 |  |  | 2 | 3
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | an endpoint to all items equiped (batch requests only send what changed) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 3 | 5 | [12 empty] | 2 | 3
|  | The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar | an endpoint to update all item and abilities position in the hotbar (batch requests only send what changed) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 2 | 4 | [12 empty] | 2 | 3
Player Economy | Auction House economy |  |  | Design | Game design | [7 empty] | 15 | 20 | 10 | 20 | [12 empty] | 15 | [29 empty] | 120 | [7 empty] | 120
|  | P2G Transactions Support |  | Engineering | Backend Engineering
|  | P2G Transactions Support | Trading System QA | QA | QA
| In-game economy |  |  | Design | Game design | Basic in-game economy configuration, placeholder balance. Need to define sources and sinks for the vertical slice | [50 empty] | 90 | [6 empty] | 30 |  |  | 120
|  | Basic Economy configuration |  | Design | Game design | Just the prices for the vertical slice - not a complete system |  |  |  |  | 20 | 25 | 40 | 60 | 10 | 20 | [12 empty] | 5
|  | Basic Economy configuration | In-game economy QA check | QA | QA
| Trading System |  |  | Design | Game design | Basic trading operations between the player and the game (buying equipment/garmets/resources from vendors). Requires shops models/props, vendors models, UI, currency implementation, minimum balance and economy. We need to make sure player has enough money to buy things after completing story quests in the VS |  | L | T0: Ideation |  |  |  | 8 | 16 | [42 empty] | 10 |  | 40 |  |  | 3 |  | 30 |  |  | 83
|  |  | Clothing Shop Basic Contents | Design | Game design | [5 empty] | 4 | 6 | 2 | 5 | 5 | 10 | [12 empty] | 3
|  |  | Shop Fake Fascia Design | Design | Game design | [9 empty] | 5 | 10 | [12 empty] | 1
|  | Currency Integration |  | Engineering | Gameplay Engineering | [32 empty] | 2 | 3 | 3 | 5 | 3 | 5 | 2 | 3 |  |  | 2 | 3
|  | P2G Transactions Support |  | Engineering | Backend Engineering | [24 empty] | no idea what is P2G |  | 4 | 7 | 10 | 40
|  | P2G Transactions Support | Trading System QA | QA | QA
|  | Premium currency icon |  | Art | Concept Art
|  | Shop props |  | Art | Environment Art
|  | Shops Concepts |  | Art | Concept Art
|  | Shops Models & Set dressing |  | Art | Environment Art
|  | Soft Currency (gold) icon |  | Art | Concept Art
|  | Trading UX/UI |  | Art | UX/UI | [7 empty] | 15 | 20 | [14 empty] | 15
Vendor backend support
|  | Vendor backend support | Create a list of sold items (redis / server) ??? fetch, create buyback endpoint, update endpoint, pipeline | Engineering | Backend Engineering | [24 empty] | 5 | 14 | 2 | 3 | 3 | 5 | [12 empty] | 5 | 7
|  | Vendor backend support | Create buy endpoint | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 1 | 2 | 2 | 3 | [12 empty] | 2 | 3
|  | Vendor backend support | Create fresh cron job to refresh item stacks for vendors (internal dashboard managment service) | Engineering | Backend Engineering | We can use nodejs's cron internal library | [23 empty] | 5 | 14 | 5 | 1 | 3 | 4 | [12 empty] | 3 | 4
|  | Vendor backend support | Create sell endpoint | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 1 | 2 | 2 | 3 | [12 empty] | 2 | 3
|  | Vendor backend support | Create vendor collection ( internal dashboard managment service) | Engineering | Backend Engineering | expiration time for special items, maxStacks, currentStacks. Do we need to create a new server for buy / sell and all interactions ? | [23 empty] | 5 | 10 | 1 | 2 | 3 | 5 | [12 empty] | 1 | 2
|  | Vendor backend support | Fetch a list of sold items | Engineering | Gameplay Engineering | [30 empty] | 2 | 3 | 1 | 2 | 2 | 4 | 2 | 4 | 2 | 3 |  |  | 2 | 3
|  | Vendor backend support | Fetch vendor collection (internal dashboard managment service) | Engineering | Backend Engineering | [24 empty] | 3 | 10 | 0.5 | 0.5 | 2 | 3 | [12 empty] | 2 | 3
|  | Vendor backend support | Release vendor in game from tempate to release | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 2 | 3 | [12 empty] | 2 | 3
|  | Vendor backend support | Update NPC tool to match vendor in unreal engine | Engineering | Gameplay Engineering | [30 empty] | 4 | 6 | 3 | 5 | 3 | 4 | 2 | 4 | 12 | 15 |  |  | 3 | 4
|  | Vendor backend support | Update UI | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 5 | 7 | 2 | 3 | 2 | 3 |  |  | 1 | 2
|  | Vendor backend support | Update vendor collection ( internal dashboard managment service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 0.5 | 2 | 3 | [12 empty] | 2 | 3
|  | Vendor backend support | Use buy endpoint | Engineering | Gameplay Engineering | [30 empty] | 2 | 3 | 1 | 2 | 1 | 3 | 2 | 4 | 2 | 3 |  |  | 2 | 3
|  | Vendor backend support | Use sell endpoint | Engineering | Gameplay Engineering | [30 empty] | 2 | 3 | 1 | 2 | 1 | 3 | 2 | 4 | 2 | 3 |  |  | 2 | 3
|  | Vendor backend support | delete items and vendor (internal dashboard managment service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 0.5 | 2 | 3 | [12 empty] | 2 | 3
|  | Vendor backend support | fetch last 20 items sold, buyback item, Create buyback functionality | Engineering | Gameplay Engineering | [24 empty] | 5 | 10 |  |  | 1 | 1 | [12 empty] | 3 | 4
|  | Vendors Concepts |  | Art | Concept Art
|  | Vendors Models |  | Art | Character Art
|  | Vendors animation |  | Art | Animation & Rigging | [40 empty] | 3 | 5 | 3 | 5 | with facial animation
Quest System | Main Questline: Critical Path | [55 empty] | 4 | 3 | [5 empty] | 20 |  | 7 | 34
Arena Fight
|  | Arena Fight | Docs, Implement, Revise | Design | Game design | [5 empty] | 7 | 14 | [16 empty] | 7
|  | Cave Intro Quest |  | Design | Game design
|  | Cave Intro Quest | Quest Design Doc | Design | Game design | Finalized QD Document including specs for other departments |  |  |  |  | 3 | 5 | [16 empty] | 4
|  | Cave Intro Quest | Quest Implementation | Design | Game design | Final, "Polished" Version of the Quest |  |  |  |  | 3 | 6 | [16 empty] | 5
|  | Cave Intro Quest | Quest Narrative Doc | Design | Narrative | Narrative/worldbuilding info about the locations, characters and objects involved in the quest |  |  |  |  | 1 | 2 | [10 empty] | 1 | 2 |  |  |  |  | 1
|  | Cave Intro Quest | Quest Playtesting & Revision | Design | Game design | Final Revision & Validation of Quest. Final Doc Revision |  |  |  |  | 2 | 3 | [16 empty] | 2
Complete PG & Last Boss Quest
|  | Complete PG & Last Boss Quest | Docs, Implement, Revise | Design | Game design | [5 empty] | 7 | 14 | [16 empty] | 7
Corruption Tower & Glide Quest
|  | Corruption Tower & Glide Quest | Quest Design Doc | Design | Game design | [5 empty] | 3 | 5 | [16 empty] | 3
|  | Corruption Tower & Glide Quest | Quest Implementation | Design | Game design | [5 empty] | 3 | 6 | [16 empty] | 5
|  | Corruption Tower & Glide Quest | Quest Narrative Doc | Design | Narrative | same as above |  |  |  |  | 1 | 2 | [10 empty] | 1 | 2 |  |  |  |  | 1
|  | Corruption Tower & Glide Quest | Quest Playtesting & Revision | Design | Game design | [5 empty] | 2 | 3 | [16 empty] | 5
Downtime Race Quest
|  | Downtime Race Quest | Docs, Implement, Revise | Design | Game design | [5 empty] | 7 | 14 | [16 empty] | 7
Gear Up & User Space Quest
|  | Gear Up & User Space Quest | Docs, Implement, Revise | Design | Game design | [5 empty] | 7 | 14 | [16 empty] | 7
Green Faction Hill Quest
|  | Green Faction Hill Quest | Quest Design Doc | Design | Game design | [5 empty] | 3 | 5 | [16 empty] | 5
|  | Green Faction Hill Quest | Quest Implementation | Design | Game design | [5 empty] | 4 | 6 | [16 empty] | 6
|  | Green Faction Hill Quest | Quest Narrative Doc | Design | Narrative | same as above |  |  |  |  | 1 | 2 | [10 empty] | 0.5 | 2 |  |  |  |  | 2
|  | Green Faction Hill Quest | Quest Playtesting & Revision | Design | Game design | [5 empty] | 2 | 3 | [16 empty] | 3
Party Up & MP Dungeon Quest
|  | Party Up & MP Dungeon Quest | Docs, Implement, Revise | Design | Game design | [5 empty] | 7 | 14 | [16 empty] | 7
|  | Quest Flow Design & Narrative Overview |  | Design | Game design | [5 empty] | 2 | 4 | [16 empty] | 3
Social Hub & Partnership Quest
|  | Social Hub & Partnership Quest | Docs, Implement, Revise | Design | Game design | [5 empty] | 7 | 14 | [16 empty] | 7
Weapon Upgrade Quest
|  | Weapon Upgrade Quest | Quest Design Doc | Design | Game design | [5 empty] | 3 | 5 | [16 empty] | 3
|  | Weapon Upgrade Quest | Quest Implementation | Design | Game design | [5 empty] | 3 | 6 | [16 empty] | 3
|  | Weapon Upgrade Quest | Quest Narrative Doc | Design | Narrative | same as above |  |  |  |  | 1 | 2 | [10 empty] | 0.5 | 1 |  |  |  |  | 1
|  | Weapon Upgrade Quest | Quest Playtesting & Revision | Design | Game design | [5 empty] | 2 | 3 | [16 empty] | 5
| Quest Integration |  |  | Design | Game design | [51 empty] | 4 | 3 | [5 empty] | 20 |  | 7 | 34
|  | Green Faction NPC Concepts |  | Art | Concept Art
|  | Green Faction NPC Models |  | Art | Character Art
|  | Green Faction NPC animations |  | Art | Animation & Rigging | [40 empty] | 3 | 5 | 3 | 5 | copy animation blueprint. not much info
|  | Green Faction NPC dialogue setup |  | Design | Narrative | [5 empty] | 3 | 6 |  |  | 3 | 8 | 4 | 6 |  |  | 1 | 4 | [6 empty] | 2
|  | Green Faction NPC dialogue setup |  | Design | Game design
|  | Green Faction NPCs placement |  | Design | Game design | [5 empty] | 2 | 5 |  |  | 2 | 5 | 2 | 8 |  |  | 3 | 5 | [6 empty] | 2
|  | Green Faction NPCs placement | QA check | QA | QA
|  | Tutorial Quest Chain Configuration & Setup |  | Design | Game design | Tutorial quest sequence fully designed with player journey and interactions described | The quest should be easily found and tracked throughout the way; should have clear start and end with rewards All needed NPCs, enemies, rewards should be placed and configured | [13 empty] | 7 | 10
|  | Tutorial Quest Chain Configuration & Setup | QA check | QA | QA
| Quest Rewards System |  |  | Design | Game design | [5 empty] | 2 | 5 | [46 empty] | 20 |  |  |  |  | 10 |  |  | 30
|  |  | Quest UI Audio | Audio | Audio | [21 empty] | 0.5 | 1 | 1
|  | Quest Reward List |  | Design | Game design | Reliant on robust inventory system | [8 empty] | 2 | 5 |  |  |  |  | 2 | 3 | [6 empty] | 2
|  | Quest Reward System design doc |  | Design | Game design | [23 empty] | 2
|  | Quest Reward UI |  | Art | UX/UI | [23 empty] | 5
|  | Rewards Choice |  | Engineering | Gameplay Engineering | Quest rewards should include options players can choose from
|  | Rewards Choice | Quest Rewards QA | QA | QA
| Quest Tools |  |  | Engineering | Backend Engineering | [53 empty] | 60 | [7 empty] | 60
|  |  |  | Engineering | Gameplay Engineering
|  | Dialogue System |  | Engineering | Backend Engineering | The game supports dialogue system with options that lead to different dialogue branches
|  | Dialogue System |  | Engineering | Gameplay Engineering | The game supports dialogue system with options that lead to different dialogue branches | [31 empty] | 3 | 5 | 5 | 15 | 1 | 2 | 2 | 3 |  |  | 0 | 0 | Dialog system already exist
|  | Dialogue System Design |  | Design | Game design | [5 empty] | 5 | 8 |  |  | 3 | 8 | [12 empty] | 3
|  | Dialogue UI |  | Art | UX/UI | [23 empty] | 10
|  | Quest Editor |  | Design | Game design | [5 empty] | 5 | 8 |  |  | 10 | 20 |  |  |  |  | 5 | 15 | [6 empty] | 2
|  | Quest Log |  | Engineering | Backend Engineering | The quests are being tracked and the log/next quest should be accessible in the game UI
|  | Quest Log |  | Engineering | Gameplay Engineering | The quests are being tracked and the log/next quest should be accessible in the game UI | [31 empty] | 3 | 5 | 5 | 10 | 1 | 2 | 2 | 3 |  |  | 5 | 10 | quest system is being reworked. UI needs to be remade
|  | Quest Log | Make quest system | [40 empty] | 30 | 45 |  |  | 20 | 20 | big rework for quest system
|  | Quest Log | Quest Log QA | QA | QA
|  | Xyron narrative |  | Design | Game design | [5 empty] | 2 | 5 |  |  | 3 | 8 |  |  |  |  | 3 | 4 | [6 empty] | 2
| Various Quest Types Support |  |  | Engineering | Gameplay Engineering | [51 empty] | 3 | 2 | 30 | [7 empty] | 35
|  | Design interface for quest types |  | Design | Game design | not critical for the vertical slice. |  |  |  |  | 2 | 3 |  |  | no idea | no idea |  |  |  |  | 7 | 9 | [6 empty] | 5
|  | Lockpicking |  | Design | Game design | The minigame to open doors, chests and safes. Player first destroys a set of tiles to reveal the mechanism. Then they interact with the parts of the mechanism to move the marble to the lock and open it | The basic version of the game implemented and functional to open the starting chest The puzzle should be solved within 30 sec | [5 empty] | 8 | 10 | 7 | 15 | 10 | 20 | [10 empty] | 2
|  | Lockpicking | Check if lockpicking solution is correct | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 4 |  |  | 2 | 3 | Syncing every step of the ball reaching target over network
|  | Lockpicking | Create a system to modify ball proaprties while traveling | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 1 | 2 | 1 | 2 | 1 | 3 | 5 | 10 |  |  | 5 | 10 | vfx, audio, velocity
|  | Lockpicking | Create an actor with a grid for all tiles | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 5 | 3 | 5 | 1 | 2 | 2 | 3 |  |  | 1 | 2 | Create a grid
|  | Lockpicking | Create ball entity actor to compelete the game | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 5 | 3 | 5 | 1 | 2 | 2 | 4 |  |  | 2 | 4 | ball move through the cells, check if reached target, check if it reached a cell, check if path is wrong and reverse path
|  | Lockpicking | Create data asset | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 2 | 3 | 3 | 5 | 1 | 2 | 1 | 1 |  |  | 1 | 1
|  | Lockpicking | Create magnatic enitity actor | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 5 | 3 | 5 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Lockpicking | Create pipe entity actor | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 5 | 3 | 5 | 1 | 2 | 1 | 2 |  |  | 1 | 2
|  | Lockpicking | Implement VFX and SFX | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 5 | 2 | 5 | 1 | 5 | 2 | 3 |  |  | 1 | 2
|  | Lockpicking | Lockpicking Concept | Art | Concept Art
|  | Lockpicking | Lockpicking Integration | Engineering | Gameplay Engineering
|  | Lockpicking | Lockpicking QA check | QA | QA
|  | Lockpicking | Lockpicking Techart | Art | TechArt | Co-dev with VFX for breakble tiles, sphere and pipes path | Visually complementary and gameplay rewarding
|  | Lockpicking | Lockpicking UI | Art | UX/UI | [7 empty] | 8 | 15 | [14 empty] | 6
|  | Lockpicking | SFX | Audio | Audio
|  | Lockpicking | Start and end condition | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 1 | 2 | 1 | 2 | 0.5 | 0.5 |  |  | 0.5 | 0.5
|  | Lockpicking | VFX | Art | VFX
|  | Other quest types support? |  | Engineering | Gameplay Engineering | The game supports different quest types: kill X enemies, collect X objects etc | Designers can configure desired quest types in the engine The behavior is in line with documentation
|  | Other quest types support? | Create quest system backend service | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 3 | 5 | 15 | 30 | [12 empty] | 20 | 20 | Quest progression, objective
|  | Other quest types support? | Create quest tool | Engineering | Gameplay Engineering | [30 empty] | 15 | 25 | 20 | 30 | 20 | 40 | 15 | 20 | 10 | 20 |  |  | 20 | 20 | Quest tool needs to be remade for new system
Social & Multiplayer | Chat system | [55 empty] | 12 | 1 | 60 |  |  |  |  | 20 |  |  | 93
|  | Chat UI |  | Art | UX/UI
|  | Chat UI | Auto scroll incomming chat messages | Art | UX/UI
|  | Chat UI | Different colours for different type of message | Art | UX/UI
|  | Chat spam filter |  | Engineering | Backend Engineering
|  | Chat spam filter | Create a system to rate limit messages | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 3 | 5 | [12 empty] | 1 | 2
|  | Chat text limit |  | Engineering | Backend Engineering
|  | Chat text limit | Create a system to limit the amount of text sent | Engineering | Backend Engineering | [24 empty] | 2 | 5 | 1 | 2 | 4 | 8 | [12 empty] | 1 | 2
|  | General systems |  | Engineering | Backend Engineering
|  | General systems | Connect to redis | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 3 | 6 | [12 empty] | 1 | 2
|  | General systems | Create a custom protocol using TCP | Engineering | Backend Engineering | [24 empty] | 5 | 10 |  |  | 5 | 10 | [12 empty] | 3 | 4
|  | General systems | Create a heartbeat system | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 0.5 | 0.5 | 3 | 5 | [12 empty] | 1 | 2
|  | General systems | Create a list of users info such as server ip and usernames | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 1 | 2 | 2 | 4 | [12 empty] | 2 | 3
|  | General systems | Create a multithreaded system | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 5 | 8 | [12 empty] | 3 | 4
|  | General systems | Create a packet system | Engineering | Backend Engineering | [24 empty] | 7 | 10 |  |  | 3 | 5 | [12 empty] | 3 | 4
|  | General systems | Create a serialization/deserialization system | Engineering | Backend Engineering | [24 empty] | 7 | 10 | 1 | 2 | 3 | 8 | [12 empty] | 2 | 3
|  | General systems | Create chat service in go | Engineering | Backend Engineering | [24 empty] | 15 | 25 | 2 | 5 | 12 | 30 | [12 empty] | 1 | 2
|  | General systems | Create pipeline and deploy | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 1 | 2 | 5 | 7 | [12 empty] | 2 | 3
|  | Guild chat |  | Engineering | Backend Engineering
|  | Guild chat | Send a message to your guild | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 2 | 4 | 8 | [12 empty] | 3 | 4
|  | Party chat |  | Engineering | Backend Engineering
|  | Party chat | Send a party message to your party | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 4 | 8 | [12 empty] | 4 | 5
|  | Private message |  | Engineering | Backend Engineering
|  | Private message | Send a private message to user | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 4 | 8 | [12 empty] | 3 | 4
|  | Profanity filter |  | Engineering | Backend Engineering
|  | Profanity filter | Create a system to filter a set of words | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 3 | 6 | [12 empty] | 3 | 5
|  | Proximity chat |  | Engineering | Backend Engineering
|  | Proximity chat | Send chat message only to people near you | Engineering | Backend Engineering | [24 empty] | 7 | 18 | 2 | 3 | 5 | 15 | [12 empty] | 4 | 5
|  | System chat |  | Engineering | Backend Engineering
|  | System chat | Create a system chat which will warn you on if the server is shutting down or if Show invites, kicks, bans in chat | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 10 | 15 | [12 empty] | 4 | 5
|  | Zone channel |  | Engineering | Backend Engineering
|  | Zone channel | Create a way to send a chat to entire zone | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 5 | 10 | [12 empty] | 3 | 4
|  | integraet chat service in unreal using websockets |  | Engineering | Gameplay Engineering
|  | integraet chat service in unreal using websockets | Create a way to receive messages on unreal server and pass that to client | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 3 | 5 | 3 | 5 | 2 | 3 | 3 | 4 |  |  | 3 | 4
|  | integraet chat service in unreal using websockets | Create a way to send a message from unreal server to chat server | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 3 | 5 | 2 | 3 | 2 | 3 |  |  | 3 | 4
|  | integraet chat service in unreal using websockets | Create a websocket connection | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 3 | 2 | 3 |  |  | 3 | 4
| Co-op - Party |  |  | Engineering | Backend Engineering | You and your guide work together to solve a basic water puzzle that opens a door. other 'players' make encouraging remarks. One has real life commitments. Opening the door pitches the team into a battle with new opponents (Carapax). There is loot to share then a portal appears with your name above it. The team says goodbye on chat and the party disbands as you step through. | [47 empty] | 2 |  |  | 5 | 2 | 60 |  |  |  |  | 6 |  |  | 75
|  | Create party puzzle |  | Engineering | Gameplay Engineering
|  | Create party puzzle | Make a puzzle | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 5 | 15 | 3 | 5 | 5 | 6 |  |  | 5 | 5 | figure out puzzle
|  | Create party puzzle | Party QA | QA | QA
|  | Party UI |  | Art | UX/UI | [23 empty] | 2
|  | Party chat |  | Engineering | Gameplay Engineering
|  | Party chat | Party QA | QA | QA
|  | Party formation |  | Engineering | Backend Engineering | [5 empty] | 3 | 6 |  |  | 3 | 8
|  | Party formation | Party chat | Design | Game design
|  | Party formation | Party system design | Design | Game design | [23 empty] | 5
|  | Party supports real players and bots |  | Engineering | Backend Engineering
| Dungeon finder | [57 empty] | 40 | [7 empty] | 40
As a player queue up for dungeon
|  | As a player queue up for dungeon | Add player to dungeon finder list | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 2 | 3 | 5 | [12 empty] | 2 | 3
|  | As a player queue up for dungeon | Connect dungeons to UI | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 4 | 8 | 5 | 10 | 2 | 3 | 4 | 5 |  |  | 5 | 8
|  | As a player queue up for dungeon | Connect to redis | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 3 | 6 | [12 empty] | 1 | 2
|  | As a player queue up for dungeon | Create Dungeon finder UI/UX | Art | UX/UI
|  | As a player queue up for dungeon | Create dungeon finder service | Engineering | Backend Engineering | [24 empty] | 10 | 30 | 1 | 1 | 10 | 20 | [12 empty] | 1 | 2
|  | As a player queue up for dungeon | Create pipeline and deploy | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 5 | 7 | [12 empty] | 2 | 3
|  | As a player queue up for dungeon | Fetch a list of players queued up for dungeon by dungon id | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 1 | 3 | 1 | 3 | [12 empty] | 1 | 2
|  | As a player queue up for dungeon | Get player status in dungeon finder | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 3 | 7 | 1 | 2 | 2 | 3 |  |  | 1 | 2
|  | As a player queue up for dungeon | Invite player to party | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 2 | 4 | [12 empty] | 2 | 3
|  | As a player queue up for dungeon | Queue group for dungeon | Engineering | Backend Engineering | [24 empty] | 7 | 18 | 1 | 3 | 3 | 6 | [12 empty] | 2 | 3
|  | As a player queue up for dungeon | Remove party from queue after party is full | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 1 | 3 | [12 empty] | 1 | 2
|  | As a player queue up for dungeon | Remove party from queue after party is full | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 3 | 5 | 1 | 2 | 2 | 3 |  |  | 2 | 3
|  | As a player queue up for dungeon | Remove player from dungeon queue | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 1 | 3 | [12 empty] | 2 | 3
|  | As a player queue up for dungeon | Send player status in dungeon finder | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 2 | 1 | 3 | [12 empty] | 1 | 2
|  | As a player queue up for dungeon | Send request to add player to dungeon | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 4 | 1 | 2 | 3 | 4 |  |  | 1 | 2
|  | As a player queue up for dungeon | Send request to fetch player from dungeon | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 3 | 5 | 1 | 2 | 3 | 4 |  |  | 1 | 2
|  | As a player queue up for dungeon | Send request to remove player from dungeon | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 3 | 5 | 1 | 2 | 2 | 3 |  |  | 1 | 2
| Guilds (S) |  |  | Design | Game design | The guild house has a grander layout than yours, with numerous blocked portals to other 'player' homes. Some players are watching gameplay on a TV (video loop). One active portal has a player waiting for you to follow him through. | [50 empty] | 20 | 1 | 40 |  |  |  |  | 10 |  |  | 71
|  | Connect Guild UI |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 |  |  |  |  | 2 | 4 |  |  |  |  | 3 | 5
|  | Guild NPCs |  | Art | Character Art
|  | Guild NPCs | Guild house blockout | Design | Level design | [11 empty] | 6 | 10 | 4 | 8 | 10 | 20 | [6 empty] | 10
|  | Guild NPCs | Sitting NPCs | Art | Animation & Rigging
|  | Guild UI |  | Art | UX/UI | [23 empty] | 3
|  | Guild chat |  | Engineering | Gameplay Engineering
|  | Guild chat | Guild Chat design | Design | Game design | [5 empty] | 3 | 5 |  |  | 3 | 8 | [12 empty] | 1
|  | Guild chat | Guild QA | QA | QA
|  | Guild house |  | Engineering | Gameplay Engineering
|  | Guild house | Guild house entry | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 2 | 5 | 2 | 5 | 3 | 4 |  |  | 1 | 2
|  | Guild house | Guild house leave | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 2 | 5 | 2 | 5 | 3 | 4 |  |  | 1 | 2
|  | Guild house | Guild house server | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 2 | 5 | 3 | 7 | 3 | 4 |  |  | 1 | 2
|  | Guild house TV + video |  | Art | Environment Art
|  | Guild house concept |  | Art | Concept Art
|  | Guild house is an instance |  | Engineering | Backend Engineering
|  | Guild house model |  | Art | Environment Art
|  | Guild house props |  | Art | Environment Art
|  | Guilds system design |  | Design | Game design | [23 empty] | 15
| In-game Mail |  |  | Design | Game design | Literally in-game mail. You can receive messages and items from the game |  | S | T2: GDD/TDD/Brief |  | 2 | 4 |  |  | 2 | 5 | [12 empty] | 2 | [25 empty] | 1 |  | 3 | 1 | 20 |  |  |  |  | 10 |  | 2 | 37
|  | Claim currancy and increase ingame gold |  | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 |  |  | 1 | 2
|  | Claim items from mail |  | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 4 | 5 | [12 empty] | 1 | 2
|  | Claim items from mail |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 1 | 2 | 1 | 3 | 2 | 3 |  |  | 1 | 2
|  | Delete mail |  | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 2 | 5 | [12 empty] | 1 | 2
|  | Delete mail |  | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 |  |  | 2 | 3
|  | In-game Mail backend |  | Engineering | Backend Engineering
|  | In-game Mail frontend/UI |  | Engineering | Gameplay Engineering
|  | In-game Mail frontend/UI | Mail QA | QA | QA
|  | In-game Mail frontend/UI | Mail UI Audio | Audio | Audio | [21 empty] | 0.5 | 1 | 1
|  | In-game UI |  | Art | UX/UI | [23 empty] | 10
|  | Mark mail as read |  | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 2 | 5 | [12 empty] | 1 | 2
|  | Mark mail as read |  | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 |  |  | 1 | 2
|  | Postbox Concept |  | Art | Concept Art
|  | Postbox Model |  | Art | Environment Art
|  | Postbox SFX |  | Audio | Audio | [21 empty] | 1 | 2 | 1
|  | Postbox VFX |  | Art | VFX
|  | Restore trash mail |  | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 5 | 7 | [12 empty] | 1 | 2
|  | Restore trash mail |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 3 | 2 | 3 |  |  | 1 | 2
|  | Send mail from one player to another with items |  | Engineering | Backend Engineering | [24 empty] | 7 | 12 | 0.5 | 1 | 5 | 7 | [12 empty] | 1 | 2
|  | Send mail from one player to another with items |  | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 3 | 5 | 5 | 7 | 3 | 5 | 4 | 5 |  |  | 2 | 3
|  | Send mail from one player to another with items | Create mail SFX | Audio | Audio
|  | Send mail from one player to another with items | Create mail UI/UX | Art | UX/UI
|  | Send mail from one player to another with items | Create new mail model | Art | Environment Art
|  | Send mail from one player to another with items | Mail QA | QA | QA
| Leaderboard system | [57 empty] | 40 | [7 empty] | 40
As a player if I play a mini game the leaderboard should update with my score
|  | As a player if I play a mini game the leaderboard should update with my score | Create UI for leaderboard in (internal dashboard) | Engineering | Backend Engineering | [24 empty] | 10 | 10 | 1 | 2 | 2 | 5 | [12 empty] | 2 | 3
|  | As a player if I play a mini game the leaderboard should update with my score | Create a leaderboard in dashboard (internal dashboard) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 2 | 4 | [12 empty] | 2 | 4
|  | As a player if I play a mini game the leaderboard should update with my score | Create leaderboard collection | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 3 | 5 | [12 empty] | 2 | 3
|  | As a player if I play a mini game the leaderboard should update with my score | Delete a leaderboard from dashboard (internal dashboard) | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 1 | 3 | [12 empty] | 1 | 2
|  | As a player if I play a mini game the leaderboard should update with my score | Delete an entry from the leaderboard from dashboard (internal dashboard) | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 1 | 3 | [12 empty] | 1 | 2
|  | As a player if I play a mini game the leaderboard should update with my score | Fetch all leaderboards (internal dashboard) | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 1 | 2 | [12 empty] | 1 | 2
|  | As a player if I play a mini game the leaderboard should update with my score | Fetch leaderboard from (social service) | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 3 | 5 | [12 empty] | 1 | 2
|  | As a player if I play a mini game the leaderboard should update with my score | Fetch leaderboard in unreal | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 3 | 7 | 1 | 2 | 2 | 3 |  |  | 1 | 2
|  | As a player if I play a mini game the leaderboard should update with my score | Update leaderboard from (social service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 3 | 5 | [12 empty] | 2 | 3
|  | As a player if I play a mini game the leaderboard should update with my score | Update leaderboard in unreal | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 |  |  | 1 | 2
| Loot Distribution |  |  | Design | Game design | When the dungeon is completed, the loot is distributed by the predefined rules |  |  |  |  | 2 | 4 | 4 | 6 | 2 | 5 | [40 empty] | 3 |  | 30 |  |  |  |  | 10 | 30 |  | 73
|  | Loot distribution design |  | Design | Game design | [23 empty] | 3
|  | Loot is distributed after the raid |  | Engineering | Gameplay Engineering
|  | Loot is distributed after the raid | Create a new loot table in tool | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 5 | 7 | 2 | 4 | 4 | 5 |  |  | 2 | 3
|  | Loot is distributed after the raid | Create a system for actors to referance loot table | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 3 | 5 | 2 | 4 | 3 | 4 |  |  | 1 | 2
|  | Loot is distributed after the raid | Create loot distribution collection ( internal dashboard managment service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 |  |  | 5 | 7 | [12 empty] | 2 | 3
|  | Loot is distributed after the raid | Create loot distribution system which lets Actors inherit from multiple templates | Engineering | Backend Engineering | [24 empty] | 10 | 20 |  |  | 3 | 6 | [12 empty] | 3 | 4
|  | Loot is distributed after the raid | Delete loot table in CH tool | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 3 | 2 | 4 | 1 | 2 |  |  | 2 | 3
|  | Loot is distributed after the raid | Edit loot table in CH tool | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 4 | 5 |  |  | 2 | 3
|  | Loot is distributed after the raid | Enemies drop item when they are killed | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 3 | 1 | 3 | 3 | 4 |  |  | 1 | 2
|  | Loot is distributed after the raid | Fetch current loot tables in CH tool | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 2 | 4 | 2 | 3 | 2 | 4 | 4 | 5 |  |  | 2 | 3
|  | Loot is distributed after the raid | Fetch loot distribution collection (internal dashboard managment service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 |  |  | 2 | 3 | [12 empty] | 2 | 3
|  | Loot is distributed after the raid | Loot distribution QA | QA | QA
|  | Loot is distributed after the raid | Refreance loot table in enemy/actor in tool | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 3 | 3 | 5 | 2 | 3 | 1 | 2 |  |  | 1 | 2
|  | Loot is distributed after the raid | Release loot table in CH tool | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 2 | 4 | 2 | 3 | 2 | 4 | 1 | 2 |  |  | 2 | 3
|  | Loot is distributed after the raid | Save temp loot table in tool | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 2 | 3 | 2 | 4 | 3 | 4 |  |  | 1 | 2
|  | Loot is distributed after the raid | Update loot distribution collection ( internal dashboard managment service) | Engineering | Backend Engineering | [24 empty] | 5 | 10 |  |  | 2 | 4 | [12 empty] | 2 | 3
|  | Loot is distributed after the raid | distrubute loot according to dungeon rules | Engineering | Gameplay Engineering | [30 empty] | 4 | 6 | 3 | 5 | 2 | 8 | 2 | 3 | 3 | 4 |  |  | 3 | 5 | uknown how it happens
| Party system | [52 empty] | 2 |  |  | 5 | 2 | 60 |  |  |  |  | 6 |  |  | 75
Player can join/invite to party
|  | Player can join/invite to party | Change leadership | Engineering | Backend Engineering | [24 empty] | 4 | 10 | 0.5 | 1 | 1 | 3 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Change leadership | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 3 | 5 | 2 | 3 | 2 | 3 |  |  | 1 | 2
|  | Player can join/invite to party | Connect to redis | Engineering | Backend Engineering | [24 empty] | 4 | 12 | 0.5 | 1 | 3 | 6 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Create a custom protocol using TCP | Engineering | Backend Engineering | [24 empty] | 5 | 10 |  |  | 5 | 10 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Create a heartbeat system | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 0.5 | 0.5 | 3 | 5 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Create a list of users info such as server ip and usernames | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 3 | 2 | 4 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Create a multithreaded system | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 5 | 8 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Create a packet system | Engineering | Backend Engineering | [24 empty] | 5 | 10 |  |  | 3 | 5 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Create a party | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 0.5 | 1 | 3 | 5 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Create a party | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 3 |  |  | 2 | 3
|  | Player can join/invite to party | Create a serialization/deserialization system | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 2 | 3 | 8 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Create party service | Engineering | Backend Engineering | [24 empty] | 7 | 15 | 1 | 1 | 10 | 20 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Create pipeline and deploy | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 1 | 5 | 7 | [12 empty] | 2 | 3
|  | Player can join/invite to party | Disband party | Engineering | Backend Engineering | if yopu are leader give someone else lead | [23 empty] | 4 | 10 | 0.5 | 1 | 1 | 4 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Disband party | Engineering | Gameplay Engineering | if yopu are leader give someone else lead | [29 empty] | 1 | 2 | 1 | 2 | 3 | 5 | 2 | 3 | 2 | 3 |  |  | 2 | 3
|  | Player can join/invite to party | Invite someone to party | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 0.5 | 1 | 2 | 4 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Invite someone to party | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 4 | 2 | 3 | 3 | 4 |  |  | 2 | 3
|  | Player can join/invite to party | Kick someone from party | Engineering | Backend Engineering | [24 empty] | 4 | 10 | 0.5 | 0.5 | 1 | 3 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Kick someone from party | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 4 | 2 | 3 | 1 | 2 |  |  | 2 | 3
|  | Player can join/invite to party | Leave party | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 1 | 3 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Leave party | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 2 | 4 | 2 | 3 | 1 | 2 |  |  | 1 | 2
|  | Player can join/invite to party | Roll check in party | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 3 | 5 | [12 empty] | 1 | 2
|  | Player can join/invite to party | Roll check in party | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 3 | 5 | 2 | 3 | 2 | 3 |  |  | 2 | 3
|  | Player can join/invite to party | Update party player position on map, mana, health | Engineering | Backend Engineering | [24 empty] | 7 | 10 |  |  | 5 | 15 | [12 empty] | 3 | 4
|  | Player can join/invite to party | Update party player position on map, mana, health | Engineering | Gameplay Engineering | [30 empty] | 3 | 5 | 2 | 4 | 5 | 10 | 3 | 4 | 7 | 9 |  |  | 3 | 4
Platform | Bugged Dungeon Integration |  |  | Design | Game design | [9 empty] | 10 | 20 | [37 empty] | 10 |  | 30 | 35 |  | 10 | 15 | [6 empty] | 100
|  | BD Quest design |  | Design | Game design | You find yourself in an alley in the city with NPCs wandering the street beyond. An old shop beckons you to enter. Xyron explains that Downtime is a nexus of many worlds waiting to be rediscovered. You find a portal into the (preloaded game) in the back of the shop. |  |  |  |  | 2 | 5
|  | BD Quest design | BD Quest narrative design | Design | Game design | See lower in the spreadsheet | [8 empty] | 3 | 8
|  | BD Quest integration |  | Engineering | Backend Engineering | [24 empty] | 10 | 25 | 1 | 2 | 15 | 30 | [12 empty] | 5 | 10
|  | BD Quest themed reward model |  | Art | Character Art
|  | BD quest special macguffin reward |  | Design | Game design | Special item you get as a reward for completing BD quest. Will be used in the final part of the quest to activate the final battle
|  | BD quest special macguffin reward | Audio | Audio | Audio | [21 empty] | 0.5 | 1 | 1
|  | BD quest special macguffin reward | Behavior implementation | Engineering | Gameplay Engineering | [30 empty] | 10 | 15 | 5 | 10 | 5 | 15 | 1 | 3 | 2 | 3 |  |  | 3 | 4
|  | BD quest special macguffin reward | Concept | Art | Concept Art
|  | BD quest special macguffin reward | Model | Art | Environment Art
|  | BD quest special macguffin reward | QA | QA | QA
|  | BD quest special macguffin reward | Special item design | Design | Game design | Green Crystal. Or a Bee |  |  |  |  | 1 | 3 |  |  | 2 | 5 | [12 empty] | 1
|  | BD quest special macguffin reward | Tech art | Art | TechArt | Working mechanics for the picked up item, co-dev w/Devs
|  | BD quest special macguffin reward | UI | Art | UX/UI | [23 empty] | 5
|  | BD quest special macguffin reward | VFX | Art | VFX
|  | Partner Shop Blockout |  | Design | Level design | [11 empty] | 4 | 8 | 3 | 7 | 5 | 8 | [6 empty] | 4
|  | Partner themed shop concept |  | Art | Concept Art
|  | Partner themed shop model |  | Art | Environment Art
|  | Partner themed shop props |  | Art | Environment Art
|  | Used Partner Portals |  | Art | Environment Art
|  | Used Partner Portals | Assets & Portals Models | Art | Environment Art
|  | Used Partner Portals | Portals Placement in the shop | Art | Environment Art
| Partner Loop |  |  | Design | Game design |  |  | M | T1: R&D | [46 empty] | 5 |  |  | 20 | [5 empty] | 17 |  | 42
|  | Create Partner Store |  | Engineering | Backend Engineering | Type of the in-game store specifically to buy partner games and assets | [23 empty] | 14 | 25 | 2 | 4 | 10 | 20 | [12 empty] | 10 | 20 | library creation for frontend
|  | Full partner loop definition/design |  | Design | Game design | The sequence that covers the entire interaction loop with the partner game, from engaging with the quest to playing the partner game and getting the rewards |  |  |  |  | 4 | 7 |  |  | 3 | 5 | [12 empty] | 5
|  | Integrate partner loop |  | Engineering | Backend Engineering | [28 empty] | 5 | 15 | [12 empty] | 5 | 10
|  | Integrate partner loop | Buy CH virtual currency | Engineering | Backend Engineering
|  | Integrate partner loop | Buy game subscription time from website and/or from game | Engineering | Backend Engineering
|  | Integrate partner loop | Claim partner item from CH mailbox | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 0.5 | 1 | 2 | 3 | [12 empty] | 2 | 3
|  | Integrate partner loop | Claim partner item from CH mailbox | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 3 | 3 | 5 | 2 | 5 | 2 | 3 |  |  | 2 | 3
|  | Integrate partner loop | Complete partner quest | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 7 | 10
|  | Integrate partner loop | Download Partner game | Engineering | Backend Engineering | [24 empty] | 7 | 12 |  |  | 5 | 8 | [12 empty] | 2 | 3
|  | Integrate partner loop | Purchase partner game from in-game store | Engineering | Backend Engineering
|  | Integrate partner loop | Redeem Partner Steam key | Engineering | Backend Engineering | [24 empty] | 7 | 12 | 0.5 | 1 | 4 | 8 | [12 empty] | 1 | 2
|  | Integrate partner loop | Run partner game from same exe as CH | Engineering | Backend Engineering
|  | Integrate partner loop | Unlock partner item in CH by playing partner game | Engineering | Backend Engineering | [24 empty] | 10 | 20 | 0.5 | 2 | 3 | 5 | [12 empty] | 2 | 3
|  | Partner functionality QA |  | QA | QA
|  | Run partner game from same exe as CH |  | Engineering | Backend Engineering
|  | Run partner game from same exe as CH | Create IPC between exe launcher and unreal and partner game | Engineering | Backend Engineering | [24 empty] | 10 | 30 |  |  | 10 | 20 | [12 empty] | 3 | 4
|  | Run partner game from same exe as CH | Create exe launcher | Engineering | Backend Engineering | [24 empty] | 10 | 30 |  |  | 10 | 20 | [12 empty] | 3 | 4
|  | Run partner game from same exe as CH | Run CH in exe launcher | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 10 | 40 |  |  | 1 | 2 |  |  | 3 | 4
|  | Run partner game from same exe as CH | Run partner game from same exe as CH | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 3 | 5 | 5 | 15 | [6 empty] | 3 | 4
|  | Run partner game from same exe as CH | Run partner in exe launcher | Engineering | Backend Engineering | [24 empty] | 10 | 25 |  |  | 20 | 30 | [12 empty] | 3 | 4
|  | Run partner game from same exe as CH | Transition to lightweight map before launching partner game from exe launcher | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 8 | 20 |  |  | 2 | 3 |  |  | 3 | 4
| Partner Portal |  |  | Design | Game design | The portal that leads to the partner world (activates partner loop sequence) |  |  |  |  | 1 | 2 | [43 empty] | 5 |  |  | 20 | [5 empty] | 17 |  | 42
|  | Partner Portal Enviro Art |  | Art | Environment Art
|  | Partner Portal Integration |  | Engineering | Backend Engineering | [24 empty] | 10 | 25 | 1 | 3 | 15 | 30 | [12 empty] | 10 | 15
|  | Partner Portal Integration |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 4 | 5 | 15 | 1 | 3 | 2 | 3 |  |  | 5 | 10
|  | Partner Portal VFX |  | Art | VFX
|  | Partner shop portal placement |  | Design | Game design | [23 empty] | 1
|  | Portals design |  | Design | Game design | [23 empty] | 1
Live Game | In game RMT Store |  |  | Design | Game design | In-game store that supports real-money transactions (spend real money to buy in-game currency). We are not integrating the payment systems at this point so just having the UI for this type of store will be enough | [52 empty] | 60 | [7 empty] | 60
|  |  | Virtual currency balance and items | Design | Game design | [23 empty] | 2
|  | Basic RMT balance config |  | Design | Game design
|  | Call purchase item endpoint in unreal and sned item to player mailbox when item is purchased |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 2 | 4 | 1 | 2 | 1 | 2 |  |  | 2 | 3
|  | Call purchase virtual currnacy endpoint from Unreal |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 2 | 4 | 1 | 2 | 2 | 3 |  |  | 1 | 2
|  | Connect UI with code |  | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 5 | 10 | 3 | 4 | 4 | 5 |  |  | 3 | 4
|  | Create a purchase virtual currancy endpoint in store service |  | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 0.5 | 3 | 5 | [12 empty] | 1 | 2
|  | Create an endpoint to add items to in-game store in dashboard management service |  | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 2 | 2 | 4 | [12 empty] | 4 | 5 | create service, endpoint, schema, pipeline, interfaces
|  | Create an endpoint to fetch all store items, prices, images, titles from store service |  | Engineering | Backend Engineering | [24 empty] | 4 | 10 | 0.5 | 2 | 3 | 5 | [12 empty] | 1 | 2
|  | Create an endpoint to fetch total owned virtual currancy from store service |  | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 1 | 3 | [12 empty] | 1 | 2
|  | Create an endpoint to pause the purcahsing of an item from in-game store in dashboard managment serivce |  | Engineering | Backend Engineering | This is for items that may be broken so we pause the purcahse of these items temportaltrlrrlrly until it is fixed | [23 empty] | 5 | 14 | 0.5 | 1 | 3 | 5 | [12 empty] | 1 | 2
|  | Create an endpoint to remove items from in-game store in dashboard management service |  | Engineering | Backend Engineering | [24 empty] | 4 | 10 | 0.5 | 0.5 | 1 | 4 | [12 empty] | 1 | 2
|  | Create an endpoint to update items to in-game store in dashboard management service |  | Engineering | Backend Engineering | [24 empty] | 3 | 7 | 0.5 | 0.5 | 2 | 4 | [12 empty] | 2 | 3
|  | Create purcahse item endpoint in store service |  | Engineering | Backend Engineering | [24 empty] | 7 | 18 | 0.5 | 1 | 3 | 6 | [12 empty] | 2 | 3
|  | Display paused banner on paused items with a tooltip explaining why the item is paused |  | Engineering | Gameplay Engineering | [30 empty] | 4 | 8 | ? | ? | 2 | 3 | 1 | 2 | 3 | 4 |  |  | 2 | 3
|  | Fetch total owned virtual currancy |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 1 | 2 | 2 | 4 | 1 | 2 | 0.5 | 1 |  |  | 1 | 2
|  | RMT Store SFX |  | Audio | Audio | [21 empty] | 7 | 10 | 7
|  | RMT Store SFX | RMT Store QA | QA | QA
|  | RMT Store UI |  | Art | UX/UI
|  | RMT store design |  | Design | Game design
|  | RMT store integration |  | Engineering | Backend Engineering
|  | RMT subscription design |  | Art | UX/UI | [7 empty] | 8 | 12 | no idea | no idea | [12 empty] | 3
|  | RMT virtual currency page |  | Art | UX/UI | [23 empty] | 3
|  | RNT partner store |  | Art | UX/UI | [23 empty] | 3
|  | Set a limit on items. example gun only 100 people can buy it. first come first serve |  | Engineering | Backend Engineering | [24 empty] | 5 | 14 | 1 | 3 | 3 | 7 | [12 empty] | 2 | 3
|  | Update in-game store when fetching store items |  | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 2 | 3 | 2 | 4 | 1 | 2 | 4 | 5 |  |  | 2 | 3
| Subscription page on the website |  |  | Engineering | Backend Engineering | [53 empty] | 60 | [7 empty] | 60
|  |  | Change play button from subscribe to play when a subscription is active | Engineering | Gameplay Engineering | [30 empty] | 2 | 4 | 3 | 5 | 1 | 3 | 1 | 2 | 2 | 3 |  |  | 1 | 2
|  |  | Create UI to display web browser inside the game launcher | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 7 | 10 | 5 | 10 | 2 | 4 | 3 | 4 |  |  | 3 | 4
|  |  | Create a subscription page in the store | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 1 | 2 | 1 | 3 | [12 empty] | 3 | 5
|  |  | Create an endpoint to cancel subsciption | Engineering | Backend Engineering | [24 empty] | 5 | 12 | 0.5 | 1 | 1 | 3 | [12 empty] | 1 | 2
|  |  | Create an endpoint to fetch current subscription information from account managment service | Engineering | Backend Engineering | [24 empty] | 5 | 10 | 0.5 | 1 | 1 | 3 | [12 empty] | 2 | 3
|  |  | Create subscription endpoint in store service with tier rewards / different time lengths (30 , 90 , 180 , 360 ) | Engineering | Backend Engineering | [24 empty] | 7 | 18 | 2 | 3 | 3 | 6 | [12 empty] | 2 | 3
|  |  | Fetch subscription information from backend service | Engineering | Gameplay Engineering | [30 empty] | 1 | 2 | 1 | 2 | 3 | 5 | 1 | 2 | 2 | 3 |  |  | 1 | 2
|  |  | New UI/UX for game launcher to support web browser | Art | UX/UI
|  |  | Pass data between in-launcher browswer and launcher | Engineering | Gameplay Engineering | [30 empty] | 5 | 10 | 5 | 10 | 5 | 10 | 2 | 4 | 7 | 8 |  |  | 3 | 4
| Virtual currency balance and items |  |  | Design | Game design
Player Build | Achievements & Trophies | [6 empty] | M | T1: R&D | MIRO BID ONLY (not in VS estimation sheets) | [46 empty] | 7 |  | 35 |  | 5 | 2 |  | 5 | 3 |  | 57
Items & Inventory | Banks | [6 empty] | M | T0: Ideation | MIRO BID ONLY (not in VS estimation sheets) | [44 empty] | 5 |  | 1 |  | 20 |  |  | 1 |  |  |  |  | 27
Player Build | Character Creation & Customization | [6 empty] | L | T1: R&D | MIRO BID ONLY (not in VS estimation sheets) | [46 empty] | 5 |  | 5 |  |  |  | 10 | 20 |  |  | 40
Social & Multiplayer | Co-op/Raids | [8 empty] | NOT FOR VS (MIRO BID ONLY) | [48 empty] | 40 | [7 empty] | 40
Combat | Combat AI behavior | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [40 empty] | 15 |  | 5 |  |  |  | 14 |  | 6 |  |  | 10 | 20 | 6 | 25 |  | 101
Social & Multiplayer | Friends | [6 empty] | M | T1: R&D | NOT FOR VS (MIRO BID ONLY) | [48 empty] | 20 |  |  |  |  | 30 |  |  | 50
Player Economy | Garment Shop | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [44 empty] | 5 |  | 4 |  |  |  | 44 | [5 empty] | 53
Social & Multiplayer | Guild House | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [50 empty] | 22 |  | 4 |  |  |  | 26
Items & Inventory | Inventory System | [6 empty] | M | T2: GDD/TDD/Brief | MIRO BID ONLY (not in VS estimation sheets) | [44 empty] | 10 |  |  |  | 20 |  |  | 2 |  | 30 | 20 |  | 82
Game Bibles | Monetization Bible | [6 empty] | M | T0: Ideation | NOT FOR VS (MIRO BID ONLY) | [46 empty] | 40 | [9 empty] | 40
Social & Multiplayer | Notifications | [6 empty] | S | T1: R&D | NOT FOR VS (MIRO BID ONLY) | [48 empty] | 30 | [7 empty] | 30
Items & Inventory | P2P Item Transfer | [6 empty] | M | T0: Ideation | NOT FOR VS (MIRO BID ONLY) | [48 empty] | 30 | [7 empty] | 30
User Space | P2P/P2G User Space Connection | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [46 empty] | 1 |  | 30 | [7 empty] | 31
Player Economy | Partner Shop | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [44 empty] | 5 |  | 4 |  |  |  | 44 | [5 empty] | 53
Platform | Player Account Authentification | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 15 | [7 empty] | 15
| Player Account Creation/Deletion | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 10 | [7 empty] | 10
| Player Account Privacy Settings & Legal | [6 empty] | M | T1: R&D | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 10 | [7 empty] | 10
Quest System | Quest Item | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [44 empty] | 3 |  | 3 |  |  |  | 3 | 2 | 2 | 4 |  |  | 17
| Quest Multiplayer | [6 empty] | L | T1: R&D | MIRO BID ONLY (not in VS estimation sheets) | [46 empty] | 5 |  | 30 |  |  |  |  | 30 |  |  | 65
Platform | Quest Tracking | [6 empty] | M | T1: R&D | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 20 | [7 empty] | 20
Quest System | Quest dialog GUI | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [43 empty] | 2 |  |  | 4 | [6 empty] | 30 |  | 4 | 40
| Quest log | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 20 |  |  |  |  | 10 |  |  | 30
| Quests as Events | [6 empty] | M | T1: R&D | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 30 |  |  |  |  | 30 |  |  | 60
Game Bibles | Red Books (emergency guidelines for Live Service) | [8 empty] | NOT FOR VS (MIRO BID ONLY) | [48 empty] | 30 | [7 empty] | 30
User Space | Saving House Layouts | [6 empty] | M | T0: Ideation | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 30 | [7 empty] | 30
Platform | Social Media Support | [6 empty] | M | T0: Ideation | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 20 | [7 empty] | 20
Quest System | Targeted VO | [6 empty] | M | T2: GDD/TDD/Brief | MIRO BID ONLY (not in VS estimation sheets) | [43 empty] | 2 | [7 empty] | 10 |  |  |  | 20 | 32
Player Economy | Virtual Currency (VC) System | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [43 empty] | 2 | 2 |  | 10 |  | 20 |  |  |  |  | 30 |  |  | 64
Platform | [Player Dashboard] Friends | [8 empty] | NOT FOR VS (MIRO BID ONLY) | [48 empty] | 30 | [7 empty] | 30
| [Player Dashboard] Game Dashboard | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 30 | [7 empty] | 30
| [Player Dashboard] Marketplace | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 30 | [7 empty] | 30
| [Player Dashboard] Player Account Features | [8 empty] | MIRO BID ONLY (not in VS estimation sheets) | [48 empty] | 30 | [7 empty] | 30
| [Player Dashboard] Search & Notifications | [8 empty] | NOT FOR VS (MIRO BID ONLY) | [48 empty] | 30 | [7 empty] | 30

## Summary
Epic | Features | Concept ~2 months T0 | Pre-production ~4 months T1-T2 | Early Prod ~4 months T3 | Mid Prod ~6 months T4 | End Prod ~4 months T5 | Alpha ~2 months T6 | Beta ~1.5 months T6 | Launch ~1 month T6 | First Release ~1.5 months T6-T7 | LS 1 Live T7 | LS 2 Live T8 | Total PW
Player Build | 11
World Systems | 29
Combat | 9
User Space | 8
Items & Inventory | 9
Player Economy | 7
Quest System | 12
Social & Multiplayer | 10
Game Bibles | 6
Platform | 19
Live Game | 7
Partner Build | 8
Product Publishing | 7
GRAND TOTAL

## Epics & Features
Epic | Feature | Sizing | Current Tier
Player Build | Player Progression | L | T1: R&D
Player Build | Skill System | L | T1: R&D
Player Build | Achievements & Trophies | M | T1: R&D
Player Build | Factions / Reputation | M | T1: R&D
Player Build | FTUE | M | T2: GDD/TDD/Brief
Player Build | Professions | L | T1: R&D
Player Build | Character Management | M | T0: Ideation
Player Build | Character Creation & Customization | L | T1: R&D
Player Build | Garment System | M | T0: Ideation
Player Build | Persona System | M | T1: R&D
Player Build | Emote System | S | T0: Ideation
World Systems | Foam Corruption | M | T2: GDD/TDD/Brief
World Systems | Miasma Corruption | M | T0: Ideation
World Systems | Water Corruption | M | T0: Ideation
World Systems | Crystal Corruption | M | T0: Ideation
World Systems | Time Corruption | M | T0: Ideation
World Systems | Enemy Corruption | M | T0: Ideation
World Systems | Oil Corruption | M | T0: Ideation
World Systems | Texture Corruption | M | T0: Ideation
World Systems | Environmental Elemental Effects (combination states) | L | T2: GDD/TDD/Brief
World Systems | Basic Movement System | L | T1: R&D
World Systems | Advanced Traversal | L | T1: R&D
World Systems | Navigation | M | T0: Ideation
World Systems | Day/Night Cycle | M | T1: R&D
World Systems | Dynamic Weather | M | T1: R&D
World Systems | Instancing | L | T0: Ideation
World Systems | Dungeon Mechanics | L | T0: Ideation
World Systems | The Dungeon | L | T0: Ideation
World Systems | Partner Portal | M | T1: R&D
World Systems | World Bosses | L | T0: Ideation
World Systems | Corruption Heatmap | M | T1: R&D
World Systems | Biome - Portal Peak | M | T4: MVP
World Systems | Biome - Hidden Hills | M | T0: Ideation
World Systems | Biome - Farmlands | M | T0: Ideation
World Systems | Biome - Mistrun Shore | M | T0: Ideation
World Systems | Biome - Whispering Woods | M | T0: Ideation
World Systems | Biome - Tranquil Sands | M | T0: Ideation
World Systems | Biome - Torrential Vale | M | T0: Ideation
World Systems | Biome - Clockwork | M | T0: Ideation
World Systems | Biome - Downtime | M | T4: MVP
Combat | Combat Framework | L | T2: GDD/TDD/Brief
Combat | Ranged Combat | M | T0: Ideation
Combat | Combat AI Behavior | L | T0: Ideation
Combat | Enemies Art | M | T0: Ideation
Combat | PvP Combat | L | T0: Ideation
Combat | Combat Balance & Telemetry | M | T2: GDD/TDD/Brief
Combat | Combat Abilities | L | T1: R&D
Combat | Magic | L | T0: Ideation
Combat | Full Motion Video (FMV) | M | T1: R&D
User Space | User Space Server & Instance | L | T2: GDD/TDD/Brief
User Space | User Space Decoration | M | T0: Ideation
User Space | P2P / P2G User Space Connection | M | T2: GDD/TDD/Brief
User Space | Building Houses | L | T1: R&D
User Space | Saving House Layouts | M | T0: Ideation
User Space | Partner Portal System (player house) | M | T0: Ideation
User Space | Arcade Cabinet | M | T1: R&D
User Space | Anywhere Door Placement | S | T0: Ideation
Items & Inventory | Item Core System | L | T2: GDD/TDD/Brief
Items & Inventory | Inventory System | M | T2: GDD/TDD/Brief
Items & Inventory | Equipment System | M | T0: Ideation
Items & Inventory | Loot Distribution | M | T2: GDD/TDD/Brief
Items & Inventory | Mounts / Pets | L | T1: R&D
Items & Inventory | Banks | M | T0: Ideation
Items & Inventory | P2P Item Transfer | M | T0: Ideation
Items & Inventory | Consumables | S | T2: GDD/TDD/Brief
Items & Inventory | Durable Items | S | T0: Ideation
Player Economy | Trading System | L | T0: Ideation
Player Economy | Currency System | M | T0: Ideation
Player Economy | Auction House | L | T0: Ideation
Player Economy | In-game Store | M | T0: Ideation
Player Economy | In-game Economy | L | T0: Ideation
Player Economy | RMT Game Economy | L | T0: Ideation
Player Economy | IG / RMT Monitoring System | M | T0: Ideation
Quest System | Quests Backend / Tooling | L | T2: GDD/TDD/Brief
Quest System | Quests as Events | M | T1: R&D
Quest System | Quest Multiplayer | L | T1: R&D
Quest System | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | L | T2: GDD/TDD/Brief
Quest System | Quest Reward System | M | T0: Ideation
Quest System | Quest Log | M | T0: Ideation
Quest System | Quest Dialog GUI | M | T0: Ideation
Quest System | Quest Narrative Content | L | T2: GDD/TDD/Brief
Quest System | In Game Cinematic (IGC) | L | T2: GDD/TDD/Brief
Quest System | Meta Quest System | M | T0: Ideation
Quest System | Quest Generator System | L | T0: Ideation
Quest System | Targeted VO | M | T2: GDD/TDD/Brief
Social & Multiplayer | Game Chat System | M | T1: R&D
Social & Multiplayer | Friends | M | T1: R&D
Social & Multiplayer | Guilds | L | T1: R&D
Social & Multiplayer | Co-op / Party | M | T1: R&D
Social & Multiplayer | Co-op / Raids | L | T1: R&D
Social & Multiplayer | Dueling | M | T1: R&D
Social & Multiplayer | In-game Mail | S | T2: GDD/TDD/Brief
Social & Multiplayer | Notifications | S | T1: R&D
Social & Multiplayer | Player Config PvP Server | M | T0: Ideation
Social & Multiplayer | LFG / Pick-up Groups | M | T0: Ideation
Game Bibles | UX/UI Bible | M | T0: Ideation
Game Bibles | Accessibility Guidelines | M | T0: Ideation
Game Bibles | Brand Bible | M | T2: GDD/TDD/Brief
Game Bibles | Art Bible | L | T3: Prototype
Game Bibles | Monetization Bible | M | T0: Ideation
Game Bibles | Red Books (Live Service emergency guidelines) | M | T0: Ideation
Platform | Player Account Creation / Deletion | M | T2: GDD/TDD/Brief
Platform | Player Account Authentication | M | T2: GDD/TDD/Brief
Platform | Player Account Privacy Settings & Legal | M | T1: R&D
Platform | Player Dashboard - Account Features | M | T1: R&D
Platform | Player Dashboard - Game Dashboard | M | T1: R&D
Platform | Player Dashboard - Friends | M | T1: R&D
Platform | Player Dashboard - Search & Notifications | M | T1: R&D
Platform | Player Dashboard - Marketplace | L | T1: R&D
Platform | Developer Dashboard - Developer Account | M | T1: R&D
Platform | Developer Dashboard - Game Dashboard | M | T1: R&D
Platform | Developer Dashboard - Settings & Support | M | T1: R&D
Platform | Quest Tracking | M | T1: R&D
Platform | Payment Processing (incl. Refunds) | L | T0: Ideation
Platform | Online Services & Backend | L | T0: Ideation
Platform | Launcher & Distribution | L | T2: GDD/TDD/Brief
Platform | Partner Loop | M | T1: R&D
Platform | Game Tool Integration (incl. Game Key Generation) | M | T1: R&D
Platform | Account Level Settings | S | T0: Ideation
Platform | Social Media Support | M | T0: Ideation
Live Game | Live GDD | M | T0: Ideation
Live Game | Content | L | T0: Ideation
Live Game | Forecast | M | T0: Ideation
Live Game | Analytics & BI | L | T0: Ideation
Live Game | Sales Dashboard | M | T0: Ideation
Live Game | Telemetry | L | T0: Ideation
Live Game | Live Service Event Plan | L | T0: Ideation
Partner Build | Partner = Feature definition | S | T0: Ideation
Partner Build | Sign Partner | S | T0: Ideation
Partner Build | Partner Brief | M | T0: Ideation
Partner Build | Partner Design Doc | M | T0: Ideation
Partner Build | Partner TDD | M | T0: Ideation
Partner Build | Partner Art Brief | M | T0: Ideation
Partner Build | Partner Build | L | T0: Ideation
Partner Build | Partner Integration | M | T0: Ideation
Product Publishing | Web Presence | M | T0: Ideation
Product Publishing | Website | M | T0: Ideation
Product Publishing | Community Persona | M | T0: Ideation
Product Publishing | Title Identity | M | T0: Ideation
Product Publishing | Player Support | M | T0: Ideation
Product Publishing | Go-To-Market Strategy & Implementation | L | T0: Ideation
Product Publishing | 3rd-party Store Publishing | M | T0: Ideation

## Roles
Role | Discipline | Notes
CEO | Leadership
Creative Director | Leadership
Head of Legal | Leadership
COO | Leadership
HR Manager | Leadership
Executive Producer | Production
Producer | Production
Game Producer | Production
Tech Producer | Production
Art Producer | Production
Game Director | Design
Game Design Lead | Design
Level Design Lead | Design
Game Designer | Design
Combat Designer | Design
Level Designer | Design
Technical Designer | Design
Writer | Design
Art Director | Art
Concept Artist | Art
UI/UX Designer | Art
Graphic Designer | Art
Character Artist | Art
Environment Artist | Art
Prop Artist | Art
Animator | Art
Character Rigger | Art
VFX Artist | Art
Technical Artist | Art
CTO | Engineering
Tech Lead | Engineering
Gameplay Developer | Engineering
Full Stack Developer | Engineering
Backend Developer | Engineering
Network Engineer | Engineering
QA | QA
Sound Designer | Audio
Platform Team | Platform

## Gates
Gate | Phase | Target Tier | Tier Name | Notes
0 | Concept | T0 | Ideation | Y-doc, pitch, vision lock; all features captured at T0
1 | Pre-production | T1-T2 | R&D / GDD-TDD-Brief | GDD/TDD/Art briefs for all greenlit features (T2)
2 | Early Prod | T3 | Prototype | Prototype every feature; many bugs allowed (T3)
3 | Mid Prod | T4 | MVP | Full MVP scope - heaviest production gate (T4)
4 | End Prod | T5 | Feature Complete | Feature complete, polish to ship quality (T5)
5 | Alpha | T6 | Player Tested | Playtest, telemetry, balance pass; gating bugs only
6 | Beta | T6 | Player Tested | External player feedback, cert prep, content lock
7 | Launch | T6 | Player Ready | Day-0 readiness, marketing, store, support
8 | First Release | T6-T7 | Player Ready / Expand | Live monitoring, hotfixes, day-1/7/30 patches
9 | LS 1 | T7 | Expand | Expansions, new content drops, season cadence (T7)
10 | LS 2 | T8 | Scale | Optimize / scale post-load, sustain plan (T8)

## Tiers
Tier | Name | Definition
T0 | Ideation | Idea captured, no commitment
T1 | R&D | Research, prototyping intent, technical feasibility
T2 | GDD / TDD / Brief ready | GDD done, TDD done, art brief done
T3 | Prototype | Functional with no skins, can be bugged
T4 | MVP | Limited quality, but full-featured
T5 | Feature Complete (at quality) | Final assets, polished, no scope cuts left
T6 | Player Ready / Tested | Playtest, alpha, beta, telemetry feedback applied
T7 | Expand | Add to feature / content
T8 | Scale | Productional optimization post-load

## Legend
Cell Color / Section | Meaning
Phase super-headers (row 1 of Plan)
Concept | Concept gate (T0 Ideation)
Pre-production | Pre-production gate (T1-T2)
Production | Early / Mid / End Prod gates (T3-T5)
Release | Alpha / Beta / Launch / First Release
Live Service | LS 1 / LS 2
Discipline | Role group color (row 3 of Plan)
Leadership | CEO, Head of Legal, Head of Finance & Ops, HR Manager
Production | Executive / Producer / Game / Tech / Art Producer
Design | Game Director, Design Leads, Designers, Writer
Art | Art Director, Concept, UI/UX, Character/Env/Prop, Anim, Rig, VFX, TA
Engineering | CTO, Tech Lead, Gameplay/Full Stack/Backend/Network
QA | QA
Audio | Sound Designer
Platform | Platform Team
Sizing key (col C)
S | Small feature
M | Medium feature
L | Large feature
How to use
Plan sheet | Fill in man-days per (feature, gate, role). Cells are blank by default.
Totals row | Bottom of Plan: SUMs each role column per gate.
Headcount row | Total PW / (gate months * 20 working days). Edit GATE_MONTHS in the script if your durations change.
Summary sheet | Auto-rolls up Plan totals per epic per gate.
Adding rows | Insert rows inside an epic block on Plan. Update Total PW SUM ranges if you extend past the current last data row.