## Plan
WORK STREAMS | [6 empty] | CONCEPT | [38 empty] | PRE-PRODUCTION | [38 empty] | PRODUCTION | [154 empty] | RELEASE | [155 empty] | LIVE SERVICE
[7 empty] | GATE 0 | CONCEPT ~2 months Target: T0 Ideation | [37 empty] | GATE 1 | PRE-PRODUCTION Target: T1-T2 R&D / GDD-TDD-Brief | [37 empty] | GATE 2 | EARLY PROD | [75 empty] | GATE 3 | MID PRO Target: T4 MVP | [37 empty] | GATE 4 | END PRO Target: T5 Feature Complete | [37 empty] | GATE 5 | ALPHA Target: T6 Playtest | [37 empty] | GATE 6 | BETA Target: T6 Playtest | [37 empty] | GATE 7 | LAUNCH Target: T6 | [37 empty] | GATE 8 | FIRST RELEASE Target: T6-T7 | [37 empty] | GATE 9 | LS 1 Live T7 | [37 empty] | GATE 10 | LS 2 Live T8
Epic | Feature | Story | Team | Size | Current Tier | Notes |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO |  | Creative Director |  | Head of Legal |  | COO |  | HR Manager |  | Executive Producer |  | Producer |  | Game Producer |  | Tech Producer |  | Art Producer |  | Game Director |  | Game Design Lead |  | Level Design Lead |  | Game Designer |  | Combat Designer |  | Level Designer |  | Technical Designer |  | Writer |  | Art Director |  | Concept Artist |  | UI/UX Designer |  | Graphic Designer |  | Character Artist |  | Environment Artist |  | Prop Artist |  | Animator |  | Character Rigger |  | VFX Artist |  | Technical Artist |  | CTO |  | Tech Lead |  | Gameplay Developer |  | Full Stack Developer |  | Backend Developer |  | Network Engineer |  | QA |  | Sound Designer |  | Platform Team |  |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team
Player Build
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Player Progression |  |  | L | T1: R&D | [107 empty] | 7 | [13 empty] | 3 | [13 empty] | 2 | [7 empty] | 20 | [9 empty] | 2
|  | Player level up documentation | Design ¦ Game design | [108 empty] | 1 | 14
|  | Player level up configuration | Design ¦ Game design | [108 empty] | 0.5 | 15
|  | player level up integration | Engineering ¦ Gameplay Engineering
|  | Player level up UI | Art ¦ UX/UI | [122 empty] | 2 | 3
|  | Character stats documentation | Design ¦ Game design | [108 empty] | 5 | 5
|  | Character stats implementation | Engineering ¦ Gameplay Engineering
|  | Character stats configuration in connection with other systems | Design ¦ Game design | [108 empty] | 1 | 10
|  | Character stats UI | Art ¦ UX/UI | [123 empty] | 15
|  | Level up & Stats QA | QA ¦ QA
|  | Player level up documentation | Design ¦ Game design
|  | Player level up configuration | Design ¦ Game design
|  | player level up integration | Engineering ¦ Gameplay Engineering
|  | Earn different types of EXP depending on objective | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Update player level and exp with (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Fetch player level and exp from (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Fetch and update UI for player level and exp | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Player level up UI | Art ¦ UX/UI
|  | Character stats documentation | Design ¦ Game design
|  | Character stats implementation | Engineering ¦ Gameplay Engineering
|  | Increase stat when player level up | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Update stats UI | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Update player stats in backend (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | fetch player stats from backend service (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Integrate stat system with other systems | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 20
|  | Items give u stats | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Character stats configuration in connection with other systems | Design ¦ Game design
|  | Character stats UI | Art ¦ UX/UI
|  | Level up & Stats QA | QA ¦ QA
| Skill System |  |  | L | T1: R&D | [107 empty] | 20 | [13 empty] | 15 | [13 empty] | 5 | [7 empty] | 35 | [9 empty] | 7
|  | Skill Tree UI Audio | Audio ¦ Audio | [154 empty] | 7 | 8
|  | Skills in-game audio | Audio ¦ Audio | [154 empty] | 7 | 8
|  | Skill System Documentation | Design ¦ Game design | [108 empty] | 4 | 15
|  | Skill System Implementation | Engineering ¦ Gameplay Engineering
|  | Skill System Configuration | Design ¦ Game design | [108 empty] | 4 | 5
|  | Skill System UI | Art ¦ UX/UI
|  | Skill system QA | QA ¦ QA
|  | Skill System Documentation | Design ¦ Game design
|  | Skill System Implementation | Engineering ¦ Gameplay Engineering
|  | Connect skill tree to UI | Engineering ¦ Gameplay Engineering | [144 empty] | 4 | 6
|  | Add new abilities to skill tree | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | Add new weapons to skill tree | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Fetech all skill trees from backend | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Update all skill trees from backend | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Sync all skill trees to backend, tool | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Create weapon skill tree / nodes in (internal dashboard service) | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Remove weapon skill tree / nodes in (internal dashboard service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update weapon skill tree / nodes in (internal dashboard service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Fetch weapon skill tree / nodes in (internal dashboard service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create new collection for weapon skill tree (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Update player skill tree per weapon (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Fetch player skill tree per weapon (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | endpoint to reset skill tree for weapons | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create frontend for skill tree in internal dashboard | Engineering ¦ Backend Engineering | [148 empty] | 5 | 7
|  | Skill System Configuration | Design ¦ Game design
|  | Skill System UI | Art ¦ UX/UI
|  | Skill system QA | QA ¦ QA
| Achievements & Trophies |  |  | M | T1: R&D | [107 empty] | 7 | [13 empty] | 5 | [7 empty] | 5 | [5 empty] | 3 | [7 empty] | 35 | [9 empty] | 2
|  | Trophies | Art ¦ Concept Art
| Factions / Reputation |  |  | M | T1: R&D
| FTUE |  |  | M | T2: GDD/TDD/Brief | [107 empty] | 16 | [11 empty] | 5 |  | 5 |  |  |  |  | 32 | 47 |  |  |  | 5 |  |  |  | 12 |  | 10 | [5 empty] | 15 | [9 empty] | 2
|  | Tutorial Cave Layout Fixes | Design ¦ Level design | [112 empty] | 7 | 10
|  | Tutorial cave set dressing fixes | Art ¦ Environment Art
|  | Tutorial Cave lighting | Art ¦ Environment Art
|  | Tutorial cave Ambience & SFX | Audio ¦ Audio | [154 empty] | 5 | 7
|  | Tutorial Configuration/set up/texts | Design ¦ Game design | [108 empty] | 2 | 3
|  | Tutorial UI | Art ¦ UX/UI | [122 empty] | 4 | 6
|  | Tutorial VFX | Art ¦ VFX
|  | Controls UI | Art ¦ UX/UI | [122 empty] | 2 | 4
|  | Tutorial cave contents | Design ¦ Game design | [108 empty] | 1 | 2
|  | Narrative | Design ¦ Narrative | [116 empty] | 0.5 | 1
|  | Tutorial QA check | QA ¦ QA
|  | Tutorial Cave Layout Fixes | Design ¦ Level design
|  | Tutorial cave set dressing fixes | Art ¦ Environment Art
|  | Tutorial Cave lighting | Art ¦ Environment Art
|  | Tutorial cave Ambience & SFX | Audio ¦ Audio
|  | Tutorial Configuration/set up/texts | Design ¦ Game design
|  | Tutorial UI | Art ¦ UX/UI
|  | Controls UI | Art ¦ VFX
|  | Tutorial QA check | QA ¦ QA
|  | FTUE Cave | Art ¦ Environment Art | [128 empty] | 32 | 32
| Professions |  |  | L | T1: R&D
|  | Component System Design | Design ¦ Game design | [108 empty] | 2 | 5
|  | Crafted Weapon Parts in-game Audio | Audio ¦ Audio | [154 empty] | 5 | 5
|  | Forge Crafting Audio | Audio ¦ Audio | [154 empty] | 3 | 5
|  | Forge Documentation | Design ¦ Game design | [108 empty] | 3 | 5
|  | Forge Concepts | Art ¦ Concept Art
|  | Forge Integration | Engineering ¦ Gameplay Engineering
|  | Forge UI | Art ¦ UX/UI | [122 empty] | 5 | 10
|  | Forge VFX | Art ¦ VFX
|  | DA combination setup | Art ¦ TechArt
|  | Crafting Desk | Art ¦ Environment Art
|  | Forge Props | Art ¦ Character Art
|  | Forge QA | QA ¦ QA
|  | Fishing Integration | Design ¦ Game design | [108 empty] | 3 | 3
|  | Fishing Rod model | Art ¦ Environment Art
|  | Fish model | Art ¦ Environment Art
|  | Fishing spot sign model | Art ¦ Environment Art
|  | Fishing UI | Art ¦ UX/UI | [123 empty] | 3
|  | Fishing Spot SFX | Audio ¦ Audio | [154 empty] | 0 | 0
|  | Fishing VFX | Art ¦ VFX
|  | Fishing QA | QA ¦ QA
|  | Forge Documentation | Design ¦ Game design
|  | Forge Concepts | Art ¦ Concept Art
|  | Forge Integration | Engineering ¦ Gameplay Engineering
|  | Forge UI | Art ¦ UX/UI
|  | Forge VFX | Art ¦ VFX
|  | DA combination setup | Art ¦ TechArt
|  | Crafting Desk | Art ¦ Environment Art
|  | Forge Props | Art ¦ Character Art
|  | Forge QA | QA ¦ QA
|  | Review fishing code | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Fishing Integration | Design ¦ Game design
|  | Fishing Rod model | Art ¦ Environment Art
|  | Fish model | Art ¦ Environment Art
|  | Fishing spot sign model | Art ¦ Environment Art
|  | Fishing UI | Art ¦ UX/UI
|  | Fishing Spot VFX | Audio ¦ Audio
|  | Fishing QA | QA ¦ QA
|  | Gathering | Design ¦ Game design
|  | Crafting | Design ¦ Game design
| Character Management |  |  | M | T0: Ideation
| Character Creation & Customization |  |  | L | T1: R&D | [107 empty] | 5 | [13 empty] | 20 | [15 empty] | 10 | [5 empty] | 5
|  | Faction: Clothing Variations | Art ¦ Character Art
|  | Faction: Banners | Art ¦ Concept Art
|  | Faction: Icons | Art ¦ Concept Art
|  | Faction: Insignias | Art ¦ Concept Art
|  | Base Body (MVP DONE) | Art ¦ Character Art
|  | Base Faces (MVP DONE) | Art ¦ Character Art
|  | Fantasy Races | Art ¦ Character Art
|  | Ethnicity Variations | Art ¦ Character Art
|  | Char Creation System | Art ¦ Character Art
| Garment System |  |  | M | T0: Ideation | [107 empty] | 20 | [13 empty] | 20 | [15 empty] | 10 | [5 empty] | 60
|  | Garment System GDD/TDD | Design ¦ Game design | [108 empty] | 4 | 7
|  | Vertical Slice garments | Design ¦ Game design | [108 empty] | 5 | 5
|  | Garment System Integration | Engineering ¦ Gameplay Engineering
|  | Garment System UI | Art ¦ UX/UI | [122 empty] | 10 | 14
|  | Equipment Concepts | Art ¦ Concept Art
|  | Equipment Models | Art ¦ Character Art
|  | Garment Type SFX | Audio ¦ Audio | [154 empty] | 2 | 3
|  | Equipment Stats integrated with character stats | Engineering ¦ Gameplay Engineering
|  | Garment System QA | QA ¦ QA
|  | Equipment QA | QA ¦ QA
|  | Garment System GDD/TDD | Design ¦ Game design
|  | Garment System Integration | Engineering ¦ Gameplay Engineering
|  | Equip and unequped based on garment system | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Garment System UI | Art ¦ UX/UI
|  | Equiment Concepts | Art ¦ Concept Art
|  | Equipment Models | Art ¦ Character Art
|  | Equipment Stats integrated with character stats | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Cull occluded body parts | Art ¦ TechArt
|  | Setup budget for skining and cloth sim | Art ¦ Animation & Rigging | [132 empty] | 5 | 7
|  | Freeze cloth sim | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Maya tool to represent cloth sim like unreal | Art ¦ Animation & Rigging | [132 empty] | 10 | 15
|  | Move socket based on clothing type | Art ¦ Animation & Rigging | [132 empty] | 5 | 10
|  | Setup capsules for cloth collision on character | Art ¦ Animation & Rigging | [132 empty] | 1 | 2
|  | Garment System QA | QA ¦ QA
|  | Equipment QA | QA ¦ QA
|  | Garment System Options | Art ¦ Character Art
|  | Garment Sets | Art ¦ Character Art
|  | Weapon Sets | Art ¦ Character Art
|  | Weapon Parts | Art ¦ Character Art
|  | Armour Sets | Art ¦ Character Art
|  | Partner Skins | Art ¦ Character Art
|  | Skins | Art ¦ Character Art
| Persona System |  |  | M | T1: R&D
| Emote System |  |  | S | T0: Ideation
World Systems
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Foam Corruption |  |  | M | T2: GDD/TDD/Brief
|  | Corrupted Vines | Design ¦ Game design | [108 empty] | 0.5 | 1
|  | Corrupted texture | Art ¦ TechArt
|  | Vine NPC Narrative | Design ¦ Narrative | [117 empty] | 1
|  | Vines Foliage | Art ¦ Environment Art
|  | Corrupted VFX | Art ¦ VFX
|  | Corrupted vines behavior & visual QA | QA ¦ QA
|  | Foam Corruption | Design ¦ Game design
|  | Foam Corruption Techart | Art ¦ TechArt
|  | Foam Corruption integration | Engineering ¦ Gameplay Engineering
|  | Foam Corruption VFX | Art ¦ VFX
|  | Foam Corruption cleansing animations | Art ¦ Animation & Rigging
|  | Foam Corruption cleansing weapon | Art ¦ Character Art
|  | Foam Corruption SFX, VFX design | Design ¦ Game design | [108 empty] | 3 | 3
|  | Foam Corruption SFX | Audio ¦ Audio | [154 empty] | 2 | 2
|  | Foam Corruption QA | QA ¦ QA
|  | Timed Corruption | Design ¦ Game design | [108 empty] | 10 | 40
|  | Timed Corruption Design | Design ¦ Game design | [108 empty] | 2 | 10
|  | Timed Corruption TechArt | Art ¦ TechArt
|  | Timed Corruption Integration | Engineering ¦ Gameplay Engineering
|  | Timed Corruption Server & Multiplayer | Engineering ¦ Backend Engineering
|  | Timed Corruption 3D Assets | Art ¦ Environment Art
|  | Timed Corruption VFX | Art ¦ VFX
|  | Timed Corruption SFX | Audio ¦ Audio | [154 empty] | 3 | 5
|  | Timed Corruption QA | QA ¦ QA
|  | Corrupted Vines | Design ¦ Game design
|  | Corrupted texture | Art ¦ TechArt
|  | Vines Foliage | Art ¦ Environment Art
|  | Corrupted VFX | Art ¦ VFX
|  | Corrupted vines behavior & visual QA | QA ¦ QA
|  | Foam Corruption | Design ¦ Game design
|  | Foam Corruption Techart | Art ¦ TechArt
|  | Foam Corruption integration | Engineering ¦ Gameplay Engineering | [144 empty] | 4 | 5
|  | Foam Corruption VFX | Art ¦ VFX
|  | Foam Corruption cleansing animations | Art ¦ Animation & Rigging | [132 empty] | 2 | 3
|  | Trigger objective when clean is done | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Quest tracking system | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Make corruption come back after a set time | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Link with corruption gun | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | Foam Corruption cleansing weapon | Art ¦ Character Art
|  | Foam Corruption SFX | Audio ¦ Audio
|  | Foam Corruption QA | QA ¦ QA
|  | Timed Corruption | Design ¦ Game design
|  | Timed Corruption Design | Design ¦ Game design
|  | Timed Corruption TechArt | Art ¦ TechArt
|  | Replicate animation | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Trigger building the bridge | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Trigger VFX when effect is completed | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Timer to revert bridge to broken state | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Toggle path once puzzle is completed to allow or disallow player from crossing the bridge by replicating collision | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | Timed Corruption 3D Assets | Art ¦ Environment Art
|  | Timed Corruption VFX | Art ¦ VFX
|  | Timed Corruption SFX | Audio ¦ Audio
|  | Timed Corruption QA | QA ¦ QA
|  | VFX Tech | Art ¦ VFX
|  | Fluid Ninja Tech R&D | Art ¦ TechArt
| Miasma Corruption |  |  | M | T0: Ideation
| Water Corruption |  |  | M | T0: Ideation
| Crystal Corruption |  |  | M | T0: Ideation
| Time Corruption |  |  | M | T0: Ideation
| Enemy Corruption |  |  | M | T0: Ideation
| Oil Corruption |  |  | M | T0: Ideation
| Texture Corruption |  |  | M | T0: Ideation
| Environmental Elemental Effects (combination states) |  |  | L | T2: GDD/TDD/Brief
| Basic Movement System |  |  | L | T1: R&D
|  | Locomotion Integration | Engineering ¦ Gameplay Engineering
|  | Walk | Engineering ¦ Gameplay Engineering
|  | Run | Engineering ¦ Gameplay Engineering
|  | Sprint | Engineering ¦ Gameplay Engineering
|  | Jump | Engineering ¦ Gameplay Engineering
|  | Double Jump | Engineering ¦ Gameplay Engineering
|  | Iteration | Design ¦ Game design | [109 empty] | 5
|  | Locomotion QA check | QA ¦ QA
|  | Locomotion Integration | Engineering ¦ Gameplay Engineering
|  | Walk | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Run | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Sprint | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Jump | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Double Jump | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Locomotion QA check | QA ¦ QA
| Advanced Traversal |  |  | L | T1: R&D
|  | Glider Stamina UI | Art ¦ UX/UI | [122 empty] | 2 | 2
|  | Gliding Concepts | Art ¦ Concept Art
|  | Gliding Integration | Engineering ¦ Gameplay Engineering
|  | Gliding Animations | Art ¦ Animation & Rigging
|  | Gliding SFX | Audio ¦ Audio | [154 empty] | 1 | 2
|  | Gliding VFX | Art ¦ VFX
|  | Gliding Device | Art ¦ Character Art
|  | Gliding QA | QA ¦ QA
|  | Portals spawning & Xyron moving through portals | Engineering ¦ Gameplay Engineering
|  | Narrative for Xyron quests | Design ¦ Narrative | [116 empty] | 1 | 2
|  | Spawning portals SFX | Audio ¦ Audio | [154 empty] | 2 | 4
|  | 5 or 6 mini quests | Design ¦ Game design | [108 empty] | 5 | 8
|  | Xyron voiceover narrative | Design ¦ Narrative | [116 empty] | 0.5 | 2
|  | Xyron voiceover | Audio ¦ Audio | [154 empty] | 7 | 8
|  | Xyron/portals spawning QA | QA ¦ QA
|  | Safety System | Design ¦ Game design | [108 empty] | 3 | 3
|  | Archway race design | Design ¦ Game design | [109 empty] | 3
|  | Persistent leaderboards | Engineering ¦ Backend Engineering
|  | Archway Placement | Design ¦ Game design | [108 empty] | 1 | 7
|  | Archway Models | Art ¦ Environment Art
|  | Archway VFX | Art ¦ VFX
|  | Win Fanfare VFX | Art ¦ VFX
|  | Archway SFX | Audio ¦ Audio | [154 empty] | 0 | 0
|  | Archway QA | QA ¦ QA
|  | Gliding Concepts | Art ¦ Concept Art
|  | Convert gliding to blend space | Art ¦ Animation & Rigging | [132 empty] | 1 | 1
|  | Spawn gliding actor | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Check if ability is unlock to glide | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | Gliding Animations | Art ¦ Animation & Rigging | [132 empty] | 1 | 1
|  | Gliding VFX | Art ¦ VFX
|  | Gliding Device | Art ¦ Character Art
|  | Gliding QA | QA ¦ QA
|  | Portals spawning & Xyron moving through portals | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | Xyron/portals spawning QA | QA ¦ QA
|  | Persistent leaderboards | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Archway Placement | Design ¦ Game design
|  | Archway Models | Art ¦ Environment Art
|  | Archway VFX | Art ¦ VFX
|  | Win Fanfare VFX | Art ¦ VFX
|  | Archway SFX | Audio ¦ Audio
|  | Archway QA | QA ¦ QA
|  | Gliding System | Art ¦ Animation & Rigging
|  | Grappling System | Art ¦ Animation & Rigging
| Navigation |  |  | M | T0: Ideation
|  | World Map | Design ¦ Game design | [108 empty] | 10 | 10
|  | Map markers sfx | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | World Map background asset | Art ¦ Concept Art
|  | World Map asset integration | Engineering ¦ Gameplay Engineering
|  | World Map UI | Art ¦ UX/UI | [123 empty] | 10
|  | Quest markers support | Engineering ¦ Gameplay Engineering
|  | Map QA check | QA ¦ QA
|  | Fog-of-war | Engineering ¦ Gameplay Engineering
|  | Fog of war QA check | QA ¦ QA
|  | Minimap | Engineering ¦ Gameplay Engineering
|  | Minimap Levels | Design ¦ Game design | [108 empty] | 5 | 5
|  | Minimap UI | Art ¦ UX/UI | [123 empty] | 10
|  | Minimap assets | Art ¦ Concept Art
|  | Minimap quest navigation support | Engineering ¦ Gameplay Engineering
|  | Minimap QA check | QA ¦ QA
|  | Compass | Engineering ¦ Gameplay Engineering
|  | Compass UI | Art ¦ UX/UI | [122 empty] | 2 | 10
|  | Compass Integration | Engineering ¦ Gameplay Engineering
|  | Compass QA check | QA ¦ QA
|  | World Map | Design ¦ Game design
|  | World Map background asset | Art ¦ Concept Art
|  | World Map asset integration | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | World Map UI | Art ¦ UX/UI
|  | Indoor Map | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 7
|  | Special NPCs positions | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Zoom out/in | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Party player position | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | POI names | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | Quest markers and objectives support | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Map QA check | QA ¦ QA
|  | Fog-of-war | Engineering ¦ Gameplay Engineering
|  | Fog of war shader | Art ¦ TechArt
|  | Create fog of war grid | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Hide/Unhide markers that are in fog of war | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Fog of war changes based on player visited locations | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | fetch fog of war and update it from unreal side | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Sync fog of war to backend | Engineering ¦ Backend Engineering | [148 empty] | 5 | 5
|  | Fog of war QA check | QA ¦ QA
|  | Minimap | Engineering ¦ Gameplay Engineering
|  | Minimap UI | Art ¦ UX/UI
|  | Minimap assets | Art ¦ Concept Art
|  | Minimap quest navigation support | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Special NPCs positions | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Zoom out/in | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | Party player position | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Minimap QA check | QA ¦ QA
|  | Compass | Engineering ¦ Gameplay Engineering
|  | Compass UI | Art ¦ UX/UI
|  | Show distance to objective | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Party player distance | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show POI distance | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Special NPCs distance | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show quest distance | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show or hide compass from options menu | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Rotate compass with camera | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Compass QA check | QA ¦ QA
|  | Lighting Tech | Art ¦ Environment Art
|  | Atmospherics | Art ¦ Environment Art
|  | Water System | Art ¦ Environment Art
| Day/Night Cycle |  |  | M | T1: R&D | [107 empty] | 10 | [13 empty] | 3 | [7 empty] | 11 |  | 15
| Dynamic Weather |  |  | M | T1: R&D | [107 empty] | 17 | [13 empty] | 20 | [7 empty] | 10 | [5 empty] | 5 |  | 90 | [5 empty] | 60
| Instancing |  |  | L | T0: Ideation | [107 empty] | 5 | [29 empty] | 10 | [5 empty] | 120
|  | GDD Documentation | Design ¦ Game design | [108 empty] | 3 | 2
|  | Instancing Documentation | Engineering ¦ Backend Engineering
|  | User Space Instancing support | Engineering ¦ Backend Engineering
|  | Guild House instancing support | Engineering ¦ Backend Engineering
|  | Dungeon Instancing | Engineering ¦ Backend Engineering
|  | Zones Instancing | Engineering ¦ Backend Engineering
|  | Instancing QA | QA ¦ QA
|  | Research phasing system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 5
|  | Research phasing system | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Document phasing system | Engineering ¦ Backend Engineering | [148 empty] | 2 | 5
|  | Document phasing system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 7
|  | Create phasing system | Engineering ¦ Gameplay Engineering | [144 empty] | 7 | 20
|  | Create phasing system | Engineering ¦ Backend Engineering | [148 empty] | 3 | 50
|  | Manage player session | Engineering ¦ Backend Engineering
|  | Record if player is online in redis | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create a session service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Instancing Documentation | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Custom HPA for Kubernetes | Engineering ¦ Backend Engineering
|  | Create Nodejs service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Integrate Kubernetes API | Engineering ¦ Backend Engineering | [148 empty] | 3 | 5
|  | Create metrics to scale up and down | Engineering ¦ Backend Engineering | [148 empty] | 4 | 6
|  | Create rules when to merge instances | Engineering ¦ Backend Engineering | [148 empty] | 4 | 6
|  | Setup Kubernetes on Azure | Engineering ¦ Backend Engineering
|  | Setup azure | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Custom service to handle dungeons | Engineering ¦ Backend Engineering
|  | Create a service in nodejs | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a list of all dungeons that are currently running in redis | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Search for dungeon by id | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch dungeon ip by id | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Delete dungeon instance | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create dungeon instance | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Call backend to figure out which dungeon to connect to | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Player general stat before disconnecting service | Engineering ¦ Backend Engineering
|  | Create a service in nodejs | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a way to save player stat (which server they were connected to last, which party were they connected to, etc..) before disconnecting | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Custom service for overworld zones | Engineering ¦ Backend Engineering
|  | Create a service in nodejs | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a list of all overworld zones that are currently running in redis | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Search for overworld zones by id | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch overworld zones ip by id | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Delete overworld zones instance | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create overworld zones instance | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Call backend to figure out which overworld zones to connect to | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Inform UE server that a player is getting migrated to another UE server | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Inform UE server that a player is getting migrated to another UE server | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create a queue service | Engineering ¦ Backend Engineering
|  | Create Nodejs service | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Instancing QA | QA ¦ QA
| Dungeon Mechanics |  |  | L | T0: Ideation | [126 empty] | 11.4 | 17.1 | [15 empty] | 20
|  | Dungeons documentation | Design ¦ Game design | [108 empty] | 2 | 5
|  | Narrative | Design ¦ Narrative | [116 empty] | 0.5 | 1
|  | Multiplayer enviromental puzzle design | Design ¦ Game design | [108 empty] | 5 | 12
|  | Multiplayer enviromental puzzle layout | Design ¦ Level design | [112 empty] | 4 | 10
|  | Multiplayer enviromental puzzle integration | Engineering ¦ Gameplay Engineering
|  | Puzzles QA | QA ¦ QA
|  | BD Quest design | Design ¦ Game design | [108 empty] | 2 | 5
|  | BD Quest narrative design | Design ¦ Game design | [108 empty] | 3 | 8
|  | Partner Shop Blockout | Design ¦ Level design | [112 empty] | 3 | 4
|  | BD Quest integration | Engineering ¦ Backend Engineering
|  | Partner themed shop concept | Art ¦ Concept Art
|  | Partner themed shop model | Art ¦ Environment Art
|  | Partner themed shop props | Art ¦ Environment Art
|  | Used Partner Portals | Art ¦ Environment Art
|  | Assets & Portals Models | Art ¦ Environment Art
|  | Portals Placement in the shop | Art ¦ Environment Art
|  | BD Quest themed reward model | Art ¦ Character Art
|  | BD quest special macguffin reward | Design ¦ Game design
|  | Special item design | Design ¦ Game design | [108 empty] | 1 | 1
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Environment Art
|  | Tech art | Art ¦ TechArt
|  | Behavior implementation | Engineering ¦ Gameplay Engineering
|  | Audio | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | UI | Art ¦ UX/UI | [123 empty] | 5
|  | VFX | Art ¦ VFX
|  | QA | QA ¦ QA
|  | Dungeons documentation | Design ¦ Game design
|  | Join dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Dungeon UI | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Transition to dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Dungeon gameplay loop | Engineering ¦ Gameplay Engineering | [144 empty] | 10 | 20
|  | Dungeon character | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Dungeon end reward and condition | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | dungeon character respawn | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | dungeon transition to out of dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Multiplayer enviromental puzzle design | Design ¦ Game design
|  | Multiplayer enviromental puzzle layout | Design ¦ Level design
|  | Multiplayer enviromental puzzle integration | Engineering ¦ Gameplay Engineering
|  | Make puzzle | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Puzzles QA | QA ¦ QA
|  | BD Quest design | Design ¦ Game design
|  | BD Quest integration | Engineering ¦ Backend Engineering | [148 empty] | 5 | 10
|  | Partner themed shop concept | Art ¦ Concept Art
|  | Partner themed shop model | Art ¦ Environment Art
|  | Partner themed shop props | Art ¦ Environment Art
|  | Used Partner Portals | Art ¦ Environment Art
|  | Assets & Portals Models | Art ¦ Environment Art
|  | Portals Placement in the shop | Art ¦ Environment Art
|  | BD Quest themed reward model | Art ¦ Character Art
|  | BD quest special macguffin reward | Design ¦ Game design
|  | Special item design | Design ¦ Game design
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Environment Art
|  | Tech art | Art ¦ TechArt
|  | Behavior implementation | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Audio | Audio ¦ Audio
|  | UI | Art ¦ UX/UI
|  | VFX | Art ¦ VFX
|  | QA | QA ¦ QA
|  | Bug Dungeon | Art ¦ Environment Art | [128 empty] | 11.4 | 17.1
|  | Bugged Dungeon Shop | Art ¦ Environment Art
| The Dungeon |  |  | L | T0: Ideation | [107 empty] | 35 |  | 10 |  | 15 | [14 empty] | 68.6 | 98.6 | [15 empty] | 10
|  | Dungeon (1 medium) | Art ¦ Environment Art | [128 empty] | 68.6 | 68.6
| Partner Portal |  |  | M | T1: R&D | [127 empty] | 5 | [7 empty] | 17 | [7 empty] | 20
|  | Partner shop portal placement | Design ¦ Game design | [109 empty] | 1
|  | Portals design | Design ¦ Game design | [109 empty] | 1
|  | Partner Portal Integration | Engineering ¦ Backend Engineering
|  | Partner Portal VFX | Art ¦ VFX
|  | Partner Portal Enviro Art | Art ¦ Environment Art
|  | Partner Portal Integration | Engineering ¦ Backend Engineering | [148 empty] | 10 | 15
|  | Partner Portal Integration | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Partner Portal VFX | Art ¦ VFX
|  | Partner Portal Enviro Art | Art ¦ Environment Art
| World Bosses |  |  | L | T0: Ideation
| Corruption Heatmap |  |  | M | T1: R&D
| Biome - Portal Peak |  |  | M | T4: MVP | [126 empty] | 384.7 | 501.6 | 57.2 | 114.2
|  | PP Design | Design ¦ Game design | [108 empty] | 3 | 5
|  | PP Blockout | Design ¦ Level design | [112 empty] | 10 | 20
|  | PP Concept | Art ¦ Concept Art
|  | PP Foliage | Art ¦ Environment Art
|  | PP Props Build | Art ¦ Environment Art
|  | PP layout | Art ¦ Environment Art
|  | PP Audio | Audio ¦ Audio | [154 empty] | 14 | 15
|  | Portal Peak QA | QA ¦ QA
|  | Portal Dimension Design | Design ¦ Game design | [108 empty] | 1 | 1
|  | Portal Dimension Blockout | Design ¦ Level design | [112 empty] | 1 | 15
|  | Portal Dimension Concept | Art ¦ Concept Art
|  | Portal Dimension Foliage | Art ¦ Environment Art
|  | Portal Dimension Props Build | Art ¦ Environment Art
|  | Portal Dimension layout | Art ¦ Environment Art
|  | Portal Dimension Audio | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | Portal Dimension QA | QA ¦ QA
|  | Final Tower Design | Design ¦ Game design | [108 empty] | 1 | 1
|  | Final Tower Blockout | Design ¦ Level design | [112 empty] | 1 | 5
|  | Final Tower Concept | Art ¦ Concept Art
|  | Final Tower Foliage | Art ¦ Environment Art
|  | Final Tower Props Build | Art ¦ Environment Art
|  | Final Tower layout | Art ¦ Environment Art
|  | Final Tower Audio | Audio ¦ Audio | [154 empty] | 3 | 2
|  | Portal Dimension QA | QA ¦ QA
|  | PP Design | Design ¦ Game design
|  | PP Blockout | Design ¦ Level design
|  | PP Concept | Art ¦ Concept Art
|  | PP Foliage | Art ¦ Environment Art
|  | PP Props Build | Art ¦ Environment Art
|  | PP layout | Art ¦ Environment Art
|  | PP Audio | Audio ¦ Audio
|  | Portal Peak QA | QA ¦ QA
|  | Portal Dimension Design | Design ¦ Game design
|  | Portal Dimension Blockout | Design ¦ Level design
|  | Portal Dimension Concept | Art ¦ Concept Art
|  | Portal Dimension Foliage | Art ¦ Environment Art
|  | Portal Dimension Props Build | Art ¦ Environment Art
|  | Portal Dimension layout | Art ¦ Environment Art
|  | Portal Dimension Audio | Audio ¦ Audio
|  | Portal Dimension QA | QA ¦ QA
|  | Architecture Kit - Mythcore | Art ¦ Environment Art | [128 empty] | 5.7 | 11.4
|  | Architecture Kit - Mythcore Ruins | Art ¦ Environment Art | [128 empty] | 5.7 | 11.4
|  | Architecture Kit - Fantasy | Art ¦ Environment Art | [128 empty] | 68.6 | 114.3
|  | Architecture Kit - Deck/Scaffolding | Art ¦ Environment Art | [128 empty] | 11.4 | 17.1
|  | Architecture Kit - Wooden Camp | Art ¦ Environment Art | [128 empty] | 17.1 | 22.9
|  | Portal Dimension | Art ¦ Environment Art | [128 empty] | 28.6 | 28.6
|  | Tower Interior | Art ¦ Environment Art | [128 empty] | 45.7 | 60
|  | Rock Kits | Art ¦ Environment Art | [128 empty] | 27.4 | 27.4
|  | Props - Gritcore | Art ¦ Environment Art | [128 empty] | 28.6 | 57.1
|  | Props - Fantasy Exterior | Art ¦ Environment Art | [128 empty] | 28.6 | 57.1
|  | Biomes - Cave | Art ¦ Environment Art | [128 empty] | 50 | 57.1
|  | Tower Exterior (Epic POI) | Art ¦ Environment Art | [128 empty] | 81.1 | 91.4
|  | Cave Interior (Med POI) | Art ¦ Environment Art | [128 empty] | 32 | 42.9
|  | Bridge (Small POI) | Art ¦ Environment Art | [128 empty] | 11.4 | 17.1
|  | Mediterranean Biome | Art ¦ Environment Art
| Biome - Hidden Hills |  |  | M | T0: Ideation | [126 empty] | 81.1 | 91.4
|  | The Two Hills Design | Design ¦ Game design | [108 empty] | 4 | 5
|  | The Two Hills Blockout | Design ¦ Level design | [112 empty] | 3 | 15
|  | The Two Hills Concept | Art ¦ Concept Art
|  | The Two Hills Foliage | Art ¦ Environment Art
|  | The Two Hills Props Build | Art ¦ Environment Art
|  | The Two Hills layout | Art ¦ Environment Art
|  | The Two Hills Audio | Audio ¦ Audio | [154 empty] | 4 | 4
|  | The Two Hills QA | QA ¦ QA
|  | The Two Hills Design | Design ¦ Game design
|  | The Two Hills Blockout | Design ¦ Level design
|  | The Two Hills Concept | Art ¦ Concept Art
|  | The Two Hills Foliage | Art ¦ Environment Art
|  | The Two Hills Props Build | Art ¦ Environment Art
|  | The Two Hills layout | Art ¦ Environment Art
|  | The Two Hills Audio | Audio ¦ Audio
|  | The Two Hills QA | QA ¦ QA
|  | The Big Battle Hill (Epic POI) | Art ¦ Environment Art | [128 empty] | 81.1 | 91.4
| Biome - Farmlands |  |  | M | T0: Ideation | [126 empty] | 176.8 | 195.4
|  | New Zone | Art ¦ Environment Art | [128 empty] | 81.1 | 92.6
|  | Biomes - New Zone | Art ¦ Environment Art | [128 empty] | 50 | 57.1
|  | Drifter's Cross (Small POI) | Art ¦ Environment Art | [128 empty] | 45.7 | 45.7
|  | Lush Biome | Art ¦ Environment Art
| Biome - Mistrun Shore |  |  | M | T0: Ideation
| Biome - Whispering Woods |  |  | M | T0: Ideation | [126 empty] | 11.4 | 17.1
|  | Waterfall Beauty Spot Concept | Art ¦ Concept Art
|  | Waterfall Beauty Spot Design | Design ¦ Game design | [108 empty] | 2 | 2
|  | Waterfall Beauty Spot Blockout | Design ¦ Level design | [112 empty] | 1 | 4
|  | Waterfall Beauty Spot Foliage | Art ¦ Environment Art
|  | Waterfall Beauty Spot Props Build | Art ¦ Environment Art
|  | Waterfall Beauty Spot layout | Art ¦ Environment Art
|  | Waterfall Beauty Spot Audio | Audio ¦ Audio | [154 empty] | 4 | 3
|  | Waterfall Spot QA | QA ¦ QA
|  | Waterfall Beauty Spot Design | Design ¦ Game design
|  | Waterfall Beauty Spot Blockout | Design ¦ Level design
|  | Waterfall Beauty Spot Concept | Art ¦ Concept Art
|  | Waterfall Beauty Spot Foliage | Art ¦ Environment Art
|  | Waterfall Beauty Spot Props Build | Art ¦ Environment Art
|  | Waterfall Beauty Spot layout | Art ¦ Environment Art
|  | Waterfall Beauty Spot Audio | Audio ¦ Audio
|  | Waterfall Spot QA | QA ¦ QA
|  | Waterfall Beauty (Small POI) | Art ¦ Environment Art | [128 empty] | 11.4 | 17.1
| Biome - Tranquil Sands |  |  | M | T0: Ideation
| Biome - Torrential Vale |  |  | M | T0: Ideation
| Biome - Clockwork |  |  | M | T0: Ideation
| Biome - Downtime |  |  | M | T4: MVP | [126 empty] | 142.6 | 171.4
|  | Multiplayer interactions (toasts) | Design ¦ Game design | [108 empty] | 2 | 2
|  | Downtime Shops closed area | Design ¦ Game design | [108 empty] | 2 | 2
|  | Downtime Social Hub Area Blockout | Design ¦ Level design | [112 empty] | 6 | 6
|  | Downtime Tavern Blockout | Design ¦ Level design | [112 empty] | 3 | 7
|  | Downtime Tavern Concept | Art ¦ Concept Art
|  | Downtime Tavern Model | Art ¦ Environment Art
|  | Downtime Tavern Props | Art ¦ Environment Art
|  | NPC behaviour document | Design ¦ Game design | [109 empty] | 2
|  | Downtime NPC placement | Design ¦ Game design | [108 empty] | 4 | 5
|  | Downtime shops storefronts models | Art ¦ Environment Art
|  | Downtime Auction House storefront model | Art ¦ Environment Art
|  | Downtime Bank storefront model | Art ¦ Environment Art
|  | Downtime Barbersmith storefront model | Art ¦ Environment Art
|  | Downtime QA | QA ¦ QA
|  | Downtime Tavern Concept | Art ¦ Concept Art
|  | Downtime Tavern Model | Art ¦ Environment Art
|  | Downtime Tavern Props | Art ¦ Environment Art
|  | Downtime NPC placement | Design ¦ Game design
|  | Downtime shops storefronts models | Art ¦ Environment Art
|  | Downtime Auction House storefront model | Art ¦ Environment Art
|  | Downtime Bank storefront model | Art ¦ Environment Art
|  | Downtime Barbersmith storefront model | Art ¦ Environment Art
|  | Downtime QA | QA ¦ QA
|  | Downtime Zone | Art ¦ Environment Art | [128 empty] | 92.6 | 114.3
|  | Biomes - Downtime | Art ¦ Environment Art | [128 empty] | 50 | 57.1
|  | Env Prop Kit - Tavern | Art ¦ Environment Art
Combat
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Combat Framework |  |  | L | T2: GDD/TDD/Brief | [107 empty] | 24 | [13 empty] | 9 | [13 empty] | 30 |  | 60 | [5 empty] | 36 | [9 empty] | 6
|  | Combat Design | Design ¦ Game design | [108 empty] | 15 | 15
|  | Attacks Design Doc - per weapon (Combo + off-hand attacks) | Design ¦ Game design | [108 empty] | 3 | 4
|  | Weapon Attributes (per weapon) | Design ¦ Game design | [108 empty] | 1 | 1
|  | Combat Animations | Art ¦ Animation & Rigging
|  | Combat Montages | Art ¦ Animation & Rigging
|  | Combat Tech anim? | Art ¦ Animation & Rigging
|  | Combat integration | Engineering ¦ Gameplay Engineering
|  | Weapons models | Art ¦ Character Art
|  | Combat VFX | Art ¦ VFX
|  | Melee Combat QA | QA ¦ QA
|  | Combat Design | Design ¦ Game design
|  | Combat Animations | Art ¦ Animation & Rigging
|  | Combat Tech anim? | Art ¦ Animation & Rigging | [132 empty] | 10 | 20
|  | Weapon spesific hand poses | Art ¦ Animation & Rigging | [132 empty] | 2 | 2
|  | Aim offset implementation | Art ¦ Animation & Rigging | [132 empty] | 2 | 4
|  | Review the combat with networking engineer | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 5
|  | Death sequance system | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Weapons models | Art ¦ Character Art
|  | Combat VFX | Art ¦ VFX
|  | Melee Combat QA | QA ¦ QA
|  | Pressure based agro | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 8
|  | Distance based agro | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Health based agro | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Utility managment | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Scaling | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | AI vs AI | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Player feedback | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Safety check | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Reflex check | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Survival check | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Social check | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Execution check | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | different types of movements | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | decision tick | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | utility abilities (healthing etc...) | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | attack abilities (attack etc...) | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
| Ranged Combat |  |  | M | T0: Ideation | [131 empty] | 30 |  | 10 | [9 empty] | 20
|  | Dual Wielding Ranged | Design ¦ Game design | [108 empty] | 2 | 4
|  | Ranged Attributes | Design ¦ Game design | [108 empty] | 5 | 5
|  | Aimed offsets | Art ¦ Animation & Rigging
| Combat AI Behavior |  |  | L | T0: Ideation | [107 empty] | 14 | [13 empty] | 6 | [9 empty] | 15 |  | 5 |  | 25 |  | 20 | [5 empty] | 6 | [9 empty] | 10
| Enemies Art |  |  | M | T0: Ideation | [107 empty] | 13 | [11 empty] | 10 |  | 30 |  |  |  | 15 | [5 empty] | 95 |  | 30 |  | 15 |  | 10 | [5 empty] | 20 | [9 empty] | 17
|  | Wolf montages | Art ¦ Animation & Rigging
|  | Wolf AI behaviour | Design ¦ Game design | [109 empty] | 2
|  | Design | Design ¦ Game design | [108 empty] | 3 | 5
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging
|  | Animation | Art ¦ Animation & Rigging
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | VFX | Art ¦ VFX
|  | Wolfy noises | Audio ¦ Audio | [154 empty] | 0 | 0
|  | Wolves QA | QA ¦ QA
|  | Goblin montages | Art ¦ Animation & Rigging
|  | Goblin AI behaviour | Design ¦ Game design | [109 empty] | 4
|  | Design | Design ¦ Game design | [108 empty] | 3 | 9
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging
|  | Animation | Art ¦ Animation & Rigging
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | VFX | Art ¦ VFX
|  | SFX | Audio ¦ Audio | [154 empty] | 7 | 7
|  | Goblins QA | QA ¦ QA
|  | Skeleton montages | Art ¦ Animation & Rigging
|  | Skeleton AI behaviour | Design ¦ Game design | [109 empty] | 4
|  | Design | Design ¦ Game design | [108 empty] | 3 | 9
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging
|  | Animation | Art ¦ Animation & Rigging
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | VFX | Art ¦ VFX
|  | SFX | Audio ¦ Audio | [154 empty] | 0 | 0
|  | Skeletons QA | QA ¦ QA
|  | Design | Design ¦ Game design | [108 empty] | 3 | 5
|  | Slimes AI behaviour | Design ¦ Game design | [109 empty] | 2
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging
|  | Animation | Art ¦ Animation & Rigging
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | VFX | Art ¦ VFX
|  | SFX | Audio ¦ Audio | [154 empty] | 0 | 0
|  | Slimes QA | QA ¦ QA
|  | Narrative | Design ¦ Game design | [108 empty] | 2 | 1
|  | Design | Design ¦ Game design | [108 empty] | 2 | 2
|  | Quest structure | Design ¦ Game design | [108 empty] | 1 | 4
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging
|  | Animation | Art ¦ Animation & Rigging
|  | Asset Validation | Art ¦ TechArt
|  | VFX | Art ¦ VFX
|  | SFX | Audio ¦ Audio | [154 empty] | 3 | 3
|  | Corrupted Enemies QA | QA ¦ QA
|  | Design | Design ¦ Game design | [108 empty] | 2 | 5
|  | Carapax AI design | Design ¦ Game design | [109 empty] | 4
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging
|  | Animation | Art ¦ Animation & Rigging
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | VFX | Art ¦ VFX
|  | SFX | Audio ¦ Audio | [154 empty] | 5 | 7
|  | Carapax QA | QA ¦ QA
|  | Design | Design ¦ Game design
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging | [132 empty] | 10 | 10
|  | Animation | Art ¦ Animation & Rigging
|  | Create animation graph | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Create control rig | Art ¦ Animation & Rigging | [132 empty] | 1 | 2
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | Make combat moves | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | VFX | Art ¦ VFX
|  | Wolves QA | QA ¦ QA
|  | Design | Design ¦ Game design
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging | [132 empty] | 10 | 10
|  | Animation | Art ¦ Animation & Rigging
|  | Create animation graph | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | RBF setup | Art ¦ Animation & Rigging | [132 empty] | 2 | 4
|  | Create control rig | Art ¦ Animation & Rigging | [132 empty] | 1 | 2
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | Make combat moves | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | VFX | Art ¦ VFX
|  | Goblins QA | QA ¦ QA
|  | Design | Design ¦ Game design
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging | [132 empty] | 10 | 10
|  | Animation | Art ¦ Animation & Rigging
|  | Create animation graph | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Seperate clothing from body | Art ¦ Animation & Rigging | [132 empty] | 5 | 7
|  | Custom death sequance | Art ¦ Animation & Rigging | [132 empty] | 5 | 7
|  | Create control rig | Art ¦ Animation & Rigging | [132 empty] | 1 | 2
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | Make combat moves | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | VFX | Art ¦ VFX
|  | Skeletons QA | QA ¦ QA
|  | Design | Design ¦ Game design
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging | [132 empty] | 2 | 2
|  | Animation | Art ¦ Animation & Rigging
|  | Create animation graph | Art ¦ Animation & Rigging | [132 empty] | 2 | 2
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | Make combat moves | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | VFX | Art ¦ VFX
|  | Slimes QA | QA ¦ QA
|  | Design | Design ¦ Game design
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging | [132 empty] | 5 | 15
|  | Animation | Art ¦ Animation & Rigging
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | Make combat moves | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | VFX | Art ¦ VFX | [136 empty] | 3 | 10
|  | Corrupted Enemies QA | QA ¦ QA
|  | Design | Design ¦ Game design
|  | Concept | Art ¦ Concept Art
|  | Model | Art ¦ Character Art
|  | Rigging | Art ¦ Animation & Rigging | [132 empty] | 10 | 10
|  | Animation | Art ¦ Animation & Rigging
|  | Create animation graph | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Seperate clothing from body | Art ¦ Animation & Rigging | [132 empty] | 2 | 2
|  | Custom death sequance | Art ¦ Animation & Rigging | [132 empty] | 1 | 2
|  | Create control rig | Art ¦ Animation & Rigging | [132 empty] | 1 | 2
|  | Asset Validation | Art ¦ TechArt
|  | Combat Behavior | Engineering ¦ Gameplay Engineering
|  | Make combat moves | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | VFX | Art ¦ VFX
|  | Carapax QA | QA ¦ QA
|  | Green Faction NPCs | Art ¦ Character Art
|  | Red Faction NPCs | Art ¦ Character Art
|  | Yellow Faction NPCs | Art ¦ Character Art
|  | Blue Faction NPCs | Art ¦ Character Art
|  | Critter NPCs - Pigs (DONE) | Art ¦ Character Art
|  | Critter NPCs - Hares (DONE) | Art ¦ Character Art
|  | Critter NPCs - Sheep (DONE) | Art ¦ Character Art
|  | Critter NPCs - Cows (DONE) | Art ¦ Character Art
|  | Critter NPCs - Chickens (DONE) | Art ¦ Character Art
|  | Critter NPCs - Horses (DONE) | Art ¦ Character Art
|  | Hero NPC - Xyron (Upgrade) | Art ¦ Character Art
|  | Hero NPC - Barbersmith (Upgrade) | Art ¦ Character Art
|  | Hero NPC - Maeve/Mayor (Upgrade) | Art ¦ Character Art
| PvP Combat |  |  | L | T0: Ideation | [107 empty] | 16 | [13 empty] | 3 |  |  |  |  | 91.4 | 205.7 | [15 empty] | 3 | [9 empty] | 2
|  | PVP Combat design | Design ¦ Game design | [108 empty] | 5 | 12
|  | PVP Combat support | Engineering ¦ Gameplay Engineering
|  | PVP only available in Arena | Engineering ¦ Gameplay Engineering
|  | PVP Arena Design | Design ¦ Game design | [108 empty] | 6 | 7
|  | PVP Combat Setup | Design ¦ Game design | [109 empty] | 6
|  | PVP Arena concept | Art ¦ Concept Art
|  | PVP Arena blockout | Design ¦ Level design | [112 empty] | 3 | 10
|  | PVP Arena Foliage | Art ¦ Environment Art
|  | PVP Arena set dressing | Art ¦ Environment Art
|  | PVP Arena props | Art ¦ Environment Art
|  | PVP Arena Audio | Audio ¦ Audio | [154 empty] | 7 | 5
|  | PVP combat QA | QA ¦ QA
|  | PVP Combat design | Design ¦ Game design
|  | Show damage numbers between players on hit | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 3
|  | Implement player prediction algorithm for networking | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Show other player HP in area fight | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | declare player who is connected as winner | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create fight timer and declare draw | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Reward player who won and display a message to the loser | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Sign up for arena fight actor | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Kick players that are in the area who are not fighting when you and someone else decide to start a fight | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | PVP area blocks player from entering and leaving | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | PVP Combat support | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | PVP only available in Arena | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create UI/UX | Art ¦ UX/UI
|  | Ensure combat system works | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | PVP Arena Design | Design ¦ Game design
|  | PVP Arena concept | Art ¦ Concept Art
|  | PVP Arena blockout | Design ¦ Level design
|  | PVP Arena Foliage | Art ¦ Environment Art
|  | PVP Arena set dressing | Art ¦ Environment Art
|  | PVP Arena props | Art ¦ Environment Art
|  | PVP Arena Audio | Audio ¦ Audio
|  | PVP combat QA | QA ¦ QA
|  | Architecture Kit - Arena | Art ¦ Environment Art | [128 empty] | 34.3 | 114.3
|  | Arena | Art ¦ Environment Art | [128 empty] | 57.1 | 91.4
| Combat Balance & Telemetry |  |  | M | T2: GDD/TDD/Brief | [143 empty] | 40
|  | Create leaderboard collection | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create a leaderboard in dashboard (internal dashboard) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 4
|  | Delete a leaderboard from dashboard (internal dashboard) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Delete an entry from the leaderboard from dashboard (internal dashboard) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create UI for leaderboard in (internal dashboard) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch all leaderboards (internal dashboard) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update leaderboard from (social service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch leaderboard from (social service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Fetch leaderboard in unreal | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Update leaderboard in unreal | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
| Combat Abilities |  |  | L | T1: R&D | [107 empty] | 20 | [11 empty] | 2 |  | 10 | [9 empty] | 25 |  | 10 |  | 20 | [7 empty] | 30 | [9 empty] | 20
|  | Abilities Design | Design ¦ Game design | [108 empty] | 8 | 9
|  | 4 Abilities designed (2 weapons) | Design ¦ Game design | [108 empty] | 5 | 20
|  | Weapon attribute system | Design ¦ Game design | [108 empty] | 3 | 5
|  | Combat Abilities UI | Art ¦ UX/UI | [122 empty] | 8 | 15
|  | HUD Combat Abilities UI | Art ¦ UX/UI | [122 empty] | 8 | 5
|  | HUD design | Art ¦ UX/UI | [122 empty] | 5 | 7
|  | Combat Abilities integrated with skill path | Engineering ¦ Gameplay Engineering
|  | Combat abilities casting animations | Art ¦ Animation & Rigging
|  | Combat Abilities QA | QA ¦ QA
|  | Combat Abilities SFX | Audio ¦ Audio | [154 empty] | 7 | 7
|  | Abilities Design | Design ¦ Game design
|  | Combat Abilities UI | Art ¦ UX/UI
|  | Integrate abilities with skill path | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Make the abilities | Engineering ¦ Gameplay Engineering | [144 empty] | 10 | 12
|  | Combat abilities casting animations | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Combat Abilities QA | QA ¦ QA
|  | Combat SFX | Audio ¦ Audio
| Magic |  |  | L | T0: Ideation | [101 empty] | 5 | [5 empty] | 30 |  | 5 | [11 empty] | 10 | [9 empty] | 30 |  | 10 |  | 20 | [7 empty] | 30
|  | Magic Weapon (e.g. wand) | Design ¦ Game design | [108 empty] | 3 | 5
|  | Weapon | Art ¦ Environment Art
|  | Magic system design (5 spells) | Design ¦ Game design | [108 empty] | 5 | 10
|  | Magic implementation | Engineering ¦ Gameplay Engineering
|  | Magic UI (1 skill tree mapped out) | Art ¦ UX/UI | [122 empty] | 5 | 7
|  | Magic casting animations | Art ¦ Animation & Rigging
|  | Magic SFX | Audio ¦ Audio | [154 empty] | 7 | 5
|  | Magic VFX | Art ¦ VFX
|  | Magic QA | QA ¦ QA
|  | Magic system design (3-4 spells) | Design ¦ Game design
|  | make wand abilities 4 | Engineering ¦ Gameplay Engineering | [144 empty] | 10 | 15
|  | wand skill tree | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | make wand an item type | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | equipd wand | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | Magic UI (1 skill tree mapped out) | Art ¦ UX/UI
|  | Magic casting animations | Art ¦ Animation & Rigging
|  | Magic SFX | Audio ¦ Audio
|  | Magic VFX | Art ¦ VFX
|  | Magic QA | QA ¦ QA
| Full Motion Video (FMV) |  |  | M | T1: R&D
|  | Intro supports FMV | Engineering ¦ Backend Engineering
|  | Create placeholder FMV playback flow | Engineering ¦ Backend Engineering
|  | Implement FMV skip behavior | Engineering ¦ Backend Engineering
|  | Implement transition after FMV | Engineering ¦ Backend Engineering
|  | FMV Production | Art ¦ Environment Art
|  | Integrate final/near-final FMV asset | Engineering ¦ Backend Engineering
|  | QA playback across target builds | QA ¦ QA
|  | Fix FMV blocker bugs | Engineering ¦ Backend Engineering
|  | Narrative - Cinematic scripting | Design ¦ Narrative | [116 empty] | 1 | 1
|  | Intro sequence plays 3 slides with voiceover | Engineering ¦ Backend Engineering
|  | Create intro sequence controller | Engineering ¦ Backend Engineering
|  | Display static slides full-screen | Engineering ¦ Backend Engineering
|  | Play voiceover synced to sequence | Engineering ¦ Backend Engineering
|  | Display subtitles synced to VO | Engineering ¦ Backend Engineering
|  | Implement skip behavior | Engineering ¦ Backend Engineering
|  | Implement transition to gameplay/menu | Engineering ¦ Backend Engineering
|  | Final art production | Art ¦ Concept Art
|  | VO production | Audio ¦ Audio | [154 empty] | 6 | 3
|  | Subtitles production | Design ¦ Game design | [108 empty] | 0.5 | 1
|  | Integrate final art + VO assets | Engineering ¦ Backend Engineering
|  | QA + fix blockers | QA ¦ QA
|  | Intro supports FMV | Engineering ¦ Gameplay Engineering
|  | Create placeholder FMV playback flow and allow designers to set the FMV easily | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | Create a system to disallow the player from moving while in FMV | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Implement FMV skip behavior | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Implement transition after FMV - Fade in/Fade out system | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | FMV Production | Art ¦ Environment Art
|  | Integrate final/near-final FMV asset | Engineering ¦ Gameplay Engineering
|  | QA playback across target builds | QA ¦ QA
|  | Intro sequence plays 3 slides with voiceover | Engineering ¦ Gameplay Engineering
|  | Create intro sequence controller | Engineering ¦ Gameplay Engineering
|  | Create a system to disallow the player from moving while in FMV | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 1
|  | Allow this to be triggered from quest | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Display static slides full-screen | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Tool for designers | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | UI Design | Art ¦ UX/UI
|  | Play voiceover synced to sequence | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Display subtitles synced to VO | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Implement skip behavior | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Implement transition to gameplay/menu | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Final art production | Art ¦ Concept Art
|  | VO production | Design ¦ Game design
|  | Subtitles production | Design ¦ Game design
|  | Integrate final art + VO assets | Design ¦ Game design
|  | QA + fix blockers | QA ¦ QA
User Space
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| User Space Server & Instance |  |  | L | T2: GDD/TDD/Brief | [126 empty] | 139.4 | 139.4 | [15 empty] | 60
|  | FTUE Design | Design ¦ Game design | [108 empty] | 3 | 5
|  | FTUE UI | Art ¦ UX/UI | [123 empty] | 5
|  | User Space Editor audio | Audio ¦ Audio | [154 empty] | 2 | 2
|  | Mutual Activity Design | Design ¦ Game design | [108 empty] | 2 | 4
|  | Mutual Activity UI | Art ¦ UX/UI | [123 empty] | 5
|  | Drinking design | Design ¦ Game design | [109 empty] | 1
|  | Drunken UI | Art ¦ UX/UI | [123 empty] | 4
|  | User Space is a separate instance | Engineering ¦ Backend Engineering
|  | User Space editor & UI | Engineering ¦ Gameplay Engineering
|  | User Space Ambience | Audio ¦ Audio | [154 empty] | 1 | 1
|  | Item SFX | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | Island ambient audio | Audio ¦ Audio | [154 empty] | 1 | 1
|  | User Space editor VFX | Art ¦ VFX
|  | User Space functionality QA | QA ¦ QA
|  | User Space GDD VS page | Design ¦ Game design | [109 empty] | 1
|  | User Space location concepts | Art ¦ Concept Art
|  | User Space location blockout | Design ¦ Level design | [112 empty] | 5 | 7
|  | User Space location set dressing | Art ¦ Environment Art
|  | User Space location props | Art ¦ Environment Art
|  | User Space location foliage | Art ¦ Environment Art
|  | User Space visuals QA | QA ¦ QA
|  | User Space is a separate instance | Engineering ¦ Backend Engineering
|  | DevOps | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | IP address list service | Engineering ¦ Backend Engineering | [148 empty] | 5 | 6
|  | Multiple players join one server and only show what is relevent to current player | Engineering ¦ Gameplay Engineering | [144 empty] | 10 | 20
|  | Figure out friend ip address to join his server when invited | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Host permissions | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Edit mode improvmeents | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Save userspace furniture location in userspace | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Fetch userspace furniture from backend | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Update userspace furniture and tell that to all players | Engineering ¦ Gameplay Engineering | [144 empty] | 4 | 5
|  | Player joining friends userspace | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Enable fishing in userspace | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Load userspace from save data | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 7
|  | User Space editor & UI | Engineering ¦ Gameplay Engineering
|  | Setup animation for userspace editing tool | Art ¦ Animation & Rigging | [132 empty] | 1 | 1
|  | Implement interaction animation with userspace items (snap) | Art ¦ Animation & Rigging | [132 empty] | 1 | 5
|  | User Space Ambience | Audio ¦ Audio
|  | User Space editor VFX | Art ¦ VFX
|  | User Space functionality QA | QA ¦ QA
|  | User Space location concepts | Art ¦ Concept Art
|  | User Space location blockout | Design ¦ Level design
|  | User Space location set dressing | Art ¦ Environment Art
|  | User Space location props | Art ¦ Environment Art
|  | User Space location foliage | Art ¦ Environment Art
|  | User Space visuals QA | QA ¦ QA
|  | Player Island 1 | Art ¦ Environment Art | [128 empty] | 69.7 | 69.7
|  | Player Island 2 | Art ¦ Environment Art | [128 empty] | 69.7 | 69.7
|  | Zone - User Space Island | Art ¦ Environment Art
| User Space Decoration |  |  | M | T0: Ideation | [107 empty] | 14 | [11 empty] | 20 | [8 empty] | 51.4 | 66.4 | [13 empty] | 30 | [9 empty] | 2
|  | User Space House concept | Art ¦ Concept Art
|  | User Space House model | Art ¦ Environment Art
|  | User Space furniture props | Art ¦ Environment Art
|  | User Space House concept | Art ¦ Concept Art
|  | User Space House model | Art ¦ Environment Art
|  | User Space furniture props | Art ¦ Environment Art
|  | Furniture - Fantasy | Art ¦ Environment Art | [128 empty] | 5.7 | 5.7
|  | Furniture - Gritcore | Art ¦ Environment Art | [128 empty] | 45.7 | 45.7
|  | Indoor Camera | Engineering ¦ Gameplay Engineering
|  | User Space Interior | Art ¦ Environment Art
|  | User Space Exterior | Art ¦ Environment Art
| P2P / P2G User Space Connection |  |  | M | T2: GDD/TDD/Brief | [107 empty] | 1 | [35 empty] | 30
| Building Houses |  |  | L | T1: R&D | [121 empty] | 3 |  |  |  |  | 134.3 | 182.9 | [15 empty] | 60 | [9 empty] | 2
|  | Architecture Kit - Player Housing | Art ¦ Environment Art | [128 empty] | 65.7 | 114.3
|  | Player Buildings | Art ¦ Environment Art | [128 empty] | 68.6 | 68.6
|  | Modular Houses | Art ¦ Environment Art
| Saving House Layouts |  |  | M | T0: Ideation | [143 empty] | 30
| Partner Portal System (player house) |  |  | M | T0: Ideation
| Arcade Cabinet |  |  | M | T1: R&D
| Anywhere Door Placement |  |  | S | T0: Ideation | [119 empty] | 5 | [15 empty] | 15 | [7 empty] | 5
|  | User space door can be placed at predefined spots | Engineering ¦ Gameplay Engineering
|  | Anywhere Door QA | QA ¦ QA
|  | User space door can be placed at predefined spots | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create endpoint to update the position, rotation and zone name of MULTIPLE anywhere door in backend (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create fetech anywhere door endpoint (player data service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update anywhere door position, rotation, zone name after fethcing anywhere door info from (player data serivce) | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create an ability to place anywhere door in the world | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create anywhere door as item in backend service. | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create anywhere door as item. | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Show if the anywhere door is placed or not placed to remove it if needed | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show anywhere door on map | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show anywhere door on minimap | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Show anywhere door on compass | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Make anywhere door as an actor | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Remove anywhere door | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | fetch anywhere door info from backend service and place it in the world | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Make spesific regions where anywhere door can be placed | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Anywhere Door QA | QA ¦ QA
Items & Inventory
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Item Core System |  |  | L | T2: GDD/TDD/Brief | [107 empty] | 3 | [11 empty] | 3 |  | 4 | [7 empty] | 3 | [7 empty] | 2 | [5 empty] | 30 | [9 empty] | 2
|  | Starting Chest | Design ¦ Game design | [108 empty] | 0.5 | 5
|  | Chest concept | Art ¦ Concept Art
|  | Chest model | Art ¦ Environment Art
|  | Chest animation | Art ¦ Animation & Rigging
|  | Chest VFX | Art ¦ VFX
|  | QA check | QA ¦ QA
|  | Shield | Design ¦ Game design | [108 empty] | 2 | 4
|  | Shield animations | Art ¦ Animation & Rigging
|  | Shield Asset | Art ¦ Environment Art
|  | Starting Sword | Design ¦ Game design | [108 empty] | 0.5 | 4
|  | Sword concept | Art ¦ Concept Art
|  | Sword model | Art ¦ Character Art
|  | Sword animations | Art ¦ Animation & Rigging
|  | Sword VFX | Art ¦ VFX
|  | Equipment Stats integrated with character stats | Design ¦ Game design | [108 empty] | 5 | 5
|  | Equipment Stats integrated with character stats | Engineering ¦ Gameplay Engineering
|  | QA check | QA ¦ QA
|  | Starting Chest | Design ¦ Game design
|  | Chest concept | Art ¦ Concept Art
|  | Chest model | Art ¦ Environment Art
|  | Chest animation | Art ¦ Animation & Rigging | [132 empty] | 1 | 1
|  | Chest VFX | Art ¦ VFX
|  | QA check | QA ¦ QA
|  | Starting Sword | Design ¦ Game design
|  | Sword concept | Art ¦ Concept Art
|  | Sword model | Art ¦ Character Art
|  | Sword animations | Art ¦ Animation & Rigging | [132 empty] | 5 | 10
|  | Sword VFX | Art ¦ VFX
|  | Equipment Stats integrated with character stats | Engineering ¦ Gameplay Engineering
|  | QA check | QA ¦ QA
| Inventory System |  |  | M | T2: GDD/TDD/Brief | [119 empty] | 10 |  | 30 | [13 empty] | 20 | [7 empty] | 20 | [9 empty] | 2
| Equipment System |  |  | M | T0: Ideation | [107 empty] | 10 | [11 empty] | 10 |  | 40 | [15 empty] | 10 | [5 empty] | 20
|  | an endpoint to all items equiped (batch requests only send what changed) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create an endpoint to store abilities in internal dashboard | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to fetch abilities internal dashboard | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to remove ability internal dashboard | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to fetch equiped items | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to euip items | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | an endpoint to update all item and abilities position in the hotbar (batch requests only send what changed) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create endpoint to fetch hotbar items and abilities | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create unit test for updating, fetching | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Send an HTTP reuqest only after 2 seconds after not moving any items or abilities in hotbar | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Get hotbar item and abiltitie positions and set them | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 3
|  | Fetch and set equiped items | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
| Loot Distribution |  |  | M | T2: GDD/TDD/Brief | [107 empty] | 3 | [13 empty] | 10 | [13 empty] | 30 | [7 empty] | 30
|  | Loot distribution design | Design ¦ Game design | [109 empty] | 3
|  | Loot is distributed after the raid | Engineering ¦ Gameplay Engineering
|  | Loot distribution QA | QA ¦ QA
|  | Loot is distributed after the raid | Engineering ¦ Gameplay Engineering
|  | Create loot distribution collection ( internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Update loot distribution collection ( internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch loot distribution collection (internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create loot distribution system which lets Actors inherit from multiple templates | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Refreance loot table in enemy/actor in tool | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create a new loot table in tool | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Save temp loot table in tool | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Edit loot table in CH tool | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Delete loot table in CH tool | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Fetch current loot tables in CH tool | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Release loot table in CH tool | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create a system for actors to referance loot table | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Enemies drop item when they are killed | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | distrubute loot according to dungeon rules | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Loot distribution QA | QA ¦ QA
| Mounts / Pets |  |  | L | T1: R&D | [107 empty] | 5 |  | 2 | [21 empty] | 13 |  | 3 |  | 5 |  | 2 | [5 empty] | 20
|  | Pet system design | Design ¦ Game design | [109 empty] | 4
|  | Pet concepts | Art ¦ Concept Art
|  | Pet model | Art ¦ Character Art
|  | Pet animations | Art ¦ Animation & Rigging
|  | Pet VFX | Art ¦ VFX
|  | Pet behavior | Engineering ¦ Gameplay Engineering
|  | Pet integration | Engineering ¦ Gameplay Engineering
|  | Pet QA | QA ¦ QA
|  | Teleport pet to player when pet is stuck | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Review pet system code | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Pet concepts | Art ¦ Concept Art
|  | Pet model | Art ¦ Character Art
|  | Pet animations | Art ¦ Animation & Rigging
|  | Pet VFX | Art ¦ VFX
|  | Pet maya rig setup | Art ¦ Animation & Rigging | [132 empty] | 2 | 2
|  | Pet animation grpah setup | Art ¦ Animation & Rigging | [132 empty] | 2 | 2
|  | Pet QA | QA ¦ QA
|  | MECH PARROT | Art ¦ Character Art
| Banks |  |  | M | T0: Ideation | [107 empty] | 1 | [11 empty] | 5 | [23 empty] | 20 | [9 empty] | 1
| P2P Item Transfer |  |  | M | T0: Ideation | [143 empty] | 30
| Consumables |  |  | S | T2: GDD/TDD/Brief | [121 empty] | 2 | [9 empty] | 5 | [21 empty] | 2
|  | Check the health potion usage | QA ¦ QA
|  | Implement drinking animation | Art ¦ Animation & Rigging | [132 empty] | 1 | 1
|  | Check the health potion usage | QA ¦ QA
|  | Potions | Art ¦ Concept Art
| Durable Items |  |  | S | T0: Ideation
Player Economy
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Trading System |  |  | L | T0: Ideation | [107 empty] | 10 | [13 empty] | 30 | [21 empty] | 40 | [9 empty] | 3
|  | Shop Fake Fascia Design | Design ¦ Game design | [108 empty] | 5 | 1
|  | Clothing Shop Basic Contents | Design ¦ Game design | [108 empty] | 2 | 3
|  | Shops Concepts | Art ¦ Concept Art
|  | Shops Models & Set dressing | Art ¦ Environment Art
|  | Shop props | Art ¦ Environment Art
|  | Vendors Concepts | Art ¦ Concept Art
|  | Vendors Models | Art ¦ Character Art
|  | Vendors animation | Art ¦ Animation & Rigging
|  | Trading UX/UI | Art ¦ UX/UI | [122 empty] | 15 | 15
|  | Currency Integration | Engineering ¦ Gameplay Engineering
|  | Soft Currency (gold) icon | Art ¦ Concept Art
|  | Premium currency icon | Art ¦ Concept Art
|  | Shops Concepts | Art ¦ Concept Art
|  | Shops Models & Set dressing | Art ¦ Environment Art
|  | Shop props | Art ¦ Environment Art
|  | Vendors Concepts | Art ¦ Concept Art
|  | Vendors Models | Art ¦ Character Art
|  | Vendors animation | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Trading UX/UI | Art ¦ UX/UI
|  | Currency Integration | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Soft Currency (gold) icon | Art ¦ Concept Art
|  | Premium currency icon | Art ¦ Concept Art
|  | P2G Transactions Support | Engineering ¦ Backend Engineering | [148 empty] | 4 | 40
|  | Trading System QA | QA ¦ QA
|  | Create vendor collection ( internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update vendor collection ( internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch vendor collection (internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create fresh cron job to refresh item stacks for vendors (internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | delete items and vendor (internal dashboard managment service) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Update NPC tool to match vendor in unreal engine | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Release vendor in game from tempate to release | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | fetch last 20 items sold, buyback item, Create buyback functionality | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Create a list of sold items (redis / server) ??? fetch, create buyback endpoint, update endpoint, pipeline | Engineering ¦ Backend Engineering | [148 empty] | 5 | 7
|  | Fetch a list of sold items | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create buy endpoint | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create sell endpoint | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Use buy endpoint | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Use sell endpoint | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Update UI | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
| Currency System |  |  | M | T0: Ideation | [107 empty] | 10 |  | 2 | [9 empty] | 2 |  | 30 | [21 empty] | 20
|  | Currency System Art | Art ¦ Concept Art
| Auction House |  |  | L | T0: Ideation | [143 empty] | 120
|  | P2G Transactions Support | Engineering ¦ Backend Engineering
|  | Trading System QA | QA ¦ QA
| In-game Store |  |  | M | T0: Ideation | [107 empty] | 8 | [11 empty] | 10 | [9 empty] | 88 | [13 empty] | 60
|  | Virtual currency balance and items | Design ¦ Game design | [109 empty] | 2
|  | RMT subscription design | Art ¦ UX/UI | [122 empty] | 8 | 3
|  | RNT partner store | Art ¦ UX/UI | [123 empty] | 3
|  | RMT virtual currency page | Art ¦ UX/UI | [123 empty] | 3
|  | RMT store integration | Engineering ¦ Backend Engineering
|  | RMT Store SFX | Audio ¦ Audio | [154 empty] | 7 | 7
|  | RMT Store QA | QA ¦ QA
|  | RMT store design | Design ¦ Game design
|  | Fetch total owned virtual currancy | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create an endpoint to fetch total owned virtual currancy from store service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Call purchase virtual currnacy endpoint from Unreal | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create a purchase virtual currancy endpoint in store service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to fetch all store items, prices, images, titles from store service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update in-game store when fetching store items | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create purcahse item endpoint in store service | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Call purchase item endpoint in unreal and sned item to player mailbox when item is purchased | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create an endpoint to add items to in-game store in dashboard management service | Engineering ¦ Backend Engineering | [148 empty] | 4 | 5
|  | Create an endpoint to update items to in-game store in dashboard management service | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create an endpoint to remove items from in-game store in dashboard management service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to pause the purcahsing of an item from in-game store in dashboard managment serivce | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Display paused banner on paused items with a tooltip explaining why the item is paused | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Set a limit on items. example gun only 100 people can buy it. first come first serve | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Connect UI with code | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | RMT Store UI | Art ¦ UX/UI
|  | Basic RMT balance config | Design ¦ Game design
|  | RMT Store SFX | Audio ¦ Audio
|  | RMT Store QA | QA ¦ QA
| In-game Economy |  |  | L | T0: Ideation | [107 empty] | 90 | [13 empty] | 30
|  | Basic Economy configuration | Design ¦ Game design | [108 empty] | 10 | 5
|  | In-game economy QA check | QA ¦ QA
|  | Basic Economy configuration | Design ¦ Game design
|  | In-game economy QA check | QA ¦ QA
| RMT Game Economy |  |  | L | T0: Ideation | [143 empty] | 60
| IG / RMT Monitoring System |  |  | M | T0: Ideation
Quest System
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Quests Backend / Tooling |  |  | L | T2: GDD/TDD/Brief | [143 empty] | 60
|  | Tutorial Quest Chain Configuration & Setup | Design ¦ Game design | [108 empty] | 7 | 10
|  | QA check | QA ¦ QA
|  | Green Faction NPC Concepts | Art ¦ Concept Art
|  | Green Faction NPC Models | Art ¦ Character Art
|  | Green Faction NPC animations | Art ¦ Animation & Rigging
|  | Green Faction NPC dialogue setup | Design ¦ Narrative | [116 empty] | 1 | 2
|  | Green Faction NPCs placement | Design ¦ Game design | [108 empty] | 2 | 2
|  | QA check | QA ¦ QA
|  | Quest Editor | Design ¦ Game design | [108 empty] | 5 | 2
|  | Dialogue System Design | Design ¦ Game design | [108 empty] | 3 | 3
|  | Dialogue System | Engineering ¦ Backend Engineering
|  | Dialogue UI | Art ¦ UX/UI | [123 empty] | 10
|  | Quest Log | Engineering ¦ Backend Engineering
|  | Quest Log QA | QA ¦ QA
|  | Xyron narrative | Design ¦ Game design | [108 empty] | 2 | 2
|  | Tutorial Quest Chain Configuration & Setup | Design ¦ Game design
|  | QA check | QA ¦ QA
|  | Green Faction NPC Concepts | Art ¦ Concept Art
|  | Green Faction NPC Models | Art ¦ Character Art
|  | Green Faction NPC animations | Art ¦ Animation & Rigging | [132 empty] | 3 | 5
|  | Green Faction NPC dialogue setup | Design ¦ Game design
|  | Green Faction NPCs placement | Design ¦ Game design
|  | QA check | QA ¦ QA
|  | Dialogue System | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 15
|  | Dialogue UI | Art ¦ UX/UI
|  | Quest Log | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | Quest Log QA | QA ¦ QA
| Quests as Events |  |  | M | T1: R&D | [121 empty] | 30 | [21 empty] | 30
| Quest Multiplayer |  |  | L | T1: R&D | [107 empty] | 5 | [13 empty] | 30 | [21 empty] | 30
| Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking |  |  | L | T2: GDD/TDD/Brief | [101 empty] | 2 | [5 empty] | 3 | [35 empty] | 30
|  | Lockpicking | Design ¦ Game design | [108 empty] | 7 | 2
|  | Lockpicking Concept | Art ¦ Concept Art
|  | Lockpicking UI | Art ¦ UX/UI | [122 empty] | 8 | 6
|  | Lockpicking Integration | Engineering ¦ Gameplay Engineering
|  | Lockpicking Techart | Art ¦ TechArt
|  | Lockpicking QA check | QA ¦ QA
|  | Design interface for quest types | Design ¦ Game design | [108 empty] | 2 | 5
|  | Other quest types support? | Engineering ¦ Gameplay Engineering
|  | Lockpicking | Design ¦ Game design
|  | Lockpicking Concept | Art ¦ Concept Art
|  | Lockpicking UI | Art ¦ UX/UI
|  | Check if lockpicking solution is correct | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create an actor with a grid for all tiles | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create data asset | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 1
|  | Create pipe entity actor | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create magnatic enitity actor | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Create ball entity actor to compelete the game | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 4
|  | Start and end condition | Engineering ¦ Gameplay Engineering | [144 empty] | 0.5 | 0.5
|  | Create a system to modify ball proaprties while traveling | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 10
|  | VFX | Art ¦ VFX
|  | SFX | Audio ¦ Audio
|  | Implement VFX and SFX | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Lockpicking Techart | Art ¦ TechArt
|  | Lockpicking QA check | QA ¦ QA
|  | Design interface for quest types | Design ¦ Game design
|  | Other quest types support? | Engineering ¦ Gameplay Engineering
|  | Create quest tool | Engineering ¦ Gameplay Engineering | [144 empty] | 20 | 20
|  | Create quest system backend service | Engineering ¦ Backend Engineering | [148 empty] | 20 | 20
|  | Lock Picking Quest | Design ¦ Game design
| Quest Reward System |  |  | M | T0: Ideation | [121 empty] | 10 | [21 empty] | 20
|  | Quest UI Audio | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | Quest Reward UI | Art ¦ UX/UI | [123 empty] | 5
|  | Quest Reward System design doc | Design ¦ Game design | [109 empty] | 2
|  | Quest Reward List | Design ¦ Game design | [108 empty] | 2 | 2
|  | Rewards Choice | Engineering ¦ Gameplay Engineering
|  | Quest Rewards QA | QA ¦ QA
|  | Rewards Choice | Engineering ¦ Gameplay Engineering
|  | Quest Rewards QA | QA ¦ QA
|  | Hearthstone (Return Home Stone) | Art ¦ Concept Art
|  | Partner Crystal | Art ¦ Concept Art
| Quest Log |  |  | M | T0: Ideation | [121 empty] | 10 | [21 empty] | 20
| Quest Dialog GUI |  |  | M | T0: Ideation | [107 empty] | 4 |  | 2 | [5 empty] | 4 | [5 empty] | 30
| Quest Narrative Content |  |  | L | T2: GDD/TDD/Brief | [101 empty] | 3 | [5 empty] | 4 | [7 empty] | 7 | [5 empty] | 20
|  | Quest Flow Design & Narrative Overview | Design ¦ Game design | [108 empty] | 2 | 3
|  | Cave Intro Quest | Design ¦ Game design
|  | Quest Narrative Doc | Design ¦ Narrative | [116 empty] | 1 | 1
|  | Quest Design Doc | Design ¦ Game design | [108 empty] | 3 | 4
|  | Quest Implementation | Design ¦ Game design | [108 empty] | 3 | 5
|  | Quest Playtesting & Revision | Design ¦ Game design | [108 empty] | 2 | 2
|  | Quest Narrative Doc | Design ¦ Narrative | [116 empty] | 0.5 | 2
|  | Quest Design Doc | Design ¦ Game design | [108 empty] | 3 | 5
|  | Quest Implementation | Design ¦ Game design | [108 empty] | 4 | 6
|  | Quest Playtesting & Revision | Design ¦ Game design | [108 empty] | 2 | 3
|  | Quest Narrative Doc | Design ¦ Narrative | [116 empty] | 1 | 1
|  | Quest Design Doc | Design ¦ Game design | [108 empty] | 3 | 3
|  | Quest Implementation | Design ¦ Game design | [108 empty] | 3 | 5
|  | Quest Playtesting & Revision | Design ¦ Game design | [108 empty] | 2 | 5
|  | Quest Narrative Doc | Design ¦ Narrative | [116 empty] | 0.5 | 1
|  | Quest Design Doc | Design ¦ Game design | [108 empty] | 3 | 3
|  | Quest Implementation | Design ¦ Game design | [108 empty] | 3 | 3
|  | Quest Playtesting & Revision | Design ¦ Game design | [108 empty] | 2 | 5
|  | Docs, Implement, Revise | Design ¦ Game design | [108 empty] | 7 | 7
|  | Docs, Implement, Revise | Design ¦ Game design | [108 empty] | 7 | 7
|  | Docs, Implement, Revise | Design ¦ Game design | [108 empty] | 7 | 7
|  | Docs, Implement, Revise | Design ¦ Game design | [108 empty] | 7 | 7
|  | Docs, Implement, Revise | Design ¦ Game design | [108 empty] | 7 | 7
|  | Docs, Implement, Revise | Design ¦ Game design | [108 empty] | 7 | 7
| In Game Cinematic (IGC) |  |  | L | T2: GDD/TDD/Brief
|  | The game supports cutscenes | Engineering ¦ Gameplay Engineering
|  | Cutscene trigger system | Engineering ¦ Gameplay Engineering
|  | Camera control during cutscene | Engineering ¦ Gameplay Engineering
|  | Player control lock/unlock | Engineering ¦ Gameplay Engineering
|  | NPC/character sequencing | Engineering ¦ Gameplay Engineering
|  | Dialogue playback (in-cutscene) | Engineering ¦ Gameplay Engineering
|  | Cutscene skip functionality | Engineering ¦ Gameplay Engineering
|  | Transition in/out of cutscene | Engineering ¦ Gameplay Engineering
|  | Basic cutscene sequencing (timeline) | Engineering ¦ Gameplay Engineering
|  | Cutscene stability (QA & fixes) | QA ¦ QA
|  | Cutscene content | Design ¦ Game design | [108 empty] | 5 | 5
|  | Narrative | Design ¦ Narrative | [116 empty] | 0.5 | 1
|  | Camera behavior implementation/fixes | Engineering ¦ Gameplay Engineering
|  | Combat Camera | Design ¦ Game design | [108 empty] | 4 | 9
|  | Camera QA | QA ¦ QA
|  | The game supports cutscenes | Engineering ¦ Gameplay Engineering
|  | Custom camera position and rotation | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Custom camera animations | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Stream camera position (world partition) | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Cutscene stability (QA & fixes) | QA ¦ QA
|  | Cutscene content | Design ¦ Game design
|  | Camera behavior implementation/fixes | Engineering ¦ Gameplay Engineering
|  | Implement camera according to design | Engineering ¦ Gameplay Engineering | [144 empty] | 6 | 7
|  | Camera QA | QA ¦ QA
| Meta Quest System |  |  | M | T0: Ideation
| Quest Generator System |  |  | L | T0: Ideation
| Targeted VO |  |  | M | T2: GDD/TDD/Brief | [109 empty] | 2 | [5 empty] | 20 | [37 empty] | 10
Social & Multiplayer
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Game Chat System |  |  | M | T1: R&D | [101 empty] | 1 | [5 empty] | 12 | [13 empty] | 20 | [21 empty] | 60
|  | General systems | Engineering ¦ Backend Engineering
|  | Create pipeline and deploy | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create chat service in go | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a serialization/deserialization system | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create a list of users info such as server ip and usernames | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create a multithreaded system | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create a custom protocol using TCP | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create a heartbeat system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a packet system | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Connect to redis | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Proximity chat | Engineering ¦ Backend Engineering
|  | Send chat message only to people near you | Engineering ¦ Backend Engineering | [148 empty] | 4 | 5
|  | Zone channel | Engineering ¦ Backend Engineering
|  | Create a way to send a chat to entire zone | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Private message | Engineering ¦ Backend Engineering
|  | Send a private message to user | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Party chat | Engineering ¦ Backend Engineering
|  | Send a party message to your party | Engineering ¦ Backend Engineering | [148 empty] | 4 | 5
|  | Guild chat | Engineering ¦ Backend Engineering
|  | Send a message to your guild | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | System chat | Engineering ¦ Backend Engineering
|  | Create a system chat which will warn you on if the server is shutting down or if Show invites, kicks, bans in chat | Engineering ¦ Backend Engineering | [148 empty] | 4 | 5
|  | Chat text limit | Engineering ¦ Backend Engineering
|  | Create a system to limit the amount of text sent | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Chat spam filter | Engineering ¦ Backend Engineering
|  | Create a system to rate limit messages | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Profanity filter | Engineering ¦ Backend Engineering
|  | Create a system to filter a set of words | Engineering ¦ Backend Engineering | [148 empty] | 3 | 5
|  | Chat UI | Art ¦ UX/UI
|  | Auto scroll incomming chat messages | Art ¦ UX/UI
|  | Different colours for different type of message | Art ¦ UX/UI
|  | integraet chat service in unreal using websockets | Engineering ¦ Gameplay Engineering
|  | Create a websocket connection | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Create a way to receive messages on unreal server and pass that to client | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Create a way to send a message from unreal server to chat server | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
| Friends |  |  | M | T1: R&D | [121 empty] | 30 | [21 empty] | 20
| Guilds |  |  | L | T1: R&D | [101 empty] | 1 | [5 empty] | 20 | [13 empty] | 10 |  |  |  |  | 186.9 | 273.3 |  | 22 | [7 empty] | 4 | [5 empty] | 40
|  | Guilds system design | Design ¦ Game design | [109 empty] | 15
|  | Guild house is an instance | Engineering ¦ Backend Engineering
|  | Guild house concept | Art ¦ Concept Art
|  | Guild house model | Art ¦ Environment Art
|  | Guild house props | Art ¦ Environment Art
|  | Guild house TV + video | Art ¦ Environment Art
|  | Guild NPCs | Art ¦ Character Art
|  | Guild house blockout | Design ¦ Level design | [112 empty] | 4 | 10
|  | Sitting NPCs | Art ¦ Animation & Rigging
|  | Guild UI | Art ¦ UX/UI | [123 empty] | 3
|  | Guild chat | Engineering ¦ Gameplay Engineering
|  | Guild Chat design | Design ¦ Game design | [108 empty] | 3 | 1
|  | Guild QA | QA ¦ QA
|  | Guild house | Engineering ¦ Gameplay Engineering
|  | Guild house entry | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Guild house leave | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Guild house server | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Guild house concept | Art ¦ Concept Art
|  | Guild house model | Art ¦ Environment Art
|  | Guild house props | Art ¦ Environment Art
|  | Guild house TV + video | Art ¦ Environment Art
|  | Guild NPCs | Art ¦ Character Art
|  | Sitting NPCs | Art ¦ Animation & Rigging
|  | Connect Guild UI | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Guild UI | Art ¦ UX/UI
|  | Guild chat | Engineering ¦ Gameplay Engineering
|  | Guild QA | QA ¦ QA
|  | Architecture Kit - Guild Hall | Art ¦ Environment Art | [128 empty] | 82.9 | 135
|  | Guild Island | Art ¦ Environment Art | [128 empty] | 69.7 | 69.7
|  | Guild Buildings | Art ¦ Environment Art | [128 empty] | 34.3 | 68.6
| Co-op / Party |  |  | M | T1: R&D | [101 empty] | 2 | [5 empty] | 5 |  | 2 | [11 empty] | 6 | [21 empty] | 60
|  | Party formation | Engineering ¦ Backend Engineering | [148 empty] | 3 | 8
|  | Party system design | Design ¦ Game design | [109 empty] | 5
|  | Party chat | Design ¦ Game design
|  | Party supports real players and bots | Engineering ¦ Backend Engineering
|  | Party UI | Art ¦ UX/UI | [123 empty] | 2
|  | Party chat | Engineering ¦ Gameplay Engineering
|  | Party QA | QA ¦ QA
|  | Party formation | Engineering ¦ Backend Engineering
|  | Party supports real players and bots | Engineering ¦ Backend Engineering
|  | Party UI | Art ¦ UX/UI
|  | Party chat | Engineering ¦ Gameplay Engineering
|  | Create party puzzle | Engineering ¦ Gameplay Engineering
|  | Make a puzzle | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 5
|  | Party QA | QA ¦ QA
|  | Create pipeline and deploy | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create party service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a serialization/deserialization system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a list of users info such as server ip and usernames | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a multithreaded system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a custom protocol using TCP | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a heartbeat system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a packet system | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Connect to redis | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create a party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Invite someone to party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Kick someone from party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Roll check in party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Leave party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Disband party | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Change leadership | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Update party player position on map, mana, health | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create a party | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Invite someone to party | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Kick someone from party | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Roll check in party | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Leave party | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Disband party | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Change leadership | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Update party player position on map, mana, health | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
| Co-op / Raids |  |  | L | T1: R&D | [143 empty] | 40
| Dueling |  |  | M | T1: R&D
| In-game Mail |  |  | S | T2: GDD/TDD/Brief | [101 empty] | 1 | [5 empty] | 3 | [7 empty] | 2 |  |  |  | 1 |  | 10 | [21 empty] | 20
|  | In-game Mail backend | Engineering ¦ Backend Engineering
|  | In-game UI | Art ¦ UX/UI | [123 empty] | 10
|  | In-game Mail frontend/UI | Engineering ¦ Gameplay Engineering
|  | Mail UI Audio | Audio ¦ Audio | [154 empty] | 0.5 | 1
|  | Mail QA | QA ¦ QA
|  | Postbox Concept | Art ¦ Concept Art
|  | Postbox VFX | Art ¦ VFX
|  | Postbox SFX | Audio ¦ Audio | [154 empty] | 1 | 1
|  | Postbox Model | Art ¦ Environment Art
|  | Restore trash mail | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Mark mail as read | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Delete mail | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Claim items from mail | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Send mail from one player to another with items | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Restore trash mail | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Mark mail as read | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Delete mail | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Claim items from mail | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Claim currancy and increase ingame gold | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Send mail from one player to another with items | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Create mail UI/UX | Art ¦ UX/UI
|  | Create mail SFX | Audio ¦ Audio
|  | Create new mail model | Art ¦ Environment Art
|  | Mail QA | QA ¦ QA
| Notifications |  |  | S | T1: R&D | [143 empty] | 30
| Player Config PvP Server |  |  | M | T0: Ideation
| LFG / Pick-up Groups |  |  | M | T0: Ideation | [143 empty] | 40
|  | Create Dungeon finder UI/UX | Art ¦ UX/UI
|  | Connect dungeons to UI | Engineering ¦ Gameplay Engineering | [144 empty] | 5 | 8
|  | Create pipeline and deploy | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create dungeon finder service | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Add player to dungeon finder list | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Fetch a list of players queued up for dungeon by dungon id | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Remove player from dungeon queue | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Connect to redis | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Invite player to party | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Queue group for dungeon | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Send request to add player to dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Send request to remove player from dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Send request to fetch player from dungeon | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Remove party from queue after party is full | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Remove party from queue after party is full | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Send player status in dungeon finder | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Get player status in dungeon finder | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
Game Bibles
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| UX/UI Bible |  |  | M | T0: Ideation
|  | Wireframes | Art ¦ UX/UI | [122 empty] | 5.7 | 8.6
| Accessibility Guidelines |  |  | M | T0: Ideation
| Brand Bible |  |  | M | T2: GDD/TDD/Brief
|  | Colour Palette | Art ¦ Concept Art | [120 empty] | 5.7 | 8.6
|  | Typography | Art ¦ Concept Art | [120 empty] | 5.7 | 8.6
|  | Game Logo | Art ¦ Concept Art | [120 empty] | 11.4 | 14.3
| Art Bible |  |  | L | T3: Prototype
|  | Environment Bible | Art ¦ Environment Art
|  | Animation Bible | Art ¦ Animation & Rigging
|  | Character Bible | Art ¦ Character Art
|  | VFX Bible | Art ¦ VFX
|  | Concept Bible | Art ¦ Concept Art
| Monetization Bible |  |  | M | T0: Ideation | [107 empty] | 40
| Red Books (Live Service emergency guidelines) |  |  | M | T0: Ideation | [143 empty] | 30
Platform
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Player Account Creation / Deletion |  |  | M | T2: GDD/TDD/Brief | [143 empty] | 10
| Player Account Authentication |  |  | M | T2: GDD/TDD/Brief | [143 empty] | 15
| Player Account Privacy Settings & Legal |  |  | M | T1: R&D | [143 empty] | 10
| Player Dashboard - Account Features |  |  | M | T1: R&D | [143 empty] | 30
| Player Dashboard - Game Dashboard |  |  | M | T1: R&D | [143 empty] | 30
| Player Dashboard - Friends |  |  | M | T1: R&D | [143 empty] | 30
| Player Dashboard - Search & Notifications |  |  | M | T1: R&D | [143 empty] | 30
| Player Dashboard - Marketplace |  |  | L | T1: R&D | [143 empty] | 30
| Developer Dashboard - Developer Account |  |  | M | T1: R&D
| Developer Dashboard - Game Dashboard |  |  | M | T1: R&D
| Developer Dashboard - Settings & Support |  |  | M | T1: R&D
| Quest Tracking |  |  | M | T1: R&D | [143 empty] | 20
| Payment Processing (incl. Refunds) |  |  | L | T0: Ideation
| Online Services & Backend |  |  | L | T0: Ideation
|  | List of servers and their ip address | Engineering ¦ Backend Engineering | [148 empty] | 4 | 5
|  | Create an endpoint to store player X, Y, Z corrdinates and rotation and server ip address | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create an endpoint to fetch player position, rotation and IP address | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create unit test for update and fetch endpoint | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Set player position, rotation, when spawning player | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Conect to last server player left from | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Save player position and rotation and ip every X seconds on server, so if the server crashes we can retrieve this information later | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | For network engineer to figure out | Engineering ¦ Gameplay Engineering
|  | Pass entrance parameters from one server to another | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
|  | Set entrace points on map | Design ¦ Game design
|  | Set spawn position according to entrance paramters | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 5
| Launcher & Distribution |  |  | L | T2: GDD/TDD/Brief
| Partner Loop |  |  | M | T1: R&D
|  | Full partner loop definition/design | Design ¦ Game design | [108 empty] | 3 | 5
|  | Create Partner Store | Engineering ¦ Backend Engineering
|  | Integrate partner loop | Engineering ¦ Backend Engineering
|  | Buy game subscription time from website and/or from game | Engineering ¦ Backend Engineering
|  | Buy CH virtual currency | Engineering ¦ Backend Engineering
|  | Complete partner quest | Engineering ¦ Backend Engineering
|  | Purchase partner game from in-game store | Engineering ¦ Backend Engineering
|  | Redeem Partner Steam key | Engineering ¦ Backend Engineering
|  | Download Partner game | Engineering ¦ Backend Engineering
|  | Run partner game from same exe as CH | Engineering ¦ Backend Engineering
|  | Unlock partner item in CH by playing partner game | Engineering ¦ Backend Engineering
|  | Claim partner item from CH mailbox | Engineering ¦ Backend Engineering
|  | Partner functionality QA | QA ¦ QA
|  | Full partner loop definition/design | Design ¦ Game design
|  | Create Partner Store | Engineering ¦ Backend Engineering | [148 empty] | 10 | 20
|  | Integrate partner loop | Engineering ¦ Backend Engineering | [148 empty] | 5 | 10
|  | Buy game subscription time from website and/or from game | Engineering ¦ Backend Engineering
|  | Buy CH virtual currency | Engineering ¦ Backend Engineering
|  | Complete partner quest | Engineering ¦ Backend Engineering | [148 empty] | 0.5 | 10
|  | Purchase partner game from in-game store | Engineering ¦ Backend Engineering
|  | Redeem Partner Steam key | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Download Partner game | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Unlock partner item in CH by playing partner game | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Claim partner item from CH mailbox | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Claim partner item from CH mailbox | Engineering ¦ Gameplay Engineering | [144 empty] | 2 | 3
|  | Run partner game from same exe as CH | Engineering ¦ Backend Engineering
|  | Run partner game from same exe as CH | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Create IPC between exe launcher and unreal and partner game | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Create exe launcher | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Run CH in exe launcher | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Run partner in exe launcher | Engineering ¦ Backend Engineering | [148 empty] | 3 | 4
|  | Transition to lightweight map before launching partner game from exe launcher | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Partner functionality QA | QA ¦ QA
| Game Tool Integration (incl. Game Key Generation) |  |  | M | T1: R&D
| Account Level Settings |  |  | S | T0: Ideation
| Social Media Support |  |  | M | T0: Ideation | [143 empty] | 20
Live Game
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Live GDD |  |  | M | T0: Ideation
| Content |  |  | L | T0: Ideation
| Forecast |  |  | M | T0: Ideation
| Analytics & BI |  |  | L | T0: Ideation
| Sales Dashboard |  |  | M | T0: Ideation
| Telemetry |  |  | L | T0: Ideation
| Live Service Event Plan |  |  | L | T0: Ideation
Partner Build
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Partner = Feature definition |  |  | S | T0: Ideation
| Sign Partner |  |  | S | T0: Ideation
| Partner Brief |  |  | M | T0: Ideation
| Partner Design Doc |  |  | M | T0: Ideation
| Partner TDD |  |  | M | T0: Ideation
| Partner Art Brief |  |  | M | T0: Ideation
| Partner Build |  |  | L | T0: Ideation
| Partner Integration |  |  | M | T0: Ideation
Product Publishing
[86 empty] | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max | Min | Max
| Web Presence |  |  | M | T0: Ideation
| Website |  |  | M | T0: Ideation
|  | Create UI to display web browser inside the game launcher | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Pass data between in-launcher browswer and launcher | Engineering ¦ Gameplay Engineering | [144 empty] | 3 | 4
|  | Change play button from subscribe to play when a subscription is active | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | Fetch subscription information from backend service | Engineering ¦ Gameplay Engineering | [144 empty] | 1 | 2
|  | New UI/UX for game launcher to support web browser | Art ¦ UX/UI
|  | Create subscription endpoint in store service with tier rewards / different time lengths (30 , 90 , 180 , 360 ) | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create an endpoint to cancel subsciption | Engineering ¦ Backend Engineering | [148 empty] | 1 | 2
|  | Create an endpoint to fetch current subscription information from account managment service | Engineering ¦ Backend Engineering | [148 empty] | 2 | 3
|  | Create a subscription page in the store | Engineering ¦ Backend Engineering | [148 empty] | 3 | 5
| Community Persona |  |  | M | T0: Ideation
| Title Identity |  |  | M | T0: Ideation
| Player Support |  |  | M | T0: Ideation
| Go-To-Market Strategy & Implementation |  |  | L | T0: Ideation
| 3rd-party Store Publishing |  |  | M | T0: Ideation

## Staff
Name | Role | Team | Department
Mustafa Sibai | CTO | Engineering | Engineering
Daniel Negri | Full Stack Developer | Web Development | Engineering
Nikos Gerontakis | Full Stack Developer | Web Development | Engineering
Samer Balushi | Backend Developer | Web Development | Engineering
Raynor D'Souza | Gameplay Developer | Gameplay | Engineering
Ilya Achmetov | Gameplay Developer | Gameplay | Engineering
Leon Huang | Gameplay Developer | Gameplay | Engineering
Ignasi Ezpeleta | Gameplay Developer | Gameplay | Engineering
Roberto | Gameplay Developer | Gameplay | Engineering
Matt | Animator | Gameplay | Engineering
David Luong | Art Director | Art Direction | Art
Wojciech Szon | VFX Artist | VFX | Art
Conor McLean | VFX Artist | VFX | Art
Michail Velissaris | VFX Artist | VFX | Art
Stefano Vietina | Technical Artist | Technical Art | Art
Samuele Piazzi | Technical Artist | Technical Art | Art
Andrea Rottini | Technical Artist | Technical Art | Art
Niko Gesell | Concept Artist | Concept Art | Art
Kerim Turay | Concept Artist | Concept Art | Art
Gerard Vicen | Concept Artist | Concept Art | Art
Julian Hartinger | Concept Artist | Concept Art | Art
Gianluca Perusi | UI/UX Designer | Concept Art | Art
Larisa Logofatu | Graphic Designer | Concept Art | Art
Alon | Animator | 3D Animation | Art
Kunjal Asher | Animator | 3D Animation | Art
Maddalena Morello | Character Rigger | 3D Animation | Art
Sasha Krieger | Character Artist | 3D Characters | Art
Dimitris Chrysanthakopoulos | Character Artist | 3D Characters | Art
Rebecca Tomasoni | Character Artist | 3D Characters | Art
Michael Dunnam | Environment Artist | 3D Environment | Art
Ella Amatooni | Environment Artist | 3D Environment | Art
Marc Vives | Environment Artist | 3D Environment | Art
Iosif Alexiou | Environment Artist | 3D Environment | Art
Nick Chrysanthakopoulos | Prop Artist | 3D Environment | Art
Chris Brough | Environment Artist | 3D Environment | Art
Robin Jubber | Game Director | Product | Design
Yorgos Dritsas | Game Designer | Game Design | Design
Nadir Latif | Combat Designer | Game Design | Design
Kieron Naylor | Technical Designer | Design | Design
Nikolas Tziotis | Level Designer | Level Design | Design
Seth Dahl | Level Designer | Level Design | Design
Panos Andriopoulos | Level Designer | Level Design | Design
Maria Cibej | Writer | Writing | Design
Dragan Vuckovic | Sound Designer | Sound Design | Audio
Aggeliki Peroutsea | Sound Designer | Sound Design | Audio
Hannah Pickard | QA | QA | QA

## Roles
Role | Discipline | Notes
CEO | Leadership
Creative Director | Leadership
Head of Legal | Leadership
COO | Leadership
HR Manager | Leadership
Executive Producer | Production
Producer | Production
Game Producer | Production
Tech Producer | Production
Art Producer | Production
Game Director | Design
Game Design Lead | Design
Level Design Lead | Design
Game Designer | Design
Combat Designer | Design
Level Designer | Design
Technical Designer | Design
Writer | Design
Art Director | Art
Concept Artist | Art
UI/UX Designer | Art
Graphic Designer | Art
Character Artist | Art
Environment Artist | Art
Prop Artist | Art
Animator | Art
Character Rigger | Art
VFX Artist | Art
Technical Artist | Art
CTO | Engineering
Tech Lead | Engineering
Gameplay Developer | Engineering
Full Stack Developer | Engineering
Backend Developer | Engineering
Network Engineer | Engineering
QA | QA
Sound Designer | Audio
Platform Team | Platform

## Gates
Gate | Phase | Target Tier | Tier Name | Notes
0 | Concept | T0 | Ideation | Y-doc, pitch, vision lock; all features captured at T0
1 | Pre-production | T1-T2 | R&D / GDD-TDD-Brief | GDD/TDD/Art briefs for all greenlit features (T2)
2 | Early Prod | T3 | Prototype | Prototype every feature; many bugs allowed (T3)
3 | Mid Prod | T4 | MVP | Full MVP scope - heaviest production gate (T4)
4 | End Prod | T5 | Feature Complete | Feature complete, polish to ship quality (T5)
5 | Alpha | T6 | Player Tested | Playtest, telemetry, balance pass; gating bugs only
6 | Beta | T6 | Player Tested | External player feedback, cert prep, content lock
7 | Launch | T6 | Player Ready | Day-0 readiness, marketing, store, support
8 | First Release | T6-T7 | Player Ready / Expand | Live monitoring, hotfixes, day-1/7/30 patches
9 | LS 1 | T7 | Expand | Expansions, new content drops, season cadence (T7)
10 | LS 2 | T8 | Scale | Optimize / scale post-load, sustain plan (T8)

## Tiers
Tier | Name | Definition
T0 | Ideation | Idea captured, no commitment
T1 | R&D | Research, prototyping intent, technical feasibility
T2 | GDD / TDD / Brief ready | GDD done, TDD done, art brief done
T3 | Prototype | Functional with no skins, can be bugged
T4 | MVP | Limited quality, but full-featured
T5 | Feature Complete (at quality) | Final assets, polished, no scope cuts left
T6 | Player Ready / Tested | Playtest, alpha, beta, telemetry feedback applied
T7 | Expand | Add to feature / content
T8 | Scale | Productional optimization post-load

## Legend
Cell Color / Section | Meaning
Phase super-headers (row 1 of Plan)
Concept | Concept gate (T0 Ideation)
Pre-production | Pre-production gate (T1-T2)
Production | Early / Mid / End Prod gates (T3-T5)
Release | Alpha / Beta / Launch / First Release
Live Service | LS 1 / LS 2
Discipline | Role group color (row 3 of Plan)
Leadership | CEO, Head of Legal, Head of Finance & Ops, HR Manager
Production | Executive / Producer / Game / Tech / Art Producer
Design | Game Director, Design Leads, Designers, Writer
Art | Art Director, Concept, UI/UX, Character/Env/Prop, Anim, Rig, VFX, TA
Engineering | CTO, Tech Lead, Gameplay/Full Stack/Backend/Network
QA | QA
Audio | Sound Designer
Platform | Platform Team
Sizing key (col C)
S | Small feature
M | Medium feature
L | Large feature
How to use
Plan sheet | Fill in man-days per (feature, gate, role). Cells are blank by default.
Totals row | Bottom of Plan: SUMs each role column per gate.
Headcount row | Total PW / (gate months * 20 working days). Edit GATE_MONTHS in the script if your durations change.
Summary sheet | Auto-rolls up Plan totals per epic per gate.
Adding rows | Insert rows inside an epic block on Plan. Update Total PW SUM ranges if you extend past the current last data row.

## Summary
Epic | Stories | Game Director Min | Game Director Max | Game Design Lead Min | Game Design Lead Max | Level Design Lead Min | Level Design Lead Max | Game Designer Min | Game Designer Max | Combat Designer Min | Combat Designer Max | Level Designer Min | Level Designer Max | Technical Designer Min | Technical Designer Max | Writer Min | Writer Max | Art Director Min | Art Director Max | Concept Artist Min | Concept Artist Max | UI/UX Designer Min | UI/UX Designer Max | Graphic Designer Min | Graphic Designer Max | Character Artist Min | Character Artist Max | Environment Artist Min | Environment Artist Max | Prop Artist Min | Prop Artist Max | Animator Min | Animator Max | Character Rigger Min | Character Rigger Max | VFX Artist Min | VFX Artist Max | Technical Artist Min | Technical Artist Max | CTO Min | CTO Max | Tech Lead Min | Tech Lead Max | Gameplay Developer Min | Gameplay Developer Max | Full Stack Developer Min | Full Stack Developer Max | Backend Developer Min | Backend Developer Max | Network Engineer Min | Network Engineer Max | QA Min | QA Max | Sound Designer Min | Sound Designer Max | Platform Team Min | Platform Team Max | Total Max
Player Build | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 35.5 | 169 | 0 | 0 | 7 | 10 | 0 | 0 | 0.5 | 1 | 0 | 0 | 0 | 5 | 23 | 123 | 0 | 0 | 0 | 0 | 64 | 79 | 0 | 5 | 24 | 44 | 0 | 0 | 0 | 22 | 0 | 30 | 0 | 0 | 0 | 0 | 33 | 244 | 0 | 0 | 22 | 36 | 0 | 0 | 0 | 0 | 29 | 49 | 0 | 0 | 817
World Systems | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 74.5 | 222 | 0 | 10 | 32 | 101 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 4 | 60 | 0 | 0 | 0 | 0 | 1810.4 | 2274.4 | 57.2 | 135.2 | 4 | 20 | 0 | 0 | 0 | 22 | 0 | 100 | 0 | 0 | 0 | 0 | 113.5 | 430 | 0 | 0 | 81 | 179 | 0 | 0 | 0 | 0 | 41.5 | 48 | 0 | 0 | 3607.6
Combat | 322 | 0 | 5 | 0 | 0 | 0 | 0 | 80.5 | 277 | 0 | 5 | 3 | 10 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 12 | 26 | 102 | 0 | 0 | 0 | 15 | 182.8 | 411.4 | 0 | 0 | 97 | 335 | 0 | 65 | 3 | 120 | 0 | 90 | 0 | 0 | 0 | 0 | 157 | 469 | 0 | 0 | 12 | 21 | 0 | 0 | 0 | 0 | 42 | 92 | 0 | 0 | 2030.4
User Space | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 26 | 0 | 0 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 17 | 0 | 0 | 0 | 0 | 598.8 | 696 | 51.4 | 66.4 | 2 | 6 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 310 | 0 | 0 | 16 | 23 | 0 | 0 | 0 | 0 | 4.5 | 9 | 0 | 0 | 1200.4
Items & Inventory | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 47 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11 | 34 | 0 | 3 | 0 | 55 | 0 | 14 | 0 | 0 | 0 | 0 | 24 | 211 | 0 | 0 | 21 | 34 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 524
Player Economy | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 129 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 23 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 339 | 0 | 0 | 40 | 95 | 0 | 0 | 0 | 0 | 7 | 10 | 0 | 0 | 794
Quest System | 114 | 0 | 5 | 0 | 0 | 0 | 0 | 116 | 154 | 0 | 4 | 0 | 0 | 0 | 0 | 4.5 | 39 | 0 | 0 | 0 | 0 | 8 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.5 | 277.5 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0.5 | 11 | 0 | 0 | 666.5
Social & Multiplayer | 145 | 0 | 5 | 0 | 0 | 0 | 0 | 3 | 61 | 0 | 2 | 4 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 91 | 0 | 0 | 0 | 0 | 373.8 | 546.6 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 54 | 394 | 0 | 0 | 87 | 143 | 0 | 0 | 0 | 0 | 1.5 | 2 | 0 | 0 | 1283.6
Game Bibles | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.8 | 31.5 | 5.7 | 8.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110.1
Platform | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 258 | 0 | 0 | 39.5 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338
Live Game | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Partner Build | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Product Publishing | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12 | 0 | 0 | 8 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
TOTAL | 1447 | 0 | 15 | 0 | 0 | 0 | 0 | 342.5 | 1130 | 0 | 25 | 51 | 138 | 0 | 0 | 8 | 49 | 0 | 0 | 22.8 | 114.5 | 89.7 | 752.6 | 0 | 0 | 0 | 15 | 3029.8 | 4007.4 | 108.6 | 319.6 | 144 | 449 | 0 | 68 | 3 | 234 | 0 | 238 | 0 | 0 | 0 | 0 | 542 | 2974.5 | 0 | 0 | 346.5 | 639 | 0 | 0 | 0 | 0 | 126 | 228 | 0 | 0 | 11396.6

## Epics & Features
Epic | Feature | Sizing | Current Tier | Stories
Player Build
| Player Progression | L | T1: R&D | 1
| Skill System | L | T1: R&D | 1
| Achievements & Trophies | M | T1: R&D | 1
| Factions / Reputation | M | T1: R&D | 1
| FTUE | M | T2: GDD/TDD/Brief | 1
| Professions | L | T1: R&D | 1
| Character Management | M | T0: Ideation | 1
| Character Creation & Customization | L | T1: R&D | 1
| Garment System | M | T0: Ideation | 1
| Persona System | M | T1: R&D | 1
| Emote System | S | T0: Ideation | 1
World Systems
| Foam Corruption | M | T2: GDD/TDD/Brief | 1
| Miasma Corruption | M | T0: Ideation | 1
| Water Corruption | M | T0: Ideation | 1
| Crystal Corruption | M | T0: Ideation | 1
| Time Corruption | M | T0: Ideation | 1
| Enemy Corruption | M | T0: Ideation | 1
| Oil Corruption | M | T0: Ideation | 1
| Texture Corruption | M | T0: Ideation | 1
| Environmental Elemental Effects (combination states) | L | T2: GDD/TDD/Brief | 1
| Basic Movement System | L | T1: R&D | 1
| Advanced Traversal | L | T1: R&D | 1
| Navigation | M | T0: Ideation | 1
| Day/Night Cycle | M | T1: R&D | 1
| Dynamic Weather | M | T1: R&D | 1
| Instancing | L | T0: Ideation | 1
| Dungeon Mechanics | L | T0: Ideation | 1
| The Dungeon | L | T0: Ideation | 1
| Partner Portal | M | T1: R&D | 1
| World Bosses | L | T0: Ideation | 1
| Corruption Heatmap | M | T1: R&D | 1
| Biome - Portal Peak | M | T4: MVP | 1
| Biome - Hidden Hills | M | T0: Ideation | 1
| Biome - Farmlands | M | T0: Ideation | 1
| Biome - Mistrun Shore | M | T0: Ideation | 1
| Biome - Whispering Woods | M | T0: Ideation | 1
| Biome - Tranquil Sands | M | T0: Ideation | 1
| Biome - Torrential Vale | M | T0: Ideation | 1
| Biome - Clockwork | M | T0: Ideation | 1
| Biome - Downtime | M | T4: MVP | 1
Combat
| Combat Framework | L | T2: GDD/TDD/Brief | 1
| Ranged Combat | M | T0: Ideation | 1
| Combat AI Behavior | L | T0: Ideation | 1
| Enemies Art | M | T0: Ideation | 1
| PvP Combat | L | T0: Ideation | 1
| Combat Balance & Telemetry | M | T2: GDD/TDD/Brief | 1
| Combat Abilities | L | T1: R&D | 1
| Magic | L | T0: Ideation | 1
| Full Motion Video (FMV) | M | T1: R&D | 1
User Space
| User Space Server & Instance | L | T2: GDD/TDD/Brief | 1
| User Space Decoration | M | T0: Ideation | 1
| P2P / P2G User Space Connection | M | T2: GDD/TDD/Brief | 1
| Building Houses | L | T1: R&D | 1
| Saving House Layouts | M | T0: Ideation | 1
| Partner Portal System (player house) | M | T0: Ideation | 1
| Arcade Cabinet | M | T1: R&D | 1
| Anywhere Door Placement | S | T0: Ideation | 1
Items & Inventory
| Item Core System | L | T2: GDD/TDD/Brief | 1
| Inventory System | M | T2: GDD/TDD/Brief | 1
| Equipment System | M | T0: Ideation | 1
| Loot Distribution | M | T2: GDD/TDD/Brief | 1
| Mounts / Pets | L | T1: R&D | 1
| Banks | M | T0: Ideation | 1
| P2P Item Transfer | M | T0: Ideation | 1
| Consumables | S | T2: GDD/TDD/Brief | 1
| Durable Items | S | T0: Ideation | 1
Player Economy
| Trading System | L | T0: Ideation | 1
| Currency System | M | T0: Ideation | 1
| Auction House | L | T0: Ideation | 1
| In-game Store | M | T0: Ideation | 1
| In-game Economy | L | T0: Ideation | 1
| RMT Game Economy | L | T0: Ideation | 1
| IG / RMT Monitoring System | M | T0: Ideation | 1
Quest System
| Quests Backend / Tooling | L | T2: GDD/TDD/Brief | 1
| Quests as Events | M | T1: R&D | 1
| Quest Multiplayer | L | T1: R&D | 1
| Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | L | T2: GDD/TDD/Brief | 1
| Quest Reward System | M | T0: Ideation | 1
| Quest Log | M | T0: Ideation | 1
| Quest Dialog GUI | M | T0: Ideation | 1
| Quest Narrative Content | L | T2: GDD/TDD/Brief | 1
| In Game Cinematic (IGC) | L | T2: GDD/TDD/Brief | 1
| Meta Quest System | M | T0: Ideation | 1
| Quest Generator System | L | T0: Ideation | 1
| Targeted VO | M | T2: GDD/TDD/Brief | 1
Social & Multiplayer
| Game Chat System | M | T1: R&D | 1
| Friends | M | T1: R&D | 1
| Guilds | L | T1: R&D | 1
| Co-op / Party | M | T1: R&D | 1
| Co-op / Raids | L | T1: R&D | 1
| Dueling | M | T1: R&D | 1
| In-game Mail | S | T2: GDD/TDD/Brief | 1
| Notifications | S | T1: R&D | 1
| Player Config PvP Server | M | T0: Ideation | 1
| LFG / Pick-up Groups | M | T0: Ideation | 1
Game Bibles
| UX/UI Bible | M | T0: Ideation | 1
| Accessibility Guidelines | M | T0: Ideation | 1
| Brand Bible | M | T2: GDD/TDD/Brief | 1
| Art Bible | L | T3: Prototype | 1
| Monetization Bible | M | T0: Ideation | 1
| Red Books (Live Service emergency guidelines) | M | T0: Ideation | 1
Platform
| Player Account Creation / Deletion | M | T2: GDD/TDD/Brief | 1
| Player Account Authentication | M | T2: GDD/TDD/Brief | 1
| Player Account Privacy Settings & Legal | M | T1: R&D | 1
| Player Dashboard - Account Features | M | T1: R&D | 1
| Player Dashboard - Game Dashboard | M | T1: R&D | 1
| Player Dashboard - Friends | M | T1: R&D | 1
| Player Dashboard - Search & Notifications | M | T1: R&D | 1
| Player Dashboard - Marketplace | L | T1: R&D | 1
| Developer Dashboard - Developer Account | M | T1: R&D | 1
| Developer Dashboard - Game Dashboard | M | T1: R&D | 1
| Developer Dashboard - Settings & Support | M | T1: R&D | 1
| Quest Tracking | M | T1: R&D | 1
| Payment Processing (incl. Refunds) | L | T0: Ideation | 1
| Online Services & Backend | L | T0: Ideation | 1
| Launcher & Distribution | L | T2: GDD/TDD/Brief | 1
| Partner Loop | M | T1: R&D | 1
| Game Tool Integration (incl. Game Key Generation) | M | T1: R&D | 1
| Account Level Settings | S | T0: Ideation | 1
| Social Media Support | M | T0: Ideation | 1
Live Game
| Live GDD | M | T0: Ideation | 1
| Content | L | T0: Ideation | 1
| Forecast | M | T0: Ideation | 1
| Analytics & BI | L | T0: Ideation | 1
| Sales Dashboard | M | T0: Ideation | 1
| Telemetry | L | T0: Ideation | 1
| Live Service Event Plan | L | T0: Ideation | 1
Partner Build
| Partner = Feature definition | S | T0: Ideation | 1
| Sign Partner | S | T0: Ideation | 1
| Partner Brief | M | T0: Ideation | 1
| Partner Design Doc | M | T0: Ideation | 1
| Partner TDD | M | T0: Ideation | 1
| Partner Art Brief | M | T0: Ideation | 1
| Partner Build | L | T0: Ideation | 1
| Partner Integration | M | T0: Ideation | 1
Product Publishing
| Web Presence | M | T0: Ideation | 1
| Website | M | T0: Ideation | 1
| Community Persona | M | T0: Ideation | 1
| Title Identity | M | T0: Ideation | 1
| Player Support | M | T0: Ideation | 1
| Go-To-Market Strategy & Implementation | L | T0: Ideation | 1
| 3rd-party Store Publishing | M | T0: Ideation | 1

## Resource Planner
Epic | Feature | Story | Role | Team | Min Days | Max Days | Primary Assignee | Primary Days | Secondary Assignee | Secondary Days | Unallocated
Player Build
Player Progression | Player Progression | Player level up documentation | Game Designer | Design ¦ Game design | 1 | 14 |  | 0 |  | 0 | 14
Player Progression | Player Progression | Player level up configuration | Game Designer | Design ¦ Game design | 0.5 | 15 |  | 0 |  | 0 | 15
Player Progression | Player Progression | player level up integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | Player level up UI | UI/UX Designer | Art ¦ UX/UI | 2 | 3 |  | 0 |  | 0 | 3
Player Progression | Player Progression | Character stats documentation | Game Designer | Design ¦ Game design | 5 | 5 |  | 0 |  | 0 | 5
Player Progression | Player Progression | Character stats implementation | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | Character stats configuration in connection with other systems | Game Designer | Design ¦ Game design | 1 | 10 |  | 0 |  | 0 | 10
Player Progression | Player Progression | Character stats UI | UI/UX Designer | Art ¦ UX/UI |  | 15 |  | 0 |  | 0 | 15
Player Progression | Player Progression | Level up & Stats QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | Player level up documentation | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | Player level up configuration | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | player level up integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | Earn different types of EXP depending on objective | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Player Progression | Player Progression | Update player level and exp with (player data service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Player Progression | Player Progression | Fetch player level and exp from (player data service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Player Progression | Player Progression | Fetch and update UI for player level and exp | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Player Progression | Player Progression | Player level up UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | Character stats documentation | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | Character stats implementation | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | Increase stat when player level up | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Player Progression | Player Progression | Update stats UI | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Player Progression | Player Progression | Update player stats in backend (player data service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Player Progression | Player Progression | fetch player stats from backend service (player data service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Player Progression | Player Progression | Integrate stat system with other systems | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 20 |  | 0 |  | 0 | 20
Player Progression | Player Progression | Items give u stats | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Player Progression | Player Progression | Character stats configuration in connection with other systems | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | Character stats UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Player Progression | Player Progression | Level up & Stats QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Skill System | Skill System | Skill Tree UI Audio | Sound Designer | Audio ¦ Audio | 7 | 8 |  | 0 |  | 0 | 8
Skill System | Skill System | Skills in-game audio | Sound Designer | Audio ¦ Audio | 7 | 8 |  | 0 |  | 0 | 8
Skill System | Skill System | Skill System Documentation | Game Designer | Design ¦ Game design | 4 | 15 |  | 0 |  | 0 | 15
Skill System | Skill System | Skill System Implementation | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Skill System | Skill System | Skill System Configuration | Game Designer | Design ¦ Game design | 4 | 5 |  | 0 |  | 0 | 5
Skill System | Skill System | Skill System UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Skill System | Skill System | Skill system QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Skill System | Skill System | Skill System Documentation | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Skill System | Skill System | Skill System Implementation | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Skill System | Skill System | Connect skill tree to UI | Gameplay Developer | Engineering ¦ Gameplay Engineering | 4 | 6 |  | 0 |  | 0 | 6
Skill System | Skill System | Add new abilities to skill tree | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
Skill System | Skill System | Add new weapons to skill tree | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Skill System | Skill System | Fetech all skill trees from backend | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Skill System | Skill System | Update all skill trees from backend | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Skill System | Skill System | Sync all skill trees to backend, tool | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Skill System | Skill System | Create weapon skill tree / nodes in (internal dashboard service) | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Skill System | Skill System | Remove weapon skill tree / nodes in (internal dashboard service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Skill System | Skill System | Update weapon skill tree / nodes in (internal dashboard service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Skill System | Skill System | Fetch weapon skill tree / nodes in (internal dashboard service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Skill System | Skill System | Create new collection for weapon skill tree (player data service) | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Skill System | Skill System | Update player skill tree per weapon (player data service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Skill System | Skill System | Fetch player skill tree per weapon (player data service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Skill System | Skill System | endpoint to reset skill tree for weapons | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Skill System | Skill System | Create frontend for skill tree in internal dashboard | Backend Developer | Engineering ¦ Backend Engineering | 5 | 7 |  | 0 |  | 0 | 7
Skill System | Skill System | Skill System Configuration | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Skill System | Skill System | Skill System UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Skill System | Skill System | Skill system QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Achievements & Trophies | Achievements & Trophies | Trophies | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Tutorial Cave Layout Fixes | Level Designer | Design ¦ Level design | 7 | 10 |  | 0 |  | 0 | 10
FTUE | FTUE | Tutorial cave set dressing fixes | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Tutorial Cave lighting | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Tutorial cave Ambience & SFX | Sound Designer | Audio ¦ Audio | 5 | 7 |  | 0 |  | 0 | 7
FTUE | FTUE | Tutorial Configuration/set up/texts | Game Designer | Design ¦ Game design | 2 | 3 |  | 0 |  | 0 | 3
FTUE | FTUE | Tutorial UI | UI/UX Designer | Art ¦ UX/UI | 4 | 6 |  | 0 |  | 0 | 6
FTUE | FTUE | Tutorial VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Controls UI | UI/UX Designer | Art ¦ UX/UI | 2 | 4 |  | 0 |  | 0 | 4
FTUE | FTUE | Tutorial cave contents | Game Designer | Design ¦ Game design | 1 | 2 |  | 0 |  | 0 | 2
FTUE | FTUE | Narrative | Writer | Design ¦ Narrative | 0.5 | 1 |  | 0 |  | 0 | 1
FTUE | FTUE | Tutorial QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Tutorial Cave Layout Fixes | Level Designer | Design ¦ Level design |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Tutorial cave set dressing fixes | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Tutorial Cave lighting | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Tutorial cave Ambience & SFX | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Tutorial Configuration/set up/texts | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Tutorial UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Controls UI | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | Tutorial QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
FTUE | FTUE | FTUE Cave | Environment Artist | Art ¦ Environment Art | 32 | 32 |  | 0 |  | 0 | 32
Professions | Professions | Component System Design | Game Designer | Design ¦ Game design | 2 | 5 |  | 0 |  | 0 | 5
Professions | Professions | Crafted Weapon Parts in-game Audio | Sound Designer | Audio ¦ Audio | 5 | 5 |  | 0 |  | 0 | 5
Professions | Professions | Forge Crafting Audio | Sound Designer | Audio ¦ Audio | 3 | 5 |  | 0 |  | 0 | 5
Professions | Professions | Forge Documentation | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
Professions | Professions | Forge Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge UI | UI/UX Designer | Art ¦ UX/UI | 5 | 10 |  | 0 |  | 0 | 10
Professions | Professions | Forge VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Professions | Professions | DA combination setup | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Professions | Professions | Crafting Desk | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge Props | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fishing Integration | Game Designer | Design ¦ Game design | 3 | 3 |  | 0 |  | 0 | 3
Professions | Professions | Fishing Rod model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fish model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fishing spot sign model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fishing UI | UI/UX Designer | Art ¦ UX/UI |  | 3 |  | 0 |  | 0 | 3
Professions | Professions | Fishing Spot SFX | Sound Designer | Audio ¦ Audio | 0 | 0 |  | 0 |  | 0 | 0
Professions | Professions | Fishing VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fishing QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge Documentation | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Professions | Professions | DA combination setup | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Professions | Professions | Crafting Desk | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge Props | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Forge QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Professions | Professions | Review fishing code | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Professions | Professions | Fishing Integration | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fishing Rod model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fish model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fishing spot sign model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fishing UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fishing Spot VFX | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Professions | Professions | Fishing QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Professions | Professions | Gathering | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Professions | Professions | Crafting | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Character Creation & Customization | Character Creation & Customization | Faction: Clothing Variations | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Character Creation & Customization | Character Creation & Customization | Faction: Banners | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Character Creation & Customization | Character Creation & Customization | Faction: Icons | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Character Creation & Customization | Character Creation & Customization | Faction: Insignias | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Character Creation & Customization | Character Creation & Customization | Base Body (MVP DONE) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Character Creation & Customization | Character Creation & Customization | Base Faces (MVP DONE) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Character Creation & Customization | Character Creation & Customization | Fantasy Races | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Character Creation & Customization | Character Creation & Customization | Ethnicity Variations | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Character Creation & Customization | Character Creation & Customization | Char Creation System | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Garment System GDD/TDD | Game Designer | Design ¦ Game design | 4 | 7 |  | 0 |  | 0 | 7
Garment System | Garment System | Vertical Slice garments | Game Designer | Design ¦ Game design | 5 | 5 |  | 0 |  | 0 | 5
Garment System | Garment System | Garment System Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Garment System UI | UI/UX Designer | Art ¦ UX/UI | 10 | 14 |  | 0 |  | 0 | 14
Garment System | Garment System | Equipment Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Equipment Models | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Garment Type SFX | Sound Designer | Audio ¦ Audio | 2 | 3 |  | 0 |  | 0 | 3
Garment System | Garment System | Equipment Stats integrated with character stats | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Garment System QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Equipment QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Garment System GDD/TDD | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Garment System Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Equip and unequped based on garment system | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Garment System | Garment System | Garment System UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Equiment Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Equipment Models | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Equipment Stats integrated with character stats | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Garment System | Garment System | Cull occluded body parts | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Setup budget for skining and cloth sim | Animator | Art ¦ Animation & Rigging | 5 | 7 |  | 0 |  | 0 | 7
Garment System | Garment System | Freeze cloth sim | Animator | Art ¦ Animation & Rigging | 3 | 5 |  | 0 |  | 0 | 5
Garment System | Garment System | Maya tool to represent cloth sim like unreal | Animator | Art ¦ Animation & Rigging | 10 | 15 |  | 0 |  | 0 | 15
Garment System | Garment System | Move socket based on clothing type | Animator | Art ¦ Animation & Rigging | 5 | 10 |  | 0 |  | 0 | 10
Garment System | Garment System | Setup capsules for cloth collision on character | Animator | Art ¦ Animation & Rigging | 1 | 2 |  | 0 |  | 0 | 2
Garment System | Garment System | Garment System QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Equipment QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Garment System Options | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Garment Sets | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Weapon Sets | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Weapon Parts | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Armour Sets | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Partner Skins | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Garment System | Garment System | Skins | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
World Systems
Foam Corruption | Foam Corruption | Corrupted Vines | Game Designer | Design ¦ Game design | 0.5 | 1 |  | 0 |  | 0 | 1
Foam Corruption | Foam Corruption | Corrupted texture | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Vine NPC Narrative | Writer | Design ¦ Narrative |  | 1 |  | 0 |  | 0 | 1
Foam Corruption | Foam Corruption | Vines Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Corrupted VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Corrupted vines behavior & visual QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption Techart | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption cleansing animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption cleansing weapon | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption SFX, VFX design | Game Designer | Design ¦ Game design | 3 | 3 |  | 0 |  | 0 | 3
Foam Corruption | Foam Corruption | Foam Corruption SFX | Sound Designer | Audio ¦ Audio | 2 | 2 |  | 0 |  | 0 | 2
Foam Corruption | Foam Corruption | Foam Corruption QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption | Game Designer | Design ¦ Game design | 10 | 40 |  | 0 |  | 0 | 40
Foam Corruption | Foam Corruption | Timed Corruption Design | Game Designer | Design ¦ Game design | 2 | 10 |  | 0 |  | 0 | 10
Foam Corruption | Foam Corruption | Timed Corruption TechArt | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption Server & Multiplayer | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption 3D Assets | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption SFX | Sound Designer | Audio ¦ Audio | 3 | 5 |  | 0 |  | 0 | 5
Foam Corruption | Foam Corruption | Timed Corruption QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Corrupted Vines | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Corrupted texture | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Vines Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Corrupted VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Corrupted vines behavior & visual QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption Techart | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption integration | Gameplay Developer | Engineering ¦ Gameplay Engineering | 4 | 5 |  | 0 |  | 0 | 5
Foam Corruption | Foam Corruption | Foam Corruption VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption cleansing animations | Animator | Art ¦ Animation & Rigging | 2 | 3 |  | 0 |  | 0 | 3
Foam Corruption | Foam Corruption | Trigger objective when clean is done | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Foam Corruption | Foam Corruption | Quest tracking system | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Foam Corruption | Foam Corruption | Make corruption come back after a set time | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Foam Corruption | Foam Corruption | Link with corruption gun | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
Foam Corruption | Foam Corruption | Foam Corruption cleansing weapon | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption SFX | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Foam Corruption QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption TechArt | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Replicate animation | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Foam Corruption | Foam Corruption | Trigger building the bridge | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Foam Corruption | Foam Corruption | Trigger VFX when effect is completed | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Foam Corruption | Foam Corruption | Timer to revert bridge to broken state | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Foam Corruption | Foam Corruption | Toggle path once puzzle is completed to allow or disallow player from crossing the bridge by replicating collision | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 1 |  | 0 |  | 0 | 1
Foam Corruption | Foam Corruption | Timed Corruption 3D Assets | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption SFX | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Timed Corruption QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | VFX Tech | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Foam Corruption | Foam Corruption | Fluid Ninja Tech R&D | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Basic Movement System | Basic Movement System | Locomotion Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Basic Movement System | Basic Movement System | Walk | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Basic Movement System | Basic Movement System | Run | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Basic Movement System | Basic Movement System | Sprint | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Basic Movement System | Basic Movement System | Jump | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Basic Movement System | Basic Movement System | Double Jump | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Basic Movement System | Basic Movement System | Iteration | Game Designer | Design ¦ Game design |  | 5 |  | 0 |  | 0 | 5
Basic Movement System | Basic Movement System | Locomotion QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Basic Movement System | Basic Movement System | Locomotion Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Basic Movement System | Basic Movement System | Walk | Gameplay Developer | Engineering ¦ Gameplay Engineering | 0.5 | 1 |  | 0 |  | 0 | 1
Basic Movement System | Basic Movement System | Run | Gameplay Developer | Engineering ¦ Gameplay Engineering | 0.5 | 1 |  | 0 |  | 0 | 1
Basic Movement System | Basic Movement System | Sprint | Gameplay Developer | Engineering ¦ Gameplay Engineering | 0.5 | 1 |  | 0 |  | 0 | 1
Basic Movement System | Basic Movement System | Jump | Gameplay Developer | Engineering ¦ Gameplay Engineering | 0.5 | 1 |  | 0 |  | 0 | 1
Basic Movement System | Basic Movement System | Double Jump | Gameplay Developer | Engineering ¦ Gameplay Engineering | 0.5 | 1 |  | 0 |  | 0 | 1
Basic Movement System | Basic Movement System | Locomotion QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Glider Stamina UI | UI/UX Designer | Art ¦ UX/UI | 2 | 2 |  | 0 |  | 0 | 2
Advanced Traversal | Advanced Traversal | Gliding Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Gliding Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Gliding Animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Gliding SFX | Sound Designer | Audio ¦ Audio | 1 | 2 |  | 0 |  | 0 | 2
Advanced Traversal | Advanced Traversal | Gliding VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Gliding Device | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Gliding QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Portals spawning & Xyron moving through portals | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Narrative for Xyron quests | Writer | Design ¦ Narrative | 1 | 2 |  | 0 |  | 0 | 2
Advanced Traversal | Advanced Traversal | Spawning portals SFX | Sound Designer | Audio ¦ Audio | 2 | 4 |  | 0 |  | 0 | 4
Advanced Traversal | Advanced Traversal | 5 or 6 mini quests | Game Designer | Design ¦ Game design | 5 | 8 |  | 0 |  | 0 | 8
Advanced Traversal | Advanced Traversal | Xyron voiceover narrative | Writer | Design ¦ Narrative | 0.5 | 2 |  | 0 |  | 0 | 2
Advanced Traversal | Advanced Traversal | Xyron voiceover | Sound Designer | Audio ¦ Audio | 7 | 8 |  | 0 |  | 0 | 8
Advanced Traversal | Advanced Traversal | Xyron/portals spawning QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Safety System | Game Designer | Design ¦ Game design | 3 | 3 |  | 0 |  | 0 | 3
Advanced Traversal | Advanced Traversal | Archway race design | Game Designer | Design ¦ Game design |  | 3 |  | 0 |  | 0 | 3
Advanced Traversal | Advanced Traversal | Persistent leaderboards | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Archway Placement | Game Designer | Design ¦ Game design | 1 | 7 |  | 0 |  | 0 | 7
Advanced Traversal | Advanced Traversal | Archway Models | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Archway VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Win Fanfare VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Archway SFX | Sound Designer | Audio ¦ Audio | 0 | 0 |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Archway QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Gliding Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Convert gliding to blend space | Animator | Art ¦ Animation & Rigging | 1 | 1 |  | 0 |  | 0 | 1
Advanced Traversal | Advanced Traversal | Spawn gliding actor | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Advanced Traversal | Advanced Traversal | Check if ability is unlock to glide | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 1 |  | 0 |  | 0 | 1
Advanced Traversal | Advanced Traversal | Gliding Animations | Animator | Art ¦ Animation & Rigging | 1 | 1 |  | 0 |  | 0 | 1
Advanced Traversal | Advanced Traversal | Gliding VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Gliding Device | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Gliding QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Portals spawning & Xyron moving through portals | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
Advanced Traversal | Advanced Traversal | Xyron/portals spawning QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Persistent leaderboards | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Advanced Traversal | Advanced Traversal | Archway Placement | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Archway Models | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Archway VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Win Fanfare VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Archway SFX | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Archway QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Gliding System | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Advanced Traversal | Advanced Traversal | Grappling System | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | World Map | Game Designer | Design ¦ Game design | 10 | 10 |  | 0 |  | 0 | 10
Navigation | Navigation | Map markers sfx | Sound Designer | Audio ¦ Audio | 0.5 | 1 |  | 0 |  | 0 | 1
Navigation | Navigation | World Map background asset | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | World Map asset integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | World Map UI | UI/UX Designer | Art ¦ UX/UI |  | 10 |  | 0 |  | 0 | 10
Navigation | Navigation | Quest markers support | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Map QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Fog-of-war | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Fog of war QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Minimap | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Minimap Levels | Game Designer | Design ¦ Game design | 5 | 5 |  | 0 |  | 0 | 5
Navigation | Navigation | Minimap UI | UI/UX Designer | Art ¦ UX/UI |  | 10 |  | 0 |  | 0 | 10
Navigation | Navigation | Minimap assets | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Minimap quest navigation support | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Minimap QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Compass | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Compass UI | UI/UX Designer | Art ¦ UX/UI | 2 | 10 |  | 0 |  | 0 | 10
Navigation | Navigation | Compass Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Compass QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | World Map | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | World Map background asset | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | World Map asset integration | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Navigation | Navigation | World Map UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Indoor Map | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 7 |  | 0 |  | 0 | 7
Navigation | Navigation | Special NPCs positions | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Navigation | Navigation | Zoom out/in | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Navigation | Navigation | Party player position | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Navigation | Navigation | POI names | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 1 |  | 0 |  | 0 | 1
Navigation | Navigation | Quest markers and objectives support | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Navigation | Navigation | Map QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Fog-of-war | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Fog of war shader | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Create fog of war grid | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Navigation | Navigation | Hide/Unhide markers that are in fog of war | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Navigation | Navigation | Fog of war changes based on player visited locations | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Navigation | Navigation | fetch fog of war and update it from unreal side | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Navigation | Navigation | Sync fog of war to backend | Backend Developer | Engineering ¦ Backend Engineering | 5 | 5 |  | 0 |  | 0 | 5
Navigation | Navigation | Fog of war QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Minimap | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Minimap UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Minimap assets | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Minimap quest navigation support | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Navigation | Navigation | Special NPCs positions | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Navigation | Navigation | Zoom out/in | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 1 |  | 0 |  | 0 | 1
Navigation | Navigation | Party player position | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Navigation | Navigation | Minimap QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Compass | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Compass UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Show distance to objective | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Navigation | Navigation | Party player distance | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Navigation | Navigation | Show POI distance | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Navigation | Navigation | Special NPCs distance | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Navigation | Navigation | Show quest distance | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Navigation | Navigation | Show or hide compass from options menu | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Navigation | Navigation | Rotate compass with camera | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Navigation | Navigation | Compass QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Lighting Tech | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Atmospherics | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Navigation | Navigation | Water System | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | GDD Documentation | Game Designer | Design ¦ Game design | 3 | 2 |  | 0 |  | 0 | 2
Instancing | Instancing | Instancing Documentation | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | User Space Instancing support | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Guild House instancing support | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Dungeon Instancing | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Zones Instancing | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Instancing QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Research phasing system | Backend Developer | Engineering ¦ Backend Engineering | 1 | 5 |  | 0 |  | 0 | 5
Instancing | Instancing | Research phasing system | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Instancing | Instancing | Document phasing system | Backend Developer | Engineering ¦ Backend Engineering | 2 | 5 |  | 0 |  | 0 | 5
Instancing | Instancing | Document phasing system | Backend Developer | Engineering ¦ Backend Engineering | 1 | 7 |  | 0 |  | 0 | 7
Instancing | Instancing | Create phasing system | Gameplay Developer | Engineering ¦ Gameplay Engineering | 7 | 20 |  | 0 |  | 0 | 20
Instancing | Instancing | Create phasing system | Backend Developer | Engineering ¦ Backend Engineering | 3 | 50 |  | 0 |  | 0 | 50
Instancing | Instancing | Manage player session | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Record if player is online in redis | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Instancing | Instancing | Create a session service | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Instancing | Instancing | Instancing Documentation | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Custom HPA for Kubernetes | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Create Nodejs service | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Instancing | Instancing | Integrate Kubernetes API | Backend Developer | Engineering ¦ Backend Engineering | 3 | 5 |  | 0 |  | 0 | 5
Instancing | Instancing | Create metrics to scale up and down | Backend Developer | Engineering ¦ Backend Engineering | 4 | 6 |  | 0 |  | 0 | 6
Instancing | Instancing | Create rules when to merge instances | Backend Developer | Engineering ¦ Backend Engineering | 4 | 6 |  | 0 |  | 0 | 6
Instancing | Instancing | Setup Kubernetes on Azure | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Setup azure | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Custom service to handle dungeons | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Create a service in nodejs | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Instancing | Instancing | Create a list of all dungeons that are currently running in redis | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Instancing | Instancing | Search for dungeon by id | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Fetch dungeon ip by id | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Delete dungeon instance | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Create dungeon instance | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Instancing | Instancing | Call backend to figure out which dungeon to connect to | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Instancing | Instancing | Player general stat before disconnecting service | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Create a service in nodejs | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Instancing | Instancing | Create a way to save player stat (which server they were connected to last, which party were they connected to, etc..) before disconnecting | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Instancing | Instancing | Custom service for overworld zones | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Create a service in nodejs | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Instancing | Instancing | Create a list of all overworld zones that are currently running in redis | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Instancing | Instancing | Search for overworld zones by id | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Fetch overworld zones ip by id | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Delete overworld zones instance | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Create overworld zones instance | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Call backend to figure out which overworld zones to connect to | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Inform UE server that a player is getting migrated to another UE server | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Instancing | Instancing | Inform UE server that a player is getting migrated to another UE server | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Instancing | Instancing | Create a queue service | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Instancing | Instancing | Create Nodejs service | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Instancing | Instancing | Instancing QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Dungeons documentation | Game Designer | Design ¦ Game design | 2 | 5 |  | 0 |  | 0 | 5
Dungeon Mechanics | Dungeon Mechanics | Narrative | Writer | Design ¦ Narrative | 0.5 | 1 |  | 0 |  | 0 | 1
Dungeon Mechanics | Dungeon Mechanics | Multiplayer enviromental puzzle design | Game Designer | Design ¦ Game design | 5 | 12 |  | 0 |  | 0 | 12
Dungeon Mechanics | Dungeon Mechanics | Multiplayer enviromental puzzle layout | Level Designer | Design ¦ Level design | 4 | 10 |  | 0 |  | 0 | 10
Dungeon Mechanics | Dungeon Mechanics | Multiplayer enviromental puzzle integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Puzzles QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | BD Quest design | Game Designer | Design ¦ Game design | 2 | 5 |  | 0 |  | 0 | 5
Dungeon Mechanics | Dungeon Mechanics | BD Quest narrative design | Game Designer | Design ¦ Game design | 3 | 8 |  | 0 |  | 0 | 8
Dungeon Mechanics | Dungeon Mechanics | Partner Shop Blockout | Level Designer | Design ¦ Level design | 3 | 4 |  | 0 |  | 0 | 4
Dungeon Mechanics | Dungeon Mechanics | BD Quest integration | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Partner themed shop concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Partner themed shop model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Partner themed shop props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Used Partner Portals | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Assets & Portals Models | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Portals Placement in the shop | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | BD Quest themed reward model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | BD quest special macguffin reward | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Special item design | Game Designer | Design ¦ Game design | 1 | 1 |  | 0 |  | 0 | 1
Dungeon Mechanics | Dungeon Mechanics | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Tech art | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Behavior implementation | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Audio | Sound Designer | Audio ¦ Audio | 0.5 | 1 |  | 0 |  | 0 | 1
Dungeon Mechanics | Dungeon Mechanics | UI | UI/UX Designer | Art ¦ UX/UI |  | 5 |  | 0 |  | 0 | 5
Dungeon Mechanics | Dungeon Mechanics | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Dungeons documentation | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Join dungeon | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Dungeon Mechanics | Dungeon Mechanics | Dungeon UI | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Dungeon Mechanics | Dungeon Mechanics | Transition to dungeon | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Dungeon Mechanics | Dungeon Mechanics | Dungeon gameplay loop | Gameplay Developer | Engineering ¦ Gameplay Engineering | 10 | 20 |  | 0 |  | 0 | 20
Dungeon Mechanics | Dungeon Mechanics | Dungeon character | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Dungeon Mechanics | Dungeon Mechanics | Dungeon end reward and condition | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Dungeon Mechanics | Dungeon Mechanics | dungeon character respawn | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Dungeon Mechanics | Dungeon Mechanics | dungeon transition to out of dungeon | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Dungeon Mechanics | Dungeon Mechanics | Multiplayer enviromental puzzle design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Multiplayer enviromental puzzle layout | Level Designer | Design ¦ Level design |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Multiplayer enviromental puzzle integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Make puzzle | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Dungeon Mechanics | Dungeon Mechanics | Puzzles QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | BD Quest design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | BD Quest integration | Backend Developer | Engineering ¦ Backend Engineering | 5 | 10 |  | 0 |  | 0 | 10
Dungeon Mechanics | Dungeon Mechanics | Partner themed shop concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Partner themed shop model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Partner themed shop props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Used Partner Portals | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Assets & Portals Models | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Portals Placement in the shop | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | BD Quest themed reward model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | BD quest special macguffin reward | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Special item design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Tech art | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Behavior implementation | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Dungeon Mechanics | Dungeon Mechanics | Audio | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Dungeon Mechanics | Dungeon Mechanics | Bug Dungeon | Environment Artist | Art ¦ Environment Art | 11.4 | 17.1 |  | 0 |  | 0 | 17.1
Dungeon Mechanics | Dungeon Mechanics | Bugged Dungeon Shop | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
The Dungeon | The Dungeon | Dungeon (1 medium) | Environment Artist | Art ¦ Environment Art | 68.6 | 68.6 |  | 0 |  | 0 | 68.6
Partner Portal | Partner Portal | Partner shop portal placement | Game Designer | Design ¦ Game design |  | 1 |  | 0 |  | 0 | 1
Partner Portal | Partner Portal | Portals design | Game Designer | Design ¦ Game design |  | 1 |  | 0 |  | 0 | 1
Partner Portal | Partner Portal | Partner Portal Integration | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Portal | Partner Portal | Partner Portal VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Partner Portal | Partner Portal | Partner Portal Enviro Art | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Partner Portal | Partner Portal | Partner Portal Integration | Backend Developer | Engineering ¦ Backend Engineering | 10 | 15 |  | 0 |  | 0 | 15
Partner Portal | Partner Portal | Partner Portal Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Partner Portal | Partner Portal | Partner Portal VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Partner Portal | Partner Portal | Partner Portal Enviro Art | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP Design | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
Biome - Portal Peak | Biome - Portal Peak | PP Blockout | Level Designer | Design ¦ Level design | 10 | 20 |  | 0 |  | 0 | 20
Biome - Portal Peak | Biome - Portal Peak | PP Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP Props Build | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP layout | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP Audio | Sound Designer | Audio ¦ Audio | 14 | 15 |  | 0 |  | 0 | 15
Biome - Portal Peak | Biome - Portal Peak | Portal Peak QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Design | Game Designer | Design ¦ Game design | 1 | 1 |  | 0 |  | 0 | 1
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Blockout | Level Designer | Design ¦ Level design | 1 | 15 |  | 0 |  | 0 | 15
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Props Build | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension layout | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Audio | Sound Designer | Audio ¦ Audio | 0.5 | 1 |  | 0 |  | 0 | 1
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Final Tower Design | Game Designer | Design ¦ Game design | 1 | 1 |  | 0 |  | 0 | 1
Biome - Portal Peak | Biome - Portal Peak | Final Tower Blockout | Level Designer | Design ¦ Level design | 1 | 5 |  | 0 |  | 0 | 5
Biome - Portal Peak | Biome - Portal Peak | Final Tower Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Final Tower Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Final Tower Props Build | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Final Tower layout | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Final Tower Audio | Sound Designer | Audio ¦ Audio | 3 | 2 |  | 0 |  | 0 | 2
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP Blockout | Level Designer | Design ¦ Level design |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP Props Build | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP layout | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | PP Audio | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Peak QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Blockout | Level Designer | Design ¦ Level design |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Props Build | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension layout | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension Audio | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Portal Peak | Biome - Portal Peak | Architecture Kit - Mythcore | Environment Artist | Art ¦ Environment Art | 5.7 | 11.4 |  | 0 |  | 0 | 11.4
Biome - Portal Peak | Biome - Portal Peak | Architecture Kit - Mythcore Ruins | Environment Artist | Art ¦ Environment Art | 5.7 | 11.4 |  | 0 |  | 0 | 11.4
Biome - Portal Peak | Biome - Portal Peak | Architecture Kit - Fantasy | Environment Artist | Art ¦ Environment Art | 68.6 | 114.3 |  | 0 |  | 0 | 114.3
Biome - Portal Peak | Biome - Portal Peak | Architecture Kit - Deck/Scaffolding | Environment Artist | Art ¦ Environment Art | 11.4 | 17.1 |  | 0 |  | 0 | 17.1
Biome - Portal Peak | Biome - Portal Peak | Architecture Kit - Wooden Camp | Environment Artist | Art ¦ Environment Art | 17.1 | 22.9 |  | 0 |  | 0 | 22.9
Biome - Portal Peak | Biome - Portal Peak | Portal Dimension | Environment Artist | Art ¦ Environment Art | 28.6 | 28.6 |  | 0 |  | 0 | 28.6
Biome - Portal Peak | Biome - Portal Peak | Tower Interior | Environment Artist | Art ¦ Environment Art | 45.7 | 60 |  | 0 |  | 0 | 60
Biome - Portal Peak | Biome - Portal Peak | Rock Kits | Environment Artist | Art ¦ Environment Art | 27.4 | 27.4 |  | 0 |  | 0 | 27.4
Biome - Portal Peak | Biome - Portal Peak | Props - Gritcore | Environment Artist | Art ¦ Environment Art | 28.6 | 57.1 |  | 0 |  | 0 | 57.1
Biome - Portal Peak | Biome - Portal Peak | Props - Fantasy Exterior | Environment Artist | Art ¦ Environment Art | 28.6 | 57.1 |  | 0 |  | 0 | 57.1
Biome - Portal Peak | Biome - Portal Peak | Biomes - Cave | Environment Artist | Art ¦ Environment Art | 50 | 57.1 |  | 0 |  | 0 | 57.1
Biome - Portal Peak | Biome - Portal Peak | Tower Exterior (Epic POI) | Environment Artist | Art ¦ Environment Art | 81.1 | 91.4 |  | 0 |  | 0 | 91.4
Biome - Portal Peak | Biome - Portal Peak | Cave Interior (Med POI) | Environment Artist | Art ¦ Environment Art | 32 | 42.9 |  | 0 |  | 0 | 42.9
Biome - Portal Peak | Biome - Portal Peak | Bridge (Small POI) | Environment Artist | Art ¦ Environment Art | 11.4 | 17.1 |  | 0 |  | 0 | 17.1
Biome - Portal Peak | Biome - Portal Peak | Mediterranean Biome | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Design | Game Designer | Design ¦ Game design | 4 | 5 |  | 0 |  | 0 | 5
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Blockout | Level Designer | Design ¦ Level design | 3 | 15 |  | 0 |  | 0 | 15
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Props Build | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills layout | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Audio | Sound Designer | Audio ¦ Audio | 4 | 4 |  | 0 |  | 0 | 4
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Blockout | Level Designer | Design ¦ Level design |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Props Build | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills layout | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills Audio | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Two Hills QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Hidden Hills | Biome - Hidden Hills | The Big Battle Hill (Epic POI) | Environment Artist | Art ¦ Environment Art | 81.1 | 91.4 |  | 0 |  | 0 | 91.4
Biome - Farmlands | Biome - Farmlands | New Zone | Environment Artist | Art ¦ Environment Art | 81.1 | 92.6 |  | 0 |  | 0 | 92.6
Biome - Farmlands | Biome - Farmlands | Biomes - New Zone | Environment Artist | Art ¦ Environment Art | 50 | 57.1 |  | 0 |  | 0 | 57.1
Biome - Farmlands | Biome - Farmlands | Drifter's Cross (Small POI) | Environment Artist | Art ¦ Environment Art | 45.7 | 45.7 |  | 0 |  | 0 | 45.7
Biome - Farmlands | Biome - Farmlands | Lush Biome | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Design | Game Designer | Design ¦ Game design | 2 | 2 |  | 0 |  | 0 | 2
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Blockout | Level Designer | Design ¦ Level design | 1 | 4 |  | 0 |  | 0 | 4
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Props Build | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot layout | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Audio | Sound Designer | Audio ¦ Audio | 4 | 3 |  | 0 |  | 0 | 3
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Spot QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Blockout | Level Designer | Design ¦ Level design |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Props Build | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot layout | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty Spot Audio | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Spot QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Whispering Woods | Biome - Whispering Woods | Waterfall Beauty (Small POI) | Environment Artist | Art ¦ Environment Art | 11.4 | 17.1 |  | 0 |  | 0 | 17.1
Biome - Downtime | Biome - Downtime | Multiplayer interactions (toasts) | Game Designer | Design ¦ Game design | 2 | 2 |  | 0 |  | 0 | 2
Biome - Downtime | Biome - Downtime | Downtime Shops closed area | Game Designer | Design ¦ Game design | 2 | 2 |  | 0 |  | 0 | 2
Biome - Downtime | Biome - Downtime | Downtime Social Hub Area Blockout | Level Designer | Design ¦ Level design | 6 | 6 |  | 0 |  | 0 | 6
Biome - Downtime | Biome - Downtime | Downtime Tavern Blockout | Level Designer | Design ¦ Level design | 3 | 7 |  | 0 |  | 0 | 7
Biome - Downtime | Biome - Downtime | Downtime Tavern Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Tavern Model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Tavern Props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | NPC behaviour document | Game Designer | Design ¦ Game design |  | 2 |  | 0 |  | 0 | 2
Biome - Downtime | Biome - Downtime | Downtime NPC placement | Game Designer | Design ¦ Game design | 4 | 5 |  | 0 |  | 0 | 5
Biome - Downtime | Biome - Downtime | Downtime shops storefronts models | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Auction House storefront model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Bank storefront model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Barbersmith storefront model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Tavern Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Tavern Model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Tavern Props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime NPC placement | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime shops storefronts models | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Auction House storefront model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Bank storefront model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Barbersmith storefront model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Biome - Downtime | Biome - Downtime | Downtime Zone | Environment Artist | Art ¦ Environment Art | 92.6 | 114.3 |  | 0 |  | 0 | 114.3
Biome - Downtime | Biome - Downtime | Biomes - Downtime | Environment Artist | Art ¦ Environment Art | 50 | 57.1 |  | 0 |  | 0 | 57.1
Biome - Downtime | Biome - Downtime | Env Prop Kit - Tavern | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Combat
Combat Framework | Combat Framework | Combat Design | Game Designer | Design ¦ Game design | 15 | 15 |  | 0 |  | 0 | 15
Combat Framework | Combat Framework | Attacks Design Doc - per weapon (Combo + off-hand attacks) | Game Designer | Design ¦ Game design | 3 | 4 |  | 0 |  | 0 | 4
Combat Framework | Combat Framework | Weapon Attributes (per weapon) | Game Designer | Design ¦ Game design | 1 | 1 |  | 0 |  | 0 | 1
Combat Framework | Combat Framework | Combat Animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Combat Montages | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Combat Tech anim? | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Combat integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Weapons models | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Combat VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Melee Combat QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Combat Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Combat Animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Combat Tech anim? | Animator | Art ¦ Animation & Rigging | 10 | 20 |  | 0 |  | 0 | 20
Combat Framework | Combat Framework | Weapon spesific hand poses | Animator | Art ¦ Animation & Rigging | 2 | 2 |  | 0 |  | 0 | 2
Combat Framework | Combat Framework | Aim offset implementation | Animator | Art ¦ Animation & Rigging | 2 | 4 |  | 0 |  | 0 | 4
Combat Framework | Combat Framework | Review the combat with networking engineer | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 5 |  | 0 |  | 0 | 5
Combat Framework | Combat Framework | Death sequance system | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Combat Framework | Combat Framework | Weapons models | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Combat VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Melee Combat QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Combat Framework | Combat Framework | Pressure based agro | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 8 |  | 0 |  | 0 | 8
Combat Framework | Combat Framework | Distance based agro | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Combat Framework | Combat Framework | Health based agro | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Combat Framework | Combat Framework | Utility managment | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Combat Framework | Combat Framework | Scaling | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Combat Framework | Combat Framework | AI vs AI | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Combat Framework | Combat Framework | Player feedback | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Combat Framework | Combat Framework | Safety check | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Combat Framework | Combat Framework | Reflex check | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Combat Framework | Combat Framework | Survival check | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Combat Framework | Combat Framework | Social check | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Combat Framework | Combat Framework | Execution check | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
Combat Framework | Combat Framework | different types of movements | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Combat Framework | Combat Framework | decision tick | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
Combat Framework | Combat Framework | utility abilities (healthing etc...) | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
Combat Framework | Combat Framework | attack abilities (attack etc...) | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
Ranged Combat | Ranged Combat | Dual Wielding Ranged | Game Designer | Design ¦ Game design | 2 | 4 |  | 0 |  | 0 | 4
Ranged Combat | Ranged Combat | Ranged Attributes | Game Designer | Design ¦ Game design | 5 | 5 |  | 0 |  | 0 | 5
Ranged Combat | Ranged Combat | Aimed offsets | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Wolf montages | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Wolf AI behaviour | Game Designer | Design ¦ Game design |  | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Wolfy noises | Sound Designer | Audio ¦ Audio | 0 | 0 |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Wolves QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Goblin montages | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Goblin AI behaviour | Game Designer | Design ¦ Game design |  | 4 |  | 0 |  | 0 | 4
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design | 3 | 9 |  | 0 |  | 0 | 9
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | SFX | Sound Designer | Audio ¦ Audio | 7 | 7 |  | 0 |  | 0 | 7
Enemies Art | Enemies Art | Goblins QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Skeleton montages | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Skeleton AI behaviour | Game Designer | Design ¦ Game design |  | 4 |  | 0 |  | 0 | 4
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design | 3 | 9 |  | 0 |  | 0 | 9
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | SFX | Sound Designer | Audio ¦ Audio | 0 | 0 |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Skeletons QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
Enemies Art | Enemies Art | Slimes AI behaviour | Game Designer | Design ¦ Game design |  | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | SFX | Sound Designer | Audio ¦ Audio | 0 | 0 |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Slimes QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Narrative | Game Designer | Design ¦ Game design | 2 | 1 |  | 0 |  | 0 | 1
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design | 2 | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Quest structure | Game Designer | Design ¦ Game design | 1 | 4 |  | 0 |  | 0 | 4
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | SFX | Sound Designer | Audio ¦ Audio | 3 | 3 |  | 0 |  | 0 | 3
Enemies Art | Enemies Art | Corrupted Enemies QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design | 2 | 5 |  | 0 |  | 0 | 5
Enemies Art | Enemies Art | Carapax AI design | Game Designer | Design ¦ Game design |  | 4 |  | 0 |  | 0 | 4
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | SFX | Sound Designer | Audio ¦ Audio | 5 | 7 |  | 0 |  | 0 | 7
Enemies Art | Enemies Art | Carapax QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging | 10 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Create animation graph | Animator | Art ¦ Animation & Rigging | 3 | 5 |  | 0 |  | 0 | 5
Enemies Art | Enemies Art | Create control rig | Animator | Art ¦ Animation & Rigging | 1 | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Make combat moves | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Wolves QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging | 10 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Create animation graph | Animator | Art ¦ Animation & Rigging | 3 | 5 |  | 0 |  | 0 | 5
Enemies Art | Enemies Art | RBF setup | Animator | Art ¦ Animation & Rigging | 2 | 4 |  | 0 |  | 0 | 4
Enemies Art | Enemies Art | Create control rig | Animator | Art ¦ Animation & Rigging | 1 | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Make combat moves | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Goblins QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging | 10 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Create animation graph | Animator | Art ¦ Animation & Rigging | 3 | 5 |  | 0 |  | 0 | 5
Enemies Art | Enemies Art | Seperate clothing from body | Animator | Art ¦ Animation & Rigging | 5 | 7 |  | 0 |  | 0 | 7
Enemies Art | Enemies Art | Custom death sequance | Animator | Art ¦ Animation & Rigging | 5 | 7 |  | 0 |  | 0 | 7
Enemies Art | Enemies Art | Create control rig | Animator | Art ¦ Animation & Rigging | 1 | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Make combat moves | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Skeletons QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging | 2 | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Create animation graph | Animator | Art ¦ Animation & Rigging | 2 | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Make combat moves | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Slimes QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging | 5 | 15 |  | 0 |  | 0 | 15
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Make combat moves | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX | 3 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | Corrupted Enemies QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Rigging | Animator | Art ¦ Animation & Rigging | 10 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | Animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Create animation graph | Animator | Art ¦ Animation & Rigging | 3 | 5 |  | 0 |  | 0 | 5
Enemies Art | Enemies Art | Seperate clothing from body | Animator | Art ¦ Animation & Rigging | 2 | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Custom death sequance | Animator | Art ¦ Animation & Rigging | 1 | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Create control rig | Animator | Art ¦ Animation & Rigging | 1 | 2 |  | 0 |  | 0 | 2
Enemies Art | Enemies Art | Asset Validation | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Combat Behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Make combat moves | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Enemies Art | Enemies Art | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Carapax QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Green Faction NPCs | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Red Faction NPCs | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Yellow Faction NPCs | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Blue Faction NPCs | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Critter NPCs - Pigs (DONE) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Critter NPCs - Hares (DONE) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Critter NPCs - Sheep (DONE) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Critter NPCs - Cows (DONE) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Critter NPCs - Chickens (DONE) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Critter NPCs - Horses (DONE) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Hero NPC - Xyron (Upgrade) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Hero NPC - Barbersmith (Upgrade) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Enemies Art | Enemies Art | Hero NPC - Maeve/Mayor (Upgrade) | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Combat design | Game Designer | Design ¦ Game design | 5 | 12 |  | 0 |  | 0 | 12
PvP Combat | PvP Combat | PVP Combat support | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP only available in Arena | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena Design | Game Designer | Design ¦ Game design | 6 | 7 |  | 0 |  | 0 | 7
PvP Combat | PvP Combat | PVP Combat Setup | Game Designer | Design ¦ Game design |  | 6 |  | 0 |  | 0 | 6
PvP Combat | PvP Combat | PVP Arena concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena blockout | Level Designer | Design ¦ Level design | 3 | 10 |  | 0 |  | 0 | 10
PvP Combat | PvP Combat | PVP Arena Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena set dressing | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena Audio | Sound Designer | Audio ¦ Audio | 7 | 5 |  | 0 |  | 0 | 5
PvP Combat | PvP Combat | PVP combat QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Combat design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | Show damage numbers between players on hit | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 3 |  | 0 |  | 0 | 3
PvP Combat | PvP Combat | Implement player prediction algorithm for networking | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
PvP Combat | PvP Combat | Show other player HP in area fight | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
PvP Combat | PvP Combat | declare player who is connected as winner | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
PvP Combat | PvP Combat | Create fight timer and declare draw | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
PvP Combat | PvP Combat | Reward player who won and display a message to the loser | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
PvP Combat | PvP Combat | Sign up for arena fight actor | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
PvP Combat | PvP Combat | Kick players that are in the area who are not fighting when you and someone else decide to start a fight | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
PvP Combat | PvP Combat | PVP area blocks player from entering and leaving | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
PvP Combat | PvP Combat | PVP Combat support | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
PvP Combat | PvP Combat | PVP only available in Arena | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
PvP Combat | PvP Combat | Create UI/UX | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | Ensure combat system works | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
PvP Combat | PvP Combat | PVP Arena Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena blockout | Level Designer | Design ¦ Level design |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena Foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena set dressing | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP Arena Audio | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | PVP combat QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
PvP Combat | PvP Combat | Architecture Kit - Arena | Environment Artist | Art ¦ Environment Art | 34.3 | 114.3 |  | 0 |  | 0 | 114.3
PvP Combat | PvP Combat | Arena | Environment Artist | Art ¦ Environment Art | 57.1 | 91.4 |  | 0 |  | 0 | 91.4
Combat Balance & Telemetry | Combat Balance & Telemetry | Create leaderboard collection | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Combat Balance & Telemetry | Combat Balance & Telemetry | Create a leaderboard in dashboard (internal dashboard) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 4 |  | 0 |  | 0 | 4
Combat Balance & Telemetry | Combat Balance & Telemetry | Delete a leaderboard from dashboard (internal dashboard) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Combat Balance & Telemetry | Combat Balance & Telemetry | Delete an entry from the leaderboard from dashboard (internal dashboard) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Combat Balance & Telemetry | Combat Balance & Telemetry | Create UI for leaderboard in (internal dashboard) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Combat Balance & Telemetry | Combat Balance & Telemetry | Fetch all leaderboards (internal dashboard) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Combat Balance & Telemetry | Combat Balance & Telemetry | Update leaderboard from (social service) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Combat Balance & Telemetry | Combat Balance & Telemetry | Fetch leaderboard from (social service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Combat Balance & Telemetry | Combat Balance & Telemetry | Fetch leaderboard in unreal | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Combat Balance & Telemetry | Combat Balance & Telemetry | Update leaderboard in unreal | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Combat Abilities | Combat Abilities | Abilities Design | Game Designer | Design ¦ Game design | 8 | 9 |  | 0 |  | 0 | 9
Combat Abilities | Combat Abilities | 4 Abilities designed (2 weapons) | Game Designer | Design ¦ Game design | 5 | 20 |  | 0 |  | 0 | 20
Combat Abilities | Combat Abilities | Weapon attribute system | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
Combat Abilities | Combat Abilities | Combat Abilities UI | UI/UX Designer | Art ¦ UX/UI | 8 | 15 |  | 0 |  | 0 | 15
Combat Abilities | Combat Abilities | HUD Combat Abilities UI | UI/UX Designer | Art ¦ UX/UI | 8 | 5 |  | 0 |  | 0 | 5
Combat Abilities | Combat Abilities | HUD design | UI/UX Designer | Art ¦ UX/UI | 5 | 7 |  | 0 |  | 0 | 7
Combat Abilities | Combat Abilities | Combat Abilities integrated with skill path | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Combat Abilities | Combat Abilities | Combat abilities casting animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Combat Abilities | Combat Abilities | Combat Abilities QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Combat Abilities | Combat Abilities | Combat Abilities SFX | Sound Designer | Audio ¦ Audio | 7 | 7 |  | 0 |  | 0 | 7
Combat Abilities | Combat Abilities | Abilities Design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Combat Abilities | Combat Abilities | Combat Abilities UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Combat Abilities | Combat Abilities | Integrate abilities with skill path | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Combat Abilities | Combat Abilities | Make the abilities | Gameplay Developer | Engineering ¦ Gameplay Engineering | 10 | 12 |  | 0 |  | 0 | 12
Combat Abilities | Combat Abilities | Combat abilities casting animations | Animator | Art ¦ Animation & Rigging | 3 | 5 |  | 0 |  | 0 | 5
Combat Abilities | Combat Abilities | Combat Abilities QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Combat Abilities | Combat Abilities | Combat SFX | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Magic | Magic | Magic Weapon (e.g. wand) | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
Magic | Magic | Weapon | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Magic | Magic | Magic system design (5 spells) | Game Designer | Design ¦ Game design | 5 | 10 |  | 0 |  | 0 | 10
Magic | Magic | Magic implementation | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Magic | Magic | Magic UI (1 skill tree mapped out) | UI/UX Designer | Art ¦ UX/UI | 5 | 7 |  | 0 |  | 0 | 7
Magic | Magic | Magic casting animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Magic | Magic | Magic SFX | Sound Designer | Audio ¦ Audio | 7 | 5 |  | 0 |  | 0 | 5
Magic | Magic | Magic VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Magic | Magic | Magic QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Magic | Magic | Magic system design (3-4 spells) | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Magic | Magic | make wand abilities 4 | Gameplay Developer | Engineering ¦ Gameplay Engineering | 10 | 15 |  | 0 |  | 0 | 15
Magic | Magic | wand skill tree | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Magic | Magic | make wand an item type | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 1 |  | 0 |  | 0 | 1
Magic | Magic | equipd wand | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 1 |  | 0 |  | 0 | 1
Magic | Magic | Magic UI (1 skill tree mapped out) | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Magic | Magic | Magic casting animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Magic | Magic | Magic SFX | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Magic | Magic | Magic VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Magic | Magic | Magic QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Intro supports FMV | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Create placeholder FMV playback flow | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Implement FMV skip behavior | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Implement transition after FMV | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | FMV Production | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Integrate final/near-final FMV asset | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | QA playback across target builds | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Fix FMV blocker bugs | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Narrative - Cinematic scripting | Writer | Design ¦ Narrative | 1 | 1 |  | 0 |  | 0 | 1
Full Motion Video (FMV) | Full Motion Video (FMV) | Intro sequence plays 3 slides with voiceover | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Create intro sequence controller | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Display static slides full-screen | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Play voiceover synced to sequence | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Display subtitles synced to VO | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Implement skip behavior | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Implement transition to gameplay/menu | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Final art production | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | VO production | Sound Designer | Audio ¦ Audio | 6 | 3 |  | 0 |  | 0 | 3
Full Motion Video (FMV) | Full Motion Video (FMV) | Subtitles production | Game Designer | Design ¦ Game design | 0.5 | 1 |  | 0 |  | 0 | 1
Full Motion Video (FMV) | Full Motion Video (FMV) | Integrate final art + VO assets | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | QA + fix blockers | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Intro supports FMV | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Create placeholder FMV playback flow and allow designers to set the FMV easily | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
Full Motion Video (FMV) | Full Motion Video (FMV) | Create a system to disallow the player from moving while in FMV | Gameplay Developer | Engineering ¦ Gameplay Engineering | 0.5 | 1 |  | 0 |  | 0 | 1
Full Motion Video (FMV) | Full Motion Video (FMV) | Implement FMV skip behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Full Motion Video (FMV) | Full Motion Video (FMV) | Implement transition after FMV - Fade in/Fade out system | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Full Motion Video (FMV) | Full Motion Video (FMV) | FMV Production | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Integrate final/near-final FMV asset | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | QA playback across target builds | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Intro sequence plays 3 slides with voiceover | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Create intro sequence controller | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Create a system to disallow the player from moving while in FMV | Gameplay Developer | Engineering ¦ Gameplay Engineering | 0.5 | 1 |  | 0 |  | 0 | 1
Full Motion Video (FMV) | Full Motion Video (FMV) | Allow this to be triggered from quest | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Full Motion Video (FMV) | Full Motion Video (FMV) | Display static slides full-screen | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Full Motion Video (FMV) | Full Motion Video (FMV) | Tool for designers | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Full Motion Video (FMV) | Full Motion Video (FMV) | UI Design | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Play voiceover synced to sequence | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Full Motion Video (FMV) | Full Motion Video (FMV) | Display subtitles synced to VO | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Full Motion Video (FMV) | Full Motion Video (FMV) | Implement skip behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Full Motion Video (FMV) | Full Motion Video (FMV) | Implement transition to gameplay/menu | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Full Motion Video (FMV) | Full Motion Video (FMV) | Final art production | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | VO production | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Subtitles production | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | Integrate final art + VO assets | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Full Motion Video (FMV) | Full Motion Video (FMV) | QA + fix blockers | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
User Space
User Space Server & Instance | User Space Server & Instance | FTUE Design | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
User Space Server & Instance | User Space Server & Instance | FTUE UI | UI/UX Designer | Art ¦ UX/UI |  | 5 |  | 0 |  | 0 | 5
User Space Server & Instance | User Space Server & Instance | User Space Editor audio | Sound Designer | Audio ¦ Audio | 2 | 2 |  | 0 |  | 0 | 2
User Space Server & Instance | User Space Server & Instance | Mutual Activity Design | Game Designer | Design ¦ Game design | 2 | 4 |  | 0 |  | 0 | 4
User Space Server & Instance | User Space Server & Instance | Mutual Activity UI | UI/UX Designer | Art ¦ UX/UI |  | 5 |  | 0 |  | 0 | 5
User Space Server & Instance | User Space Server & Instance | Drinking design | Game Designer | Design ¦ Game design |  | 1 |  | 0 |  | 0 | 1
User Space Server & Instance | User Space Server & Instance | Drunken UI | UI/UX Designer | Art ¦ UX/UI |  | 4 |  | 0 |  | 0 | 4
User Space Server & Instance | User Space Server & Instance | User Space is a separate instance | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space editor & UI | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space Ambience | Sound Designer | Audio ¦ Audio | 1 | 1 |  | 0 |  | 0 | 1
User Space Server & Instance | User Space Server & Instance | Item SFX | Sound Designer | Audio ¦ Audio | 0.5 | 1 |  | 0 |  | 0 | 1
User Space Server & Instance | User Space Server & Instance | Island ambient audio | Sound Designer | Audio ¦ Audio | 1 | 1 |  | 0 |  | 0 | 1
User Space Server & Instance | User Space Server & Instance | User Space editor VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space functionality QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space GDD VS page | Game Designer | Design ¦ Game design |  | 1 |  | 0 |  | 0 | 1
User Space Server & Instance | User Space Server & Instance | User Space location concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space location blockout | Level Designer | Design ¦ Level design | 5 | 7 |  | 0 |  | 0 | 7
User Space Server & Instance | User Space Server & Instance | User Space location set dressing | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space location props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space location foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space visuals QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space is a separate instance | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | DevOps | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
User Space Server & Instance | User Space Server & Instance | IP address list service | Backend Developer | Engineering ¦ Backend Engineering | 5 | 6 |  | 0 |  | 0 | 6
User Space Server & Instance | User Space Server & Instance | Multiple players join one server and only show what is relevent to current player | Gameplay Developer | Engineering ¦ Gameplay Engineering | 10 | 20 |  | 0 |  | 0 | 20
User Space Server & Instance | User Space Server & Instance | Figure out friend ip address to join his server when invited | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
User Space Server & Instance | User Space Server & Instance | Host permissions | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
User Space Server & Instance | User Space Server & Instance | Edit mode improvmeents | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
User Space Server & Instance | User Space Server & Instance | Save userspace furniture location in userspace | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
User Space Server & Instance | User Space Server & Instance | Fetch userspace furniture from backend | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
User Space Server & Instance | User Space Server & Instance | Update userspace furniture and tell that to all players | Gameplay Developer | Engineering ¦ Gameplay Engineering | 4 | 5 |  | 0 |  | 0 | 5
User Space Server & Instance | User Space Server & Instance | Player joining friends userspace | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
User Space Server & Instance | User Space Server & Instance | Enable fishing in userspace | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
User Space Server & Instance | User Space Server & Instance | Load userspace from save data | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 7 |  | 0 |  | 0 | 7
User Space Server & Instance | User Space Server & Instance | User Space editor & UI | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | Setup animation for userspace editing tool | Animator | Art ¦ Animation & Rigging | 1 | 1 |  | 0 |  | 0 | 1
User Space Server & Instance | User Space Server & Instance | Implement interaction animation with userspace items (snap) | Animator | Art ¦ Animation & Rigging | 1 | 5 |  | 0 |  | 0 | 5
User Space Server & Instance | User Space Server & Instance | User Space Ambience | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space editor VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space functionality QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space location concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space location blockout | Level Designer | Design ¦ Level design |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space location set dressing | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space location props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space location foliage | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | User Space visuals QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
User Space Server & Instance | User Space Server & Instance | Player Island 1 | Environment Artist | Art ¦ Environment Art | 69.7 | 69.7 |  | 0 |  | 0 | 69.7
User Space Server & Instance | User Space Server & Instance | Player Island 2 | Environment Artist | Art ¦ Environment Art | 69.7 | 69.7 |  | 0 |  | 0 | 69.7
User Space Server & Instance | User Space Server & Instance | Zone - User Space Island | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Decoration | User Space Decoration | User Space House concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
User Space Decoration | User Space Decoration | User Space House model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Decoration | User Space Decoration | User Space furniture props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Decoration | User Space Decoration | User Space House concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
User Space Decoration | User Space Decoration | User Space House model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Decoration | User Space Decoration | User Space furniture props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Decoration | User Space Decoration | Furniture - Fantasy | Environment Artist | Art ¦ Environment Art | 5.7 | 5.7 |  | 0 |  | 0 | 5.7
User Space Decoration | User Space Decoration | Furniture - Gritcore | Environment Artist | Art ¦ Environment Art | 45.7 | 45.7 |  | 0 |  | 0 | 45.7
User Space Decoration | User Space Decoration | Indoor Camera | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
User Space Decoration | User Space Decoration | User Space Interior | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
User Space Decoration | User Space Decoration | User Space Exterior | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Building Houses | Building Houses | Architecture Kit - Player Housing | Environment Artist | Art ¦ Environment Art | 65.7 | 114.3 |  | 0 |  | 0 | 114.3
Building Houses | Building Houses | Player Buildings | Environment Artist | Art ¦ Environment Art | 68.6 | 68.6 |  | 0 |  | 0 | 68.6
Building Houses | Building Houses | Modular Houses | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Anywhere Door Placement | Anywhere Door Placement | User space door can be placed at predefined spots | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Anywhere Door Placement | Anywhere Door Placement | Anywhere Door QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Anywhere Door Placement | Anywhere Door Placement | User space door can be placed at predefined spots | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Anywhere Door Placement | Anywhere Door Placement | Create endpoint to update the position, rotation and zone name of MULTIPLE anywhere door in backend (player data service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Create fetech anywhere door endpoint (player data service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Update anywhere door position, rotation, zone name after fethcing anywhere door info from (player data serivce) | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Create an ability to place anywhere door in the world | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Create anywhere door as item in backend service. | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Create anywhere door as item. | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Anywhere Door Placement | Anywhere Door Placement | Show if the anywhere door is placed or not placed to remove it if needed | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Show anywhere door on map | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Show anywhere door on minimap | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Show anywhere door on compass | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Anywhere Door Placement | Anywhere Door Placement | Make anywhere door as an actor | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Remove anywhere door | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | fetch anywhere door info from backend service and place it in the world | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Make spesific regions where anywhere door can be placed | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Anywhere Door Placement | Anywhere Door Placement | Anywhere Door QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Items & Inventory
Item Core System | Item Core System | Starting Chest | Game Designer | Design ¦ Game design | 0.5 | 5 |  | 0 |  | 0 | 5
Item Core System | Item Core System | Chest concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Chest model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Chest animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Chest VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Shield | Game Designer | Design ¦ Game design | 2 | 4 |  | 0 |  | 0 | 4
Item Core System | Item Core System | Shield animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Shield Asset | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Starting Sword | Game Designer | Design ¦ Game design | 0.5 | 4 |  | 0 |  | 0 | 4
Item Core System | Item Core System | Sword concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Sword model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Sword animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Sword VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Equipment Stats integrated with character stats | Game Designer | Design ¦ Game design | 5 | 5 |  | 0 |  | 0 | 5
Item Core System | Item Core System | Equipment Stats integrated with character stats | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Starting Chest | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Chest concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Chest model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Chest animation | Animator | Art ¦ Animation & Rigging | 1 | 1 |  | 0 |  | 0 | 1
Item Core System | Item Core System | Chest VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Starting Sword | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Sword concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Sword model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Sword animations | Animator | Art ¦ Animation & Rigging | 5 | 10 |  | 0 |  | 0 | 10
Item Core System | Item Core System | Sword VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | Equipment Stats integrated with character stats | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Item Core System | Item Core System | QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Equipment System | Equipment System | an endpoint to all items equiped (batch requests only send what changed) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Equipment System | Equipment System | Create an endpoint to store abilities in internal dashboard | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Equipment System | Equipment System | Create an endpoint to fetch abilities internal dashboard | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Equipment System | Equipment System | Create an endpoint to remove ability internal dashboard | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Equipment System | Equipment System | Create an endpoint to fetch equiped items | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Equipment System | Equipment System | Create an endpoint to euip items | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Equipment System | Equipment System | an endpoint to update all item and abilities position in the hotbar (batch requests only send what changed) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Equipment System | Equipment System | Create endpoint to fetch hotbar items and abilities | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Equipment System | Equipment System | Create unit test for updating, fetching | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Equipment System | Equipment System | Send an HTTP reuqest only after 2 seconds after not moving any items or abilities in hotbar | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Equipment System | Equipment System | Get hotbar item and abiltitie positions and set them | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 3 |  | 0 |  | 0 | 3
Equipment System | Equipment System | Fetch and set equiped items | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Loot Distribution | Loot Distribution | Loot distribution design | Game Designer | Design ¦ Game design |  | 3 |  | 0 |  | 0 | 3
Loot Distribution | Loot Distribution | Loot is distributed after the raid | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Loot Distribution | Loot Distribution | Loot distribution QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Loot Distribution | Loot Distribution | Loot is distributed after the raid | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Loot Distribution | Loot Distribution | Create loot distribution collection ( internal dashboard managment service) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Loot Distribution | Loot Distribution | Update loot distribution collection ( internal dashboard managment service) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Loot Distribution | Loot Distribution | Fetch loot distribution collection (internal dashboard managment service) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Loot Distribution | Loot Distribution | Create loot distribution system which lets Actors inherit from multiple templates | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Loot Distribution | Loot Distribution | Refreance loot table in enemy/actor in tool | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Loot Distribution | Loot Distribution | Create a new loot table in tool | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Loot Distribution | Loot Distribution | Save temp loot table in tool | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Loot Distribution | Loot Distribution | Edit loot table in CH tool | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Loot Distribution | Loot Distribution | Delete loot table in CH tool | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Loot Distribution | Loot Distribution | Fetch current loot tables in CH tool | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Loot Distribution | Loot Distribution | Release loot table in CH tool | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Loot Distribution | Loot Distribution | Create a system for actors to referance loot table | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Loot Distribution | Loot Distribution | Enemies drop item when they are killed | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Loot Distribution | Loot Distribution | distrubute loot according to dungeon rules | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Loot Distribution | Loot Distribution | Loot distribution QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet system design | Game Designer | Design ¦ Game design |  | 4 |  | 0 |  | 0 | 4
Mounts / Pets | Mounts / Pets | Pet concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet behavior | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Teleport pet to player when pet is stuck | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Mounts / Pets | Mounts / Pets | Review pet system code | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Mounts / Pets | Mounts / Pets | Pet concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet model | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | Pet maya rig setup | Animator | Art ¦ Animation & Rigging | 2 | 2 |  | 0 |  | 0 | 2
Mounts / Pets | Mounts / Pets | Pet animation grpah setup | Animator | Art ¦ Animation & Rigging | 2 | 2 |  | 0 |  | 0 | 2
Mounts / Pets | Mounts / Pets | Pet QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Mounts / Pets | Mounts / Pets | MECH PARROT | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Consumables | Consumables | Check the health potion usage | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Consumables | Consumables | Implement drinking animation | Animator | Art ¦ Animation & Rigging | 1 | 1 |  | 0 |  | 0 | 1
Consumables | Consumables | Check the health potion usage | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Consumables | Consumables | Potions | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Player Economy
Trading System | Trading System | Shop Fake Fascia Design | Game Designer | Design ¦ Game design | 5 | 1 |  | 0 |  | 0 | 1
Trading System | Trading System | Clothing Shop Basic Contents | Game Designer | Design ¦ Game design | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | Shops Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Shops Models & Set dressing | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Shop props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Vendors Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Vendors Models | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Vendors animation | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Trading UX/UI | UI/UX Designer | Art ¦ UX/UI | 15 | 15 |  | 0 |  | 0 | 15
Trading System | Trading System | Currency Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Soft Currency (gold) icon | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Premium currency icon | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Shops Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Shops Models & Set dressing | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Shop props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Vendors Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Vendors Models | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Vendors animation | Animator | Art ¦ Animation & Rigging | 3 | 5 |  | 0 |  | 0 | 5
Trading System | Trading System | Trading UX/UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Currency Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | Soft Currency (gold) icon | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Premium currency icon | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | P2G Transactions Support | Backend Developer | Engineering ¦ Backend Engineering | 4 | 40 |  | 0 |  | 0 | 40
Trading System | Trading System | Trading System QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Trading System | Trading System | Create vendor collection ( internal dashboard managment service) | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Trading System | Trading System | Update vendor collection ( internal dashboard managment service) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | Fetch vendor collection (internal dashboard managment service) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | Create fresh cron job to refresh item stacks for vendors (internal dashboard managment service) | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Trading System | Trading System | delete items and vendor (internal dashboard managment service) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | Update NPC tool to match vendor in unreal engine | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Trading System | Trading System | Release vendor in game from tempate to release | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | fetch last 20 items sold, buyback item, Create buyback functionality | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Trading System | Trading System | Create a list of sold items (redis / server) ??? fetch, create buyback endpoint, update endpoint, pipeline | Backend Developer | Engineering ¦ Backend Engineering | 5 | 7 |  | 0 |  | 0 | 7
Trading System | Trading System | Fetch a list of sold items | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | Create buy endpoint | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | Create sell endpoint | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | Use buy endpoint | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | Use sell endpoint | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Trading System | Trading System | Update UI | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Currency System | Currency System | Currency System Art | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Auction House | Auction House | P2G Transactions Support | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Auction House | Auction House | Trading System QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
In-game Store | In-game Store | Virtual currency balance and items | Game Designer | Design ¦ Game design |  | 2 |  | 0 |  | 0 | 2
In-game Store | In-game Store | RMT subscription design | UI/UX Designer | Art ¦ UX/UI | 8 | 3 |  | 0 |  | 0 | 3
In-game Store | In-game Store | RNT partner store | UI/UX Designer | Art ¦ UX/UI |  | 3 |  | 0 |  | 0 | 3
In-game Store | In-game Store | RMT virtual currency page | UI/UX Designer | Art ¦ UX/UI |  | 3 |  | 0 |  | 0 | 3
In-game Store | In-game Store | RMT store integration | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
In-game Store | In-game Store | RMT Store SFX | Sound Designer | Audio ¦ Audio | 7 | 7 |  | 0 |  | 0 | 7
In-game Store | In-game Store | RMT Store QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
In-game Store | In-game Store | RMT store design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
In-game Store | In-game Store | Fetch total owned virtual currancy | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Store | In-game Store | Create an endpoint to fetch total owned virtual currancy from store service | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Store | In-game Store | Call purchase virtual currnacy endpoint from Unreal | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Store | In-game Store | Create a purchase virtual currancy endpoint in store service | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Store | In-game Store | Create an endpoint to fetch all store items, prices, images, titles from store service | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Store | In-game Store | Update in-game store when fetching store items | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
In-game Store | In-game Store | Create purcahse item endpoint in store service | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
In-game Store | In-game Store | Call purchase item endpoint in unreal and sned item to player mailbox when item is purchased | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
In-game Store | In-game Store | Create an endpoint to add items to in-game store in dashboard management service | Backend Developer | Engineering ¦ Backend Engineering | 4 | 5 |  | 0 |  | 0 | 5
In-game Store | In-game Store | Create an endpoint to update items to in-game store in dashboard management service | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
In-game Store | In-game Store | Create an endpoint to remove items from in-game store in dashboard management service | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Store | In-game Store | Create an endpoint to pause the purcahsing of an item from in-game store in dashboard managment serivce | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Store | In-game Store | Display paused banner on paused items with a tooltip explaining why the item is paused | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
In-game Store | In-game Store | Set a limit on items. example gun only 100 people can buy it. first come first serve | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
In-game Store | In-game Store | Connect UI with code | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
In-game Store | In-game Store | RMT Store UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
In-game Store | In-game Store | Basic RMT balance config | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
In-game Store | In-game Store | RMT Store SFX | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
In-game Store | In-game Store | RMT Store QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
In-game Economy | In-game Economy | Basic Economy configuration | Game Designer | Design ¦ Game design | 10 | 5 |  | 0 |  | 0 | 5
In-game Economy | In-game Economy | In-game economy QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
In-game Economy | In-game Economy | Basic Economy configuration | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
In-game Economy | In-game Economy | In-game economy QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quest System
Quests Backend / Tooling | Quests Backend / Tooling | Tutorial Quest Chain Configuration & Setup | Game Designer | Design ¦ Game design | 7 | 10 |  | 0 |  | 0 | 10
Quests Backend / Tooling | Quests Backend / Tooling | QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Green Faction NPC Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Green Faction NPC Models | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Green Faction NPC animations | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Green Faction NPC dialogue setup | Writer | Design ¦ Narrative | 1 | 2 |  | 0 |  | 0 | 2
Quests Backend / Tooling | Quests Backend / Tooling | Green Faction NPCs placement | Game Designer | Design ¦ Game design | 2 | 2 |  | 0 |  | 0 | 2
Quests Backend / Tooling | Quests Backend / Tooling | QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Quest Editor | Game Designer | Design ¦ Game design | 5 | 2 |  | 0 |  | 0 | 2
Quests Backend / Tooling | Quests Backend / Tooling | Dialogue System Design | Game Designer | Design ¦ Game design | 3 | 3 |  | 0 |  | 0 | 3
Quests Backend / Tooling | Quests Backend / Tooling | Dialogue System | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Dialogue UI | UI/UX Designer | Art ¦ UX/UI |  | 10 |  | 0 |  | 0 | 10
Quests Backend / Tooling | Quests Backend / Tooling | Quest Log | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Quest Log QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Xyron narrative | Game Designer | Design ¦ Game design | 2 | 2 |  | 0 |  | 0 | 2
Quests Backend / Tooling | Quests Backend / Tooling | Tutorial Quest Chain Configuration & Setup | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Green Faction NPC Concepts | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Green Faction NPC Models | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Green Faction NPC animations | Animator | Art ¦ Animation & Rigging | 3 | 5 |  | 0 |  | 0 | 5
Quests Backend / Tooling | Quests Backend / Tooling | Green Faction NPC dialogue setup | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Green Faction NPCs placement | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Dialogue System | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 15 |  | 0 |  | 0 | 15
Quests Backend / Tooling | Quests Backend / Tooling | Dialogue UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Quests Backend / Tooling | Quests Backend / Tooling | Quest Log | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Quests Backend / Tooling | Quests Backend / Tooling | Quest Log QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking | Game Designer | Design ¦ Game design | 7 | 2 |  | 0 |  | 0 | 2
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking UI | UI/UX Designer | Art ¦ UX/UI | 8 | 6 |  | 0 |  | 0 | 6
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking Integration | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking Techart | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Design interface for quest types | Game Designer | Design ¦ Game design | 2 | 5 |  | 0 |  | 0 | 5
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Other quest types support? | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Check if lockpicking solution is correct | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Create an actor with a grid for all tiles | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Create data asset | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 1 |  | 0 |  | 0 | 1
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Create pipe entity actor | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Create magnatic enitity actor | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Create ball entity actor to compelete the game | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 4 |  | 0 |  | 0 | 4
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Start and end condition | Gameplay Developer | Engineering ¦ Gameplay Engineering | 0.5 | 0.5 |  | 0 |  | 0 | 0.5
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Create a system to modify ball proaprties while traveling | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 10 |  | 0 |  | 0 | 10
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | SFX | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Implement VFX and SFX | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking Techart | Technical Artist | Art ¦ TechArt |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lockpicking QA check | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Design interface for quest types | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Other quest types support? | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Create quest tool | Gameplay Developer | Engineering ¦ Gameplay Engineering | 20 | 20 |  | 0 |  | 0 | 20
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Create quest system backend service | Backend Developer | Engineering ¦ Backend Engineering | 20 | 20 |  | 0 |  | 0 | 20
Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | Lock Picking Quest | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Quest Reward System | Quest Reward System | Quest UI Audio | Sound Designer | Audio ¦ Audio | 0.5 | 1 |  | 0 |  | 0 | 1
Quest Reward System | Quest Reward System | Quest Reward UI | UI/UX Designer | Art ¦ UX/UI |  | 5 |  | 0 |  | 0 | 5
Quest Reward System | Quest Reward System | Quest Reward System design doc | Game Designer | Design ¦ Game design |  | 2 |  | 0 |  | 0 | 2
Quest Reward System | Quest Reward System | Quest Reward List | Game Designer | Design ¦ Game design | 2 | 2 |  | 0 |  | 0 | 2
Quest Reward System | Quest Reward System | Rewards Choice | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Quest Reward System | Quest Reward System | Quest Rewards QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quest Reward System | Quest Reward System | Rewards Choice | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Quest Reward System | Quest Reward System | Quest Rewards QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Quest Reward System | Quest Reward System | Hearthstone (Return Home Stone) | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Quest Reward System | Quest Reward System | Partner Crystal | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Quest Narrative Content | Quest Narrative Content | Quest Flow Design & Narrative Overview | Game Designer | Design ¦ Game design | 2 | 3 |  | 0 |  | 0 | 3
Quest Narrative Content | Quest Narrative Content | Cave Intro Quest | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Quest Narrative Content | Quest Narrative Content | Quest Narrative Doc | Writer | Design ¦ Narrative | 1 | 1 |  | 0 |  | 0 | 1
Quest Narrative Content | Quest Narrative Content | Quest Design Doc | Game Designer | Design ¦ Game design | 3 | 4 |  | 0 |  | 0 | 4
Quest Narrative Content | Quest Narrative Content | Quest Implementation | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
Quest Narrative Content | Quest Narrative Content | Quest Playtesting & Revision | Game Designer | Design ¦ Game design | 2 | 2 |  | 0 |  | 0 | 2
Quest Narrative Content | Quest Narrative Content | Quest Narrative Doc | Writer | Design ¦ Narrative | 0.5 | 2 |  | 0 |  | 0 | 2
Quest Narrative Content | Quest Narrative Content | Quest Design Doc | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
Quest Narrative Content | Quest Narrative Content | Quest Implementation | Game Designer | Design ¦ Game design | 4 | 6 |  | 0 |  | 0 | 6
Quest Narrative Content | Quest Narrative Content | Quest Playtesting & Revision | Game Designer | Design ¦ Game design | 2 | 3 |  | 0 |  | 0 | 3
Quest Narrative Content | Quest Narrative Content | Quest Narrative Doc | Writer | Design ¦ Narrative | 1 | 1 |  | 0 |  | 0 | 1
Quest Narrative Content | Quest Narrative Content | Quest Design Doc | Game Designer | Design ¦ Game design | 3 | 3 |  | 0 |  | 0 | 3
Quest Narrative Content | Quest Narrative Content | Quest Implementation | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
Quest Narrative Content | Quest Narrative Content | Quest Playtesting & Revision | Game Designer | Design ¦ Game design | 2 | 5 |  | 0 |  | 0 | 5
Quest Narrative Content | Quest Narrative Content | Quest Narrative Doc | Writer | Design ¦ Narrative | 0.5 | 1 |  | 0 |  | 0 | 1
Quest Narrative Content | Quest Narrative Content | Quest Design Doc | Game Designer | Design ¦ Game design | 3 | 3 |  | 0 |  | 0 | 3
Quest Narrative Content | Quest Narrative Content | Quest Implementation | Game Designer | Design ¦ Game design | 3 | 3 |  | 0 |  | 0 | 3
Quest Narrative Content | Quest Narrative Content | Quest Playtesting & Revision | Game Designer | Design ¦ Game design | 2 | 5 |  | 0 |  | 0 | 5
Quest Narrative Content | Quest Narrative Content | Docs, Implement, Revise | Game Designer | Design ¦ Game design | 7 | 7 |  | 0 |  | 0 | 7
Quest Narrative Content | Quest Narrative Content | Docs, Implement, Revise | Game Designer | Design ¦ Game design | 7 | 7 |  | 0 |  | 0 | 7
Quest Narrative Content | Quest Narrative Content | Docs, Implement, Revise | Game Designer | Design ¦ Game design | 7 | 7 |  | 0 |  | 0 | 7
Quest Narrative Content | Quest Narrative Content | Docs, Implement, Revise | Game Designer | Design ¦ Game design | 7 | 7 |  | 0 |  | 0 | 7
Quest Narrative Content | Quest Narrative Content | Docs, Implement, Revise | Game Designer | Design ¦ Game design | 7 | 7 |  | 0 |  | 0 | 7
Quest Narrative Content | Quest Narrative Content | Docs, Implement, Revise | Game Designer | Design ¦ Game design | 7 | 7 |  | 0 |  | 0 | 7
In Game Cinematic (IGC) | In Game Cinematic (IGC) | The game supports cutscenes | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Cutscene trigger system | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Camera control during cutscene | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Player control lock/unlock | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | NPC/character sequencing | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Dialogue playback (in-cutscene) | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Cutscene skip functionality | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Transition in/out of cutscene | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Basic cutscene sequencing (timeline) | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Cutscene stability (QA & fixes) | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Cutscene content | Game Designer | Design ¦ Game design | 5 | 5 |  | 0 |  | 0 | 5
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Narrative | Writer | Design ¦ Narrative | 0.5 | 1 |  | 0 |  | 0 | 1
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Camera behavior implementation/fixes | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Combat Camera | Game Designer | Design ¦ Game design | 4 | 9 |  | 0 |  | 0 | 9
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Camera QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | The game supports cutscenes | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Custom camera position and rotation | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Custom camera animations | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Stream camera position (world partition) | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Cutscene stability (QA & fixes) | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Cutscene content | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Camera behavior implementation/fixes | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Implement camera according to design | Gameplay Developer | Engineering ¦ Gameplay Engineering | 6 | 7 |  | 0 |  | 0 | 7
In Game Cinematic (IGC) | In Game Cinematic (IGC) | Camera QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Social & Multiplayer
Game Chat System | Game Chat System | General systems | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Create pipeline and deploy | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Game Chat System | Game Chat System | Create chat service in go | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Game Chat System | Game Chat System | Create a serialization/deserialization system | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Game Chat System | Game Chat System | Create a list of users info such as server ip and usernames | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Game Chat System | Game Chat System | Create a multithreaded system | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Game Chat System | Game Chat System | Create a custom protocol using TCP | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Game Chat System | Game Chat System | Create a heartbeat system | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Game Chat System | Game Chat System | Create a packet system | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Game Chat System | Game Chat System | Connect to redis | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Game Chat System | Game Chat System | Proximity chat | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Send chat message only to people near you | Backend Developer | Engineering ¦ Backend Engineering | 4 | 5 |  | 0 |  | 0 | 5
Game Chat System | Game Chat System | Zone channel | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Create a way to send a chat to entire zone | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Game Chat System | Game Chat System | Private message | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Send a private message to user | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Game Chat System | Game Chat System | Party chat | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Send a party message to your party | Backend Developer | Engineering ¦ Backend Engineering | 4 | 5 |  | 0 |  | 0 | 5
Game Chat System | Game Chat System | Guild chat | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Send a message to your guild | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Game Chat System | Game Chat System | System chat | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Create a system chat which will warn you on if the server is shutting down or if Show invites, kicks, bans in chat | Backend Developer | Engineering ¦ Backend Engineering | 4 | 5 |  | 0 |  | 0 | 5
Game Chat System | Game Chat System | Chat text limit | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Create a system to limit the amount of text sent | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Game Chat System | Game Chat System | Chat spam filter | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Create a system to rate limit messages | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Game Chat System | Game Chat System | Profanity filter | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Create a system to filter a set of words | Backend Developer | Engineering ¦ Backend Engineering | 3 | 5 |  | 0 |  | 0 | 5
Game Chat System | Game Chat System | Chat UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Auto scroll incomming chat messages | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Different colours for different type of message | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | integraet chat service in unreal using websockets | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Game Chat System | Game Chat System | Create a websocket connection | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Game Chat System | Game Chat System | Create a way to receive messages on unreal server and pass that to client | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Game Chat System | Game Chat System | Create a way to send a message from unreal server to chat server | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Guilds | Guilds | Guilds system design | Game Designer | Design ¦ Game design |  | 15 |  | 0 |  | 0 | 15
Guilds | Guilds | Guild house is an instance | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild house concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild house model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild house props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild house TV + video | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild NPCs | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild house blockout | Level Designer | Design ¦ Level design | 4 | 10 |  | 0 |  | 0 | 10
Guilds | Guilds | Sitting NPCs | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild UI | UI/UX Designer | Art ¦ UX/UI |  | 3 |  | 0 |  | 0 | 3
Guilds | Guilds | Guild chat | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild Chat design | Game Designer | Design ¦ Game design | 3 | 1 |  | 0 |  | 0 | 1
Guilds | Guilds | Guild QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild house | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild house entry | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Guilds | Guilds | Guild house leave | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Guilds | Guilds | Guild house server | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Guilds | Guilds | Guild house concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild house model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild house props | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild house TV + video | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild NPCs | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Sitting NPCs | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Connect Guild UI | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Guilds | Guilds | Guild UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild chat | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Guild QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Guilds | Guilds | Architecture Kit - Guild Hall | Environment Artist | Art ¦ Environment Art | 82.9 | 135 |  | 0 |  | 0 | 135
Guilds | Guilds | Guild Island | Environment Artist | Art ¦ Environment Art | 69.7 | 69.7 |  | 0 |  | 0 | 69.7
Guilds | Guilds | Guild Buildings | Environment Artist | Art ¦ Environment Art | 34.3 | 68.6 |  | 0 |  | 0 | 68.6
Co-op / Party | Co-op / Party | Party formation | Backend Developer | Engineering ¦ Backend Engineering | 3 | 8 |  | 0 |  | 0 | 8
Co-op / Party | Co-op / Party | Party system design | Game Designer | Design ¦ Game design |  | 5 |  | 0 |  | 0 | 5
Co-op / Party | Co-op / Party | Party chat | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Co-op / Party | Co-op / Party | Party supports real players and bots | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Co-op / Party | Co-op / Party | Party UI | UI/UX Designer | Art ¦ UX/UI |  | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Party chat | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Co-op / Party | Co-op / Party | Party QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Co-op / Party | Co-op / Party | Party formation | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Co-op / Party | Co-op / Party | Party supports real players and bots | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Co-op / Party | Co-op / Party | Party UI | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Co-op / Party | Co-op / Party | Party chat | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Co-op / Party | Co-op / Party | Create party puzzle | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Co-op / Party | Co-op / Party | Make a puzzle | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 5 |  | 0 |  | 0 | 5
Co-op / Party | Co-op / Party | Party QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Co-op / Party | Co-op / Party | Create pipeline and deploy | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Co-op / Party | Co-op / Party | Create party service | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Create a serialization/deserialization system | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Create a list of users info such as server ip and usernames | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Create a multithreaded system | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Create a custom protocol using TCP | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Create a heartbeat system | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Create a packet system | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Connect to redis | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Create a party | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Invite someone to party | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Kick someone from party | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Roll check in party | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Leave party | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Disband party | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Change leadership | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Update party player position on map, mana, health | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Co-op / Party | Co-op / Party | Create a party | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Co-op / Party | Co-op / Party | Invite someone to party | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Co-op / Party | Co-op / Party | Kick someone from party | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Co-op / Party | Co-op / Party | Roll check in party | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Co-op / Party | Co-op / Party | Leave party | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Disband party | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Co-op / Party | Co-op / Party | Change leadership | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Co-op / Party | Co-op / Party | Update party player position on map, mana, health | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
In-game Mail | In-game Mail | In-game Mail backend | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
In-game Mail | In-game Mail | In-game UI | UI/UX Designer | Art ¦ UX/UI |  | 10 |  | 0 |  | 0 | 10
In-game Mail | In-game Mail | In-game Mail frontend/UI | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
In-game Mail | In-game Mail | Mail UI Audio | Sound Designer | Audio ¦ Audio | 0.5 | 1 |  | 0 |  | 0 | 1
In-game Mail | In-game Mail | Mail QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
In-game Mail | In-game Mail | Postbox Concept | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
In-game Mail | In-game Mail | Postbox VFX | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
In-game Mail | In-game Mail | Postbox SFX | Sound Designer | Audio ¦ Audio | 1 | 1 |  | 0 |  | 0 | 1
In-game Mail | In-game Mail | Postbox Model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
In-game Mail | In-game Mail | Restore trash mail | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Mail | In-game Mail | Mark mail as read | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Mail | In-game Mail | Delete mail | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Mail | In-game Mail | Claim items from mail | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Mail | In-game Mail | Send mail from one player to another with items | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Mail | In-game Mail | Restore trash mail | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Mail | In-game Mail | Mark mail as read | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Mail | In-game Mail | Delete mail | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
In-game Mail | In-game Mail | Claim items from mail | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Mail | In-game Mail | Claim currancy and increase ingame gold | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
In-game Mail | In-game Mail | Send mail from one player to another with items | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
In-game Mail | In-game Mail | Create mail UI/UX | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
In-game Mail | In-game Mail | Create mail SFX | Sound Designer | Audio ¦ Audio |  |  |  | 0 |  | 0 | 0
In-game Mail | In-game Mail | Create new mail model | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
In-game Mail | In-game Mail | Mail QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
LFG / Pick-up Groups | LFG / Pick-up Groups | Create Dungeon finder UI/UX | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
LFG / Pick-up Groups | LFG / Pick-up Groups | Connect dungeons to UI | Gameplay Developer | Engineering ¦ Gameplay Engineering | 5 | 8 |  | 0 |  | 0 | 8
LFG / Pick-up Groups | LFG / Pick-up Groups | Create pipeline and deploy | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
LFG / Pick-up Groups | LFG / Pick-up Groups | Create dungeon finder service | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
LFG / Pick-up Groups | LFG / Pick-up Groups | Add player to dungeon finder list | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
LFG / Pick-up Groups | LFG / Pick-up Groups | Fetch a list of players queued up for dungeon by dungon id | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
LFG / Pick-up Groups | LFG / Pick-up Groups | Remove player from dungeon queue | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
LFG / Pick-up Groups | LFG / Pick-up Groups | Connect to redis | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
LFG / Pick-up Groups | LFG / Pick-up Groups | Invite player to party | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
LFG / Pick-up Groups | LFG / Pick-up Groups | Queue group for dungeon | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
LFG / Pick-up Groups | LFG / Pick-up Groups | Send request to add player to dungeon | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
LFG / Pick-up Groups | LFG / Pick-up Groups | Send request to remove player from dungeon | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
LFG / Pick-up Groups | LFG / Pick-up Groups | Send request to fetch player from dungeon | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
LFG / Pick-up Groups | LFG / Pick-up Groups | Remove party from queue after party is full | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
LFG / Pick-up Groups | LFG / Pick-up Groups | Remove party from queue after party is full | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
LFG / Pick-up Groups | LFG / Pick-up Groups | Send player status in dungeon finder | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
LFG / Pick-up Groups | LFG / Pick-up Groups | Get player status in dungeon finder | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Game Bibles
UX/UI Bible | UX/UI Bible | Wireframes | UI/UX Designer | Art ¦ UX/UI | 5.7 | 8.6 |  | 0 |  | 0 | 8.6
Brand Bible | Brand Bible | Colour Palette | Concept Artist | Art ¦ Concept Art | 5.7 | 8.6 |  | 0 |  | 0 | 8.6
Brand Bible | Brand Bible | Typography | Concept Artist | Art ¦ Concept Art | 5.7 | 8.6 |  | 0 |  | 0 | 8.6
Brand Bible | Brand Bible | Game Logo | Concept Artist | Art ¦ Concept Art | 11.4 | 14.3 |  | 0 |  | 0 | 14.3
Art Bible | Art Bible | Environment Bible | Environment Artist | Art ¦ Environment Art |  |  |  | 0 |  | 0 | 0
Art Bible | Art Bible | Animation Bible | Animator | Art ¦ Animation & Rigging |  |  |  | 0 |  | 0 | 0
Art Bible | Art Bible | Character Bible | Character Artist | Art ¦ Character Art |  |  |  | 0 |  | 0 | 0
Art Bible | Art Bible | VFX Bible | VFX Artist | Art ¦ VFX |  |  |  | 0 |  | 0 | 0
Art Bible | Art Bible | Concept Bible | Concept Artist | Art ¦ Concept Art |  |  |  | 0 |  | 0 | 0
Platform
Online Services & Backend | Online Services & Backend | List of servers and their ip address | Backend Developer | Engineering ¦ Backend Engineering | 4 | 5 |  | 0 |  | 0 | 5
Online Services & Backend | Online Services & Backend | Create an endpoint to store player X, Y, Z corrdinates and rotation and server ip address | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Online Services & Backend | Online Services & Backend | Create an endpoint to fetch player position, rotation and IP address | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Online Services & Backend | Online Services & Backend | Create unit test for update and fetch endpoint | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Online Services & Backend | Online Services & Backend | Set player position, rotation, when spawning player | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Online Services & Backend | Online Services & Backend | Conect to last server player left from | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Online Services & Backend | Online Services & Backend | Save player position and rotation and ip every X seconds on server, so if the server crashes we can retrieve this information later | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Online Services & Backend | Online Services & Backend | For network engineer to figure out | Gameplay Developer | Engineering ¦ Gameplay Engineering |  |  |  | 0 |  | 0 | 0
Online Services & Backend | Online Services & Backend | Pass entrance parameters from one server to another | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Online Services & Backend | Online Services & Backend | Set entrace points on map | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Online Services & Backend | Online Services & Backend | Set spawn position according to entrance paramters | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 5 |  | 0 |  | 0 | 5
Partner Loop | Partner Loop | Full partner loop definition/design | Game Designer | Design ¦ Game design | 3 | 5 |  | 0 |  | 0 | 5
Partner Loop | Partner Loop | Create Partner Store | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Integrate partner loop | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Buy game subscription time from website and/or from game | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Buy CH virtual currency | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Complete partner quest | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Purchase partner game from in-game store | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Redeem Partner Steam key | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Download Partner game | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Run partner game from same exe as CH | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Unlock partner item in CH by playing partner game | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Claim partner item from CH mailbox | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Partner functionality QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Full partner loop definition/design | Game Designer | Design ¦ Game design |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Create Partner Store | Backend Developer | Engineering ¦ Backend Engineering | 10 | 20 |  | 0 |  | 0 | 20
Partner Loop | Partner Loop | Integrate partner loop | Backend Developer | Engineering ¦ Backend Engineering | 5 | 10 |  | 0 |  | 0 | 10
Partner Loop | Partner Loop | Buy game subscription time from website and/or from game | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Buy CH virtual currency | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Complete partner quest | Backend Developer | Engineering ¦ Backend Engineering | 0.5 | 10 |  | 0 |  | 0 | 10
Partner Loop | Partner Loop | Purchase partner game from in-game store | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Redeem Partner Steam key | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Partner Loop | Partner Loop | Download Partner game | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Partner Loop | Partner Loop | Unlock partner item in CH by playing partner game | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Partner Loop | Partner Loop | Claim partner item from CH mailbox | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Partner Loop | Partner Loop | Claim partner item from CH mailbox | Gameplay Developer | Engineering ¦ Gameplay Engineering | 2 | 3 |  | 0 |  | 0 | 3
Partner Loop | Partner Loop | Run partner game from same exe as CH | Backend Developer | Engineering ¦ Backend Engineering |  |  |  | 0 |  | 0 | 0
Partner Loop | Partner Loop | Run partner game from same exe as CH | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Partner Loop | Partner Loop | Create IPC between exe launcher and unreal and partner game | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Partner Loop | Partner Loop | Create exe launcher | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Partner Loop | Partner Loop | Run CH in exe launcher | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Partner Loop | Partner Loop | Run partner in exe launcher | Backend Developer | Engineering ¦ Backend Engineering | 3 | 4 |  | 0 |  | 0 | 4
Partner Loop | Partner Loop | Transition to lightweight map before launching partner game from exe launcher | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Partner Loop | Partner Loop | Partner functionality QA | QA | QA ¦ QA |  |  |  | 0 |  | 0 | 0
Live Game
Partner Build
Product Publishing
Website | Website | Create UI to display web browser inside the game launcher | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Website | Website | Pass data between in-launcher browswer and launcher | Gameplay Developer | Engineering ¦ Gameplay Engineering | 3 | 4 |  | 0 |  | 0 | 4
Website | Website | Change play button from subscribe to play when a subscription is active | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Website | Website | Fetch subscription information from backend service | Gameplay Developer | Engineering ¦ Gameplay Engineering | 1 | 2 |  | 0 |  | 0 | 2
Website | Website | New UI/UX for game launcher to support web browser | UI/UX Designer | Art ¦ UX/UI |  |  |  | 0 |  | 0 | 0
Website | Website | Create subscription endpoint in store service with tier rewards / different time lengths (30 , 90 , 180 , 360 ) | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Website | Website | Create an endpoint to cancel subsciption | Backend Developer | Engineering ¦ Backend Engineering | 1 | 2 |  | 0 |  | 0 | 2
Website | Website | Create an endpoint to fetch current subscription information from account managment service | Backend Developer | Engineering ¦ Backend Engineering | 2 | 3 |  | 0 |  | 0 | 3
Website | Website | Create a subscription page in the store | Backend Developer | Engineering ¦ Backend Engineering | 3 | 5 |  | 0 |  | 0 | 5

## Person Dashboard
Person | Role | Department | Primary Stories | Primary Days | Secondary Stories | Secondary Days | Total Days | Available Days | Utilisation | Overloaded?
Mustafa Sibai | CTO | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Daniel Negri | Full Stack Developer | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Nikos Gerontakis | Full Stack Developer | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Samer Balushi | Backend Developer | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Raynor D'Souza | Gameplay Developer | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Ilya Achmetov | Gameplay Developer | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Leon Huang | Gameplay Developer | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Ignasi Ezpeleta | Gameplay Developer | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Roberto | Gameplay Developer | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Matt | Animator | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0%
David Luong | Art Director | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Wojciech Szon | VFX Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Conor McLean | VFX Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Michail Velissaris | VFX Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Stefano Vietina | Technical Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Samuele Piazzi | Technical Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Andrea Rottini | Technical Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Niko Gesell | Concept Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Kerim Turay | Concept Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Gerard Vicen | Concept Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Julian Hartinger | Concept Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Gianluca Perusi | UI/UX Designer | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Larisa Logofatu | Graphic Designer | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Alon | Animator | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Kunjal Asher | Animator | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Maddalena Morello | Character Rigger | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Sasha Krieger | Character Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Dimitris Chrysanthakopoulos | Character Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Rebecca Tomasoni | Character Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Michael Dunnam | Environment Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Ella Amatooni | Environment Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Marc Vives | Environment Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Iosif Alexiou | Environment Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Nick Chrysanthakopoulos | Prop Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Chris Brough | Environment Artist | Art | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Robin Jubber | Game Director | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Yorgos Dritsas | Game Designer | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Nadir Latif | Combat Designer | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Kieron Naylor | Technical Designer | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Nikolas Tziotis | Level Designer | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Seth Dahl | Level Designer | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Panos Andriopoulos | Level Designer | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Maria Cibej | Writer | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Dragan Vuckovic | Sound Designer | Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Aggeliki Peroutsea | Sound Designer | Audio | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hannah Pickard | QA | QA | 0 | 0 | 0 | 0 | 0 | 0 | 0%

## Feature Timeline
Epic | Feature | Total Stories | Total Max Days | Roles Involved
Player Build
Player Build | Player Progression | 28 | 109 | Backend Developer, Game Designer, Gameplay Developer, QA, UI/UX Designer
Player Build | Skill System | 27 | 90 | Backend Developer, Game Designer, Gameplay Developer, QA, Sound Designer, UI/UX Designer
Player Build | Achievements & Trophies | 1 | 0 | Concept Artist
Player Build | FTUE | 20 | 65 | Environment Artist, Game Designer, Level Designer, QA, Sound Designer, UI/UX Designer, VFX Artist, Writer
Player Build | Professions | 39 | 39 | Character Artist, Concept Artist, Environment Artist, Game Designer, Gameplay Developer, QA, Sound Designer, Technical Artist, UI/UX Designer, VFX Artist
Player Build | Character Creation & Customization | 9 | 0 | Character Artist, Concept Artist
Player Build | Garment System | 32 | 74 | Animator, Character Artist, Concept Artist, Game Designer, Gameplay Developer, QA, Sound Designer, Technical Artist, UI/UX Designer
World Systems
World Systems | Foam Corruption | 55 | 50 | Animator, Backend Developer, Character Artist, Environment Artist, Game Designer, Gameplay Developer, QA, Sound Designer, Technical Artist, VFX Artist, Writer
World Systems | Basic Movement System | 15 | 10 | Game Designer, Gameplay Developer, QA
World Systems | Advanced Traversal | 43 | 46 | Animator, Backend Developer, Character Artist, Concept Artist, Environment Artist, Game Designer, Gameplay Developer, QA, Sound Designer, UI/UX Designer, VFX Artist, Writer
World Systems | Navigation | 59 | 113 | Backend Developer, Concept Artist, Environment Artist, Game Designer, Gameplay Developer, QA, Sound Designer, Technical Artist, UI/UX Designer
World Systems | Instancing | 48 | 90 | Backend Developer, Game Designer, Gameplay Developer, QA
World Systems | Dungeon Mechanics | 62 | 123.1 | Backend Developer, Character Artist, Concept Artist, Environment Artist, Game Designer, Gameplay Developer, Level Designer, QA, Sound Designer, Technical Artist, UI/UX Designer, VFX Artist, Writer
World Systems | The Dungeon | 1 | 68.6 | Environment Artist
World Systems | Partner Portal | 9 | 27 | Backend Developer, Environment Artist, Game Designer, Gameplay Developer, VFX Artist
World Systems | Biome - Portal Peak | 55 | 665.8 | Concept Artist, Environment Artist, Game Designer, Level Designer, QA, Sound Designer
World Systems | Biome - Hidden Hills | 17 | 115.4 | Concept Artist, Environment Artist, Game Designer, Level Designer, QA, Sound Designer
World Systems | Biome - Farmlands | 4 | 195.4 | Environment Artist
World Systems | Biome - Whispering Woods | 17 | 26.1 | Concept Artist, Environment Artist, Game Designer, Level Designer, QA, Sound Designer
World Systems | Biome - Downtime | 26 | 195.4 | Concept Artist, Environment Artist, Game Designer, Level Designer, QA
Combat
Combat | Combat Framework | 36 | 153 | Animator, Character Artist, Game Designer, Gameplay Developer, QA, VFX Artist
Combat | Ranged Combat | 3 | 9 | Animator, Game Designer
Combat | Enemies Art | 156 | 242 | Animator, Character Artist, Concept Artist, Game Designer, Gameplay Developer, QA, Sound Designer, Technical Artist, VFX Artist
Combat | PvP Combat | 36 | 286.7 | Concept Artist, Environment Artist, Game Designer, Gameplay Developer, Level Designer, QA, Sound Designer, UI/UX Designer
Combat | Combat Balance & Telemetry | 10 | 25 | Backend Developer, Gameplay Developer
Combat | Combat Abilities | 17 | 88 | Animator, Game Designer, Gameplay Developer, QA, Sound Designer, UI/UX Designer
Combat | Magic | 19 | 47 | Animator, Environment Artist, Game Designer, Gameplay Developer, QA, Sound Designer, UI/UX Designer, VFX Artist
Combat | Full Motion Video (FMV) | 45 | 42 | Backend Developer, Concept Artist, Environment Artist, Game Designer, Gameplay Developer, QA, Sound Designer, UI/UX Designer, Writer
User Space
User Space | User Space Server & Instance | 49 | 266.4 | Animator, Backend Developer, Concept Artist, Environment Artist, Game Designer, Gameplay Developer, Level Designer, QA, Sound Designer, UI/UX Designer, VFX Artist
User Space | User Space Decoration | 11 | 51.4 | Concept Artist, Environment Artist, Gameplay Developer
User Space | Building Houses | 3 | 182.9 | Environment Artist
User Space | Anywhere Door Placement | 18 | 34 | Backend Developer, Gameplay Developer, QA
Items & Inventory
Items & Inventory | Item Core System | 30 | 24 | Animator, Character Artist, Concept Artist, Environment Artist, Game Designer, Gameplay Developer, QA, VFX Artist
Items & Inventory | Equipment System | 12 | 30 | Backend Developer, Gameplay Developer
Items & Inventory | Loot Distribution | 19 | 44 | Backend Developer, Game Designer, Gameplay Developer, QA
Items & Inventory | Mounts / Pets | 18 | 12 | Animator, Character Artist, Concept Artist, Game Designer, Gameplay Developer, QA, VFX Artist
Items & Inventory | Consumables | 4 | 1 | Animator, Concept Artist, QA
Player Economy
Player Economy | Trading System | 39 | 77 | Animator, Backend Developer, Character Artist, Concept Artist, Environment Artist, Game Designer, Gameplay Developer, QA, UI/UX Designer
Player Economy | Currency System | 1 | 0 | Concept Artist
Player Economy | Auction House | 2 | 0 | Backend Developer, QA
Player Economy | In-game Store | 27 | 59 | Backend Developer, Game Designer, Gameplay Developer, QA, Sound Designer, UI/UX Designer
Player Economy | In-game Economy | 4 | 5 | Game Designer, QA
Quest System
Quest System | Quests Backend / Tooling | 27 | 36 | Animator, Backend Developer, Character Artist, Concept Artist, Game Designer, Gameplay Developer, QA, UI/UX Designer, Writer
Quest System | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | 29 | 79.5 | Backend Developer, Concept Artist, Game Designer, Gameplay Developer, QA, Sound Designer, Technical Artist, UI/UX Designer, VFX Artist
Quest System | Quest Reward System | 10 | 10 | Concept Artist, Game Designer, Gameplay Developer, QA, Sound Designer, UI/UX Designer
Quest System | Quest Narrative Content | 24 | 99 | Game Designer, Writer
Quest System | In Game Cinematic (IGC) | 24 | 31 | Game Designer, Gameplay Developer, QA, Writer
Social & Multiplayer
Social & Multiplayer | Game Chat System | 35 | 75 | Backend Developer, Gameplay Developer, UI/UX Designer
Social & Multiplayer | Guilds | 30 | 313.3 | Animator, Backend Developer, Character Artist, Concept Artist, Environment Artist, Game Designer, Gameplay Developer, Level Designer, QA, UI/UX Designer
Social & Multiplayer | Co-op / Party | 39 | 72 | Backend Developer, Game Designer, Gameplay Developer, QA, UI/UX Designer
Social & Multiplayer | In-game Mail | 24 | 36 | Backend Developer, Concept Artist, Environment Artist, Gameplay Developer, QA, Sound Designer, UI/UX Designer, VFX Artist
Social & Multiplayer | LFG / Pick-up Groups | 17 | 44 | Backend Developer, Gameplay Developer, UI/UX Designer
Game Bibles
Game Bibles | UX/UI Bible | 1 | 0 | UI/UX Designer
Game Bibles | Brand Bible | 3 | 0 | Concept Artist
Game Bibles | Art Bible | 5 | 0 | Animator, Character Artist, Concept Artist, Environment Artist, VFX Artist
Platform
Platform | Online Services & Backend | 11 | 30 | Backend Developer, Game Designer, Gameplay Developer
Platform | Partner Loop | 33 | 73 | Backend Developer, Game Designer, Gameplay Developer, QA
Live Game
Partner Build
Product Publishing
Product Publishing | Website | 9 | 25 | Backend Developer, Gameplay Developer, UI/UX Designer