## Plan
WORK STREAMS |  |  |  |  | CONCEPT | [38 empty] | PRE-PRODUCTION | [38 empty] | PRODUCTION | [116 empty] | RELEASE | [155 empty] | LIVE SERVICE | [77 empty] | EARLY PROD — MIN | [37 empty] | EARLY PROD — MAX
[5 empty] | GATE 0 | CONCEPT ~2 months Target: T0 Ideation | [37 empty] | GATE 1 | PRE-PRODUCTION Target: T1-T2 R&D / GDD-TDD-Brief | [37 empty] | GATE 2 | EARLY PROD Target: T3 Prototype | [37 empty] | GATE 3 | MID PRO Target: T4 MVP | [37 empty] | GATE 4 | END PROD Target: T5 Feature Complete | [37 empty] | GATE 5 | ALPHA Target: T6 Player Tested | [37 empty] | GATE 6 | BETA Target: T6 Player Tested | [37 empty] | GATE 7 | LAUNCH Target: T6 Player Ready | [37 empty] | GATE 8 | FIRST RELEASE ~1.5 months Target: T6-T7 Player Ready / Expand | [37 empty] | GATE 9 | LS 1 Live Target: T7 Expand | [37 empty] | GATE 10 | LS 2 Live Target: T8 Scale
Epic | Feature | Size | Current Tier | Notes |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team |  | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team | CEO | Creative Director | Head of Legal | COO | HR Manager | Executive Producer | Producer | Game Producer | Tech Producer | Art Producer | Game Director | Game Design Lead | Level Design Lead | Game Designer | Combat Designer | Level Designer | Technical Designer | Writer | Art Director | Concept Artist | UI/UX Designer | Graphic Designer | Character Artist | Environment Artist | Prop Artist | Animator | Character Rigger | VFX Artist | Technical Artist | CTO | Tech Lead | Gameplay Developer | Full Stack Developer | Backend Developer | Network Engineer | QA | Sound Designer | Platform Team
Player Build
| Player Progression | L | T1: R&D | Design / Game design | [92 empty] | 7 | [6 empty] | 3 | [6 empty] | 2 |  |  |  | 20 |  |  |  |  | 2 | [326 empty] | 7 | [6 empty] | 3 | [6 empty] | 2 |  |  |  | 20 |  |  |  |  | 2 | [14 empty] | 7 | [6 empty] | 3 | [6 empty] | 2 |  |  |  | 20 |  |  |  |  | 2
| Character stats UI |  |  | Art / UX/UI | [99 empty] | 15
| Level up & Stats QA |  |  | QA / QA
| Character stats configuration in connection with other systems |  |  | Design / Game design | [92 empty] | 10 | [349 empty] | 1 | [37 empty] | 25
| Character stats documentation |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 5 | [37 empty] | 12
| Character stats implementation |  |  | Engineering / Gameplay Engineering
| Increase stat when player level up |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Integrate stat system with other systems |  |  | Engineering / Gameplay Engineering | [110 empty] | 20 | [349 empty] | 1 | [37 empty] | 20
| Items give u stats |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Update player stats in backend (player data service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Update stats UI |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| fetch player stats from backend service (player data service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Player level up UI |  |  | Art / UX/UI | [99 empty] | 3 | [349 empty] | 2 | [37 empty] | 10
| Player level up configuration |  |  | Design / Game design | [92 empty] | 15 | [349 empty] | 0.5 | [37 empty] | 20
| Player level up documentation |  |  | Design / Game design | [92 empty] | 14 | [349 empty] | 1 | [37 empty] | 18
| player level up integration |  |  | Engineering / Gameplay Engineering
| Earn different types of EXP depending on objective |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fetch and update UI for player level and exp |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fetch player level and exp from (player data service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Update player level and exp with (player data service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Garment System | M | T0: Ideation | Design / Game design | [92 empty] | 20 | [6 empty] | 20 | [7 empty] | 10 |  |  | 60 | [331 empty] | 7 | [6 empty] | 20 | [7 empty] | 10 |  |  | 60 | [19 empty] | 10 | [6 empty] | 20 | [7 empty] | 10 |  |  | 60
| Equiment Concepts |  |  | Art / Concept Art
| Equipment Concepts |  |  | Art / Concept Art
| Equipment Models |  |  | Art / Character Art
| Garment Type SFX |  |  | Audio / Audio | [115 empty] | 3 | [349 empty] | 2 | [37 empty] | 4
| Equipment Stats integrated with character stats |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Equipment QA |  |  | QA / QA
| Garment System QA |  |  | QA / QA
| Garment System GDD/TDD |  |  | Design / Game design | [92 empty] | 7 | [349 empty] | 4 | [37 empty] | 10
| Vertical Slice garments |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 5 | [37 empty] | 7
| Garment System Integration |  |  | Engineering / Gameplay Engineering
| Equip and unequped based on garment system |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Garment System UI |  |  | Art / UX/UI | [99 empty] | 14 | [349 empty] | 10 | [37 empty] | 15
Player equips clothing
| Cull occluded body parts |  |  | Art / TechArt
| Equipment QA |  |  | QA / QA
| Freeze cloth sim |  |  | Art / Animation & Rigging | [104 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Garment System QA |  |  | QA / QA
| Maya tool to represent cloth sim like unreal |  |  | Art / Animation & Rigging | [104 empty] | 15 | [349 empty] | 10 | [37 empty] | 15
| Move socket based on clothing type |  |  | Art / Animation & Rigging | [104 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Setup budget for skining and cloth sim |  |  | Art / Animation & Rigging | [104 empty] | 7 | [349 empty] | 5 | [37 empty] | 7
| Setup capsules for cloth collision on character |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| In-game Tutorial |  |  | Design / Game design | [92 empty] | 16 | [5 empty] | 5 | 5 |  |  | 15 |  | 5 |  | 12 | 10 |  |  | 15 |  |  |  |  | 2 | [326 empty] | 16 | [5 empty] | 5 | 5 |  |  | 15 |  | 5 |  | 12 | 10 |  |  | 15 |  |  |  |  | 2 | [14 empty] | 16 | [5 empty] | 5 | 5 |  |  | 15 |  | 5 |  | 12 | 10 |  |  | 15 |  |  |  |  | 2
| Skill System (1 skill tree active) |  |  | Design / Game design | [92 empty] | 20 | [6 empty] | 15 | [6 empty] | 5 |  |  |  | 35 |  |  |  |  | 7 | [326 empty] | 20 | [6 empty] | 15 | [6 empty] | 5 |  |  |  | 35 |  |  |  |  | 7 | [14 empty] | 20 | [6 empty] | 15 | [6 empty] | 5 |  |  |  | 35 |  |  |  |  | 7
| Controls UI |  |  | Art / UX/UI | [92 empty] | 16 | [5 empty] | 5 | 4 |  |  | 15 |  | 5 |  | 12 | 10 |  |  | 15 |  |  |  |  | 2 | [326 empty] | 16 | [5 empty] | 5 | 2 |  |  | 15 |  | 5 |  | 12 | 10 |  |  | 15 |  |  |  |  | 2 | [14 empty] | 16 | [5 empty] | 5 | 4 |  |  | 15 |  | 5 |  | 12 | 10 |  |  | 15 |  |  |  |  | 2
| Controls UI |  |  | Art / VFX
| Narrative |  |  | Design / Narrative | [96 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| Tutorial QA check |  |  | QA / QA
| Tutorial cave contents |  |  | Design / Game design | [92 empty] | 2 | [349 empty] | 1 | [37 empty] | 5
| Skill System Configuration |  |  | Design / Game design | [92 empty] | 5 | [6 empty] | 15 | [6 empty] | 5 |  |  |  | 35 |  |  |  |  | 7 | [326 empty] | 4 | [6 empty] | 15 | [6 empty] | 5 |  |  |  | 35 |  |  |  |  | 7 | [14 empty] | 25 | [6 empty] | 15 | [6 empty] | 5 |  |  |  | 35 |  |  |  |  | 7
| Skill System Documentation |  |  | Design / Game design | [92 empty] | 15 | [349 empty] | 4 | [37 empty] | 13
| Skill System Implementation |  |  | Engineering / Gameplay Engineering
| Add new abilities to skill tree |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| Add new weapons to skill tree |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Connect skill tree to UI |  |  | Engineering / Gameplay Engineering | [110 empty] | 6 | [349 empty] | 4 | [37 empty] | 6
| Create frontend for skill tree in internal dashboard |  |  | Engineering / Backend Engineering | [112 empty] | 7 | [349 empty] | 5 | [37 empty] | 7
| Create new collection for weapon skill tree (player data service) |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create weapon skill tree / nodes in (internal dashboard service) |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Fetch player skill tree per weapon (player data service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fetch weapon skill tree / nodes in (internal dashboard service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fetech all skill trees from backend |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Remove weapon skill tree / nodes in (internal dashboard service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Sync all skill trees to backend, tool |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Update all skill trees from backend |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Update player skill tree per weapon (player data service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Update weapon skill tree / nodes in (internal dashboard service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| endpoint to reset skill tree for weapons |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Skill System UI |  |  | Art / UX/UI
| Skill system QA |  |  | QA / QA
| Skill Tree UI Audio |  |  | Audio / Audio | [115 empty] | 8 | [349 empty] | 7 | [37 empty] | 14
| Skills in-game audio |  |  | Audio / Audio | [115 empty] | 8 | [349 empty] | 7 | [37 empty] | 14
| Tutorial Cave Layout Fixes |  |  | Design / Level design | [92 empty] | 16 |  | 10 |  |  |  | 5 | 5 |  |  | 15 |  | 5 |  | 12 | 10 |  |  | 15 |  |  |  |  | 2 | [326 empty] | 16 |  | 7 |  |  |  | 5 | 5 |  |  | 15 |  | 5 |  | 12 | 10 |  |  | 15 |  |  |  |  | 2 | [14 empty] | 16 |  | 15 |  |  |  | 5 | 5 |  |  | 15 |  | 5 |  | 12 | 10 |  |  | 15 |  |  |  |  | 2
| Tutorial Cave lighting |  |  | Art / Environment Art
| Tutorial Configuration/set up/texts |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 2 | [37 empty] | 20
| Tutorial UI |  |  | Art / UX/UI | [99 empty] | 6 | [349 empty] | 4 | [37 empty] | 10
| Tutorial VFX |  |  | Art / VFX
| Tutorial cave Ambience & SFX |  |  | Audio / Audio | [115 empty] | 7 | [349 empty] | 5 | [37 empty] | 10
| Tutorial cave set dressing fixes |  |  | Art / Environment Art
World Systems
| Advanced Traversal | L | T1: R&D | Design / Game design | [92 empty] | 2 | [349 empty] | 5 | [37 empty] | 25
| Glider Stamina UI |  |  | Art / UX/UI | [99 empty] | 2 | [349 empty] | 2 | [37 empty] | 3
| Gliding Animations |  |  | Art / Animation & Rigging | [104 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| Gliding Concepts |  |  | Art / Concept Art
| Check if ability is unlock to glide |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| Convert gliding to blend space |  |  | Art / Animation & Rigging | [104 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| Spawn gliding actor |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Gliding Device |  |  | Art / Character Art
| Gliding QA |  |  | QA / QA
| Gliding Integration |  |  | Engineering / Gameplay Engineering
| Gliding SFX |  |  | Audio / Audio | [115 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Gliding VFX |  |  | Art / VFX
| Portals spawning & Xyron moving through portals |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| 5 or 6 mini quests |  |  | Design / Game design | [92 empty] | 8 | [349 empty] | 5 | [37 empty] | 20
| Narrative for Xyron quests |  |  | Design / Narrative | [96 empty] | 2 | [349 empty] | 1 | [37 empty] | 10
| Spawning portals SFX |  |  | Audio / Audio | [115 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| Xyron voiceover narrative |  |  | Design / Narrative | [96 empty] | 2 | [349 empty] | 0.5 | [37 empty] | 5
| Xyron/portals spawning QA |  |  | QA / QA
| Xyron voiceover |  |  | Audio / Audio | [115 empty] | 8 | [349 empty] | 7 | [37 empty] | 14
| Xyron/portals spawning QA |  |  | QA / QA
| Navigation | M | T0: Ideation | Design / Game design
| Compass |  |  | Engineering / Gameplay Engineering
| Compass Integration |  |  | Engineering / Gameplay Engineering
| Compass QA check |  |  | QA / QA
| Compass UI |  |  | Art / UX/UI | [99 empty] | 10 | [349 empty] | 2 | [37 empty] | 5
| Party player distance |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Rotate compass with camera |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Show POI distance |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Show distance to objective |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Show or hide compass from options menu |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Show quest distance |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Special NPCs distance |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fog-of-war |  |  | Engineering / Gameplay Engineering
| Create fog of war grid |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fog of war QA check |  |  | QA / QA
| Fog of war changes based on player visited locations |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fog of war shader |  |  | Art / TechArt
| Hide/Unhide markers that are in fog of war |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Sync fog of war to backend |  |  | Engineering / Backend Engineering | [112 empty] | 5 | [349 empty] | 5 | [37 empty] | 5
| fetch fog of war and update it from unreal side |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Minimap |  |  | Engineering / Gameplay Engineering
| Minimap Levels |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 5 | [37 empty] | 20
| Minimap QA check |  |  | QA / QA
| Minimap UI |  |  | Art / UX/UI | [99 empty] | 10
| Minimap assets |  |  | Art / Concept Art
| Minimap quest navigation support |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Party player position |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Special NPCs positions |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Zoom out/in |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| World Map |  |  | Design / Game design | [92 empty] | 10 | [349 empty] | 10 | [37 empty] | 25
| Indoor Map |  |  | Engineering / Gameplay Engineering | [110 empty] | 7 | [349 empty] | 5 | [37 empty] | 7
| Map QA check |  |  | QA / QA
| Map markers sfx |  |  | Audio / Audio | [115 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| POI names |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| Party player position |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Quest markers and objectives support |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Quest markers support |  |  | Engineering / Gameplay Engineering
| Special NPCs positions |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| World Map UI |  |  | Art / UX/UI | [99 empty] | 10
| World Map asset integration |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| World Map background asset |  |  | Art / Concept Art
| Zoom out/in |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Instancing | L | T0: Ideation | Engineering / Backend Engineering | [92 empty] | 5 | [14 empty] | 10 |  |  | 120 | [331 empty] | 5 | [14 empty] | 10 |  |  | 120 | [19 empty] | 5 | [14 empty] | 10 |  |  | 120
| Create a queue service |  |  | Engineering / Backend Engineering
| Create Nodejs service |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Instancing QA |  |  | QA / QA
| Custom HPA for Kubernetes |  |  | Engineering / Backend Engineering
| Create Nodejs service |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create metrics to scale up and down |  |  | Engineering / Backend Engineering | [112 empty] | 6 | [349 empty] | 4 | [37 empty] | 6
| Create rules when to merge instances |  |  | Engineering / Backend Engineering | [112 empty] | 6 | [349 empty] | 4 | [37 empty] | 6
| Integrate Kubernetes API |  |  | Engineering / Backend Engineering | [112 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Custom service for overworld zones |  |  | Engineering / Backend Engineering
| Call backend to figure out which overworld zones to connect to |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create overworld zones instance |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create a list of all overworld zones that are currently running in redis |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create a service in nodejs |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Delete overworld zones instance |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fetch overworld zones ip by id |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Inform UE server that a player is getting migrated to another UE server |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Inform UE server that a player is getting migrated to another UE server |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Search for overworld zones by id |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Custom service to handle dungeons |  |  | Engineering / Backend Engineering
| Call backend to figure out which dungeon to connect to |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a list of all dungeons that are currently running in redis |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create a service in nodejs |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create dungeon instance |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Delete dungeon instance |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fetch dungeon ip by id |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Search for dungeon by id |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Dungeon Instancing |  |  | Engineering / Backend Engineering
| GDD Documentation |  |  | Design / Game design | [92 empty] | 2 | [349 empty] | 3 | [37 empty] | 20
| Guild House instancing support |  |  | Engineering / Backend Engineering
| Instancing Documentation |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Player general stat before disconnecting service |  |  | Engineering / Backend Engineering
| Create a service in nodejs |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a way to save player stat (which server they were connected to last, which party were they connected to, etc..) before disconnecting |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Setup Kubernetes on Azure |  |  | Engineering / Backend Engineering
| Setup azure |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| User Space Instancing support |  |  | Engineering / Backend Engineering
| Zones Instancing |  |  | Engineering / Backend Engineering
| Instancing QA |  |  | QA / QA
| Full Motion Video (FMV) |  |  | Design / Game design | [92 empty] | 1
| Static pictures intro + voiceover |  |  | Design / Game design | [92 empty] | 10 | [349 empty] | 8 | [37 empty] | 30
| In-game cutscenes |  |  | Engineering / Gameplay Engineering
| Basic movement system |  |  | Design / Game design
| World Resources |  |  | Design / Game design
| Corruption |  |  | Design / Game design | [89 empty] | 2 |  |  | 3 | [17 empty] | 30 | [328 empty] | 2 |  |  | 3 | [17 empty] | 30 | [16 empty] | 2 |  |  | 3 | [17 empty] | 30
| Forge |  |  | Design / Game design | [92 empty] | 12 | [349 empty] | 5 | [37 empty] | 20
| Dungeons mechanics |  |  | Design / Game design | [110 empty] | 20 | [331 empty] | 5 | [17 empty] | 20 | [19 empty] | 15 | [17 empty] | 20
| Puzzles |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 10 | [37 empty] | 15
| Downtime Final set dressing (L) |  |  | Art / Environment Art
| Speedup Archway |  |  | Design / Game design | [442 empty] | 3 | [37 empty] | 10
| Portal Peak (Medium) |  |  | Design / Game design
| POI: The Two Hills (S) |  |  | Design / Game design
| POI: Portal Dimension (XS) |  |  | Design / Game design
| POI: Final Tower |  |  | Design / Game design
| POI: Waterfall Beauty Spot (S) |  |  | Design / Game design
| Wolves |  |  | Design / Game design
| Goblins |  |  | Design / Game design
| Skeletons |  |  | Design / Game design
| Slimes |  |  | Design / Game design
| Corrupted Guardian |  |  | Design / Game design
| Carapax (Hero, but one type) |  |  | Design / Game design
| World/buiding scale design |  |  | Design / Game design | [92 empty] | 21
| Camera behavior |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 2 | [37 empty] | 14
Create a system to allow a player to interact with the world and have event only happen for that player in a multiplayer setting
| Session |  |  | Engineering / Backend Engineering
| Portal Dimension (XS) |  |  | Design / Game design
| Corrupted enemies |  |  | Design / Game design
Sync last known player position
| Create phasing system |  |  | Engineering / Gameplay Engineering
| Create phasing system |  |  | Engineering / Backend Engineering
| Document phasing system |  |  | Engineering / Backend Engineering
| Document phasing system |  |  | Engineering / Backend Engineering
| Research phasing system |  |  | Engineering / Backend Engineering
| Research phasing system |  |  | Engineering / Gameplay Engineering
| Animation |  |  | Art / Animation & Rigging
| Animation |  |  | Art / Animation & Rigging
| Animation |  |  | Art / Animation & Rigging
| Animation |  |  | Art / Animation & Rigging
| Animation |  |  | Art / Animation & Rigging
| Animation |  |  | Art / Animation & Rigging
| Animation |  |  | Art / Animation & Rigging
| Create animation graph |  |  | Art / Animation & Rigging | [104 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Create animation graph |  |  | Art / Animation & Rigging | [104 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Create animation graph |  |  | Art / Animation & Rigging | [104 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Create animation graph |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 2 | [37 empty] | 2
| Create animation graph |  |  | Art / Animation & Rigging | [104 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Create control rig |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create control rig |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create control rig |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create control rig |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Custom death sequance |  |  | Art / Animation & Rigging | [104 empty] | 7 | [349 empty] | 5 | [37 empty] | 7
| Custom death sequance |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| RBF setup |  |  | Art / Animation & Rigging | [104 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| Seperate clothing from body |  |  | Art / Animation & Rigging | [104 empty] | 7 | [349 empty] | 5 | [37 empty] | 7
| Seperate clothing from body |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 2 | [37 empty] | 2
| Archway Models |  |  | Art / Environment Art
| Archway Placement |  |  | Design / Game design | [442 empty] | 1 | [37 empty] | 7
| Archway SFX |  |  | Audio / Audio | [115 empty] | 0 | [349 empty] | 0 | [37 empty] | 0
| Archway QA |  |  | QA / QA
| Archway VFX |  |  | Art / VFX
| Win Fanfare VFX |  |  | Art / VFX
| Archway race design |  |  | Design / Game design | [92 empty] | 3
| Camera behavior implementation/fixes |  |  | Engineering / Gameplay Engineering
| Camera QA |  |  | QA / QA
| Implement camera according to design |  |  | Engineering / Gameplay Engineering | [110 empty] | 7 | [349 empty] | 6 | [37 empty] | 7
| Carapax AI design |  |  | Design / Game design | [92 empty] | 4
| Combat Behavior |  |  | Engineering / Gameplay Engineering
| Combat Behavior |  |  | Engineering / Gameplay Engineering
| Combat Behavior |  |  | Engineering / Gameplay Engineering
| Combat Behavior |  |  | Engineering / Gameplay Engineering
| Combat Behavior |  |  | Engineering / Gameplay Engineering
| Combat Behavior |  |  | Engineering / Gameplay Engineering
| Make combat moves |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Make combat moves |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Make combat moves |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Make combat moves |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Make combat moves |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Make combat moves |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Combat Camera |  |  | Design / Game design | [92 empty] | 9 | [349 empty] | 4 | [37 empty] | 10
| Camera QA |  |  | QA / QA
| Component System Design |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 2 | [37 empty] | 12
| Concept |  |  | Art / Concept Art
| Concept |  |  | Art / Concept Art
| Concept |  |  | Art / Concept Art
| Concept |  |  | Art / Concept Art
| Concept |  |  | Art / Concept Art
| Concept |  |  | Art / Concept Art
| Concept |  |  | Art / Concept Art
| Corrupted Vines |  |  | Design / Game design | [89 empty] | 2 |  |  | 1 | [17 empty] | 30 | [328 empty] | 2 |  |  | 0.5 | [17 empty] | 30 | [16 empty] | 2 |  |  | 5 | [17 empty] | 30
| Corrupted VFX |  |  | Art / VFX
| Corrupted texture |  |  | Art / TechArt
| Corrupted vines behavior & visual QA |  |  | QA / QA
| Vine NPC Narrative |  |  | Design / Narrative | [96 empty] | 1
| Vines Foliage |  |  | Art / Environment Art
| Crafted Weapon Parts in-game Audio |  |  | Audio / Audio | [115 empty] | 5 | [349 empty] | 5 | [37 empty] | 10
| Crafting Desk |  |  | Art / Environment Art
| Cutscene content |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 5 | [37 empty] | 20
| Narrative |  |  | Design / Narrative | [96 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| DA combination setup |  |  | Art / TechArt
| Design |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 10
| Design |  |  | Design / Game design | [92 empty] | 9 | [349 empty] | 3 | [37 empty] | 10
| Design |  |  | Design / Game design | [92 empty] | 9 | [349 empty] | 3 | [37 empty] | 10
| Design |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 10
| Design |  |  | Design / Game design | [92 empty] | 2 | [349 empty] | 2 | [37 empty] | 10
| Design |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 2 | [37 empty] | 5
| Design |  |  | Design / Game design
| Quest structure |  |  | Design / Game design | [92 empty] | 4 | [349 empty] | 1 | [37 empty] | 3
| Downtime Auction House storefront model |  |  | Art / Environment Art
| Downtime Bank storefront model |  |  | Art / Environment Art
| Downtime Barbersmith storefront model |  |  | Art / Environment Art
| Downtime QA |  |  | QA / QA
| Downtime NPC placement |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 4 | [37 empty] | 10
| Downtime Shops closed area |  |  | Design / Game design | [92 empty] | 2 | [349 empty] | 2 | [37 empty] | 5
| Downtime Social Hub Area Blockout |  |  | Design / Level design | [94 empty] | 6 | [349 empty] | 6 | [37 empty] | 15
| Downtime Tavern Blockout |  |  | Design / Level design | [94 empty] | 7 | [349 empty] | 3 | [37 empty] | 15
| Downtime Tavern Concept |  |  | Art / Concept Art
| Downtime Tavern Model |  |  | Art / Environment Art
| Downtime Tavern Props |  |  | Art / Environment Art
| Downtime shops storefronts models |  |  | Art / Environment Art
| Dungeon impelmenation | [113 empty] | 20 | [349 empty] | 20 | [37 empty] | 20
| Dungeon UI |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Dungeon character |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Dungeon end reward and condition |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Dungeon gameplay loop |  |  | Engineering / Gameplay Engineering | [110 empty] | 20 | [349 empty] | 10 | [37 empty] | 20
| Join dungeon |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Transition to dungeon |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| dungeon character respawn |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| dungeon transition to out of dungeon |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Dungeons documentation |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 2 | [37 empty] | 15
| Narrative |  |  | Design / Narrative | [96 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 2
| Equipment Stats integrated with character stats |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 5 | [37 empty] | 10
| Equipment Stats integrated with character stats |  |  | Engineering / Gameplay Engineering
| QA check |  |  | QA / QA
| Final Tower Audio |  |  | Audio / Audio | [115 empty] | 2 | [349 empty] | 3 | [37 empty] | 5
| Portal Dimension QA |  |  | QA / QA
| Final Tower Blockout |  |  | Design / Level design | [94 empty] | 5 | [349 empty] | 1 | [37 empty] | 15
| Final Tower Concept |  |  | Art / Concept Art
| Final Tower Design |  |  | Design / Game design | [92 empty] | 1 | [349 empty] | 1 | [37 empty] | 4
| Final Tower Foliage |  |  | Art / Environment Art
| Final Tower Props Build |  |  | Art / Environment Art
| Final Tower layout |  |  | Art / Environment Art
| Foam Corruption |  |  | Design / Game design | [89 empty] | 2 |  |  | 3 | [17 empty] | 30 | [328 empty] | 2 |  |  | 3 | [17 empty] | 30 | [16 empty] | 2 |  |  | 3 | [17 empty] | 30
| Foam Corruption QA |  |  | QA / QA
| Foam Corruption SFX |  |  | Audio / Audio | [115 empty] | 2 | [349 empty] | 2 | [37 empty] | 3
| Foam Corruption SFX, VFX design |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 3 | [37 empty] | 10
| Foam Corruption Techart |  |  | Art / TechArt
| Foam Corruption VFX |  |  | Art / VFX
| Foam Corruption cleansing animations |  |  | Art / Animation & Rigging | [104 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Foam Corruption cleansing weapon |  |  | Art / Character Art
| Foam Corruption integration |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 4 | [37 empty] | 5
| Link with corruption gun |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| Make corruption come back after a set time |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Quest tracking system |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Trigger objective when clean is done |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Forge Concepts |  |  | Art / Concept Art
| Forge Crafting Audio |  |  | Audio / Audio | [115 empty] | 5 | [349 empty] | 3 | [37 empty] | 7
| Forge Documentation |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 10
| Forge Integration |  |  | Engineering / Gameplay Engineering
| Forge Props |  |  | Art / Character Art
| Forge QA |  |  | QA / QA
| DA combination setup |  |  | Art / TechArt
| Forge UI |  |  | Art / UX/UI | [99 empty] | 10 | [349 empty] | 5 | [37 empty] | 15
| Forge VFX |  |  | Art / VFX
| Goblin AI behaviour |  |  | Design / Game design | [92 empty] | 4
| Goblin montages |  |  | Art / Animation & Rigging
| Asset Validation |  |  | Art / TechArt
| Asset Validation |  |  | Art / TechArt
| Asset Validation |  |  | Art / TechArt
| Asset Validation |  |  | Art / TechArt
| Asset Validation |  |  | Art / TechArt
| Asset Validation |  |  | Art / TechArt
| Asset Validation |  |  | Art / TechArt
| Intro sequence plays 3 slides with voiceover |  |  | Engineering / Backend Engineering
| Intro sequence plays 3 slides with voiceover |  |  | Engineering / Gameplay Engineering
| Allow this to be triggered from quest |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create a system to disallow the player from moving while in FMV |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| Create intro sequence controller |  |  | Engineering / Backend Engineering
| Create intro sequence controller |  |  | Engineering / Gameplay Engineering
| Display static slides full-screen |  |  | Engineering / Backend Engineering
| Display static slides full-screen |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Display subtitles synced to VO |  |  | Engineering / Backend Engineering
| Display subtitles synced to VO |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Final art production |  |  | Art / Concept Art
| Implement skip behavior |  |  | Engineering / Backend Engineering
| Implement skip behavior |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Implement transition to gameplay/menu |  |  | Engineering / Backend Engineering
| Implement transition to gameplay/menu |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Integrate final art + VO assets |  |  | Engineering / Backend Engineering
| Integrate final art + VO assets |  |  | Design / Game design
| Play voiceover synced to sequence |  |  | Engineering / Backend Engineering
| Play voiceover synced to sequence |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| QA + fix blockers |  |  | QA / QA
| Subtitles production |  |  | Design / Game design | [92 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 5
| Tool for designers |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| UI Design |  |  | Art / UX/UI
| VO production |  |  | Audio / Audio | [115 empty] | 3 | [349 empty] | 6 | [37 empty] | 10
| VO production |  |  | Design / Game design
| Intro supports FMV |  |  | Engineering / Backend Engineering
| Intro supports FMV |  |  | Engineering / Gameplay Engineering
| Create a system to disallow the player from moving while in FMV |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| Create placeholder FMV playback flow |  |  | Engineering / Backend Engineering
| Create placeholder FMV playback flow and allow designers to set the FMV easily |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| FMV Production |  |  | Art / Environment Art
| Fix FMV blocker bugs |  |  | Engineering / Backend Engineering
| Implement FMV skip behavior |  |  | Engineering / Backend Engineering
| Implement FMV skip behavior |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Implement transition after FMV |  |  | Engineering / Backend Engineering
| Implement transition after FMV - Fade in/Fade out system |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Integrate final/near-final FMV asset |  |  | Engineering / Backend Engineering
| Integrate final/near-final FMV asset |  |  | Engineering / Gameplay Engineering
| Narrative - Cinematic scripting |  |  | Design / Narrative | [96 empty] | 1 | [349 empty] | 1 | [37 empty] | 3
| QA playback across target builds |  |  | QA / QA
| Locomotion Integration |  |  | Engineering / Gameplay Engineering
| Double Jump |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| Iteration |  |  | Design / Game design | [92 empty] | 5
| Jump |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| Locomotion QA check |  |  | QA / QA
| Run |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| Sprint |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| Walk |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| Manage player session |  |  | Engineering / Backend Engineering
| Create a session service |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Record if player is online in redis |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Model |  |  | Art / Character Art
| Model |  |  | Art / Character Art
| Model |  |  | Art / Character Art
| Model |  |  | Art / Character Art
| Model |  |  | Art / Character Art
| Model |  |  | Art / Character Art
| Model |  |  | Art / Character Art
| Multiplayer enviromental puzzle design |  |  | Design / Game design | [92 empty] | 12 | [349 empty] | 5 | [37 empty] | 20
| Multiplayer enviromental puzzle integration |  |  | Engineering / Gameplay Engineering
| Make puzzle |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Puzzles QA |  |  | QA / QA
| Multiplayer enviromental puzzle layout |  |  | Design / Level design | [94 empty] | 10 | [349 empty] | 4 | [37 empty] | 20
| Multiplayer interactions (toasts) |  |  | Design / Game design | [92 empty] | 2 | [349 empty] | 2 | [37 empty] | 15
| NPC behaviour document |  |  | Design / Game design | [92 empty] | 2
| Narrative |  |  | Design / Game design | [92 empty] | 1 | [349 empty] | 2 | [37 empty] | 5
| PP Audio |  |  | Audio / Audio | [115 empty] | 15 | [349 empty] | 14 | [37 empty] | 18
| Portal Peak QA |  |  | QA / QA
| PP Blockout |  |  | Design / Level design | [94 empty] | 20 | [349 empty] | 10 | [37 empty] | 30
| PP Concept |  |  | Art / Concept Art
| PP Design |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 10
| PP Foliage |  |  | Art / Environment Art
| PP Props Build |  |  | Art / Environment Art
| PP layout |  |  | Art / Environment Art
| Persistent leaderboards |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
Player can server travel between zones semlessly
| For network engineer to figure out |  |  | Engineering / Gameplay Engineering
Player can server travel between zones with loading screen
| Pass entrance parameters from one server to another |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Set entrace points on map |  |  | Design / Game design
| Set spawn position according to entrance paramters |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Portal Dimension Audio |  |  | Audio / Audio | [115 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| Portal Dimension Audio |  |  | Audio / Audio
| Portal Dimension QA |  |  | QA / QA
| Portal Dimension QA |  |  | QA / QA
| Portal Dimension Blockout |  |  | Design / Level design | [444 empty] | 1 | [37 empty] | 15
| Portal Dimension Blockout |  |  | Design / Level design
| Portal Dimension Concept |  |  | Art / Concept Art
| Portal Dimension Concept |  |  | Art / Concept Art
| Portal Dimension Design |  |  | Design / Game design | [92 empty] | 1 | [349 empty] | 1 | [37 empty] | 4
| Portal Dimension Design |  |  | Design / Game design
| Portal Dimension Foliage |  |  | Art / Environment Art
| Portal Dimension Foliage |  |  | Art / Environment Art
| Portal Dimension Props Build |  |  | Art / Environment Art
| Portal Dimension Props Build |  |  | Art / Environment Art
| Portal Dimension layout |  |  | Art / Environment Art
| Portal Dimension layout |  |  | Art / Environment Art
| Rigging |  |  | Art / Animation & Rigging | [104 empty] | 10 | [349 empty] | 10 | [37 empty] | 10
| Rigging |  |  | Art / Animation & Rigging | [104 empty] | 10 | [349 empty] | 10 | [37 empty] | 10
| Rigging |  |  | Art / Animation & Rigging | [104 empty] | 10 | [349 empty] | 10 | [37 empty] | 10
| Rigging |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 2 | [37 empty] | 2
| Rigging |  |  | Art / Animation & Rigging
| Rigging |  |  | Art / Animation & Rigging | [104 empty] | 10 | [349 empty] | 10 | [37 empty] | 10
| Rigging |  |  | Art / Animation & Rigging | [104 empty] | 15 | [349 empty] | 5 | [37 empty] | 15
| SFX |  |  | Audio / Audio | [115 empty] | 7 | [349 empty] | 7 | [37 empty] | 14
| SFX |  |  | Audio / Audio | [115 empty] | 0 | [349 empty] | 0 | [37 empty] | 0
| SFX |  |  | Audio / Audio | [115 empty] | 0 | [349 empty] | 0 | [37 empty] | 0
| SFX |  |  | Audio / Audio | [115 empty] | 3 | [349 empty] | 3 | [37 empty] | 7
| SFX |  |  | Audio / Audio | [115 empty] | 7 | [349 empty] | 5 | [37 empty] | 8
| Carapax QA |  |  | QA / QA
| Corrupted Enemies QA |  |  | QA / QA
| Goblins QA |  |  | QA / QA
| Skeletons QA |  |  | QA / QA
| Slimes QA |  |  | QA / QA
| Safety System |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 3 | [37 empty] | 5
| Shield |  |  | Design / Game design | [92 empty] | 4 | [349 empty] | 2 | [37 empty] | 6
| Shield Asset |  |  | Art / Environment Art
| Shield animations |  |  | Art / Animation & Rigging
| Skeleton AI behaviour |  |  | Design / Game design | [92 empty] | 4
| Skeleton montages |  |  | Art / Animation & Rigging
| Slimes AI behaviour |  |  | Design / Game design | [92 empty] | 2
| Starting Chest |  |  | Design / Game design | [442 empty] | 0.5 | [37 empty] | 5
| Chest VFX |  |  | Art / VFX
| Chest animation |  |  | Art / Animation & Rigging | [104 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| Chest concept |  |  | Art / Concept Art
| Chest model |  |  | Art / Environment Art
| QA check |  |  | QA / QA
| Starting Sword |  |  | Design / Game design | [92 empty] | 4 | [349 empty] | 0.5 | [37 empty] | 5
| Equipment Stats integrated with character stats |  |  | Engineering / Gameplay Engineering
| QA check |  |  | QA / QA
| Sword VFX |  |  | Art / VFX
| Sword animations |  |  | Art / Animation & Rigging | [104 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Sword concept |  |  | Art / Concept Art
| Sword model |  |  | Art / Character Art
| The Two Hills Audio |  |  | Audio / Audio | [115 empty] | 4 | [349 empty] | 4 | [37 empty] | 6
| The Two Hills QA |  |  | QA / QA
| The Two Hills Blockout |  |  | Design / Level design | [94 empty] | 15 | [349 empty] | 3 | [37 empty] | 15
| The Two Hills Concept |  |  | Art / Concept Art
| The Two Hills Design |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 4 | [37 empty] | 10
| The Two Hills Foliage |  |  | Art / Environment Art
| The Two Hills Props Build |  |  | Art / Environment Art
| The Two Hills layout |  |  | Art / Environment Art
| The game supports cutscenes |  |  | Engineering / Gameplay Engineering
| Basic cutscene sequencing (timeline) |  |  | Engineering / Gameplay Engineering
| Camera control during cutscene |  |  | Engineering / Gameplay Engineering
| Custom camera animations |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Custom camera position and rotation |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Cutscene skip functionality |  |  | Engineering / Gameplay Engineering
| Cutscene stability (QA & fixes) |  |  | QA / QA
| Cutscene trigger system |  |  | Engineering / Gameplay Engineering
| Dialogue playback (in-cutscene) |  |  | Engineering / Gameplay Engineering
| NPC/character sequencing |  |  | Engineering / Gameplay Engineering
| Player control lock/unlock |  |  | Engineering / Gameplay Engineering
| Stream camera position (world partition) |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Transition in/out of cutscene |  |  | Engineering / Gameplay Engineering
| Timed Corruption |  |  | Design / Game design | [89 empty] | 2 |  |  | 3 | [17 empty] | 30 | [328 empty] | 2 |  |  | 10 | [17 empty] | 30 | [16 empty] | 2 |  |  | 40 | [17 empty] | 30
| Replicate animation |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Timed Corruption 3D Assets |  |  | Art / Environment Art
| Timed Corruption Design |  |  | Design / Game design | [92 empty] | 10 | [349 empty] | 2 | [37 empty] | 15
| Timed Corruption Integration |  |  | Engineering / Gameplay Engineering
| Timed Corruption QA |  |  | QA / QA
| Timed Corruption SFX |  |  | Audio / Audio | [115 empty] | 5 | [349 empty] | 3 | [37 empty] | 6
| Timed Corruption Server & Multiplayer |  |  | Engineering / Backend Engineering
| Timed Corruption TechArt |  |  | Art / TechArt
| Timed Corruption VFX |  |  | Art / VFX
| Timer to revert bridge to broken state |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Toggle path once puzzle is completed to allow or disallow player from crossing the bridge by replicating collision |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| Trigger VFX when effect is completed |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Trigger building the bridge |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| VFX |  |  | Art / VFX
| VFX |  |  | Art / VFX
| VFX |  |  | Art / VFX
| VFX |  |  | Art / VFX
| VFX |  |  | Art / VFX
| VFX |  |  | Art / VFX
| VFX |  |  | Art / VFX
| Carapax QA |  |  | QA / QA
| Corrupted Enemies QA |  |  | QA / QA
| Goblins QA |  |  | QA / QA
| Skeletons QA |  |  | QA / QA
| Slimes QA |  |  | QA / QA
| Wolves QA |  |  | QA / QA
| Waterfall Beauty Spot Audio |  |  | Audio / Audio | [115 empty] | 3 | [349 empty] | 4 | [37 empty] | 6
| Waterfall Spot QA |  |  | QA / QA
| Waterfall Beauty Spot Blockout |  |  | Design / Level design | [94 empty] | 4 | [349 empty] | 1 | [37 empty] | 6
| Waterfall Beauty Spot Concept |  |  | Art / Concept Art
| Waterfall Beauty Spot Design |  |  | Design / Game design | [92 empty] | 2 | [349 empty] | 2 | [37 empty] | 5
| Waterfall Beauty Spot Foliage |  |  | Art / Environment Art
| Waterfall Beauty Spot Props Build |  |  | Art / Environment Art
| Waterfall Beauty Spot layout |  |  | Art / Environment Art
When the player login he should be in the same last spot he logged out (player data service)
| Conect to last server player left from |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to fetch player position, rotation and IP address |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to store player X, Y, Z corrdinates and rotation and server ip address |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create unit test for update and fetch endpoint |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| List of servers and their ip address |  |  | Engineering / Backend Engineering | [112 empty] | 5 | [349 empty] | 4 | [37 empty] | 5
| Save player position and rotation and ip every X seconds on server, so if the server crashes we can retrieve this information later |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Set player position, rotation, when spawning player |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Wolf AI behaviour |  |  | Design / Game design | [92 empty] | 2
| Wolf montages |  |  | Art / Animation & Rigging
| Wolfy noises |  |  | Audio / Audio | [115 empty] | 0 | [349 empty] | 0 | [37 empty] | 0
| Wolves QA |  |  | QA / QA
Combat
| Melee Combat Framework |  |  | Design / Game design | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6
| Ranged (Corruption Gun) |  |  | Design / Game design | [92 empty] | 4 | [11 empty] | 30 | 10 |  |  |  |  | 20 | [331 empty] | 4 | [11 empty] | 30 | 10 |  |  |  |  | 20 | [19 empty] | 8 | [11 empty] | 30 | 10 |  |  |  |  | 20
| Combat abilities |  |  | Design / Game design | [92 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20 | [326 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20 | [14 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20
| Basic Magic system |  |  | Design / Game design | [89 empty] | 5 |  |  | 25 | 5 | [5 empty] | 10 |  |  |  |  | 30 | 10 | 20 |  |  |  | 30 | [328 empty] | 5 |  |  | 5 | 5 | [5 empty] | 10 |  |  |  |  | 30 | 10 | 20 |  |  |  | 30 | [16 empty] | 5 |  |  | 25 | 5 | [5 empty] | 10 |  |  |  |  | 30 | 10 | 20 |  |  |  | 30
| Consumables | [102 empty] | 2 |  |  |  |  | 5 | [10 empty] | 2 | [333 empty] | 2 |  |  |  |  | 5 | [10 empty] | 2 | [21 empty] | 2 |  |  |  |  | 5 | [10 empty] | 2
| PVP Combat |  |  | Design / Game design | [92 empty] | 16 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 2 | [326 empty] | 20 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 2 | [14 empty] | 30 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 2
| Combat director | [95 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6
| Combat component | [95 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6
| Abilities Design |  |  | Design / Game design | [92 empty] | 9 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20 | [326 empty] | 8 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20 | [14 empty] | 10 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20
| 4 Abilities designed (2 weapons) |  |  | Design / Game design | [92 empty] | 20 | [349 empty] | 5 | [37 empty] | 22
| Weapon attribute system |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 8
| Aim offset implementation |  |  | Art / Animation & Rigging | [92 empty] | 24 | [6 empty] | 9 |  |  |  |  | 4 |  | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 |  |  |  |  | 2 |  | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 |  |  |  |  | 4 |  | 30 | 60 |  |  | 36 |  |  |  |  | 6
| Aimed offsets |  |  | Art / Animation & Rigging | [104 empty] | 30 | 10 |  |  |  |  | 20 | [343 empty] | 30 | 10 |  |  |  |  | 20 | [31 empty] | 30 | 10 |  |  |  |  | 20
| Area implementation | [95 empty] | 16 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 2 | [326 empty] | 16 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 2 | [14 empty] | 16 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 2
| Create UI/UX |  |  | Art / UX/UI
| Create fight timer and declare draw |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Implement player prediction algorithm for networking |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Kick players that are in the area who are not fighting when you and someone else decide to start a fight |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| PVP Combat support |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| PVP area blocks player from entering and leaving |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| PVP only available in Arena |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Reward player who won and display a message to the loser |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Show damage numbers between players on hit |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 1 | [37 empty] | 3
| Show other player HP in area fight |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| Sign up for arena fight actor |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| declare player who is connected as winner |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Attacks Design Doc - per weapon (Combo + off-hand attacks) |  |  | Design / Game design | [92 empty] | 4 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [326 empty] | 3 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [14 empty] | 5 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6
| Check the health potion usage |  |  | QA / QA | [99 empty] | 2 |  |  |  |  | 5 | [10 empty] | 2 | [333 empty] | 2 |  |  |  |  | 5 | [10 empty] | 2 | [21 empty] | 2 |  |  |  |  | 5 | [10 empty] | 2
| Combat Abilities SFX |  |  | Audio / Audio | [92 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 7 | [326 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 7 | [14 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 14
| Combat Abilities UI |  |  | Art / UX/UI | [99 empty] | 15 | [349 empty] | 8 | [37 empty] | 15
| Combat Abilities integrated with skill path |  |  | Engineering / Gameplay Engineering
| Combat Animations |  |  | Art / Animation & Rigging | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6
| Combat Design |  |  | Design / Game design | [92 empty] | 15 | [349 empty] | 15 | [37 empty] | 20
| Combat Montages |  |  | Art / Animation & Rigging
| Combat SFX |  |  | Audio / Audio | [92 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20 | [326 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20 | [14 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20
| Combat Tech anim? |  |  | Art / Animation & Rigging | [92 empty] | 24 | [6 empty] | 9 |  |  |  |  | 20 |  | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 |  |  |  |  | 10 |  | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 |  |  |  |  | 20 |  | 30 | 60 |  |  | 36 |  |  |  |  | 6
| Combat VFX |  |  | Art / VFX
| Melee Combat QA |  |  | QA / QA
| Combat abilities casting animations |  |  | Art / Animation & Rigging | [92 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 5 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20 | [326 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 3 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20 | [14 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 5 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20
| Combat Abilities QA |  |  | QA / QA
| Combat integration |  |  | Engineering / Gameplay Engineering | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6
| Death sequance system |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Dual Wielding Ranged |  |  | Design / Game design | [92 empty] | 4 | [11 empty] | 30 | 10 |  |  |  |  | 20 | [331 empty] | 2 | [11 empty] | 30 | 10 |  |  |  |  | 20 | [19 empty] | 6 | [11 empty] | 30 | 10 |  |  |  |  | 20
| Ensure combat system works |  |  | Engineering / Gameplay Engineering | [92 empty] | 16 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 2 | [326 empty] | 16 | [6 empty] | 3 | [10 empty] | 2 |  |  |  |  | 2 | [14 empty] | 16 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 2
| HUD Combat Abilities UI |  |  | Art / UX/UI | [92 empty] | 20 | [5 empty] | 2 | 5 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20 | [326 empty] | 20 | [5 empty] | 2 | 8 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20 | [14 empty] | 20 | [5 empty] | 2 | 15 |  |  |  |  | 25 | 10 | 20 |  |  |  | 30 |  |  |  |  | 20
| HUD design |  |  | Art / UX/UI | [99 empty] | 7 | [349 empty] | 5 | [37 empty] | 10
| Impelment all ai decision | [95 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6
| Impelment all ai decision | [95 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 36 |  |  |  |  | 6
| AI vs AI |  |  | Engineering / Gameplay Engineering | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 5 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 3 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 5 |  |  |  |  | 6
| Distance based agro |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Execution check |  |  | Engineering / Gameplay Engineering | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 4 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 2 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 4 |  |  |  |  | 6
| Health based agro |  |  | Engineering / Gameplay Engineering | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 2 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 1 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 2 |  |  |  |  | 6
| Player feedback |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Pressure based agro |  |  | Engineering / Gameplay Engineering | [110 empty] | 8 | [349 empty] | 5 | [37 empty] | 8
| Reflex check |  |  | Engineering / Gameplay Engineering | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 10 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 5 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 10 |  |  |  |  | 6
| Safety check |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Scaling |  |  | Engineering / Gameplay Engineering | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 2 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 1 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 2 |  |  |  |  | 6
| Social check |  |  | Engineering / Gameplay Engineering | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 10 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 5 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 10 |  |  |  |  | 6
| Survival check |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Utility managment |  |  | Engineering / Gameplay Engineering | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 10 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 5 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 10 |  |  |  |  | 6
| attack abilities (attack etc...) |  |  | Engineering / Gameplay Engineering | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 4 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 2 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 4 |  |  |  |  | 6
| decision tick |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| different types of movements |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| utility abilities (healthing etc...) |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| Integrate abilities with skill path |  |  | Engineering / Gameplay Engineering | [92 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 3 |  |  |  |  | 20 | [326 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 2 |  |  |  |  | 20 | [14 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 3 |  |  |  |  | 20
| Magic SFX |  |  | Audio / Audio | [89 empty] | 5 |  |  | 30 | 5 | [5 empty] | 10 |  |  |  |  | 30 | 10 | 20 |  |  |  | 30 |  |  |  |  | 5 | [323 empty] | 5 |  |  | 30 | 5 | [5 empty] | 10 |  |  |  |  | 30 | 10 | 20 |  |  |  | 30 |  |  |  |  | 7 | [11 empty] | 5 |  |  | 30 | 5 | [5 empty] | 10 |  |  |  |  | 30 | 10 | 20 |  |  |  | 30 |  |  |  |  | 10
| Magic UI (1 skill tree mapped out) |  |  | Art / UX/UI | [99 empty] | 7 | [349 empty] | 5 | [37 empty] | 9
| Magic VFX |  |  | Art / VFX
| Magic QA |  |  | QA / QA
| Magic Weapon (e.g. wand) |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 10
| Weapon |  |  | Art / Environment Art
| Magic casting animations |  |  | Art / Animation & Rigging
| Magic implementation |  |  | Engineering / Gameplay Engineering
| Magic system design (3-4 spells) |  |  | Design / Game design
| Magic system design (5 spells) |  |  | Design / Game design | [92 empty] | 10 | [349 empty] | 5 | [37 empty] | 15
| Make the abilities |  |  | Engineering / Gameplay Engineering | [92 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 12 |  |  |  |  | 20 | [326 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 10 |  |  |  |  | 20 | [14 empty] | 20 | [5 empty] | 2 | 10 |  |  |  |  | 25 | 10 | 20 |  |  |  | 12 |  |  |  |  | 20
| PVP Arena Audio |  |  | Audio / Audio | [92 empty] | 16 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 5 | [326 empty] | 16 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 7 | [14 empty] | 16 | [6 empty] | 3 | [10 empty] | 3 |  |  |  |  | 14
| PVP combat QA |  |  | QA / QA
| PVP Arena Design |  |  | Design / Game design | [92 empty] | 7 | [349 empty] | 6 | [37 empty] | 10
| PVP Arena Foliage |  |  | Art / Environment Art
| PVP Arena blockout |  |  | Design / Level design | [94 empty] | 10 | [349 empty] | 3 | [37 empty] | 15
| PVP Arena concept |  |  | Art / Concept Art
| PVP Arena props |  |  | Art / Environment Art
| PVP Arena set dressing |  |  | Art / Environment Art
| PVP Combat Setup |  |  | Design / Game design | [92 empty] | 6
| PVP Combat design |  |  | Design / Game design | [92 empty] | 12 | [349 empty] | 5 | [37 empty] | 20
| PVP Combat support |  |  | Engineering / Gameplay Engineering
| PVP only available in Arena |  |  | Engineering / Gameplay Engineering
| Player should be able to drink a potion | [102 empty] | 2 |  |  |  |  | 5 | [10 empty] | 2 | [333 empty] | 2 |  |  |  |  | 5 | [10 empty] | 2 | [21 empty] | 2 |  |  |  |  | 5 | [10 empty] | 2
| Implement drinking animation |  |  | Art / Animation & Rigging | [104 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| Ranged Attributes |  |  | Design / Game design | [92 empty] | 5 | [11 empty] | 30 | 10 |  |  |  |  | 20 | [331 empty] | 5 | [11 empty] | 30 | 10 |  |  |  |  | 20 | [19 empty] | 10 | [11 empty] | 30 | 10 |  |  |  |  | 20
| Review the combat with networking engineer |  |  | Engineering / Gameplay Engineering | [92 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 5 |  |  |  |  | 6 | [326 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 5 |  |  |  |  | 6 | [14 empty] | 24 | [6 empty] | 9 | [6 empty] | 30 | 60 |  |  | 5 |  |  |  |  | 6
| Weapon Attributes (per weapon) |  |  | Design / Game design | [92 empty] | 1 | [349 empty] | 1 | [37 empty] | 5
| Weapon spesific hand poses |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 2 | [37 empty] | 2
| Weapons models |  |  | Art / Character Art
| equipd wand |  |  | Engineering / Gameplay Engineering | [89 empty] | 5 |  |  | 30 | 5 | [5 empty] | 10 |  |  |  |  | 30 | 10 | 20 |  |  |  | 1 | [328 empty] | 5 |  |  | 30 | 5 | [5 empty] | 10 |  |  |  |  | 30 | 10 | 20 |  |  |  | 1 | [16 empty] | 5 |  |  | 30 | 5 | [5 empty] | 10 |  |  |  |  | 30 | 10 | 20 |  |  |  | 1
| make wand abilities 4 |  |  | Engineering / Gameplay Engineering | [110 empty] | 15 | [349 empty] | 10 | [37 empty] | 15
| make wand an item type |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| wand skill tree |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
User Space
| User Space Server & Instance | L | T2: GDD/TDD/Brief | Engineering / Backend Engineering | [110 empty] | 60 | [349 empty] | 60 | [37 empty] | 60
| Drinking design |  |  | Design / Game design | [92 empty] | 1
| Drunken UI |  |  | Art / UX/UI | [99 empty] | 4
| FTUE Design |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 8
| FTUE UI |  |  | Art / UX/UI | [99 empty] | 5
| Mutual Activity Design |  |  | Design / Game design | [92 empty] | 4 | [349 empty] | 2 | [37 empty] | 10
| Mutual Activity UI |  |  | Art / UX/UI | [99 empty] | 5
| User Space Editor audio |  |  | Audio / Audio | [115 empty] | 2 | [349 empty] | 2 | [37 empty] | 3
| User Space Ambience |  |  | Audio / Audio | [115 empty] | 1 | [349 empty] | 1 | [37 empty] | 2
| Island ambient audio |  |  | Audio / Audio | [115 empty] | 1 | [349 empty] | 1 | [37 empty] | 2
| Item SFX |  |  | Audio / Audio | [115 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| User Space editor & UI |  |  | Engineering / Gameplay Engineering
| Implement interaction animation with userspace items (snap) |  |  | Art / Animation & Rigging | [104 empty] | 5 | [349 empty] | 1 | [37 empty] | 5
| Setup animation for userspace editing tool |  |  | Art / Animation & Rigging | [104 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| User Space editor VFX |  |  | Art / VFX
| User Space functionality QA |  |  | QA / QA
| User Space is a separate instance |  |  | Engineering / Backend Engineering
| DevOps |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Edit mode improvmeents |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Enable fishing in userspace |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fetch userspace furniture from backend |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Figure out friend ip address to join his server when invited |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Host permissions |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| IP address list service |  |  | Engineering / Backend Engineering | [112 empty] | 6 | [349 empty] | 5 | [37 empty] | 6
| Load userspace from save data |  |  | Engineering / Gameplay Engineering | [110 empty] | 7 | [349 empty] | 5 | [37 empty] | 7
| Multiple players join one server and only show what is relevent to current player |  |  | Engineering / Gameplay Engineering | [110 empty] | 20 | [349 empty] | 10 | [37 empty] | 20
| Player joining friends userspace |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Save userspace furniture location in userspace |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Update userspace furniture and tell that to all players |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 4 | [37 empty] | 5
| User Space Decoration | M | T0: Ideation | Art / Environment Art | [92 empty] | 14 | [5 empty] | 20 |  |  |  |  | 15 | [6 empty] | 30 |  |  |  |  | 2 | [326 empty] | 14 | [5 empty] | 20 |  |  |  |  | 15 | [6 empty] | 30 |  |  |  |  | 2 | [14 empty] | 14 | [5 empty] | 20 |  |  |  |  | 15 | [6 empty] | 30 |  |  |  |  | 2
| User Space House concept |  |  | Art / Concept Art
| User Space House model |  |  | Art / Environment Art
| User Space furniture props |  |  | Art / Environment Art
| Anywhere door placement |  |  | Engineering / Gameplay Engineering | [98 empty] | 5 | [7 empty] | 15 |  |  |  | 5 | [337 empty] | 5 | [7 empty] | 15 |  |  |  | 5 | [25 empty] | 5 | [7 empty] | 15 |  |  |  | 5
| User Space Island (S) |  |  | Design / Game design
| Pets (mechanical parrot reuse) |  |  | Design / Game design | [92 empty] | 5 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 20 | [331 empty] | 3 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 20 | [19 empty] | 15 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 20
| Fishing |  |  | Design / Game design
| Create an ability to place anywhere door in the world |  |  | Engineering / Gameplay Engineering | [98 empty] | 5 | [7 empty] | 15 |  |  |  | 2 | [337 empty] | 5 | [7 empty] | 15 |  |  |  | 1 | [25 empty] | 5 | [7 empty] | 15 |  |  |  | 2
| Create anywhere door as item in backend service. |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create anywhere door as item. |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create endpoint to update the position, rotation and zone name of MULTIPLE anywhere door in backend (player data service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create fetech anywhere door endpoint (player data service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fish model |  |  | Art / Environment Art
| Fishing Integration |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 3 | [37 empty] | 10
| Fishing Rod model |  |  | Art / Environment Art
| Fishing Spot SFX |  |  | Audio / Audio | [115 empty] | 0 | [349 empty] | 0 | [37 empty] | 0
| Fishing Spot VFX |  |  | Audio / Audio
| Fishing QA |  |  | QA / QA
| Fishing UI |  |  | Art / UX/UI | [99 empty] | 3
| Fishing VFX |  |  | Art / VFX
| Fishing QA |  |  | QA / QA
| Fishing spot sign model |  |  | Art / Environment Art
| Make anywhere door as an actor |  |  | Engineering / Gameplay Engineering | [98 empty] | 5 | [7 empty] | 15 |  |  |  | 2 | [337 empty] | 5 | [7 empty] | 15 |  |  |  | 1 | [25 empty] | 5 | [7 empty] | 15 |  |  |  | 2
| Make spesific regions where anywhere door can be placed |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Anywhere Door QA |  |  | QA / QA
| Pet VFX |  |  | Art / VFX | [92 empty] | 5 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 20 | [331 empty] | 5 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 20 | [19 empty] | 5 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 20
| Pet animation grpah setup |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 2 | [37 empty] | 2
| Pet QA |  |  | QA / QA
| Pet animations |  |  | Art / Animation & Rigging
| Pet behavior |  |  | Engineering / Gameplay Engineering
| Pet concepts |  |  | Art / Concept Art
| Pet integration |  |  | Engineering / Gameplay Engineering
| Pet QA |  |  | QA / QA
| Pet maya rig setup |  |  | Art / Animation & Rigging | [104 empty] | 2 | [349 empty] | 2 | [37 empty] | 2
| Pet model |  |  | Art / Character Art
| Pet system design |  |  | Design / Game design | [92 empty] | 4
| Remove anywhere door |  |  | Engineering / Gameplay Engineering | [98 empty] | 5 | [7 empty] | 15 |  |  |  | 2 | [337 empty] | 5 | [7 empty] | 15 |  |  |  | 1 | [25 empty] | 5 | [7 empty] | 15 |  |  |  | 2
| Review fishing code |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Review pet system code |  |  | Engineering / Gameplay Engineering | [92 empty] | 5 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 2 | [331 empty] | 5 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 1 | [19 empty] | 5 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 2
| Show anywhere door on compass |  |  | Engineering / Gameplay Engineering | [98 empty] | 5 | [7 empty] | 15 |  |  |  | 4 | [337 empty] | 5 | [7 empty] | 15 |  |  |  | 3 | [25 empty] | 5 | [7 empty] | 15 |  |  |  | 4
| Show anywhere door on map |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Show anywhere door on minimap |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Show if the anywhere door is placed or not placed to remove it if needed |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Teleport pet to player when pet is stuck |  |  | Engineering / Gameplay Engineering | [92 empty] | 5 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 2 | [331 empty] | 5 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 1 | [19 empty] | 5 | 2 | [10 empty] | 13 | 3 | 5 | 2 |  |  | 2
| Update anywhere door position, rotation, zone name after fethcing anywhere door info from (player data serivce) |  |  | Engineering / Gameplay Engineering | [98 empty] | 5 | [7 empty] | 15 |  |  |  | 2 | [337 empty] | 5 | [7 empty] | 15 |  |  |  | 1 | [25 empty] | 5 | [7 empty] | 15 |  |  |  | 2
| User Space GDD VS page |  |  | Design / Game design | [92 empty] | 1
| User Space location blockout |  |  | Design / Level design | [94 empty] | 7 | [349 empty] | 5 | [37 empty] | 15
| User Space location concepts |  |  | Art / Concept Art
| User Space location foliage |  |  | Art / Environment Art
| User Space visuals QA |  |  | QA / QA
| User Space location props |  |  | Art / Environment Art
| User Space location set dressing |  |  | Art / Environment Art
| User space door can be placed at predefined spots |  |  | Engineering / Gameplay Engineering | [98 empty] | 5 | [7 empty] | 15 |  |  |  | 3 | [337 empty] | 5 | [7 empty] | 15 |  |  |  | 2 | [25 empty] | 5 | [7 empty] | 15 |  |  |  | 3
| Anywhere Door QA |  |  | QA / QA
| fetch anywhere door info from backend service and place it in the world |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
Items & Inventory
Sync hotbar to db
The player should be able to login into the game and have all his abilties and items stored where he left them on the hotbar
| Create an endpoint to euip items |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create an endpoint to fetch abilities internal dashboard |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to fetch equiped items |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to remove ability internal dashboard |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to store abilities in internal dashboard |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create endpoint to fetch hotbar items and abilities |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create unit test for updating, fetching |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fetch and set equiped items |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Get hotbar item and abiltitie positions and set them |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 1 | [37 empty] | 3
| Send an HTTP reuqest only after 2 seconds after not moving any items or abilities in hotbar |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| an endpoint to all items equiped (batch requests only send what changed) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| an endpoint to update all item and abilities position in the hotbar (batch requests only send what changed) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
Player Economy
| Trading System | L | T0: Ideation | Design / Game design | [92 empty] | 10 | [6 empty] | 30 | [10 empty] | 40 |  |  |  |  | 3 | [326 empty] | 8 | [6 empty] | 30 | [10 empty] | 40 |  |  |  |  | 3 | [14 empty] | 16 | [6 empty] | 30 | [10 empty] | 40 |  |  |  |  | 3
| Clothing Shop Basic Contents |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 2 | [37 empty] | 10
| Shop Fake Fascia Design |  |  | Design / Game design | [92 empty] | 1 | [349 empty] | 5 | [37 empty] | 10
| Currency Integration |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| P2G Transactions Support |  |  | Engineering / Backend Engineering
| Trading System QA |  |  | QA / QA
| Premium currency icon |  |  | Art / Concept Art
| Shop props |  |  | Art / Environment Art
| Shops Concepts |  |  | Art / Concept Art
| Shops Models & Set dressing |  |  | Art / Environment Art
| Soft Currency (gold) icon |  |  | Art / Concept Art
| Trading UX/UI |  |  | Art / UX/UI | [99 empty] | 15 | [349 empty] | 15 | [37 empty] | 20
Vendor backend support
| Create a list of sold items (redis / server) ??? fetch, create buyback endpoint, update endpoint, pipeline |  |  | Engineering / Backend Engineering | [112 empty] | 7 | [349 empty] | 5 | [37 empty] | 7
| Create buy endpoint |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create fresh cron job to refresh item stacks for vendors (internal dashboard managment service) |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create sell endpoint |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create vendor collection ( internal dashboard managment service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fetch a list of sold items |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fetch vendor collection (internal dashboard managment service) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Release vendor in game from tempate to release |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Update NPC tool to match vendor in unreal engine |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Update UI |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Update vendor collection ( internal dashboard managment service) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Use buy endpoint |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Use sell endpoint |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| delete items and vendor (internal dashboard managment service) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| fetch last 20 items sold, buyback item, Create buyback functionality |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Vendors Concepts |  |  | Art / Concept Art
| Vendors Models |  |  | Art / Character Art
| Vendors animation |  |  | Art / Animation & Rigging | [104 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Auction House economy |  |  | Design / Game design | [92 empty] | 15 | [17 empty] | 120 | [331 empty] | 10 | [17 empty] | 120 | [19 empty] | 20 | [17 empty] | 120
| In-game economy |  |  | Design / Game design | [92 empty] | 90 | [6 empty] | 30 | [342 empty] | 90 | [6 empty] | 30 | [30 empty] | 90 | [6 empty] | 30
| Basic Economy configuration |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 10 | [37 empty] | 60
| In-game economy QA check |  |  | QA / QA
| P2G Transactions Support |  |  | Engineering / Backend Engineering | [110 empty] | 120 | [349 empty] | 120 | [37 empty] | 120
| Trading System QA |  |  | QA / QA
Quest System
| Various Quest Types Support |  |  | Engineering / Gameplay Engineering | [89 empty] | 2 |  |  | 3 | [17 empty] | 30 | [328 empty] | 2 |  |  | 3 | [17 empty] | 30 | [16 empty] | 2 |  |  | 3 | [17 empty] | 30
| Quest Integration |  |  | Design / Game design
| Quest Tools |  |  | Engineering / Backend Engineering | [110 empty] | 60 | [349 empty] | 60 | [37 empty] | 60
| Quest Rewards System |  |  | Design / Game design | [99 empty] | 10 | [10 empty] | 20 | [331 empty] | 2 | [6 empty] | 10 | [10 empty] | 20 | [19 empty] | 5 | [6 empty] | 10 | [10 empty] | 20
Main Questline: Critical Path
| Quest Tools |  |  | Engineering / Gameplay Engineering | [110 empty] | 60 | [349 empty] | 60 | [37 empty] | 60
| Quest UI Audio |  |  | Audio / Audio | [99 empty] | 10 | [10 empty] | 20 |  |  |  |  | 1 | [333 empty] | 10 | [10 empty] | 20 |  |  |  |  | 0.5 | [21 empty] | 10 | [10 empty] | 20 |  |  |  |  | 1
Arena Fight
| Docs, Implement, Revise |  |  | Design / Game design | [92 empty] | 7 | [349 empty] | 7 | [37 empty] | 14
| Cave Intro Quest |  |  | Design / Game design
| Quest Design Doc |  |  | Design / Game design | [92 empty] | 4 | [349 empty] | 3 | [37 empty] | 5
| Quest Implementation |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 6
| Quest Narrative Doc |  |  | Design / Narrative | [96 empty] | 1 | [349 empty] | 1 | [37 empty] | 2
| Quest Playtesting & Revision |  |  | Design / Game design | [92 empty] | 2 | [349 empty] | 2 | [37 empty] | 3
Complete PG & Last Boss Quest
| Docs, Implement, Revise |  |  | Design / Game design | [92 empty] | 7 | [349 empty] | 7 | [37 empty] | 14
Corruption Tower & Glide Quest
| Quest Design Doc |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 3 | [37 empty] | 5
| Quest Implementation |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 6
| Quest Narrative Doc |  |  | Design / Narrative | [96 empty] | 1 | [349 empty] | 1 | [37 empty] | 2
| Quest Playtesting & Revision |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 2 | [37 empty] | 3
| Design interface for quest types |  |  | Design / Game design | [89 empty] | 2 |  |  | 5 | [17 empty] | 30 | [328 empty] | 2 |  |  | 2 | [17 empty] | 30 | [16 empty] | 2 |  |  | 9 | [17 empty] | 30
| Dialogue System |  |  | Engineering / Backend Engineering | [110 empty] | 60 | [349 empty] | 60 | [37 empty] | 60
| Dialogue System |  |  | Engineering / Gameplay Engineering | [110 empty] | 0 | [349 empty] | 0 | [37 empty] | 0
| Dialogue System Design |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 3 | [37 empty] | 8
| Dialogue UI |  |  | Art / UX/UI | [99 empty] | 10
Downtime Race Quest
| Docs, Implement, Revise |  |  | Design / Game design | [92 empty] | 7 | [349 empty] | 7 | [37 empty] | 14
Gear Up & User Space Quest
| Docs, Implement, Revise |  |  | Design / Game design | [92 empty] | 7 | [349 empty] | 7 | [37 empty] | 14
Green Faction Hill Quest
| Quest Design Doc |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Quest Implementation |  |  | Design / Game design | [92 empty] | 6 | [349 empty] | 4 | [37 empty] | 6
| Quest Narrative Doc |  |  | Design / Narrative | [96 empty] | 2 | [349 empty] | 0.5 | [37 empty] | 2
| Quest Playtesting & Revision |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Green Faction NPC Concepts |  |  | Art / Concept Art
| Green Faction NPC Models |  |  | Art / Character Art
| Green Faction NPC animations |  |  | Art / Animation & Rigging | [104 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Green Faction NPC dialogue setup |  |  | Design / Narrative | [96 empty] | 2 | [349 empty] | 1 | [37 empty] | 8
| Green Faction NPC dialogue setup |  |  | Design / Game design
| Green Faction NPCs placement |  |  | Design / Game design | [92 empty] | 2 | [349 empty] | 2 | [37 empty] | 8
| QA check |  |  | QA / QA
| Lockpicking |  |  | Design / Game design | [89 empty] | 2 |  |  | 2 | [17 empty] | 30 | [328 empty] | 2 |  |  | 7 | [17 empty] | 30 | [16 empty] | 2 |  |  | 20 | [17 empty] | 30
| Check if lockpicking solution is correct |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create a system to modify ball proaprties while traveling |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Create an actor with a grid for all tiles |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create ball entity actor to compelete the game |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| Create data asset |  |  | Engineering / Gameplay Engineering | [110 empty] | 1 | [349 empty] | 1 | [37 empty] | 1
| Create magnatic enitity actor |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create pipe entity actor |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Implement VFX and SFX |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Lockpicking Concept |  |  | Art / Concept Art
| Lockpicking Integration |  |  | Engineering / Gameplay Engineering
| Lockpicking QA check |  |  | QA / QA
| Lockpicking Techart |  |  | Art / TechArt
| Lockpicking UI |  |  | Art / UX/UI | [99 empty] | 6 | [349 empty] | 8 | [37 empty] | 15
| SFX |  |  | Audio / Audio
| Start and end condition |  |  | Engineering / Gameplay Engineering | [110 empty] | 0.5 | [349 empty] | 0.5 | [37 empty] | 0.5
| VFX |  |  | Art / VFX
| Other quest types support? |  |  | Engineering / Gameplay Engineering
| Create quest system backend service |  |  | Engineering / Backend Engineering | [112 empty] | 20 | [349 empty] | 20 | [37 empty] | 20
| Create quest tool |  |  | Engineering / Gameplay Engineering | [110 empty] | 20 | [349 empty] | 20 | [37 empty] | 20
Party Up & MP Dungeon Quest
| Docs, Implement, Revise |  |  | Design / Game design | [92 empty] | 7 | [349 empty] | 7 | [37 empty] | 14
| Quest Editor |  |  | Design / Game design | [92 empty] | 2 | [17 empty] | 60 | [331 empty] | 5 | [17 empty] | 60 | [19 empty] | 20 | [17 empty] | 60
| Quest Flow Design & Narrative Overview |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 2 | [37 empty] | 4
| Quest Log |  |  | Engineering / Backend Engineering | [110 empty] | 60 | [349 empty] | 60 | [37 empty] | 60
| Quest Log |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
Make quest system
| Quest Log QA |  |  | QA / QA
| Quest Reward List |  |  | Design / Game design | [92 empty] | 2 | [6 empty] | 10 | [10 empty] | 20 | [331 empty] | 2 | [6 empty] | 10 | [10 empty] | 20 | [19 empty] | 5 | [6 empty] | 10 | [10 empty] | 20
| Quest Reward System design doc |  |  | Design / Game design | [92 empty] | 2
| Quest Reward UI |  |  | Art / UX/UI | [99 empty] | 5
| Rewards Choice |  |  | Engineering / Gameplay Engineering
| Quest Rewards QA |  |  | QA / QA
Social Hub & Partnership Quest
| Docs, Implement, Revise |  |  | Design / Game design | [92 empty] | 7 | [349 empty] | 7 | [37 empty] | 14
| Tutorial Quest Chain Configuration & Setup |  |  | Design / Game design | [442 empty] | 7 | [37 empty] | 10
| QA check |  |  | QA / QA
Weapon Upgrade Quest
| Quest Design Doc |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 3 | [37 empty] | 5
| Quest Implementation |  |  | Design / Game design | [92 empty] | 3 | [349 empty] | 3 | [37 empty] | 6
| Quest Narrative Doc |  |  | Design / Narrative | [96 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 2
| Quest Playtesting & Revision |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 2 | [37 empty] | 3
| Xyron narrative |  |  | Design / Game design | [92 empty] | 2 | [17 empty] | 60 | [331 empty] | 2 | [17 empty] | 60 | [19 empty] | 8 | [17 empty] | 60
Social & Multiplayer
| In-game Mail | S | T2: GDD/TDD/Brief | Design / Game design | [89 empty] | 1 |  |  | 2 |  |  |  | 2 |  | 1 | 10 | [10 empty] | 20 | [328 empty] | 1 |  |  | 2 |  |  |  | 2 |  | 1 | 10 | [10 empty] | 20 | [16 empty] | 1 |  |  | 5 |  |  |  | 2 |  | 1 | 10 | [10 empty] | 20
| Claim currancy and increase ingame gold |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Claim items from mail |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Claim items from mail |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Delete mail |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Delete mail |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| In-game Mail backend |  |  | Engineering / Backend Engineering
| In-game Mail frontend/UI |  |  | Engineering / Gameplay Engineering
| Mail QA |  |  | QA / QA
| Mail UI Audio |  |  | Audio / Audio | [115 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| In-game UI |  |  | Art / UX/UI | [99 empty] | 10
| Mark mail as read |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Mark mail as read |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Postbox Concept |  |  | Art / Concept Art
| Postbox Model |  |  | Art / Environment Art
| Postbox SFX |  |  | Audio / Audio | [115 empty] | 1 | [349 empty] | 1 | [37 empty] | 2
| Postbox VFX |  |  | Art / VFX
| Restore trash mail |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Restore trash mail |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Send mail from one player to another with items |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Send mail from one player to another with items |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create mail SFX |  |  | Audio / Audio
| Create mail UI/UX |  |  | Art / UX/UI
| Create new mail model |  |  | Art / Environment Art
| Mail QA |  |  | QA / QA
| Guilds (S) |  |  | Design / Game design | [89 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 40 | [328 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 40 | [16 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 40
| Co-op - Party |  |  | Engineering / Backend Engineering | [89 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [328 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [16 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60
| Loot Distribution |  |  | Design / Game design | [92 empty] | 3 | [6 empty] | 10 | [6 empty] | 30 |  |  |  | 30 | [331 empty] | 2 | [6 empty] | 10 | [6 empty] | 30 |  |  |  | 30 | [19 empty] | 6 | [6 empty] | 10 | [6 empty] | 30 |  |  |  | 30
| Leaderboard system | [113 empty] | 40 | [349 empty] | 40 | [37 empty] | 40
| Chat system | [92 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [328 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [16 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60
| Dungeon finder | [113 empty] | 40 | [349 empty] | 40 | [37 empty] | 40
| Party system | [92 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [328 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [16 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60
| As a player if I play a mini game the leaderboard should update with my score | [113 empty] | 40 | [349 empty] | 40 | [37 empty] | 40
| Create UI for leaderboard in (internal dashboard) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create a leaderboard in dashboard (internal dashboard) |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 2 | [37 empty] | 4
| Create leaderboard collection |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Delete a leaderboard from dashboard (internal dashboard) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Delete an entry from the leaderboard from dashboard (internal dashboard) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fetch all leaderboards (internal dashboard) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fetch leaderboard from (social service) |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fetch leaderboard in unreal |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Update leaderboard from (social service) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Update leaderboard in unreal |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| As a player queue up for dungeon | [113 empty] | 40 | [349 empty] | 40 | [37 empty] | 40
| Add player to dungeon finder list |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Connect dungeons to UI |  |  | Engineering / Gameplay Engineering | [110 empty] | 8 | [349 empty] | 5 | [37 empty] | 8
| Connect to redis |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create Dungeon finder UI/UX |  |  | Art / UX/UI
| Create dungeon finder service |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create pipeline and deploy |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fetch a list of players queued up for dungeon by dungon id |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Get player status in dungeon finder |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Invite player to party |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Queue group for dungeon |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Remove party from queue after party is full |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Remove party from queue after party is full |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Remove player from dungeon queue |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Send player status in dungeon finder |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Send request to add player to dungeon |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Send request to fetch player from dungeon |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Send request to remove player from dungeon |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Chat UI |  |  | Art / UX/UI | [89 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [328 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [16 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60
| Auto scroll incomming chat messages |  |  | Art / UX/UI
| Different colours for different type of message |  |  | Art / UX/UI
| Chat spam filter |  |  | Engineering / Backend Engineering
| Create a system to rate limit messages |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Chat text limit |  |  | Engineering / Backend Engineering
| Create a system to limit the amount of text sent |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Connect Guild UI |  |  | Engineering / Gameplay Engineering | [89 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 5 | [328 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 3 | [16 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 5
| Create party puzzle |  |  | Engineering / Gameplay Engineering | [89 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [328 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [16 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60
| Make a puzzle |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 5 | [37 empty] | 5
| Party QA |  |  | QA / QA
| General systems |  |  | Engineering / Backend Engineering | [89 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [328 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [16 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60
| Connect to redis |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a custom protocol using TCP |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create a heartbeat system |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a list of users info such as server ip and usernames |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create a multithreaded system |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create a packet system |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create a serialization/deserialization system |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create chat service in go |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create pipeline and deploy |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Guild NPCs |  |  | Art / Character Art | [89 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 40 | [328 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 40 | [16 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 40
| Guild house blockout |  |  | Design / Level design | [94 empty] | 10 | [349 empty] | 4 | [37 empty] | 20
| Sitting NPCs |  |  | Art / Animation & Rigging
| Guild UI |  |  | Art / UX/UI | [99 empty] | 3
| Guild chat |  |  | Engineering / Gameplay Engineering
| Guild chat |  |  | Engineering / Backend Engineering | [89 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [328 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [16 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60
| Guild Chat design |  |  | Design / Game design | [89 empty] | 1 |  |  | 1 | [6 empty] | 10 | [10 empty] | 40 | [328 empty] | 1 |  |  | 3 | [6 empty] | 10 | [10 empty] | 40 | [16 empty] | 1 |  |  | 8 | [6 empty] | 10 | [10 empty] | 40
| Guild QA |  |  | QA / QA
| Send a message to your guild |  |  | Engineering / Backend Engineering | [89 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 |  | 4 | [326 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 |  | 3 | [14 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 |  | 4
| Guild house |  |  | Engineering / Gameplay Engineering | [89 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 40 | [328 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 40 | [16 empty] | 1 |  |  | 20 | [6 empty] | 10 | [10 empty] | 40
| Guild house entry |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Guild house leave |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Guild house server |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Guild house TV + video |  |  | Art / Environment Art
| Guild house concept |  |  | Art / Concept Art
| Guild house is an instance |  |  | Engineering / Backend Engineering
| Guild house model |  |  | Art / Environment Art
| Guild house props |  |  | Art / Environment Art
| Guilds system design |  |  | Design / Game design | [92 empty] | 15
| Loot distribution design |  |  | Design / Game design | [92 empty] | 3 | [6 empty] | 10 | [6 empty] | 30 |  |  |  | 30 | [331 empty] | 3 | [6 empty] | 10 | [6 empty] | 30 |  |  |  | 30 | [19 empty] | 3 | [6 empty] | 10 | [6 empty] | 30 |  |  |  | 30
| Loot is distributed after the raid |  |  | Engineering / Gameplay Engineering
| Create a new loot table in tool |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create a system for actors to referance loot table |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create loot distribution collection ( internal dashboard managment service) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create loot distribution system which lets Actors inherit from multiple templates |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Delete loot table in CH tool |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Edit loot table in CH tool |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Enemies drop item when they are killed |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Fetch current loot tables in CH tool |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fetch loot distribution collection (internal dashboard managment service) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Loot distribution QA |  |  | QA / QA
| Refreance loot table in enemy/actor in tool |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Release loot table in CH tool |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Save temp loot table in tool |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Update loot distribution collection ( internal dashboard managment service) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| distrubute loot according to dungeon rules |  |  | Engineering / Gameplay Engineering | [110 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Party UI |  |  | Art / UX/UI | [89 empty] | 2 |  |  | 5 | 2 | [5 empty] | 2 | [10 empty] | 60 | [328 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [16 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60
| Party chat |  |  | Engineering / Gameplay Engineering
| Party chat |  |  | Engineering / Backend Engineering | [89 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [328 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [16 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60
| Party QA |  |  | QA / QA | [89 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [328 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [16 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60
| Send a party message to your party |  |  | Engineering / Backend Engineering | [89 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 |  | 5 | [326 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 |  | 4 | [14 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 |  | 5
| Party formation |  |  | Engineering / Backend Engineering | [89 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [328 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 |  | 3 | [14 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 |  | 8
| Party chat |  |  | Design / Game design
| Party system design |  |  | Design / Game design | [92 empty] | 5
| Party supports real players and bots |  |  | Engineering / Backend Engineering
| Player can join/invite to party | [92 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [328 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60 | [16 empty] | 2 |  |  | 5 | 2 | [5 empty] | 6 | [10 empty] | 60
| Change leadership |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Change leadership |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Connect to redis |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a custom protocol using TCP |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a heartbeat system |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a list of users info such as server ip and usernames |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a multithreaded system |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a packet system |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a party |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create a party |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create a serialization/deserialization system |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create party service |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create pipeline and deploy |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Disband party |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Disband party |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Invite someone to party |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Invite someone to party |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Kick someone from party |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Kick someone from party |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Leave party |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Leave party |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Roll check in party |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Roll check in party |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Update party player position on map, mana, health |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Update party player position on map, mana, health |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Private message |  |  | Engineering / Backend Engineering | [89 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [328 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60 | [16 empty] | 1 |  |  | 12 | [6 empty] | 20 | [10 empty] | 60
| Send a private message to user |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Profanity filter |  |  | Engineering / Backend Engineering
| Create a system to filter a set of words |  |  | Engineering / Backend Engineering | [112 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Proximity chat |  |  | Engineering / Backend Engineering
| Send chat message only to people near you |  |  | Engineering / Backend Engineering | [112 empty] | 5 | [349 empty] | 4 | [37 empty] | 5
| System chat |  |  | Engineering / Backend Engineering
| Create a system chat which will warn you on if the server is shutting down or if Show invites, kicks, bans in chat |  |  | Engineering / Backend Engineering | [112 empty] | 5 | [349 empty] | 4 | [37 empty] | 5
| Zone channel |  |  | Engineering / Backend Engineering
| Create a way to send a chat to entire zone |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| integraet chat service in unreal using websockets |  |  | Engineering / Gameplay Engineering
| Create a way to receive messages on unreal server and pass that to client |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create a way to send a message from unreal server to chat server |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create a websocket connection |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
Platform
| Partner Loop | M | T1: R&D | Design / Game design
| Create Partner Store |  |  | Engineering / Backend Engineering | [112 empty] | 20 | [349 empty] | 10 | [37 empty] | 20
| Full partner loop definition/design |  |  | Design / Game design | [92 empty] | 5 | [349 empty] | 3 | [37 empty] | 7
| Integrate partner loop |  |  | Engineering / Backend Engineering | [112 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Buy CH virtual currency |  |  | Engineering / Backend Engineering
| Buy game subscription time from website and/or from game |  |  | Engineering / Backend Engineering
| Claim partner item from CH mailbox |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Claim partner item from CH mailbox |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Complete partner quest |  |  | Engineering / Backend Engineering
| Download Partner game |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Purchase partner game from in-game store |  |  | Engineering / Backend Engineering
| Redeem Partner Steam key |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Run partner game from same exe as CH |  |  | Engineering / Backend Engineering
| Unlock partner item in CH by playing partner game |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Partner functionality QA |  |  | QA / QA
| Run partner game from same exe as CH |  |  | Engineering / Backend Engineering
| Create IPC between exe launcher and unreal and partner game |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create exe launcher |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Run CH in exe launcher |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Run partner game from same exe as CH |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Run partner in exe launcher |  |  | Engineering / Backend Engineering | [112 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Transition to lightweight map before launching partner game from exe launcher |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Bugged Dungeon Integration |  |  | Design / Game design | [92 empty] | 35 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10 | [331 empty] | 10 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10 | [19 empty] | 20 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10
| Partner Portal |  |  | Design / Game design | [102 empty] | 5 |  |  |  | 17 |  |  |  | 20 | [331 empty] | 1 | [9 empty] | 5 |  |  |  | 17 |  |  |  | 20 | [19 empty] | 2 | [9 empty] | 5 |  |  |  | 17 |  |  |  | 20
| BD Quest design |  |  | Design / Game design | [92 empty] | 35 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10 | [331 empty] | 2 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10 | [19 empty] | 5 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10
| BD Quest narrative design |  |  | Design / Game design | [442 empty] | 3 | [37 empty] | 8
| BD Quest integration |  |  | Engineering / Backend Engineering | [112 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| BD Quest themed reward model |  |  | Art / Character Art
| BD quest special macguffin reward |  |  | Design / Game design
| Audio |  |  | Audio / Audio | [115 empty] | 1 | [349 empty] | 0.5 | [37 empty] | 1
| Behavior implementation |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Concept |  |  | Art / Concept Art
| Model |  |  | Art / Environment Art
| QA |  |  | QA / QA
| Special item design |  |  | Design / Game design | [92 empty] | 1 | [349 empty] | 1 | [37 empty] | 5
| Tech art |  |  | Art / TechArt
| UI |  |  | Art / UX/UI | [99 empty] | 5
| VFX |  |  | Art / VFX
| Partner Portal Enviro Art |  |  | Art / Environment Art | [102 empty] | 5 |  |  |  | 17 |  |  |  | 20 | [341 empty] | 5 |  |  |  | 17 |  |  |  | 20 | [29 empty] | 5 |  |  |  | 17 |  |  |  | 20
| Partner Portal Integration |  |  | Engineering / Backend Engineering | [112 empty] | 15 | [349 empty] | 10 | [37 empty] | 15
| Partner Portal Integration |  |  | Engineering / Gameplay Engineering | [110 empty] | 10 | [349 empty] | 5 | [37 empty] | 10
| Partner Portal VFX |  |  | Art / VFX
| Partner Shop Blockout |  |  | Design / Level design | [92 empty] | 35 | 10 | 4 | [7 empty] | 30 | [7 empty] | 10 | [331 empty] | 35 | 10 | 3 | [7 empty] | 30 | [7 empty] | 10 | [19 empty] | 35 | 10 | 8 | [7 empty] | 30 | [7 empty] | 10
| Partner shop portal placement |  |  | Design / Game design | [92 empty] | 1 | [9 empty] | 5 |  |  |  | 17 |  |  |  | 20 | [341 empty] | 5 |  |  |  | 17 |  |  |  | 20 | [29 empty] | 5 |  |  |  | 17 |  |  |  | 20
| Partner themed shop concept |  |  | Art / Concept Art | [92 empty] | 35 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10 | [331 empty] | 35 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10 | [19 empty] | 35 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10
| Partner themed shop model |  |  | Art / Environment Art
| Partner themed shop props |  |  | Art / Environment Art
| Portals design |  |  | Design / Game design | [92 empty] | 1 | [9 empty] | 5 |  |  |  | 17 |  |  |  | 20 | [341 empty] | 5 |  |  |  | 17 |  |  |  | 20 | [29 empty] | 5 |  |  |  | 17 |  |  |  | 20
| Used Partner Portals |  |  | Art / Environment Art | [92 empty] | 35 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10 | [331 empty] | 35 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10 | [19 empty] | 35 | 10 | 15 | [7 empty] | 30 | [7 empty] | 10
| Assets & Portals Models |  |  | Art / Environment Art
| Portals Placement in the shop |  |  | Art / Environment Art
Live Game
| In game RMT Store |  |  | Design / Game design | [110 empty] | 60 | [349 empty] | 60 | [37 empty] | 60
| Subscription page on the website |  |  | Engineering / Backend Engineering | [110 empty] | 60 | [349 empty] | 60 | [37 empty] | 60
| Virtual currency balance and items |  |  | Design / Game design
| Change play button from subscribe to play when a subscription is active |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create UI to display web browser inside the game launcher |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create a subscription page in the store |  |  | Engineering / Backend Engineering | [112 empty] | 5 | [349 empty] | 3 | [37 empty] | 5
| Create an endpoint to cancel subsciption |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to fetch current subscription information from account managment service |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create subscription endpoint in store service with tier rewards / different time lengths (30 , 90 , 180 , 360 ) |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fetch subscription information from backend service |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| New UI/UX for game launcher to support web browser |  |  | Art / UX/UI
| Pass data between in-launcher browswer and launcher |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Virtual currency balance and items |  |  | Design / Game design | [92 empty] | 2 | [17 empty] | 60 | [349 empty] | 60 | [37 empty] | 60
| Basic RMT balance config |  |  | Design / Game design
| Call purchase item endpoint in unreal and sned item to player mailbox when item is purchased |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Call purchase virtual currnacy endpoint from Unreal |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Connect UI with code |  |  | Engineering / Gameplay Engineering | [110 empty] | 4 | [349 empty] | 3 | [37 empty] | 4
| Create a purchase virtual currancy endpoint in store service |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to add items to in-game store in dashboard management service |  |  | Engineering / Backend Engineering | [112 empty] | 5 | [349 empty] | 4 | [37 empty] | 5
| Create an endpoint to fetch all store items, prices, images, titles from store service |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to fetch total owned virtual currancy from store service |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to pause the purcahsing of an item from in-game store in dashboard managment serivce |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to remove items from in-game store in dashboard management service |  |  | Engineering / Backend Engineering | [112 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| Create an endpoint to update items to in-game store in dashboard management service |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Create purcahse item endpoint in store service |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Display paused banner on paused items with a tooltip explaining why the item is paused |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Fetch total owned virtual currancy |  |  | Engineering / Gameplay Engineering | [110 empty] | 2 | [349 empty] | 1 | [37 empty] | 2
| RMT Store SFX |  |  | Audio / Audio | [115 empty] | 7 | [349 empty] | 7 | [37 empty] | 10
| RMT Store QA |  |  | QA / QA
| RMT Store UI |  |  | Art / UX/UI
| RMT store design |  |  | Design / Game design
| RMT store integration |  |  | Engineering / Backend Engineering
| RMT subscription design |  |  | Art / UX/UI | [99 empty] | 3 | [349 empty] | 8 | [37 empty] | 12
| RMT virtual currency page |  |  | Art / UX/UI | [99 empty] | 3
| RNT partner store |  |  | Art / UX/UI | [99 empty] | 3
| Set a limit on items. example gun only 100 people can buy it. first come first serve |  |  | Engineering / Backend Engineering | [112 empty] | 3 | [349 empty] | 2 | [37 empty] | 3
| Update in-game store when fetching store items |  |  | Engineering / Gameplay Engineering | [110 empty] | 3 | [349 empty] | 2 | [37 empty] | 3

## Summary
Epic | Features | Concept ~2 months T0 | Pre-production ~4 months T1-T2 | Early Prod ~4 months T3 | Mid Prod ~6 months T4 | End Prod ~4 months T5 | Alpha ~2 months T6 | Beta ~1.5 months T6 | Launch ~1 month T6 | First Release ~1.5 months T6-T7 | LS 1 Live T7 | LS 2 Live T8 | Total PW
Player Build | 11 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
World Systems | 29 | 0 | 0 | 223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223
Combat | 9 | 0 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336
User Space | 8 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
Items & Inventory | 9 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
Player Economy | 7 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111
Quest System | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
Social & Multiplayer | 10 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
Game Bibles | 6 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
Platform | 19 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53
Live Game | 7 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Partner Build | 8 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143
Product Publishing | 7 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
GRAND TOTAL |  | 0 | 0 | 1126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126

## Epics & Features
Epic | Feature | Sizing | Current Tier
Player Build | Player Progression | L | T1: R&D
Player Build | Skill System | L | T1: R&D
Player Build | Achievements & Trophies | M | T1: R&D
Player Build | Factions / Reputation | M | T1: R&D
Player Build | FTUE | M | T2: GDD/TDD/Brief
Player Build | Professions | L | T1: R&D
Player Build | Character Management | M | T0: Ideation
Player Build | Character Creation & Customization | L | T1: R&D
Player Build | Garment System | M | T0: Ideation
Player Build | Persona System | M | T1: R&D
Player Build | Emote System | S | T0: Ideation
World Systems | Foam Corruption | M | T2: GDD/TDD/Brief
World Systems | Miasma Corruption | M | T0: Ideation
World Systems | Water Corruption | M | T0: Ideation
World Systems | Crystal Corruption | M | T0: Ideation
World Systems | Time Corruption | M | T0: Ideation
World Systems | Enemy Corruption | M | T0: Ideation
World Systems | Oil Corruption | M | T0: Ideation
World Systems | Texture Corruption | M | T0: Ideation
World Systems | Environmental Elemental Effects (combination states) | L | T2: GDD/TDD/Brief
World Systems | Basic Movement System | L | T1: R&D
World Systems | Advanced Traversal | L | T1: R&D
World Systems | Navigation | M | T0: Ideation
World Systems | Day/Night Cycle | M | T1: R&D
World Systems | Dynamic Weather | M | T1: R&D
World Systems | Instancing | L | T0: Ideation
World Systems | Dungeon Mechanics | L | T0: Ideation
World Systems | The Dungeon | L | T0: Ideation
World Systems | Partner Portal | M | T1: R&D
World Systems | World Bosses | L | T0: Ideation
World Systems | Corruption Heatmap | M | T1: R&D
World Systems | Biome - Portal Peak | M | T4: MVP
World Systems | Biome - Hidden Hills | M | T0: Ideation
World Systems | Biome - Farmlands | M | T0: Ideation
World Systems | Biome - Mistrun Shore | M | T0: Ideation
World Systems | Biome - Whispering Woods | M | T0: Ideation
World Systems | Biome - Tranquil Sands | M | T0: Ideation
World Systems | Biome - Torrential Vale | M | T0: Ideation
World Systems | Biome - Clockwork | M | T0: Ideation
World Systems | Biome - Downtime | M | T4: MVP
Combat | Combat Framework | L | T2: GDD/TDD/Brief
Combat | Ranged Combat | M | T0: Ideation
Combat | Combat AI Behavior | L | T0: Ideation
Combat | Enemies Art | M | T0: Ideation
Combat | PvP Combat | L | T0: Ideation
Combat | Combat Balance & Telemetry | M | T2: GDD/TDD/Brief
Combat | Combat Abilities | L | T1: R&D
Combat | Magic | L | T0: Ideation
Combat | Full Motion Video (FMV) | M | T1: R&D
User Space | User Space Server & Instance | L | T2: GDD/TDD/Brief
User Space | User Space Decoration | M | T0: Ideation
User Space | P2P / P2G User Space Connection | M | T2: GDD/TDD/Brief
User Space | Building Houses | L | T1: R&D
User Space | Saving House Layouts | M | T0: Ideation
User Space | Partner Portal System (player house) | M | T0: Ideation
User Space | Arcade Cabinet | M | T1: R&D
User Space | Anywhere Door Placement | S | T0: Ideation
Items & Inventory | Item Core System | L | T2: GDD/TDD/Brief
Items & Inventory | Inventory System | M | T2: GDD/TDD/Brief
Items & Inventory | Equipment System | M | T0: Ideation
Items & Inventory | Loot Distribution | M | T2: GDD/TDD/Brief
Items & Inventory | Mounts / Pets | L | T1: R&D
Items & Inventory | Banks | M | T0: Ideation
Items & Inventory | P2P Item Transfer | M | T0: Ideation
Items & Inventory | Consumables | S | T2: GDD/TDD/Brief
Items & Inventory | Durable Items | S | T0: Ideation
Player Economy | Trading System | L | T0: Ideation
Player Economy | Currency System | M | T0: Ideation
Player Economy | Auction House | L | T0: Ideation
Player Economy | In-game Store | M | T0: Ideation
Player Economy | In-game Economy | L | T0: Ideation
Player Economy | RMT Game Economy | L | T0: Ideation
Player Economy | IG / RMT Monitoring System | M | T0: Ideation
Quest System | Quests Backend / Tooling | L | T2: GDD/TDD/Brief
Quest System | Quests as Events | M | T1: R&D
Quest System | Quest Multiplayer | L | T1: R&D
Quest System | Quest Types - Courier / Escort / Kill / Collect / Mystery / Time / Partner / Lockpicking | L | T2: GDD/TDD/Brief
Quest System | Quest Reward System | M | T0: Ideation
Quest System | Quest Log | M | T0: Ideation
Quest System | Quest Dialog GUI | M | T0: Ideation
Quest System | Quest Narrative Content | L | T2: GDD/TDD/Brief
Quest System | In Game Cinematic (IGC) | L | T2: GDD/TDD/Brief
Quest System | Meta Quest System | M | T0: Ideation
Quest System | Quest Generator System | L | T0: Ideation
Quest System | Targeted VO | M | T2: GDD/TDD/Brief
Social & Multiplayer | Game Chat System | M | T1: R&D
Social & Multiplayer | Friends | M | T1: R&D
Social & Multiplayer | Guilds | L | T1: R&D
Social & Multiplayer | Co-op / Party | M | T1: R&D
Social & Multiplayer | Co-op / Raids | L | T1: R&D
Social & Multiplayer | Dueling | M | T1: R&D
Social & Multiplayer | In-game Mail | S | T2: GDD/TDD/Brief
Social & Multiplayer | Notifications | S | T1: R&D
Social & Multiplayer | Player Config PvP Server | M | T0: Ideation
Social & Multiplayer | LFG / Pick-up Groups | M | T0: Ideation
Game Bibles | UX/UI Bible | M | T0: Ideation
Game Bibles | Accessibility Guidelines | M | T0: Ideation
Game Bibles | Brand Bible | M | T2: GDD/TDD/Brief
Game Bibles | Art Bible | L | T3: Prototype
Game Bibles | Monetization Bible | M | T0: Ideation
Game Bibles | Red Books (Live Service emergency guidelines) | M | T0: Ideation
Platform | Player Account Creation / Deletion | M | T2: GDD/TDD/Brief
Platform | Player Account Authentication | M | T2: GDD/TDD/Brief
Platform | Player Account Privacy Settings & Legal | M | T1: R&D
Platform | Player Dashboard - Account Features | M | T1: R&D
Platform | Player Dashboard - Game Dashboard | M | T1: R&D
Platform | Player Dashboard - Friends | M | T1: R&D
Platform | Player Dashboard - Search & Notifications | M | T1: R&D
Platform | Player Dashboard - Marketplace | L | T1: R&D
Platform | Developer Dashboard - Developer Account | M | T1: R&D
Platform | Developer Dashboard - Game Dashboard | M | T1: R&D
Platform | Developer Dashboard - Settings & Support | M | T1: R&D
Platform | Quest Tracking | M | T1: R&D
Platform | Payment Processing (incl. Refunds) | L | T0: Ideation
Platform | Online Services & Backend | L | T0: Ideation
Platform | Launcher & Distribution | L | T2: GDD/TDD/Brief
Platform | Partner Loop | M | T1: R&D
Platform | Game Tool Integration (incl. Game Key Generation) | M | T1: R&D
Platform | Account Level Settings | S | T0: Ideation
Platform | Social Media Support | M | T0: Ideation
Live Game | Live GDD | M | T0: Ideation
Live Game | Content | L | T0: Ideation
Live Game | Forecast | M | T0: Ideation
Live Game | Analytics & BI | L | T0: Ideation
Live Game | Sales Dashboard | M | T0: Ideation
Live Game | Telemetry | L | T0: Ideation
Live Game | Live Service Event Plan | L | T0: Ideation
Partner Build | Partner = Feature definition | S | T0: Ideation
Partner Build | Sign Partner | S | T0: Ideation
Partner Build | Partner Brief | M | T0: Ideation
Partner Build | Partner Design Doc | M | T0: Ideation
Partner Build | Partner TDD | M | T0: Ideation
Partner Build | Partner Art Brief | M | T0: Ideation
Partner Build | Partner Build | L | T0: Ideation
Partner Build | Partner Integration | M | T0: Ideation
Product Publishing | Web Presence | M | T0: Ideation
Product Publishing | Website | M | T0: Ideation
Product Publishing | Community Persona | M | T0: Ideation
Product Publishing | Title Identity | M | T0: Ideation
Product Publishing | Player Support | M | T0: Ideation
Product Publishing | Go-To-Market Strategy & Implementation | L | T0: Ideation
Product Publishing | 3rd-party Store Publishing | M | T0: Ideation

## Roles
Role | Discipline | Notes
CEO | Leadership
Creative Director | Leadership
Head of Legal | Leadership
COO | Leadership
HR Manager | Leadership
Executive Producer | Production
Producer | Production
Game Producer | Production
Tech Producer | Production
Art Producer | Production
Game Director | Design
Game Design Lead | Design
Level Design Lead | Design
Game Designer | Design
Combat Designer | Design
Level Designer | Design
Technical Designer | Design
Writer | Design
Art Director | Art
Concept Artist | Art
UI/UX Designer | Art
Graphic Designer | Art
Character Artist | Art
Environment Artist | Art
Prop Artist | Art
Animator | Art
Character Rigger | Art
VFX Artist | Art
Technical Artist | Art
CTO | Engineering
Tech Lead | Engineering
Gameplay Developer | Engineering
Full Stack Developer | Engineering
Backend Developer | Engineering
Network Engineer | Engineering
QA | QA
Sound Designer | Audio
Platform Team | Platform

## Gates
Gate | Phase | Target Tier | Tier Name | Notes
0 | Concept | T0 | Ideation | Y-doc, pitch, vision lock; all features captured at T0
1 | Pre-production | T1-T2 | R&D / GDD-TDD-Brief | GDD/TDD/Art briefs for all greenlit features (T2)
2 | Early Prod | T3 | Prototype | Prototype every feature; many bugs allowed (T3)
3 | Mid Prod | T4 | MVP | Full MVP scope - heaviest production gate (T4)
4 | End Prod | T5 | Feature Complete | Feature complete, polish to ship quality (T5)
5 | Alpha | T6 | Player Tested | Playtest, telemetry, balance pass; gating bugs only
6 | Beta | T6 | Player Tested | External player feedback, cert prep, content lock
7 | Launch | T6 | Player Ready | Day-0 readiness, marketing, store, support
8 | First Release | T6-T7 | Player Ready / Expand | Live monitoring, hotfixes, day-1/7/30 patches
9 | LS 1 | T7 | Expand | Expansions, new content drops, season cadence (T7)
10 | LS 2 | T8 | Scale | Optimize / scale post-load, sustain plan (T8)

## Tiers
Tier | Name | Definition
T0 | Ideation | Idea captured, no commitment
T1 | R&D | Research, prototyping intent, technical feasibility
T2 | GDD / TDD / Brief ready | GDD done, TDD done, art brief done
T3 | Prototype | Functional with no skins, can be bugged
T4 | MVP | Limited quality, but full-featured
T5 | Feature Complete (at quality) | Final assets, polished, no scope cuts left
T6 | Player Ready / Tested | Playtest, alpha, beta, telemetry feedback applied
T7 | Expand | Add to feature / content
T8 | Scale | Productional optimization post-load

## Legend
Cell Color / Section | Meaning
Phase super-headers (row 1 of Plan)
Concept | Concept gate (T0 Ideation)
Pre-production | Pre-production gate (T1-T2)
Production | Early / Mid / End Prod gates (T3-T5)
Release | Alpha / Beta / Launch / First Release
Live Service | LS 1 / LS 2
Discipline | Role group color (row 3 of Plan)
Leadership | CEO, Head of Legal, Head of Finance & Ops, HR Manager
Production | Executive / Producer / Game / Tech / Art Producer
Design | Game Director, Design Leads, Designers, Writer
Art | Art Director, Concept, UI/UX, Character/Env/Prop, Anim, Rig, VFX, TA
Engineering | CTO, Tech Lead, Gameplay/Full Stack/Backend/Network
QA | QA
Audio | Sound Designer
Platform | Platform Team
Sizing key (col C)
S | Small feature
M | Medium feature
L | Large feature
How to use
Plan sheet | Fill in man-days per (feature, gate, role). Cells are blank by default.
Totals row | Bottom of Plan: SUMs each role column per gate.
Headcount row | Total PW / (gate months * 20 working days). Edit GATE_MONTHS in the script if your durations change.
Summary sheet | Auto-rolls up Plan totals per epic per gate.
Adding rows | Insert rows inside an epic block on Plan. Update Total PW SUM ranges if you extend past the current last data row.