## Sorted by Epic
[7 empty] | Yorgos |  | Nadir |  | Kieron |  | Panos |  | Nikolas |  | Seth |  | Maria |  | Hannah |  | Aggeliki |  | Final (days)
Epic | Feature | Story | Task | Team | Description | Definition of Success | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max
Player Build
| In-game Tutorial |  |  | Game design | Finalized in-game tutorial explaining basic mechanics to the player, set in the starting location | The tutorial is clear and straightforward UX/UI pass Players can't die during the tutorial sequence No major visual or functional bugs
|  | Tutorial Cave Layout Fixes |  | Level design | Shorter and easier to complete cave blockout | Reduced completion time No spots where the player can die | 8 | 12 |  |  |  |  | 7 | 14 |  |  | 10 | 15 | [6 empty] | 10
|  | Tutorial cave set dressing fixes |  | Environment Art | Adapt the set dressing of the cave to the updated blockout | No major art changes or new content produced, no change of the art style
|  | Tutorial Cave lighting |  | Environment Art
|  | Tutorial cave Ambience & SFX |  | Audio | [18 empty] | 5 | 10 | 7
|  | Tutorial Configuration/set up/texts |  | Game design | Place the tutorial hints so player understands the basic game mechanics (movement, navigation, interaction with objects) | Hints are clear and understandable Hints go over all main in-game mechanics the player needs to start the game | 2 | 3 | 2 | 3 | 10 | 20 | 3 | 8 | [10 empty] | 3
|  | Tutorial UI |  | UX/UI | Make sure the UI in the tutorial cave is well visible and aligned with the tutorial cave art style |  |  |  | 4 | 10 | [14 empty] | 6
|  | Tutorial VFX |  | VFX
|  | Controls UI |  | UX/UI | Clear controls UI and convenient keyboard layout |  |  |  | 2 | 4 | [14 empty] | 4
|  |  | Tutorial cave contents | Game design | [8 empty] | 2 | 5 |  |  | 1 | ~ | [6 empty] | 2
|  |  | Narrative | Narrative | [14 empty] | 0.5 | 1 |  |  |  |  | 1
|  |  | Tutorial QA check | QA
Player Build
| Garment System |  |  | Game design | Classic garment system with equipment slots for different pieces of clothing/gear. Needs finalized documentation, sufficient number of equipment parts and UI. Also should be integrated with character stats if equipment affects them |  |  |  | 7 | 10
|  | Garment System GDD/TDD |  | Game design |  |  | 6 | 10 | 4 | 8 | 5 | 10 | 6 | 10 |  |  | 7 | 10 | 5 | 6 |  |  |  |  | 7
|  |  | Vertical Slice garments | Game design |  |  | 5 | 7 | [16 empty] | 5
|  | Garment System Integration |  | Gameplay Engineering
|  | Garment System UI |  | UX/UI |  |  |  |  | 10 | 15 | [14 empty] | 14
|  | Equipment Concepts |  | Concept Art
|  | Equipment Models |  | Character Art
|  |  | Garment Type SFX | Audio | (on buy,sell, wear, unequip) | [17 empty] | 2 | 4 | 3
|  | Equipment Stats integrated with character stats |  | Gameplay Engineering
|  |  | Garment System QA | QA
|  |  | Equipment QA | QA
Player Build
| Player Progression |  |  | Game design | Players can gain XP for in-game actions (combat, quests, etc) and level up. Level up affects chararcter stats and skills. Character stats are defined and configured and connected with other in-game systems (combat, skills, etc)
|  | Player level up documentation |  | Game design |  |  | 10 | 18 | 10 | 15 | 5 | 10 | 6 | 10 |  |  | 1 | 4 | [6 empty] | 14
|  | Player level up configuration |  | Game design |  |  | 10 | 15 | 5 | 7 | 10 | 20 |  |  |  |  | 0.5 | ~ | [6 empty] | 15
|  | player level up integration |  | Gameplay Engineering
|  | Player level up UI |  | UX/UI |  |  |  |  | 2 | 5 | [6 empty] | 5 | 10 | [6 empty] | 3
|  | Character stats documentation |  | Game design |  |  | 7 | 12 | 5 | 8 | 5 | 10 | 6 | 10 | [10 empty] | 5
|  | Character stats implementation |  | Gameplay Engineering
|  | Character stats configuration in connection with other systems |  | Game design |  |  |  |  | 5 | 10 | 15 | 25 |  |  |  |  | 1 | ~ | [6 empty] | 10
|  | Character stats UI |  | UX/UI | [20 empty] | 15
|  |  | Level up & Stats QA | QA
| Skill System (1 skill tree active) |  |  | Game design | Basic skill system supported with one skill tree active and interactive. 2 more skill trees shown but not active. Skill progression is integrated with other game systems (stats etc)
|  | Skill Tree UI Audio |  | Audio | [18 empty] | 7 | 14 | 8
|  | Skills in-game audio |  | Audio | [18 empty] | 7 | 14 | 8
|  | Skill System Documentation |  | Game design |  |  | 8 | 12 | 10 | 13 | 5 | 10 | 6 | 10 |  |  | 4 | 8 | [6 empty] | 15
|  | Skill System Implementation |  | Gameplay Engineering
|  | Skill System Configuration |  | Game design |  |  |  |  | 4 | 5 | 15 | 25 | [12 empty] | 5
|  | Skill System UI |  | UX/UI
|  |  | Skill system QA | QA
World Systems |  |  |  | Game design
| Full Motion Video (FMV) |  |  | Game design | [6 empty] | no idea | no idea | [12 empty] | 1
|  | Intro supports FMV |  | Backend Engineering | The game supports full motion videos integration and playback | FMV triggers correctly Playback completes or skips No crashes or black screens Transitions to next state
|  |  | Create placeholder FMV playback flow | Backend Engineering | System to trigger fmv from within a quest, or at startup
|  |  | Implement FMV skip behavior | Backend Engineering | Skip should not be accidental (e.g. hold down skip button) - and there should also be a way to pause playback
|  |  | Implement transition after FMV | Backend Engineering | Transition to explicit camera rotation and location
|  |  | FMV Production | Environment Art | To determine possible scopes with GD and AD
|  |  | Integrate final/near-final FMV asset | Backend Engineering | Create an editable system so that anybody can make a change here
|  |  | QA playback across target builds | QA
|  |  | Fix FMV blocker bugs | Backend Engineering
|  |  | Narrative - Cinematic scripting | Narrative | [14 empty] | 1 | 3 |  |  |  |  | 1
| Static pictures intro + voiceover |  |  | Game design | This is the proposed backup if an FMV cannot be produced within budget. |  | 8 | 10 | 15 | 20 | 10 | 30 | [12 empty] | 10
|  | Intro sequence plays 3 slides with voiceover |  | Backend Engineering | Intro sequence supports static pictures playback with voiceover and subtitles | The pictures are played correctly Voiceover and subtitles are synced to the scene Skip functionality works No major bugs or blockers
|  |  | Create intro sequence controller | Backend Engineering
|  |  | Display static slides full-screen | Backend Engineering
|  |  | Play voiceover synced to sequence | Backend Engineering
|  |  | Display subtitles synced to VO | Backend Engineering
|  |  | Implement skip behavior | Backend Engineering
|  |  | Implement transition to gameplay/menu | Backend Engineering
|  |  | Final art production | Concept Art
|  |  | VO production | Audio |  |  |  |  | 6 | 10 | no idea | no idea | [12 empty] | 3
|  |  | Subtitles production | Game design |  |  |  |  | 2 | 4 | 2 | 5 | [6 empty] | 0.5 | 2 |  |  |  |  | 1
|  |  | Integrate final art + VO assets | Backend Engineering
|  |  | QA + fix blockers | QA
| In-game cutscenes |  |  | Gameplay Engineering
|  | The game supports cutscenes |  | Gameplay Engineering | In-engine cutscene mechanism is implemented, designers can set the necessary scenes in defined places of the game. Documentation exists for proposed system (talk to GD). Basically this uses Unreal's Sequencer, or a simplified version, so that designers can trigger a basic movie from a dialogue box or quest intro. | Cutscenes are triggered and played correctly Camera behavior is correct Skip mechanism implemented No major bugs or blockers
|  |  | Cutscene trigger system | Gameplay Engineering
|  |  | Camera control during cutscene | Gameplay Engineering
|  |  | Player control lock/unlock | Gameplay Engineering
|  |  | NPC/character sequencing | Gameplay Engineering
|  |  | Dialogue playback (in-cutscene) | Gameplay Engineering
|  |  | Cutscene skip functionality | Gameplay Engineering
|  |  | Transition in/out of cutscene | Gameplay Engineering
|  |  | Basic cutscene sequencing (timeline) | Gameplay Engineering
|  |  | Cutscene stability (QA & fixes) | QA
|  | Cutscene content |  | Game design | Define all required content and direct the cutscenes; make sure all required assets exist | Basic cutscenes directed, MVP quality | 15 | 20 | 10 | 20 | 5 | 10 | [12 empty] | 5
|  |  | Narrative | Narrative | [14 empty] | 0.5 | 1 |  |  |  |  | 1
World Systems
| Basic movement system |  |  | Game design | [6 empty] | no idea | no idea
|  | Locomotion Integration |  | Gameplay Engineering | Player can access all main movement mechanics | No major bugs with functionality or visuals All needed animations implemented
|  |  | Walk | Gameplay Engineering
|  |  | Run | Gameplay Engineering
|  |  | Sprint | Gameplay Engineering
|  |  | Jump | Gameplay Engineering
|  |  | Double Jump | Gameplay Engineering
|  |  | Iteration | Game design | [20 empty] | 5
|  |  | Locomotion QA check | QA
World Systems
| World Resources |  |  | Game design
|  | Starting Chest |  | Game design | NOTE: This entire story may be redundant. We already have chests. There is already a task for adding one to the initial cave. Player can find a chest in the tutorial cave that has the sword inside | The chest should be located on the player's way. The player should be incentivised to interact with the chest. Progress should rely on opening the chest. | 1 | 2 | 1 | 2 | 3 | 5 | 0.5 | 1 |  |  | 0.5 | 1
|  |  | Chest concept | Concept Art
|  |  | Chest model | Environment Art
|  |  | Chest animation | Animation & Rigging
|  |  | Chest VFX | VFX | Open "sparkle" and rewarding feedback, Ballista minigame
|  |  | QA check | QA
|  | Shield |  | Game design | NOTE: Should be in combat section |  | 4 | 6 | 2 | 4 | 3 | 5 | [12 empty] | 4
|  |  | Shield animations | Animation & Rigging
|  |  | Shield Asset | Environment Art
|  | Starting Sword |  | Game design | NOTE: Should be in combat section Starting player weapon. Should be good enough to fight starting enemies and not get easily killed |  |  |  | 2 | 4 | 3 | 5 |  |  |  |  | 0.5 | 0.5 | [6 empty] | 4
|  |  | Sword concept | Concept Art
|  |  | Sword model | Character Art
|  |  | Sword animations | Animation & Rigging
|  |  | Sword VFX | VFX | Swing sword trail (visual: color, opacity) | Readable and underline weapon movement and area of damage plus distinction with standard/enchanted/poisoned
|  | Equipment Stats integrated with character stats |  | Game design | Reliant on character design (do stats change) |  | 5 | 10 | 5 | 8 | 5 | 10 | [12 empty] | 5
|  |  | Equipment Stats integrated with character stats | Gameplay Engineering
|  |  | QA check | QA
World Systems
| Navigation |  |  | Game design
|  | World Map |  | Game design | World map integrated with accessible areas visible and major points of interest placed + quality of life features to be designed | Player can access and navigate the world map Map has correct assets and quest tracking functionality | 10 | 14 | 15 | 25 | 10 | 20 | 10 | 20 | [10 empty] | 10
|  |  | Map markers sfx | Audio | [18 empty] | 0.5 | 1 | 1
|  |  | World Map background asset | Concept Art
|  |  | World Map asset integration | Gameplay Engineering
|  |  | World Map UI | UX/UI | [20 empty] | 10
|  |  | Quest markers support | Gameplay Engineering
|  |  | Map QA check | QA
|  | Fog-of-war |  | Gameplay Engineering | Parts of the map are hidden until the player reaches them or gets information about them | The hide/reveal functionality works without major bugs
|  |  | Fog of war QA check | QA
|  | Minimap |  | Gameplay Engineering
|  |  | Minimap Levels | Game design |  |  | 5 | 8 | I personally endorse this |  | 10 | 20 | [12 empty] | 5
|  |  | Minimap UI | UX/UI | Minimap is constantly present on the screen to help players navigate; it supports quest tracking | [19 empty] | 10
|  |  | Minimap assets | Concept Art
|  |  | Minimap quest navigation support | Gameplay Engineering
|  |  | Minimap QA check | QA
|  | Compass |  | Gameplay Engineering | Basic navigation tool that shown direction to the selected marker/quest (or north) at the top of the screen
|  |  | Compass UI | UX/UI |  |  |  |  | 2 | 5 | [14 empty] | 10
|  |  | Compass Integration | Gameplay Engineering
|  |  | Compass QA check | QA
| Corruption |  |  | Game design
|  | Corrupted Vines |  | Game design | The texture on the vines that implies they are corrupted. No functionality, just visual |  | 2 | 3 |  |  | 3 | 5 |  |  |  |  | 0.5 | 0.5 | [6 empty] | 1
|  |  | Corrupted texture | TechArt | Material suitable to communicate cleaning mechanics and hazard | Match Art Direction, tested and working for different size and elements
|  |  | Vine NPC Narrative | Narrative | [20 empty] | 1
|  |  | Vines Foliage | Environment Art
|  |  | Corrupted VFX | VFX | Upgrade features form TA material
|  |  | Corrupted vines behavior & visual QA | QA
|  | Foam Corruption |  | Game design
|  |  | Foam Corruption Techart | TechArt | Volumetric Corruption dependancy with additional specific elements | Readable as same mechanics, adaptable to assets and areas, performant
|  |  | Foam Corruption integration | Gameplay Engineering
|  |  | Foam Corruption VFX | VFX | Upgrade features form TA material
|  |  | Foam Corruption cleansing animations | Animation & Rigging
|  |  | Foam Corruption cleansing weapon | Character Art
|  |  | Foam Corruption SFX, VFX design | Game design |  |  | 3 | 5 |  |  | 5 | 10 | [12 empty] | 3
|  |  | Foam Corruption SFX | Audio | [18 empty] | 2 | 3 | 2
|  |  | Foam Corruption QA | QA
|  | Timed Corruption |  | Game design | A simple mechanic to implement using animation curves. An object such as a door or bridge has been broken into multiple parts, and the player has to use magic to rebuild it, visually reversing time. There will be puzzle and multiplayer opportunities. For instance one player may need to restore a bridge while another player crosses it to reach a switch. There can also be a multi-stage set of things that have collapsed or prematurely rusted. The player has to work out which ones to reverse, in which order, to recreate the original setting (all pieces lock into place once this has been achieved, for a short time). |  |  |  | 10 | 15 | 20 | 40
|  |  | Timed Corruption Design | Game design |  |  | 3 | 5 | 5 | 9 | 5 | 10 | 10 | 15 |  |  | 2 | 3 | [6 empty] | 10
|  |  | Timed Corruption TechArt | TechArt
|  |  | Timed Corruption Integration | Gameplay Engineering
|  |  | Timed Corruption Server & Multiplayer | Backend Engineering
|  |  | Timed Corruption 3D Assets | Environment Art
|  |  | Timed Corruption VFX | VFX | Upgrade features form TA material
|  |  | Timed Corruption SFX | Audio | [18 empty] | 3 | 6 | 5
|  |  | Timed Corruption QA | QA
| Advanced Traversal |  |  | Game design | Only gliding for now. Gliding is an airborne locomotion state, not a flight simulation. While gliding, the player retains directional movement control similar to ground traversal, but with reduced acceleration, limited top speed, and continuous stamina drain. |  |  |  | 15 | 25 | 5 | 10 | [12 empty] | 2
|  | Glider Stamina UI |  | UX/UI |  |  |  |  | 2 | 3 | [14 empty] | 2
|  | Gliding Concepts |  | Concept Art
|  | Gliding Integration |  | Gameplay Engineering
|  | Gliding Animations |  | Animation & Rigging
|  | Gliding SFX |  | Audio | [18 empty] | 1 | 2 | 2
|  | Gliding VFX |  | VFX
|  | Gliding Device |  | Character Art
|  |  | Gliding QA | QA
|  | Portals spawning & Xyron moving through portals |  | Gameplay Engineering
|  |  | Narrative for Xyron quests | Narrative |  |  | 2 | 3 | 4 | 6 | 5 | 10 |  |  |  |  | 1 | 2 | 1 | 3 |  |  |  |  | 2
|  |  | Spawning portals SFX | Audio | [18 empty] | 2 | 4 | 4
|  |  | 5 or 6 mini quests | Game design |  |  | 6 | 8 | 7 | 12 | 10 | 20 | 5-6d | 10-12d |  |  | 5 | 8 | [6 empty] | 8
|  |  | Xyron voiceover narrative | Narrative |  |  | 3 | 5 |  |  | 1 | 3 | [6 empty] | 0.5 | 1 |  |  |  |  | 2
|  | Xyron voiceover |  | Audio | [18 empty] | 7 | 14 | 8
|  |  | Xyron/portals spawning QA | QA
World Systems
| Forge |  |  | Game design | Weapon crafting mechanic that allows to combine different parts of the weapon to get a new one | recipe based crafting system |  |  | 12 | 18 | 5 | 20 | [12 empty] | 12
|  | Component System Design |  | Game design |  |  | 2 | 4 | 9 | 12 | 3 | 5 |  |  |  |  | 5 | 10 | [6 empty] | 5
|  | Crafted Weapon Parts in-game Audio |  | Audio | [18 empty] | 5 | 10 | 5
|  | Forge Crafting Audio |  | Audio | [18 empty] | 3 | 7 | 5
|  | Forge Documentation |  | Game design |  |  | 4 | 6 | 5 | 7 | 3 | 5 | 6 | 10 | [10 empty] | 5
|  | Forge Concepts |  | Concept Art
|  | Forge Integration |  | Gameplay Engineering
|  | Forge UI |  | UX/UI |  |  |  |  | 7 | 10 | 5 | 15 | [12 empty] | 10
|  | Forge VFX |  | VFX
|  | DA combination setup |  | TechArt | Weapon color customization parallel to garments plus pieces and parts assembly
|  | Crafting Desk |  | Environment Art
|  | Forge Props |  | Character Art
|  |  | Forge QA | QA
World Systems
| Instancing |  |  | Backend Engineering | Allow players or parties to enter private versions of locations with isolated gameplay state.
|  | GDD Documentation |  | Game design |  |  | 4 | 6 |  |  | 3 | 5 | 15 | 20 | [10 empty] | 2
|  | Instancing Documentation |  | Backend Engineering
|  | User Space Instancing support |  | Backend Engineering
|  | Guild House instancing support |  | Backend Engineering
|  | Dungeon Instancing |  | Backend Engineering
|  | Zones Instancing |  | Backend Engineering
|  |  | Instancing QA | QA
| Dungeons mechanics |  |  | Game design | Design different mechanics that can be used in dungeons. Only design stage for the vertical slice |  |  |  | 7 | 10 | 5 | 15
|  | Dungeons documentation |  | Game design |  |  | 2 | 4 | 2 | 4 | 3 | 5 | 6 | 15 | [10 empty] | 5
|  |  | Narrative | Narrative | [14 empty] | 0.5 | 2 |  |  |  |  | 1
| Puzzles |  |  | Game design | Implement a puzzle that requires multiple players to interact with environment elements to progress. |  |  |  | 12 | 15 | 10 | 15 | [12 empty] | 5
|  | Multiplayer enviromental puzzle design |  | Game design | Time Corruption puzzle (bridge + switch - 2 players) |  | 5 | 8 | 5 | 9 | 10 | 20 | 6 | 10 | [10 empty] | 12
|  | Multiplayer enviromental puzzle layout |  | Level design | [8 empty] | 6 | 10 | 10 | 20 | 4 | 7 | [6 empty] | 10
|  | Multiplayer enviromental puzzle integration |  | Gameplay Engineering
|  |  | Puzzles QA | QA
World Systems
| Downtime Final set dressing (L) |  |  | Environment Art | Finalized Downtime (MVP quality). No blockouts. Focus on the social area (tavern) + several shop fronts that are not accessible inside
|  | Multiplayer interactions (toasts) |  | Game design |  |  | 2 | 3 |  |  | 3 | 15 | [12 empty] | 2
|  | Downtime Shops closed area |  | Game design |  |  | 2 | 3 |  |  | 3 | 5 | [12 empty] | 2
|  | Downtime Social Hub Area Blockout |  | Level design | [6 empty] | blockouts are LD? | yes | 6 | 10 | 7 | 12 | 7 | 15 | [6 empty] | 6
|  | Downtime Tavern Blockout |  | Level design | [8 empty] | 6 | 10 | 3 | 7 | 7 | 15 | [6 empty] | 7
|  | Downtime Tavern Concept |  | Concept Art
|  | Downtime Tavern Model |  | Environment Art
|  | Downtime Tavern Props |  | Environment Art
|  | NPC behaviour document |  | Game design | [20 empty] | 2
|  | Downtime NPC placement |  | Game design |  |  | 5 | 7 |  |  | 5 | 8 | 4 | 10 | [10 empty] | 5
|  | Downtime shops storefronts models |  | Environment Art
|  | Downtime Auction House storefront model |  | Environment Art
|  | Downtime Bank storefront model |  | Environment Art
|  | Downtime Barbersmith storefront model |  | Environment Art
|  |  | Downtime QA | QA
| Speedup Archway |  |  | Game design | The archway through Downtime going through the entire town. The goal is to show the player the town without making them actually walking around it. The main function is the competition between player for who completes it faster. Should have persistent leaderboards. |  |  |  | 4 | 10 | 3 | 5
|  | Safety System |  | Game design |  |  |  |  | -- | -- | 3 | 5 | [12 empty] | 3
|  | Archway race design |  | Game design | Downtime specifically | [19 empty] | 3
|  | Persistent leaderboards |  | Backend Engineering
|  | Archway Placement |  | Game design |  |  | 2 | 4 | 2 | 4 | 2 | 5 | 4 | 7 |  |  | 1 | 2
|  | Archway Models |  | Environment Art
|  | Archway VFX |  | VFX
|  |  | Win Fanfare VFX | VFX
|  | Archway SFX |  | Audio | [18 empty] | 0 | 0 | 0
|  |  | Archway QA | QA
World Systems
| Portal Peak (Medium) |  |  | Game design | Just making sure that there are no blockouts/unfinished parts in PP player can see - probably mainly for enviro artists
|  | PP Design |  | Game design |  |  | 3 | 5 |  |  |  |  | 6 | 10 | [10 empty] | 5
|  | PP Blockout |  | Level design | [8 empty] | 10 | 20 | 20 | 25 | 15 | 30 | [6 empty] | 20
|  | PP Concept |  | Concept Art
|  | PP Foliage |  | Environment Art
|  | PP Props Build |  | Environment Art
|  | PP layout |  | Environment Art
|  | PP Audio |  | Audio | [18 empty] | 14 | 18 | 15
|  |  | Portal Peak QA | QA
| POI: The Two Hills (S) |  |  | Game design | Two towers sequence with traversal and stuff. Player returns here after Downtime for the final scene
|  | The Two Hills Design |  | Game design |  |  | 4 | 6 |  |  |  |  | 4 | 10 | [10 empty] | 5
|  | The Two Hills Blockout |  | Level design | approx. 15 min of gameplay. Content of Platforming and Scattered Enemies | [7 empty] | 6 | 15 | 3 | 7 | 7 | 15 | [6 empty] | 15
|  | The Two Hills Concept |  | Concept Art
|  | The Two Hills Foliage |  | Environment Art
|  | The Two Hills Props Build |  | Environment Art
|  | The Two Hills layout |  | Environment Art
|  | The Two Hills Audio |  | Audio | [18 empty] | 4 | 6 | 4
|  |  | The Two Hills QA | QA
| POI: Portal Dimension (XS) |  |  | Game design | Intermediate layer before loading into the partner game
|  | Portal Dimension Design |  | Game design | [8 empty] | 3 | 4 |  |  |  |  | 1 | [5 empty] | 1
|  | Portal Dimension Blockout |  | Level design | [8 empty] | 4 | 8 | 4 | 15 | 1 | 5 | 2
|  | Portal Dimension Concept |  | Concept Art
|  | Portal Dimension Foliage |  | Environment Art
|  | Portal Dimension Props Build |  | Environment Art
|  | Portal Dimension layout |  | Environment Art
|  | Portal Dimension Audio |  | Audio | [18 empty] | 0.5 | 1 | 1
|  |  | Portal Dimension QA | QA
| POI: Final Tower |  |  | Game design | Intermediate layer before loading into the partner game
|  | Final Tower Design |  | Game design | Nikolas is desperate to call it Obsidian Tower | [7 empty] | 3 | 4 |  |  |  |  | 1 | [5 empty] | 1
|  | Final Tower Blockout |  | Level design | [8 empty] | 4 | 8 | 4 | 15 | 1 | 5 | 2 | [5 empty] | 5
|  | Final Tower Concept |  | Concept Art
|  | Final Tower Foliage |  | Environment Art
|  | Final Tower Props Build |  | Environment Art
|  | Final Tower layout |  | Environment Art
|  | Final Tower Audio |  | Audio | [18 empty] | 3 | 5 | 2
|  |  | Portal Dimension QA | QA
| POI: Waterfall Beauty Spot (S) |  |  | Game design | Shattered Pools can be used? user Space door placement here
|  | Waterfall Beauty Spot Concept |  | Concept Art
|  | Waterfall Beauty Spot Design |  | Game design |  |  | 2 | 4 |  |  |  |  | 2 | 5 | [10 empty] | 2
|  | Waterfall Beauty Spot Blockout |  | Level design | [8 empty] | 4 | 6 | 2 | 5 | 1 | 3 | [6 empty] | 4
|  | Waterfall Beauty Spot Foliage |  | Environment Art
|  | Waterfall Beauty Spot Props Build |  | Environment Art
|  | Waterfall Beauty Spot layout |  | Environment Art
|  | Waterfall Beauty Spot Audio |  | Audio | [18 empty] | 4 | 6 | 3
|  |  | Waterfall Spot QA | QA
| Wolves |  |  | Game design
|  | Wolf montages |  | Animation & Rigging
|  | Wolf AI behaviour |  | Game design | [20 empty] | 2
|  | Design |  | Game design |  |  | 4 | 6 | 7 | 10 | 3 | 5 | [12 empty] | 5
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt | Geo topology, UVs space optim., textures compliant to D/NRM/ORME/Mask rules, LOD0/1/2 decimation 100%/50%/25%
|  | Combat Behavior |  | Gameplay Engineering
|  | VFX |  | VFX
|  | Wolfy noises |  | Audio | [18 empty] | 0 | 0 | 0
|  |  | Wolves QA | QA
| Goblins |  |  | Game design
|  | Goblin montages |  | Animation & Rigging
|  | Goblin AI behaviour |  | Game design | [20 empty] | 4
|  | Design |  | Game design |  |  |  |  | 7 | 10 | 3 | 10 | [12 empty] | 9
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt
|  | Combat Behavior |  | Gameplay Engineering
|  | VFX |  | VFX
|  | SFX |  | Audio | [18 empty] | 7 | 14 | 7
|  |  | Goblins QA | QA
| Skeletons |  |  | Game design
|  | Skeleton montages |  | Animation & Rigging
|  | Skeleton AI behaviour |  | Game design | [20 empty] | 4
|  | Design |  | Game design |  |  |  |  | 7 | 10 | 3 | 5 | [12 empty] | 9
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt
|  | Combat Behavior |  | Gameplay Engineering
|  | VFX |  | VFX
|  | SFX |  | Audio | [18 empty] | 0 | 0 | 0
|  |  | Skeletons QA | QA
| Slimes |  |  | Game design
|  | Design |  | Game design |  |  | 4 | 6 | 7 | 10 | 3 | 5 | [12 empty] | 5
|  | Slimes AI behaviour |  | Game design | [20 empty] | 2
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt
|  | Combat Behavior |  | Gameplay Engineering
|  | VFX |  | VFX
|  | SFX |  | Audio | [18 empty] | 0 | 0 | 0
|  |  | Slimes QA | QA
| Corrupted Guardian |  |  | Game design | Corrupted Enemies are not required for the Vertical Slice - except for one reanimated robot, who technically falls under this category. He wakes up, looks menacing, then is destroyed by the crystal found in the partner game.
|  | Narrative |  | Game design |  |  | 2 | 3 |  |  | 2 | 5 | [12 empty] | 1
|  | Design |  | Game design | Includes the quest structure |  | 2 | 4 | 5 | 10 | 5 | 10 | [12 empty] | 2
|  |  | Quest structure | Game design |  |  | 1 | 3 | [16 empty] | 4
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt
|  | VFX |  | VFX
|  | SFX |  | Audio | [18 empty] | 3 | 7 | 3
|  |  | Corrupted Enemies QA | QA
| Carapax (Hero, but one type) |  |  | Game design
|  | Design |  | Game design |  |  | 2 | 3 |  |  | 3 | 5 | [12 empty] | 5
|  | Carapax AI design |  | Game design | [20 empty] | 4
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt
|  | Combat Behavior |  | Gameplay Engineering
|  | VFX |  | VFX
|  | SFX |  | Audio | [18 empty] | 5 | 8 | 7
|  |  | Carapax QA | QA
World Systems
| World/buiding scale design |  |  | Game design | World scale and building scale :defined and accepted throughout the game. | Scales definition are locked in documentation Parts of the game that are out of scale are fixed | [8 empty] | 1 month | 6 months | [8 empty] | 21
| Camera behavior |  |  | Game design | Camera behavior designed for different game situations and actions |  | 2 | 4 | 8 | 14 | 5 | 5 | [12 empty] | 5
|  | Camera behavior implementation/fixes |  | Gameplay Engineering | Camera behavior is implemented according to the design | Camera acts according to the design without major/blocking bugs
|  | Combat Camera |  | Game design |  |  | 4 | 6 | 6 | 9 | 5 | 10 | [12 empty] | 9
|  |  | Camera QA | QA
Quest System
| Various Quest Types Support |  |  | Gameplay Engineering
|  | Lockpicking |  | Game design | The minigame to open doors, chests and safes. Player first destroys a set of tiles to reveal the mechanism. Then they interact with the parts of the mechanism to move the marble to the lock and open it | The basic version of the game implemented and functional to open the starting chest The puzzle should be solved within 30 sec |  |  | 8 | 10 | 7 | 15 | 10 | 20 | [10 empty] | 2
|  |  | Lockpicking Concept | Concept Art
|  |  | Lockpicking UI | UX/UI |  |  |  |  | 8 | 15 | [14 empty] | 6
|  |  | Lockpicking Integration | Gameplay Engineering
|  |  | Lockpicking Techart | TechArt | Co-dev with VFX for breakble tiles, sphere and pipes path | Visually complementary and gameplay rewarding
|  |  | Lockpicking QA check | QA
|  | Design interface for quest types |  | Game design | not critical for the vertical slice. |  | 2 | 3 |  |  | no idea | no idea |  |  |  |  | 7 | 9 | [6 empty] | 5
|  | Other quest types support? |  | Gameplay Engineering | The game supports different quest types: kill X enemies, collect X objects etc | Designers can configure desired quest types in the engine The behavior is in line with documentation
Quest System
| Quest Integration |  |  | Game design
|  | Tutorial Quest Chain Configuration & Setup |  | Game design | Tutorial quest sequence fully designed with player journey and interactions described | The quest should be easily found and tracked throughout the way; should have clear start and end with rewards All needed NPCs, enemies, rewards should be placed and configured | [10 empty] | 7 | 10
|  |  | QA check | QA
|  | Green Faction NPC Concepts |  | Concept Art
|  | Green Faction NPC Models |  | Character Art
|  | Green Faction NPC animations |  | Animation & Rigging
|  | Green Faction NPC dialogue setup |  | Narrative |  |  | 3 | 6 |  |  | 3 | 8 | 4 | 6 |  |  | 1 | 4 | [6 empty] | 2
|  | Green Faction NPCs placement |  | Game design |  |  | 2 | 5 |  |  | 2 | 5 | 2 | 8 |  |  | 3 | 5 | [6 empty] | 2
|  |  | QA check | QA
| Quest Tools |  |  | Backend Engineering
|  | Quest Editor |  | Game design |  |  | 5 | 8 |  |  | 10 | 20 |  |  |  |  | 5 | 15 | [6 empty] | 2
|  | Dialogue System Design |  | Game design |  |  | 5 | 8 |  |  | 3 | 8 | [12 empty] | 3
|  | Dialogue System |  | Backend Engineering | The game supports dialogue system with options that lead to different dialogue branches
|  | Dialogue UI |  | UX/UI | [20 empty] | 10
|  | Quest Log |  | Backend Engineering | The quests are being tracked and the log/next quest should be accessible in the game UI
|  |  | Quest Log QA | QA
|  | Xyron narrative |  | Game design |  |  | 2 | 5 |  |  | 3 | 8 |  |  |  |  | 3 | 4 | [6 empty] | 2
Quest System
| Quest Rewards System |  |  | Game design |  |  | 2 | 5
|  |  | Quest UI Audio | Audio | [18 empty] | 0.5 | 1 | 1
|  | Quest Reward UI |  | UX/UI | [20 empty] | 5
|  | Quest Reward System design doc |  | Game design | [20 empty] | 2
|  | Quest Reward List |  | Game design | Reliant on robust inventory system | [5 empty] | 2 | 5 |  |  |  |  | 2 | 3 | [6 empty] | 2
|  | Rewards Choice |  | Gameplay Engineering | Quest rewards should include options players can choose from
|  |  | Quest Rewards QA | QA
User Space
| User Space Server & Instance |  |  | Backend Engineering | User Space is a separate instance and a player's home. Players place the door to access it. For the vertical slice, the door is placed in a POI in Portal Peak and the player is loaded into a separate location with a half-build house.
|  |  | FTUE Design | Game design |  |  | 4 | 6 |  |  | 3 | 8 |  |  |  |  | 4 | 7 | [6 empty] | 5
|  |  | FTUE UI | UX/UI | [20 empty] | 5
|  |  | User Space Editor audio | Audio | [18 empty] | 2 | 3 | 2
|  |  | Mutual Activity Design | Game design |  |  | 4 | 6 |  |  | 5 | 10 |  |  |  |  | 2 | 5 | [6 empty] | 4
|  |  | Mutual Activity UI | UX/UI | [20 empty] | 5
|  |  | Drinking design | Game design | [20 empty] | 1
|  |  | Drunken UI | UX/UI | [20 empty] | 4
|  | User Space is a separate instance |  | Backend Engineering
|  | User Space editor & UI |  | Gameplay Engineering
|  | User Space Ambience |  | Audio | [18 empty] | 1 | 2 | 1
|  |  | Item SFX | Audio | [18 empty] | 0.5 | 1 | 1
|  |  | Island ambient audio | Audio | [18 empty] | 1 | 2 | 1
|  | User Space editor VFX |  | VFX
|  |  | User Space functionality QA | QA
| Anywhere door placement |  |  | Gameplay Engineering
|  | User space door can be placed at predefined spots |  | Gameplay Engineering | We choose predefined spots in Portal peak (flat surface) where player can place their door. The door stays there and serves as a permanent user Space entrance
|  |  | Anywhere Door QA | QA
| User Space Decoration |  |  | Environment Art | The model of the house and sufficient furniture pieces that can be placed in the User Space
|  | User Space House concept |  | Concept Art
|  | User Space House model |  | Environment Art
|  | User Space furniture props |  | Environment Art
| User Space Island (S) |  |  | Game design | A separate location that serves as a player home. Inclides a half-build house, pets, a pond/river and fishing spots
|  | User Space GDD VS page |  | Game design | [20 empty] | 1
|  | User Space location concepts |  | Concept Art
|  | User Space location blockout |  | Level design | [8 empty] | 6 | 10 | 7 | 15 | 5 | 10 | [6 empty] | 7
|  | User Space location set dressing |  | Environment Art
|  | User Space location props |  | Environment Art
|  | User Space location foliage |  | Environment Art
|  |  | User Space visuals QA | QA
| Pets (mechanical parrot reuse) |  |  | Game design | Demo of the pets functionality. Pure cosmetic for the time being. Should be already supported. Decided to proceed with the parrot that was modelled for the pirates enemies |  | 3 | 5 |  |  | 8 | 15
|  | Pet system design |  | Game design | [20 empty] | 4
|  | Pet concepts |  | Concept Art
|  | Pet model |  | Character Art
|  | Pet animations |  | Animation & Rigging
|  | Pet VFX |  | VFX
|  | Pet behavior |  | Gameplay Engineering
|  | Pet integration |  | Gameplay Engineering
|  |  | Pet QA | QA
| Fishing |  |  | Game design | Fishing minigame/profession. Quite self-explanatory. Basically ready but needs final assets, animations and QA
|  | Fishing Integration |  | Game design | [6 empty] | 3 | 10 | [12 empty] | 3
|  | Fishing Rod model |  | Environment Art
|  | Fish model |  | Environment Art
|  | Fishing spot sign model |  | Environment Art
|  | Fishing UI |  | UX/UI | [20 empty] | 3
|  | Fishing Spot SFX |  | Audio | [18 empty] | 0 | 0 | 0
|  | Fishing VFX |  | VFX
|  |  | Fishing QA | QA
Social & Multiplayer
| Guilds (S) |  |  | Game design | The guild house has a grander layout than yours, with numerous blocked portals to other 'player' homes. Some players are watching gameplay on a TV (video loop). One active portal has a player waiting for you to follow him through.
|  | Guilds system design |  | Game design | [20 empty] | 15
|  | Guild house is an instance |  | Backend Engineering
|  | Guild house concept |  | Concept Art
|  | Guild house model |  | Environment Art
|  | Guild house props |  | Environment Art
|  | Guild house TV + video |  | Environment Art
|  | Guild NPCs |  | Character Art
|  |  | Guild house blockout | Level design | [8 empty] | 6 | 10 | 4 | 8 | 10 | 20 | [6 empty] | 10
|  |  | Sitting NPCs | Animation & Rigging
|  | Guild UI |  | UX/UI | [20 empty] | 3
|  | Guild chat |  | Gameplay Engineering
|  |  | Guild Chat design | Game design |  |  | 3 | 5 |  |  | 3 | 8 | [12 empty] | 1
|  |  | Guild QA | QA
| Co-op - Party |  |  | Backend Engineering | You and your guide work together to solve a basic water puzzle that opens a door. other 'players' make encouraging remarks. One has real life commitments. Opening the door pitches the team into a battle with new opponents (Carapax). There is loot to share then a portal appears with your name above it. The team says goodbye on chat and the party disbands as you step through.
|  | Party formation |  | Backend Engineering |  |  | 3 | 6 |  |  | 3 | 8
|  |  | Party system design | Game design | [20 empty] | 5
|  |  | Party chat | Game design
|  | Party supports real players and bots |  | Backend Engineering
|  | Party UI |  | UX/UI | [20 empty] | 2
|  | Party chat |  | Gameplay Engineering
|  |  | Party QA | QA
| Loot Distribution |  |  | Game design | When the dungeon is completed, the loot is distributed by the predefined rules |  | 2 | 4 | 4 | 6 | 2 | 5
|  | Loot distribution design |  | Game design | [20 empty] | 3
|  | Loot is distributed after the raid |  | Gameplay Engineering
|  |  | Loot distribution QA | QA
Social & Multiplayer
| In-game Mail |  |  | Game design | Literally in-game mail. You can receive messages and items from the game |  | 2 | 4 |  |  | 2 | 5 | [12 empty] | 2
|  | In-game Mail backend |  | Backend Engineering
|  | In-game UI |  | UX/UI | [20 empty] | 10
|  | In-game Mail frontend/UI |  | Gameplay Engineering
|  |  | Mail UI Audio | Audio | [18 empty] | 0.5 | 1 | 1
|  |  | Mail QA | QA
|  | Postbox Concept |  | Concept Art
|  | Postbox VFX |  | VFX
|  | Postbox SFX |  | Audio | [18 empty] | 1 | 2 | 1
|  | Postbox Model |  | Environment Art
Combat System
| Melee Combat Framework |  |  | Game design | Player can engage in melee combat with various enemies throughout the game. Combat has all needed movements and animation and supports sword + shield for the player and heavy weapon and magic for bots (party).
|  | Combat Design |  | Game design |  |  |  |  | 15 | 20 | 15 | 20 | [12 empty] | 15
|  | Attacks Design Doc - per weapon (Combo + off-hand attacks) |  | Game design |  |  |  |  | 3 | 4 | 3 | 5 | [12 empty] | 4
|  | Weapon Attributes (per weapon) |  | Game design |  |  |  |  | 1 | 2 | 3 | 5 | [12 empty] | 1
|  | Combat Animations |  | Animation & Rigging
|  | Combat Montages |  | Animation & Rigging
|  | Combat Tech anim? |  | Animation & Rigging
|  | Combat integration |  | Gameplay Engineering
|  | Weapons models |  | Character Art
|  | Combat VFX |  | VFX
|  |  | Melee Combat QA | QA
| Ranged (Corruption Gun) |  |  | Game design |  |  |  |  | 4 | 8 | [14 empty] | 4
|  | Dual Wielding Ranged |  | Game design |  |  |  |  | 4 | 6 | 2 | 5 | [12 empty] | 4
|  | Ranged Attributes |  | Game design |  |  |  |  | 5 | 8 | 5 | 10 | [12 empty] | 5
|  | Aimed offsets |  | Animation & Rigging
| Combat abilities |  |  | Game design | A set of abilities to use during combat (powerful hits, special moves, etc). Can be gained through the skill system. Equipped in the abilities bar
|  | Abilities Design |  | Game design | Define the set of abilities available for the vertical slice (1-2 available from the beginning plus 1-2 unlocked through progression) |  |  |  | 8 | 10 | [14 empty] | 9
|  |  | 4 Abilities designed (2 weapons) | Game design |  |  |  |  | 16 | 22 | 5 | 10 | [12 empty] | 20
|  |  | Weapon attribute system | Game design |  |  |  |  | 3 | 7 | 3 | 8 | [12 empty] | 5
|  | Combat Abilities UI |  | UX/UI |  |  |  |  | 8 | 15 | [14 empty] | 15
|  | HUD Combat Abilities UI |  | UX/UI |  |  |  |  | 8 | 15 | [14 empty] | 5
|  |  | HUD design | UX/UI |  |  |  |  | 5 | 7 | 5 | 10 | [12 empty] | 7
|  | Combat Abilities integrated with skill path |  | Gameplay Engineering
|  | Combat abilities casting animations |  | Animation & Rigging
|  |  | Combat Abilities QA | QA
|  | Combat Abilities SFX |  | Audio | These are for special moves, not base combat | [17 empty] | 7 | 14 | 7
| Basic Magic system |  |  | Game design | Basic magic systems with 3-4 different spells (attack & heal). The player won't have access to spells but the bots/other players (pre-configured builds) should be able to use it during the coop segment |  |  |  | 20 | 25 | 5 | 15 | [12 empty] | 25
|  | Magic Weapon (e.g. wand) |  | Game design |  |  |  |  | 5 | 10 | 3 | 10 | [12 empty] | 5
|  |  | Weapon | Environment Art
|  | Magic system design (5 spells) |  | Game design |  |  |  |  | 10 | 15 | 5 | 15 | [12 empty] | 10
|  | Magic implementation |  | Gameplay Engineering
|  | Magic UI (1 skill tree mapped out) |  | UX/UI |  |  |  |  | 5 | 9 | [14 empty] | 7
|  | Magic casting animations |  | Animation & Rigging
|  | Magic SFX |  | Audio | [18 empty] | 7 | 10 | 5
|  | Magic VFX |  | VFX | Elemental x4 (Fire, Ice, Lighting, Earth) | Visibility, AOE, distinction
|  |  | Magic QA | QA
Consumables
|  | Check the health potion usage |  | QA | We only use the heal potion for the vertical slice - the functionality, props and VFX should be implemented and working but need check if everyhting is okay
Combat System
| PVP Combat |  |  | Game design | Basic PVP combat support, no special PVP moves or animations. Should only be active in the Arena, no free PVP interactions in the world |  |  |  | 20 | 30
|  | PVP Combat design |  | Game design |  |  |  |  | 10 | 18 | 10 | 20 |  |  |  |  | 5 | 10 | [6 empty] | 12
|  | PVP Combat support |  | Gameplay Engineering
|  | PVP only available in Arena |  | Gameplay Engineering
|  | PVP Arena Design |  | Game design | [8 empty] | 6 | 10 | [10 empty] | 7
|  | PVP Combat Setup |  | Game design | [20 empty] | 6
|  | PVP Arena concept |  | Concept Art
|  | PVP Arena blockout |  | Level design | [8 empty] | 6 | 15 | 3 | 7 | 10 | 15 | [6 empty] | 10
|  | PVP Arena Foliage |  | Environment Art
|  | PVP Arena set dressing |  | Environment Art
|  | PVP Arena props |  | Environment Art
|  | PVP Arena Audio |  | Audio | [18 empty] | 7 | 14 | 5
|  |  | PVP combat QA | QA
Player Economy
| Trading System |  |  | Game design | Basic trading operations between the player and the game (buying equipment/garmets/resources from vendors). Requires shops models/props, vendors models, UI, currency implementation, minimum balance and economy. We need to make sure player has enough money to buy things after completing story quests in the VS |  |  |  | 8 | 16
|  |  | Shop Fake Fascia Design | Game design | [6 empty] | 5 | 10 | [12 empty] | 1
|  |  | Clothing Shop Basic Contents | Game design |  |  | 4 | 6 | 2 | 5 | 5 | 10 | [12 empty] | 3
|  | Shops Concepts |  | Concept Art
|  | Shops Models & Set dressing |  | Environment Art
|  | Shop props |  | Environment Art
|  | Vendors Concepts |  | Concept Art
|  | Vendors Models |  | Character Art
|  | Vendors animation |  | Animation & Rigging
|  | Trading UX/UI |  | UX/UI |  |  |  |  | 15 | 20 | [14 empty] | 15
|  | Currency Integration |  | Gameplay Engineering
|  | Soft Currency (gold) icon |  | Concept Art
|  | Premium currency icon |  | Concept Art
| Auction House economy |  |  | Game design |  |  |  |  | 15 | 20 | 10 | 20 | [12 empty] | 15
|  | P2G Transactions Support |  | Backend Engineering
|  |  | Trading System QA | QA
| In-game economy |  |  | Game design | Basic in-game economy configuration, placeholder balance. Need to define sources and sinks for the vertical slice
|  | Basic Economy configuration |  | Game design | Just the prices for the vertical slice - not a complete system |  | 20 | 25 | 40 | 60 | 10 | 20 | [12 empty] | 5
|  |  | In-game economy QA check | QA
Live Service Support
| In game RMT Store |  |  | Game design | In-game store that supports real-money transactions (spend real money to buy in-game currency). We are not integrating the payment systems at this point so just having the UI for this type of store will be enough
|  |  | Virtual currency balance and items | Game design | [20 empty] | 2
|  | RMT subscription design |  | UX/UI |  |  |  |  | 8 | 12 | no idea | no idea | [12 empty] | 3
|  | RNT partner store |  | UX/UI | [20 empty] | 3
|  | RMT virtual currency page |  | UX/UI | [20 empty] | 3
|  | RMT store integration |  | Backend Engineering
|  | RMT Store SFX |  | Audio | [18 empty] | 7 | 10 | 7
|  |  | RMT Store QA | QA
| Subscription page on the website |  |  | Backend Engineering
Platform
| Bugged Dungeon Integration |  |  | Game design | [6 empty] | 10 | 20
|  | BD Quest design |  | Game design | You find yourself in an alley in the city with NPCs wandering the street beyond. An old shop beckons you to enter. Xyron explains that Downtime is a nexus of many worlds waiting to be rediscovered. You find a portal into the (preloaded game) in the back of the shop. |  | 2 | 5
|  |  | BD Quest narrative design | Game design | See lower in the spreadsheet | [5 empty] | 3 | 8
|  | Partner Shop Blockout |  | Level design | [8 empty] | 4 | 8 | 3 | 7 | 5 | 8 | [6 empty] | 4
|  | BD Quest integration |  | Backend Engineering
|  | Partner themed shop concept |  | Concept Art
|  | Partner themed shop model |  | Environment Art
|  | Partner themed shop props |  | Environment Art
|  | Used Partner Portals |  | Environment Art
|  |  | Assets & Portals Models | Environment Art
|  |  | Portals Placement in the shop | Environment Art
|  | BD Quest themed reward model |  | Character Art
|  | BD quest special macguffin reward |  | Game design | Special item you get as a reward for completing BD quest. Will be used in the final part of the quest to activate the final battle
|  |  | Special item design | Game design | Green Crystal. Or a Bee |  | 1 | 3 |  |  | 2 | 5 | [12 empty] | 1
|  |  | Concept | Concept Art
|  |  | Model | Environment Art
|  |  | Tech art | TechArt | Working mechanics for the picked up item, co-dev w/Devs
|  |  | Behavior implementation | Gameplay Engineering
|  |  | Audio | Audio | [18 empty] | 0.5 | 1 | 1
|  |  | UI | UX/UI | [20 empty] | 5
|  |  | VFX | VFX
|  |  | QA | QA
| Partner Portal |  |  | Game design | The portal that leads to the partner world (activates partner loop sequence) |  | 1 | 2
|  | Partner shop portal placement |  | Game design | [20 empty] | 1
|  | Portals design |  | Game design | [20 empty] | 1
|  | Partner Portal Integration |  | Backend Engineering
|  | Partner Portal VFX |  | VFX
|  | Partner Portal Enviro Art |  | Environment Art
| Partner Loop |  |  | Game design
|  | Full partner loop definition/design |  | Game design | The sequence that covers the entire interaction loop with the partner game, from engaging with the quest to playing the partner game and getting the rewards |  | 4 | 7 |  |  | 3 | 5 | [12 empty] | 5
|  | Create Partner Store |  | Backend Engineering | Type of the in-game store specifically to buy partner games and assets
|  | Integrate partner loop |  | Backend Engineering
|  |  | Buy game subscription time from website and/or from game | Backend Engineering
|  |  | Buy CH virtual currency | Backend Engineering
|  |  | Complete partner quest | Backend Engineering
|  |  | Purchase partner game from in-game store | Backend Engineering
|  |  | Redeem Partner Steam key | Backend Engineering
|  |  | Download Partner game | Backend Engineering
|  |  | Run partner game from same exe as CH | Backend Engineering
|  |  | Unlock partner item in CH by playing partner game | Backend Engineering
|  |  | Claim partner item from CH mailbox | Backend Engineering
|  | Partner functionality QA |  | QA
Quest System
Main Questline: Critical Path
|  | Quest Flow Design & Narrative Overview |  | Game design |  |  | 2 | 4 | [16 empty] | 3
|  | Cave Intro Quest |  | Game design
|  |  | Quest Narrative Doc | Narrative | Narrative/worldbuilding info about the locations, characters and objects involved in the quest |  | 1 | 2 | [10 empty] | 1 | 2 |  |  |  |  | 1
|  |  | Quest Design Doc | Game design | Finalized QD Document including specs for other departments |  | 3 | 5 | [16 empty] | 4
|  |  | Quest Implementation | Game design | Final, "Polished" Version of the Quest |  | 3 | 6 | [16 empty] | 5
|  |  | Quest Playtesting & Revision | Game design | Final Revision & Validation of Quest. Final Doc Revision |  | 2 | 3 | [16 empty] | 2
Green Faction Hill Quest
|  |  | Quest Narrative Doc | Narrative | same as above |  | 1 | 2 | [10 empty] | 0.5 | 2 |  |  |  |  | 2
|  |  | Quest Design Doc | Game design |  |  | 3 | 5 | [16 empty] | 5
|  |  | Quest Implementation | Game design |  |  | 4 | 6 | [16 empty] | 6
|  |  | Quest Playtesting & Revision | Game design |  |  | 2 | 3 | [16 empty] | 3
Corruption Tower & Glide Quest
|  |  | Quest Narrative Doc | Narrative | same as above |  | 1 | 2 | [10 empty] | 1 | 2 |  |  |  |  | 1
|  |  | Quest Design Doc | Game design |  |  | 3 | 5 | [16 empty] | 3
|  |  | Quest Implementation | Game design |  |  | 3 | 6 | [16 empty] | 5
|  |  | Quest Playtesting & Revision | Game design |  |  | 2 | 3 | [16 empty] | 5
Weapon Upgrade Quest
|  |  | Quest Narrative Doc | Narrative | same as above |  | 1 | 2 | [10 empty] | 0.5 | 1 |  |  |  |  | 1
|  |  | Quest Design Doc | Game design |  |  | 3 | 5 | [16 empty] | 3
|  |  | Quest Implementation | Game design |  |  | 3 | 6 | [16 empty] | 3
|  |  | Quest Playtesting & Revision | Game design |  |  | 2 | 3 | [16 empty] | 5
Gear Up & User Space Quest
|  |  | Docs, Implement, Revise | Game design |  |  | 7 | 14 | [16 empty] | 7
Party Up & MP Dungeon Quest
|  |  | Docs, Implement, Revise | Game design |  |  | 7 | 14 | [16 empty] | 7
Arena Fight
|  |  | Docs, Implement, Revise | Game design |  |  | 7 | 14 | [16 empty] | 7
Downtime Race Quest
|  |  | Docs, Implement, Revise | Game design |  |  | 7 | 14 | [16 empty] | 7
Social Hub & Partnership Quest
|  |  | Docs, Implement, Revise | Game design |  |  | 7 | 14 | [16 empty] | 7
Complete PG & Last Boss Quest
|  |  | Docs, Implement, Revise | Game design |  |  | 7 | 14 | [16 empty] | 7

## Sheet1
[7 empty] | Yorgos |  | Nadir |  | Kieron |  | Panos |  | Nikolas |  | Seth |  | Maria |  | Hannah |  | Aggeliki |  | Final
Epic | Feature | Story | Task | Team | Description | Definition of Success | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max | Est Min | Est Max
World Systems |  |  |  | Game design
| Full Motion Video (FMV) |  |  | Game design
|  | Intro supports FMV |  | Backend Engineering | The game supports full motion videos integration and playback | FMV triggers correctly Playback completes or skips No crashes or black screens Transitions to next state
|  |  | Create placeholder FMV playback flow | Backend Engineering | System to trigger fmv from within a quest, or at startup
|  |  | Implement FMV skip behavior | Backend Engineering | Skip should not be accidental (e.g. hold down skip button) - and there should also be a way to pause playback
|  |  | Implement transition after FMV | Backend Engineering | Transition to explicit camera rotation and location
|  |  | FMV Production | Environment Art | To determine possible scopes with GD and AD
|  |  | Integrate final/near-final FMV asset | Backend Engineering | Create an editable system so that anybody can make a change here
|  |  | QA playback across target builds | QA
|  |  | Fix FMV blocker bugs | Backend Engineering
| Static pictures intro + voiceover |  |  | Game design | This is the proposed backup if an FMV cannot be produced within budget.
|  | Intro sequence plays 3 slides with voiceover |  | Backend Engineering | Intro sequence supports static pictures playback with voiceover and subtitles | The pictures are played correctly Voiceover and subtitles are synced to the scene Skip functionality works No major bugs or blockers
|  |  | Create intro sequence controller | Backend Engineering
|  |  | Display static slides full-screen | Backend Engineering
|  |  | Play voiceover synced to sequence | Backend Engineering
|  |  | Display subtitles synced to VO | Backend Engineering
|  |  | Implement skip behavior | Backend Engineering
|  |  | Implement transition to gameplay/menu | Backend Engineering
|  |  | Final art production | Concept Art
|  |  | VO production | Game design
|  |  | Subtitles production | Game design
|  |  | Integrate final art + VO assets | Backend Engineering
|  |  | QA + fix blockers | QA
| In-game cutscenes |  |  | Gameplay Engineering
|  | The game supports cutscenes |  | Gameplay Engineering | In-engine cutscene mechanism is implemented, designers can set the necessary scenes in defined places of the game. Documentation exists for proposed system (talk to GD). Basically this uses Unreal's Sequencer, or a simplified version, so that designers can trigger a basic movie from a dialogue box or quest intro. | Cutscenes are triggered and played correctly Camera behavior is correct Skip mechanism implemented No major bugs or blockers
|  |  | Cutscene trigger system | Gameplay Engineering
|  |  | Camera control during cutscene | Gameplay Engineering
|  |  | Player control lock/unlock | Gameplay Engineering
|  |  | NPC/character sequencing | Gameplay Engineering
|  |  | Dialogue playback (in-cutscene) | Gameplay Engineering
|  |  | Cutscene skip functionality | Gameplay Engineering
|  |  | Transition in/out of cutscene | Gameplay Engineering
|  |  | Basic cutscene sequencing (timeline) | Gameplay Engineering
|  |  | Cutscene stability (QA & fixes) | QA
|  | Cutscene content |  | Game design | Define all required content and direct the cutscenes; make sure all required assets exist | Basic cutscenes directed, MVP quality
Player Build
| In-game Tutorial |  |  | Game design | Finalized in-game tutorial explaining basic mechanics to the player, set in the starting location | The tutorial is clear and straightforward UX/UI pass Players can't die during the tutorial sequence No major visual or functional bugs
|  | Tutorial Cave Layout Fixes |  | Level design | Shorter and easier to complete cave blockout | Reduced completion time No spots where the player can die
|  | Tutorial cave set dressing fixes |  | Environment Art | Adapt the set dressing of the cave to the updated blockout | No major art changes or new content produced, no change of the art style
|  | Tutorial Cave lighting |  | Environment Art
|  | Tutorial cave Ambience & SFX |  | Audio
|  | Tutorial Configuration/set up/texts |  | Game design | Place the tutorial hints so player understands the basic game mechanics (movement, navigation, interaction with objects) | Hints are clear and understandable Hints go over all main in-game mechanics the player needs to start the game
|  | Tutorial UI |  | UX/UI | Make sure the UI in the tutorial cave is well visible and aligned with the tutorial cave art style
|  | Tutorial VFX |  | VFX
|  | Controls UI |  | UX/UI | Clear controls UI and convenient keyboard layout
|  |  | Tutorial cave contents | Game design
|  |  | Tutorial QA check | QA
World Systems
| Basic movement system |  |  | Game design
|  | Locomotion Integration |  | Gameplay Engineering | Player can access all main movement mechanics | No major bugs with functionality or visuals All needed animations implemented
|  |  | Walk | Gameplay Engineering
|  |  | Run | Gameplay Engineering
|  |  | Sprint | Gameplay Engineering
|  |  | Jump | Gameplay Engineering
|  |  | Double Jump | Gameplay Engineering
|  |  | Locomotion QA check | QA
Quest System
| Various Quest Types Support |  |  | Gameplay Engineering
|  | Lockpicking |  | Game design | The minigame to open doors, chests and safes. Player first destroys a set of tiles to reveal the mechanism. Then they interact with the parts of the mechanism to move the marble to the lock and open it | The basic version of the game implemented and functional to open the starting chest The puzzle should be solved within 30 sec
|  |  | Lockpicking Concept | Concept Art
|  |  | Lockpicking UI | UX/UI
|  |  | Lockpicking Integration | Gameplay Engineering
|  |  | Lockpicking Techart | TechArt | Co-dev with VFX for breakble tiles, sphere and pipes path | Visually complementary and gameplay rewarding
|  |  | Lockpicking QA check | QA
|  | Design interface for quest types |  | Game design | not critical for the vertical slice.
|  | Other quest types support? |  | Gameplay Engineering | The game supports different quest types: kill X enemies, collect X objects etc | Designers can configure desired quest types in the engine The behavior is in line with documentation
World Systems
| World Resources |  |  | Game design
|  | Starting Chest |  | Game design | Player can find a chest in the tutorial cave that has the sword inside | The chest should be located on the player's way. The player should be incentivised to interact with the chest. Progress should rely on opening the chest.
|  |  | Chest concept | Concept Art
|  |  | Chest model | Environment Art
|  |  | Chest animation | Animation & Rigging
|  |  | Chest VFX | VFX | Open "sparkle" and rewarding feedback, Ballista minigame
|  |  | QA check | QA
|  | Shield |  | Game design
|  |  | Shield animations | Animation & Rigging
|  |  | Shield Asset | Environment Art
|  | Starting Sword |  | Game design | Starting player weapon. Should be good enough to fight starting enemies and not get easily killed
|  |  | Sword concept | Concept Art
|  |  | Sword model | Character Art
|  |  | Sword animations | Animation & Rigging
|  |  | Sword VFX | VFX | Swing sword trail (visual: color, opacity) | Readable and underline weapon movement and area of damage plus distinction with standard/enchanted/poisoned
|  | Equipment Stats integrated with character stats |  | Game design
|  |  | Equipment Stats integrated with character stats | Gameplay Engineering
|  |  | QA check | QA
Quest System
| Quest Integration |  |  | Game design
|  | Tutorial Quest Chain Configuration & Setup |  | Game design | Tutorial quest sequence fully designed with player journey and interactions described | The quest should be easily found and tracked throughout the way; should have clear start and end with rewards All needed NPCs, enemies, rewards should be placed and configured
|  |  | QA check | QA
|  | Green Faction NPC Concepts |  | Concept Art
|  | Green Faction NPC Models |  | Character Art
|  | Green Faction NPC animations |  | Animation & Rigging
|  | Green Faction NPC dialogue setup |  | Game design
|  | Green Faction NPCs placement |  | Game design
|  |  | QA check | QA
| Quest Tools |  |  | Backend Engineering
|  | Quest Editor |  | Game design
|  | Dialogue System Design |  | Game design
|  | Dialogue System |  | Backend Engineering | The game supports dialogue system with options that lead to different dialogue branches
|  | Dialogue UI |  | UX/UI
|  | Quest Log |  | Backend Engineering | The quests are being tracked and the log/next quest should be accessible in the game UI
|  |  | Quest Log QA | QA
|  | Xyron narrative |  | Game design
|  | Drifter's Cross Narrative |  | Game design
World Systems
| Navigation |  |  | Game design
|  | World Map |  | Game design | World map integrated with accessible areas visible and major points of interest placed + quality of life features to be designed | Player can access and navigate the world map Map has correct assets and quest tracking functionality
|  |  | Map markers sfx | Audio
|  |  | World Map background asset | Concept Art
|  |  | World Map asset integration | Gameplay Engineering
|  |  | World Map UI | UX/UI
|  |  | Quest markers support | Gameplay Engineering
|  |  | Map QA check | QA
|  | Fog-of-war |  | Gameplay Engineering | Parts of the map are hidden until the player reaches them or gets information about them | The hide/reveal functionality works without major bugs
|  |  | Fog of war QA check | QA
|  | Minimap |  | Gameplay Engineering
|  |  | Minimap Levels | Game design
|  |  | Minimap UI | UX/UI | Minimap is constantly present on the screen to help players navigate; it supports quest tracking
|  |  | Minimap assets | Concept Art
|  |  | Minimap quest navigation support | Gameplay Engineering
|  |  | Minimap QA check | QA
|  | Compass |  | Gameplay Engineering | Basic navigation tool that shown direction to the selected marker/quest (or north) at the top of the screen
|  |  | Compass UI | UX/UI
|  |  | Compass Integration | Gameplay Engineering
|  |  | Compass QA check | QA
| Corruption |  |  | Game design
|  | Corrupted Vines |  | Game design | The texture on the vines that implies they are corrupted. No functionality, just visual
|  |  | Corrupted texture | TechArt | Material suitable to communicate cleaning mechanics and hazard | Match Art Direction, tested and working for different size and elements
|  |  | Vines Foliage | Environment Art
|  |  | Corrupted VFX | VFX | Upgrade features form TA material
|  |  | Corrupted vines behavior & visual QA | QA
|  | Foam Corruption |  | Game design | Another clean up system that could be investigated is a physical model that is removed in parts. This would need a destruction system like Red Faction, or a voxel system to represent a poisonous foam that covers the environment and can be cleaned up by multiple players simultaneously. This is the alternative to Environmental Corruption, which may prove easier to implement in multiplayer.
|  |  | Foam Corruption Techart | TechArt | Volumetric Corruption dependancy with additional specific elements | Readable as same mechanics, adaptable to assets and areas, performant
|  |  | Foam Corruption integration | Gameplay Engineering
|  |  | Foam Corruption VFX | VFX | Upgrade features form TA material
|  |  | Foam Corruption cleansing animations | Animation & Rigging
|  |  | Foam Corruption cleansing weapon | Character Art
|  |  | Foam Corruption SFX, VFX design | Game design
|  |  | Foam Corruption SFX | Audio
|  |  | Foam Corruption QA | QA
|  | Timed Corruption |  | Game design | A simple mechanic to implement using animation curves. An object such as a door or bridge has been broken into multiple parts, and the player has to use magic to rebuild it, visually reversing time. There will be puzzle and multiplayer opportunities. For instance one player may need to restore a bridge while another player crosses it to reach a switch. There can also be a multi-stage set of things that have collapsed or prematurely rusted. The player has to work out which ones to reverse, in which order, to recreate the original setting (all pieces lock into place once this has been achieved, for a short time).
|  |  | Timed Corruption Design | Game design
|  |  | Timed Corruption TechArt | TechArt
|  |  | Timed Corruption Integration | Gameplay Engineering
|  |  | Timed Corruption Server & Multiplayer | Backend Engineering
|  |  | Timed Corruption 3D Assets | Environment Art
|  |  | Timed Corruption VFX | VFX | Upgrade features form TA material
|  |  | Timed Corruption SFX | Audio
|  |  | Timed Corruption QA | QA
| Advanced Traversal |  |  | Game design | Only gliding for now. Gliding is an airborne locomotion state, not a flight simulation. While gliding, the player retains directional movement control similar to ground traversal, but with reduced acceleration, limited top speed, and continuous stamina drain.
|  | Glider Stamina UI |  | UX/UI
|  | Gliding Concepts |  | Concept Art
|  | Gliding Integration |  | Gameplay Engineering
|  | Gliding Animations |  | Animation & Rigging
|  | Gliding SFX |  | Audio
|  | Gliding VFX |  | VFX
|  | Gliding Device |  | Character Art
|  |  | Gliding QA | QA
|  | Portals spawning & Xyron moving through portals |  | Gameplay Engineering
|  |  | Narrative for Xyron quests | Game design
|  |  | Spawning portals SFX | Audio
|  |  | 5 or 6 mini quests | Game design
|  |  | Xyron voiceover choices | Game design
|  |  | Xyron voiceover | Audio
|  |  | Xyron/portals spawning QA | QA
Combat System
| Melee Combat Framework |  |  | Game design | Player can engage in melee combat with various enemies throughout the game. Combat has all needed movements and animation and supports sword + shield for the player and heavy weapon and magic for bots (party).
|  | Combat Design |  | Game design
|  | Combat Animations |  | Animation & Rigging
|  | Combat Montages |  | Animation & Rigging
|  | Combat Tech anim? |  | Animation & Rigging
|  | Combat integration |  | Gameplay Engineering
|  | Weapons models |  | Character Art
|  | Combat VFX |  | VFX
|  |  | Melee Combat QA | QA
| Ranged (Corruption Gun) |  |  | Game design
|  | Dual Wielding Ranged |  | Game design
|  | Ranged Attributes |  | Game design
|  | Aimed offsets |  | Animation & Rigging
| Combat abilities |  |  | Game design | A set of abilities to use during combat (powerful hits, special moves, etc). Can be gained through the skill system. Equipped in the abilities bar
|  | Abilities Design |  | Game design | Define the set of abilities available for the vertical slice (1-2 available from the beginning plus 1-2 unlocked through progression)
|  |  | 4 Abilities designed | Game design
|  |  | Weapon attribute system | Game design
|  | Combat Abilities UI |  | UX/UI
|  | HUD Combat Abilities UI |  | UX/UI
|  |  | HUD design | Game design
|  | Combat Abilities integrated with skill path |  | Gameplay Engineering
|  | Combat abilities casting animations |  | Animation & Rigging
|  |  | Combat Abilities QA | QA
|  | Combat SFX |  | Audio
| Basic Magic system |  |  | Game design | Basic magic systems with 3-4 different spells (attack & heal). The player won't have access to spells but the bots/other players (pre-configured builds) should be able to use it during the coop segment
|  | Magic Weapon (e.g. wand) |  | Game design
|  |  | Weapon | Environment Art
|  | Magic system design (5 spells) |  | Game design
|  | Magic implementation |  | Gameplay Engineering
|  | Magic UI (1 skill tree mapped out) |  | UX/UI
|  | Magic casting animations |  | Animation & Rigging
|  | Magic SFX |  | Audio
|  | Magic VFX |  | VFX | Elemental x4 (Fire, Ice, Lighting, Earth) | Visibility, AOE, distinction
|  |  | Magic QA | QA
Consumables
|  | Check the health potion usage |  | QA | We only use the heal potion for the vertical slice - the functionality, props and VFX should be implemented and working but need check if everyhting is okay
Quest System
| Quest Rewards System |  |  | Game design
|  |  | Quest UI Audio | Audio
|  | Quest Reward List |  | Game design
|  | Rewards Choice |  | Gameplay Engineering | Quest rewards should include options players can choose from
|  |  | Quest Rewards QA | QA
World Systems
| Forge |  |  | Game design | Weapon crafting mechanic that allows to combine different parts of the weapon to get a new one
|  | Component System Design |  | Game design
|  | Crafted Weapon Parts in-game Audio |  | Audio
|  | Forge Crafting Audio |  | Audio
|  | Forge Documentation |  | Game design
|  | Forge Concepts |  | Concept Art
|  | Forge Integration |  | Gameplay Engineering
|  | Forge UI |  | UX/UI
|  | Forge VFX |  | VFX
|  | DA combination setup |  | TechArt | Weapon color customization parallel to garments plus pieces and parts assembly
|  | Crafting Desk |  | Environment Art
|  | Forge Props |  | Character Art
|  |  | Forge QA | QA
Player Economy
| Trading System |  |  | Game design | Basic trading operations between the player and the game (buying equipment/garmets/resources from vendors). Requires shops models/props, vendors models, UI, currency implementation, minimum balance and economy. We need to make sure player has enough money to buy things after completing story quests in the VS
|  |  | Shop Fake Fascia Design | Game design
|  |  | Clothing Shop Basic Contents | Game design
|  | Shops Concepts |  | Concept Art
|  | Shops Models & Set dressing |  | Environment Art
|  | Shop props |  | Environment Art
|  | Vendors Concepts |  | Concept Art
|  | Vendors Models |  | Character Art
|  | Vendors animation |  | Animation & Rigging
|  | Trading UX/UI |  | UX/UI
|  | Currency Integration |  | Gameplay Engineering
|  | Soft Currency (gold) icon |  | Concept Art
|  | Premium currency icon |  | Concept Art
| Auction House economy |  |  | Game design
|  | P2G Transactions Support |  | Backend Engineering
|  |  | Trading System QA | QA
| In-game economy |  |  | Game design | Basic in-game economy configuration, placeholder balance. Need to define sources and syncs for the vertical slice
|  | Basic Economy configuration |  | Game design
|  |  | In-game economy QA check | QA
Player Build
| Garment System |  |  | Game design | Classic garment system with equipment slots for different pieces of clothing/gear. Needs finalized documentation, sufficient number of equipment parts and UI. Also should be integrated with character stats if equipment affects them
|  | Garment System GDD/TDD |  | Game design
|  |  | Vertical Slice garments | Game design
|  | Garment System Integration |  | Gameplay Engineering
|  | Garment System UI |  | UX/UI
|  | Equiment Concepts |  | Concept Art
|  | Equipment Models |  | Character Art
|  |  | Garment Type SFX | Audio | (on buy,sell, wear, unequip)
|  | Equipment Stats integrated with character stats |  | Gameplay Engineering
|  |  | Garment System QA | QA
|  |  | Equipment QA | QA
User Space
| User Space Server & Instance |  |  | Backend Engineering | User Space is a separate instance and a player's home. Players place the door to access it. For the vertical slice, the door is placed in a POI in Portal Peak and the player is loaded into a separate location with a half-build house.
|  |  | FTUE Design | Game design
|  |  | FTUE UI | UX/UI
|  |  | User Space Editor audio | Audio
|  |  | Mutual Activity Design | Game design
|  | User Space is a separate instance |  | Backend Engineering
|  | User Space editor & UI |  | Gameplay Engineering
|  | User Space Ambience |  | Audio
|  |  | Item SFX | Audio
|  |  | Island ambient audio | Audio
|  | User Space editor VFX |  | VFX
|  |  | User Space functionality QA | QA
| Anywhere door placement |  |  | Gameplay Engineering
|  | User space door can be placed at predefined spots |  | Gameplay Engineering | We choose predefined spots in Portal peak (flat surface) where player can place their door. The door stays there and serves as a permanent user Space entrance
|  |  | Anywhere Door QA | QA
| User Space Decoration |  |  | Environment Art | The model of the house and sufficient furniture pieces that can be placed in the User Space
|  | User Space House concept |  | Concept Art
|  | User Space House model |  | Environment Art
|  | User Space furniture props |  | Environment Art
| User Space Island (S) |  |  | Game design | A separate location that serves as a player home. Inclides a half-build house, pets, a pond/river and fishing spots
|  | User Space location concepts |  | Concept Art
|  | User Space location blockout |  | Level design
|  | User Space location set dressing |  | Environment Art
|  | User Space location props |  | Environment Art
|  | User Space location foliage |  | Environment Art
|  |  | User Space visuals QA | QA
| Pets (mechanical parrot reuse) |  |  | Game design | Demo of the pets functionality. Pure cosmetic for the time being. Should be already supported. Decided to proceed with the parrot that was modelled for the pirates enemies
|  | Pet concepts |  | Concept Art
|  | Pet model |  | Character Art
|  | Pet animations |  | Animation & Rigging
|  | Pet VFX |  | VFX
|  | Pet behavior |  | Gameplay Engineering
|  | Pet integration |  | Gameplay Engineering
|  |  | Pet QA | QA
| Fishing |  |  | Game design | Fishing minigame/profession. Quite self-explanatory. Basically ready but needs final assets, animations and QA
|  | Fishing Integration |  | Game design
|  | Fishing Rod model |  | Environment Art
|  | Fish model |  | Environment Art
|  | Fishing spot sign model |  | Environment Art
|  | Fishing UI |  | UX/UI
|  | Fishing Spot VFX |  | Audio
|  |  | Fishing QA | QA
Social & Multiplayer
| Guilds (S) |  |  | Game design | The guild house has a grander layout than yours, with numerous blocked portals to other 'player' homes. Some players are watching gameplay on a TV (video loop). One active portal has a player waiting for you to follow him through.
|  | Guild house is an instance |  | Backend Engineering
|  | Guild house concept |  | Concept Art
|  | Guild house model |  | Environment Art
|  | Guild house props |  | Environment Art
|  | Guild house TV + video |  | Environment Art
|  | Guild NPCs |  | Character Art
|  |  | Guild house blockout | Game design
|  |  | Sitting NPCs | Animation & Rigging
|  | Guild UI |  | UX/UI
|  | Guild chat |  | Gameplay Engineering
|  |  | Guild Chat design | Game design
|  |  | Guild QA | QA
| Co-op - Party |  |  | Backend Engineering | You and your guide work together to solve a basic water puzzle that opens a door. other 'players' make encouraging remarks. One has real life commitments. Opening the door pitches the team into a battle with new opponents (Carapax). There is loot to share then a portal appears with your name above it. The team says goodbye on chat and the party disbands as you step through.
|  | Party formation |  | Backend Engineering
|  |  | Party chat | Game design
|  | Party supports real players and bots |  | Backend Engineering
|  | Party UI |  | UX/UI
|  | Party chat |  | Gameplay Engineering
|  |  | Party QA | QA
| Loot Distribution |  |  | Game design | When the dungeon is completed, the loot is distributed by the predefined rules
|  | Loot is distributed after the raid |  | Gameplay Engineering
|  |  | Loot distribution QA | QA
World Systems
| Instancing |  |  | Backend Engineering | Allow players or parties to enter private versions of locations with isolated gameplay state.
|  | GDD Documentation |  | Game design
|  | Instancing Documentation |  | Backend Engineering
|  | User Space Instancing support |  | Backend Engineering
|  | Guild House instancing support |  | Backend Engineering
|  | Dungeon Instancing |  | Backend Engineering
|  | Zones Instancing |  | Backend Engineering
|  |  | Instancing QA | QA
| Dungeons mechanics |  |  | Game design | Design different mechanics that can be used in dungeons. Only design stage for the vertical slice
|  | Dungeons documentation |  | Game design
| Puzzles |  |  | Game design | Implement a puzzle that requires multiple players to interact with environment elements to progress.
|  | Multiplayer enviromental puzzle design |  | Game design | Time Corruption puzzle (bridge + switch - 2 players)
|  | Multiplayer enviromental puzzle layout |  | Level design
|  | Multiplayer enviromental puzzle integration |  | Gameplay Engineering
|  |  | Puzzles QA | QA
Player Build
| Player Progression |  |  | Game design | Players can gain XP for in-game actions (combat, quests, etc) and level up. Level up affects chararcter stats and skills. Character stats are defined and configured and connected with other in-game systems (combat, skills, etc)
|  | Player level up documentation |  | Game design
|  | Player level up configuration |  | Game design
|  | player level up integration |  | Gameplay Engineering
|  | Player level up UI |  | UX/UI
|  | Character stats documentation |  | Game design
|  | Character stats implementation |  | Gameplay Engineering
|  | Character stats configuration in connection with other systems |  | Game design
|  | Character stats UI |  | UX/UI
|  |  | Level up & Stats QA | QA
| Skill System (1 skill tree active) |  |  | Game design | Basic skill system supported with one skill tree active and interactive. 2 more skill trees shown but not active. Skill progression is integrated with other game systems (stats etc)
|  | Skill Tree UI Audio |  | Audio
|  | Skills in-game audio |  | Audio
|  | Skill System Documentation |  | Game design
|  | Skill System Implementation |  | Gameplay Engineering
|  | Skill System Configuration |  | Game design
|  | Skill System UI |  | UX/UI
|  |  | Skill system QA | QA
Combat System
| PVP Combat |  |  | Game design | Basic PVP combat support, no special PVP moves or animations. Should only be active in the Arena, no free PVP interactions in the world
|  | PVP Combat design |  | Game design
|  | PVP Combat support |  | Gameplay Engineering
|  | PVP only available in Arena |  | Gameplay Engineering
|  | PVP Arena Design |  | Game design
|  | PVP Arena concept |  | Concept Art
|  | PVP Arena blockout |  | Level design
|  | PVP Arena Foliage |  | Environment Art
|  | PVP Arena set dressing |  | Environment Art
|  | PVP Arena props |  | Environment Art
|  | PVP Arena Audio |  | Audio
|  |  | PVP combat QA | QA
World Systems
| Downtime Final set dressing (L) |  |  | Environment Art | Finalized Downtime (MVP quality). No blockouts. Focus on the social area (tavern) + several shop fronts that are not accessible inside
|  | Multiplayer interactions (toasts) |  | Game design
|  | Downtime Shops closed area |  | Game design
|  | Downtime Social Hub Area Blockout |  | Game design
|  | Downtime Tavern Blockout |  | Game design
|  | Downtime Tavern Concept |  | Concept Art
|  | Downtime Tavern Model |  | Environment Art
|  | Downtime Tavern Props |  | Environment Art
|  | Downtime NPC placement |  | Game design
|  | Downtime shops storefronts models |  | Environment Art
|  | Downtime Auction House storefront model |  | Environment Art
|  | Downtime Bank storefront model |  | Environment Art
|  | Downtime Barbersmith storefront model |  | Environment Art
|  |  | Downtime QA | QA
| Speedup Archway |  |  | Game design | The archway through Downtime going through the entire town. The goal is to show the player the town without making them actually walking around it. The main function is the competition between player for who completes it faster. Should have persistent leaderboards.
|  | Safety System |  | Game design
|  | Persistent leaderboards |  | Backend Engineering
|  | Archway Placement |  | Game design
|  | Archway Models |  | Environment Art
|  | Archway VFX |  | VFX
|  |  | Win Fanfare VFX | VFX
|  | Archway SFX |  | Audio
|  |  | Archway QA | QA
Social & Multiplayer
| In-game Mail |  |  | Game design | Literally in-game mail. You can receive messages and items from the game
|  | In-game Mail backend |  | Backend Engineering
|  | In-game Mail frontend/UI |  | Gameplay Engineering
|  |  | Mail UI Audio | Audio
|  |  | Mail QA | QA
|  | Postbox Concept |  | Concept Art
|  | Postbox VFX |  | VFX
|  | Postbox SFX |  | Audio
|  | Postbox Model |  | Environment Art
Platform
| Bugged Dungeon Integration |  |  | Game design
|  | BD Quest design |  | Game design | You find yourself in an alley in the city with NPCs wandering the street beyond. An old shop beckons you to enter. Xyron explains that Downtime is a nexus of many worlds waiting to be rediscovered. You find a portal into the (preloaded game) in the back of the shop.
|  |  | BD Quest narrative design | Game design
|  | Partner Shop Blockout |  | Game design
|  | BD Quest integration |  | Backend Engineering
|  | Partner themed shop concept |  | Concept Art
|  | Partner themed shop model |  | Environment Art
|  | Partner themed shop props |  | Environment Art
|  | Used Partner Portals |  | Environment Art
|  |  | Assets & Portals Models | Environment Art
|  |  | Portals Placement in the shop | Environment Art
|  | BD Quest themed reward model |  | Character Art
|  | BD quest special macguffin reward |  | Game design | Special item you get as a reward for completing BD quest. Will be used in the final part of the quest to activate the final battle
|  |  | Special item design | Game design
|  |  | Concept | Concept Art
|  |  | Model | Environment Art
|  |  | Tech art | TechArt | Working mechanics for the picked up item, co-dev w/Devs
|  |  | Behavior implementation | Gameplay Engineering
|  |  | Audio | Audio
|  |  | UI | UX/UI
|  |  | VFX | VFX
|  |  | QA | QA
| Partner Portal |  |  | Game design | The portal that leads to the partner world (activates partner loop sequence)
|  | Partner Portal Integration |  | Backend Engineering
|  | Partner Portal VFX |  | VFX
|  | Partner Portal Enviro Art |  | Environment Art
| Partner Loop |  |  | Game design
|  | Full partner loop definition/design |  | Game design | The sequence that covers the entire interaction loop with the partner game, from engaging with the quest to playing the partner game and getting the rewards
|  | Create Partner Store |  | Backend Engineering | Type of the in-game store specifically to buy partner games and assets
|  | Integrate partner loop |  | Backend Engineering
|  |  | Buy game subscription time from website and/or from game | Backend Engineering
|  |  | Buy CH virtual currency | Backend Engineering
|  |  | Complete partner quest | Backend Engineering
|  |  | Purchase partner game from in-game store | Backend Engineering
|  |  | Redeem Partner Steam key | Backend Engineering
|  |  | Download Partner game | Backend Engineering
|  |  | Run partner game from same exe as CH | Backend Engineering
|  |  | Unlock partner item in CH by playing partner game | Backend Engineering
|  |  | Claim partner item from CH mailbox | Backend Engineering
|  | Partner functionality QA |  | QA
Live Service Support
| In game RMT Store |  |  | Game design | In-game store that supports real-money transactions (spend real money to buy in-game currency). We are not integrating the payment systems at this point so just having the UI for this type of store will be enough
|  | RMT store design |  | Game design
|  | RMT store integration |  | Backend Engineering
|  | RMT Store UI |  | UX/UI
|  | Basic RMT balance config |  | Game design
|  | RMT Store SFX |  | Audio
|  |  | RMT Store QA | QA
| Subscription page on the website |  |  | Backend Engineering
| Virtual currency balance and items |  |  | Game design
World Systems
| Portal Peak (Medium) |  |  | Game design | Just making sure that there are no blockouts/unfinished parts in PP player can see - probably mainly for enviro artists
|  | PP Design |  | Game design
|  | PP Blockout |  | Level design
|  | PP Concept |  | Concept Art
|  | PP Foliage |  | Environment Art
|  | PP Props Build |  | Environment Art
|  | PP layout |  | Environment Art
|  | PP Audio |  | Audio
|  |  | Portal Peak QA | QA
| POI: The Two Hills (S) |  |  | Game design | Two towers sequence with traversal and stuff. Player returns here after Downtime for the final scene
|  | The Two Hills Design |  | Game design
|  | The Two Hills Blockout |  | Level design
|  | The Two Hills Concept |  | Concept Art
|  | The Two Hills Foliage |  | Environment Art
|  | The Two Hills Props Build |  | Environment Art
|  | The Two Hills layout |  | Environment Art
|  | The Two Hills Audio |  | Audio
|  |  | The Two Hills QA | QA
| POI: Portal Dimension (XS) |  |  | Game design | Intermediate layer before loading into the partner game
|  | Portal Dimension Design |  | Game design
|  | Portal Dimension Blockout |  | Level design
|  | Portal Dimension Concept |  | Concept Art
|  | Portal Dimension Foliage |  | Environment Art
|  | Portal Dimension Props Build |  | Environment Art
|  | Portal Dimension layout |  | Environment Art
|  | Portal Dimension Audio |  | Audio
|  |  | Portal Dimension QA | QA
| POI: Waterfall Beauty Spot (S) |  |  | Game design | Shattered Pools can be used? user Space door placement here
|  | Waterfall Beauty Spot Concept |  | Concept Art
|  | Waterfall Beauty Spot Design |  | Game design
|  | Waterfall Beauty Spot Blockout |  | Level design
|  | Waterfall Beauty Spot Foliage |  | Environment Art
|  | Waterfall Beauty Spot Props Build |  | Environment Art
|  | Waterfall Beauty Spot layout |  | Environment Art
|  | Waterfall Beauty Spot Audio |  | Audio
|  |  | Waterfall Spot QA | QA
| Wolves |  |  | Game design
|  | Wolf montages |  | Animation & Rigging
|  | Design |  | Game design
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt | Geo topology, UVs space optim., textures compliant to D/NRM/ORME/Mask rules, LOD0/1/2 decimation 100%/50%/25%
|  | Combat Behavior |  | Gameplay Engineering
|  | VFX |  | VFX
|  | Wolfy noises |  | Audio
|  |  | Wolves QA | QA
| Goblins |  |  | Game design
Goblin montages
|  | Goblin variant |  | Game design
|  | Design |  | Game design
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt
|  | Combat Behavior |  | Gameplay Engineering
|  | VFX |  | VFX
|  | SFX |  | Audio
|  |  | Goblins QA | QA
| Skeletons |  |  | Game design
Skeleton montages
|  | Design |  | Game design
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt
|  | Combat Behavior |  | Gameplay Engineering
|  | VFX |  | VFX
|  | SFX |  | Audio
|  |  | Skeletons QA | QA
| Slimes |  |  | Game design
|  | Design |  | Game design
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt
|  | Combat Behavior |  | Gameplay Engineering
|  | VFX |  | VFX
|  | SFX |  | Audio
|  |  | Slimes QA | QA
| Corrupted Guardian |  |  | Game design | Corrupted Enemies are not required for the Vertical Slice - except for one reanimated robot, who technically falls under this category. He wakes up, looks menacing, then is destroyed by the crystal found in the partner game.
|  | Narrative |  | Game design
|  | Design |  | Game design | Includes the quest structure
|  |  | Quest structure | Game design
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt
|  | VFX |  | VFX
|  | SFX |  | Audio
|  |  | Corrupted Enemies QA | QA
| Carapax (Hero, but one type) |  |  | Game design
|  | Design |  | Game design
|  | Concept |  | Concept Art
|  | Model |  | Character Art
|  | Rigging |  | Animation & Rigging
|  | Animation |  | Animation & Rigging
|  | Implementation | Asset Validation | TechArt
|  | Combat Behavior |  | Gameplay Engineering
|  | VFX |  | VFX
|  | SFX |  | Audio
|  |  | Carapax QA | QA
World Systems
| World/buiding scale design |  |  | Game design | World scale and buildings scale are defined and accepeted throughout the game | Scales definition are locked in documentation Parts of the game that are out of scale are fixed
| Camera behavior |  |  | Game design | Camera behavior designed for different game situations and actions
|  | Camera behavior implementation/fixes |  | Gameplay Engineering | Camera behavior is implemented according to the design | Camera acts according to the design without major/blocking bugs
|  | Combat Camera |  | Game design
|  |  | Camera QA | QA