## Roadmap Planning Schedule
Step | Target Date(s) | Activity | Detail / Notes | Owner(s) | Status | Dependencies / Risks
WEEK OF 17 MARCH (This Week)
1 | Thu 19 or Fri 20 Mar | Post AMA description and call for questions | Describe the AMA format and invite the team to submit questions. Gives the weekend to think before anything else moves. | Glen
WEEK OF 23 MARCH
2 | Mon 23 or Tue 24 Mar | Glen and Robin session: knock out the details | Get in a room together and work through the detail of what the game is. | Glen, Robin
3 | Wed 25 or Thu 26 Mar | Review with Vardis and Aris: game alignment | Review what the game is and confirm alignment with Vardis and Aris. | Glen, Robin, Vardis, Aris |  | Depends on Step 2 being complete
4 | Fri 27 Mar | Review with HoDs: alignment check | Review with HoDs and confirm everyone is aligned before the AMA. | Glen, HoDs |  | Depends on Step 3 being complete
WEEK OF 30 MARCH
5 | Mon 30 Mar | Hold the AMA | Better held on a Monday than a Friday. Present the game direction and take questions. | Glen, Robin |  | Depends on Steps 2, 3, 4 being complete
6 | Mon 30 Mar to Wed 1 Apr | Open follow-up Slack channel | Open a dedicated Slack channel at time of AMA for follow-up questions. List the channel for 3 days only, then close. | Glen
7 | Tue 31 Mar or Wed 1 Apr | Announce HoD travel to London for roadmap planning | Important to notify the team this is happening. Do this while AMA energy is fresh and the team can see forward momentum. | Glen
8 | Mon 30 Mar onward (ongoing prep) | Lay out all features, systems, platform | All features, systems, and platform need to be laid out to the best of your ability. This is prep work ahead of London. HoDs should be contributing remotely before they travel. | Glen, Robin, HoDs |  | Ongoing through to London trip
LOGISTICS WINDOW: 30 MAR to 10 APR
| 30 Mar to 10 Apr | Confirm travel logistics with Vardis and Aris | They have already agreed to pay for the trip. Communicate clearly on costs (flights, accommodation, duration). This will not be cheap and will interrupt studio work, so expectations need to be set: we come back with a roadmap we can believe in. | Glen, Vardis, Aris |  | RISK: Two weeks is tight for international travel booking. Flag costs this week if possible.
WEEK OF 14 APRIL (Target for London, adjust if travel requires)
9 | Mon 14 to Wed 16 (or Thu 17) Apr | HoDs come to London: roadmap planning sessions | Nail down the path forward. Prep from Step 8 means you are not starting from scratch in the room. Come back with a roadmap the team can believe in. | Glen, Robin, HoDs, Vardis, Aris |  | Depends on Step 8 prep being substantially complete. Depends on travel logistics being confirmed.
WEEK OF 21 APRIL (First full week back in office)
10 | Tue 21 to Thu 23 Apr | Cross-department meetings with Leads (2-3 days) | Cross-dept meetings, NOT dept meetings. Hannah needs to be included. 10a. Describe features in as much detail as possible. 10b. Get Leads estimates (high / medium / low). This becomes the skeleton for Jira structure. 10c. Define feature leads and cross-team groups. Some people will be on multiple features given headcount; work through that in the room. | Glen, HoDs, Leads, Hannah |  | Depends on Step 9 being complete
WEEK OF 28 APRIL
11 | Mon 28 to Wed 30 Apr | Clean up roadmap and post to public studio site | Post the roadmap for the whole studio to see. | Glen, Robin |  | Depends on Step 10 being complete
12 | Wed 30 Apr to Fri 2 May | Leads meet with teams to answer roadmap questions | Leads present the roadmap to their teams and answer questions. Recommendation: HoDs attend the first time. Sets the tone that leadership is behind it. Up to the HoDs. | Leads, HoDs (recommended) |  | Depends on Step 11 being complete
MAY ONWARD
13 | Early May (ongoing) | Begin feature backlogs and quarterly sprint planning | Lay out feature backlogs for 3-month runs. Sprint planning once every 3 months. Update teams at each cycle. This is the ongoing operating cadence. | Glen, HoDs, Leads