## CONTEXT
Beta LiveOps Overview
The Beta runs from March 9 to March 22.
We will start moderate scale events on the 9th , since we will count KPIs already from that day, even if we might have less players than on the 13th of March and following days.
The massive push to drive daily active users kicks off on March 13th.
The main goal of this setup is to maximize Day 1 and Day 7 retention by giving players incredibly strong reasons to log in, play a match, and come back the next day. Additionally to increase chances of players reaching Day 7, we will have incentives for every day login.
Other goals include: Converting players to more competitive modes: ranked, Tournaments and newly added Knockout Mode; since retention seems to be highest for competitive players.
Below are more details goals taken into consideration and put into related segments with more in-depth explanation:
(events below might be outdated - this is purely for context) check other Tabs for up to date events
I. RETENTION (D1, D7)
This is main goal for the Beta playtest. We want players to come back tomorrow, the day after, and all the way to Day 7; for all new players regardless of day they joined in; with biggest event and communication push from the 13th of March to the end, due to biggest expected player influx.
1. Comeback Tomorrow gives a massive Legendary+ player just for logging in the day after their first session, starting March 13. This is one of the biggest kickers that also works well in CPI campaigns.
2. Daily Logins reward a Rare+ pack every single day of the Beta. Simple task, good reward.
3. Complete the Team tasks players with scoring a Ranked goal daily to earn a specific position player, slowly building a full squad over the event. This is mix of retention and ranked play.
4. To lock in the Day 7 retention, the 7-Day Streak rewards a top-tier Mythical card for a full week of consecutive logins.
5. Finally, the Winback mechanic automatically drops an Epic+ pack to anyone who goes inactive for 3 days, and 2x Epic+ for 7 days - pulling them back for D7 target.
II. COMPANION APP INSTALLS & USAGE
We want players connected to the game when they are away from their PC. However more importantly allowing us to pull them back into the game with messages and rewards reminders. Goal here is to convince players to use the app and stay open for notification.
1. Downloading the App immediately rewards a high-value Epic+ pack.
2. To keep the app installed and active, players get a Daily App Reward of 2x Uncommon+ packs that can only be claimed on their phone.
3. To make sure we will be able to reach with App Notifications we give out Rare+ pack for Enabling Push notifications
III. COMMUNITY, WISHLISTS & ACCOUNT LINKING ENGAGEMENT
This is about using the Beta hype to build our long-term player base for the Live launch and get more way of communication and tracking.
1. Wishlisting GOALS on platforms rewards players with a 1x Rare package. Since we won’t track if specific players actually wish listed the game the reward is moderate quality. We only check if they clicked on the link.
2. Connect your platforms is important to track players and require more time from player the reward is higher: 1x Epic+
3. Joining Discord for community building. We probably can’t check the joining so the award is 2x Uncommon+
4. BETA rewards news is purely informative – where we summarize the Main Events. No reward.
IV. RANKED GAMES ENGAGEMENT (WIP)
We need to push players into the competitive queue to test our matchmaking and skill brackets. Challenges are tied directly to playing and winning Ranked matches.
This is also heavily supported by the "Complete the Team" retention event, which forces players to score at least one goal in Ranked every single day to get their rewards.
V. NEW KNOCKOUT MODE ENGAGEMENT
We need to make sure the new knockout mode gets heavily played.
1. Participate in Knockout is rewarded for marches playerd
2. Progress to next tier in a Knockout (Bronze -> Final) rewards will increase for each Tier (based on times of wins)
VI. ENGAGEMENT HOOKS
These are events and awards designed to support both retention events and engagement in various other ways.
1. New Starter Pack gives everyone a strong 1x Rare+ captain and 1x Uncommon+ supporting player. However the amount of other packs was set to 0 compared to default, to make players interact with events rather than being hand-out too many players at the start.
2. Introducing Extra Kits will feature new cosmetic kits (Pulse V01, V02, 03) purchasable in the store between March 14 and March 22 to drive engagement during the first weekend also create the need for Points.
3. Peak Hours Swap Coin Exchange allows players to swap 10 unwanted cards (ranging from Basic to Rare) for Points equal to 10% of the cards' value. This is available exclusively during weekends to artificially boost CCU and is connected to Kits purchases.
4. Swap Players for National Packs lets players trade 10 Common or Uncommon unwanted cards for a card of the same rarity from a specific top nation. This acts as a incentive for countries with a top player count influx.
VII. REINFORCE EVENTS VIA PUSH NOTIFICATIONS
This is our tool to remind players to log in before they drop off.
1. Day 1 & Day 7 Alerts would be used to send "24 hours left" warnings so players don't miss their biggest streak rewards. Need to be checked if possible to setup
2. Comeback Tomorrow Reminder will directly nudge players on Day 1 to log in and grab that massive Legendary+ card waiting for them.
3. Everyday reminder of players being able to receive another player for specific field position. We’d remove that on Tuesday to test it’s impact. Also would be good to test different hours of Notification sending.
4. New Kits purchasable reminder. To be sent to drive weekend engagement

## MAIN Events (x - 13.03)
[8 empty] | week 0 | [6 empty] | Week 1 | [7 empty] | Post LIve Ops Evaluation
[8 empty] | 9.03 | 10.03 | 11.03 | 12.03 | 13.03 | 14.03 | 15.03 | 16.03 | 17.03 | 18.03 | 19.03 | 20.03 | 21.03 | 22.03
GOAL DRIVERS/ Internal Names | REQUIREMENTS | REWARDS | RECCURENCE | EXTRA INFORMATION | HIGHLIGHT (FTUE menu) | TIMING | Confirmation/tech questions? | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | END | Performance (0-1) | Learnings
RETENTION (D1, D7)
Comeback Tomorrow (D1 Hook) | Login next day | 1x Legendary+ | 1x |  | X | from 13.03 to 22.03 | bar: Fri to Sun
Come back on Day 7 | Log in on day 7 after 1st login (D7 Hook) | 1x Mythical | 1x |  |  | from 13.03 to 22.03 | bar: Fri to Sun
Come back everyday (D1-D9) | Login every day | 1x Rare | Daily |  |  | ALL BETA | bar: Mon to Sun
Complete the team (D0-D9) | Score a ranked goal on a specific day with: | 1x Epic position player | 1x Day | Every day different player: STx, CFx, WFx, AMx, WMx, CMx, DMx, WBx, FB, CB, | X | from 13.03 to 22.03 | bar: Fri to Sun
Winback (D3) | Return after 3 days of inactivity | 1x Epic + | 1x | doesnt seem to be working with "Online" function. There is comeback category on challenges, but no way to configure it for comeback event. |  | from 13.03 to 22.03 | bar: Fri to Sun
Winback (D7) | Return after 7 days of inactivity | 2x Epic + | 1x |  |  | from 16.03 to 22.03 | bar: Mon to Sun
Double/Triple XP (Weekends) | XP in the game is increased for the weekend | 2x XP 1st weekend, 3x XP 2nd Weekend | Weekends | 13-15 march, 20-23 march. Not able to implement at this time. |  | Weekends on BETA | bar: Mon to END
Win 3 matches - Daily challange | Win any 3 games in any non-bot game mode (D0-D9) | Day 1-2 (10x Basic) Day 3-4 (10x Common) Day 5-6 (5x Uncommon) Day 7-8 (3x Rare) Day 9-10 (2x Epic) | Daily | This will be set for each days manually |  | from 13.03 to 22.03 | bar: Fri to Sun
COMPANION APP INSTALLS & USAGE
Download the Companion App and login | Download and login 1st time the Companion App | 1x Epic | 1x | First login |  | ALL BETA | bar: Mon to Sun
Login do companion app every day | Claim daily reward inside Companion App | 2x Uncommon+ | Daily | to keep the appp installed |  | ALL BETA | bar: Mon to Sun
Enable Push Notification | Enable Push Notification | 2x Rare+ | 1x | can track, cannot reward |  | ALL BETA | bar: Mon to Sun
COMMUNITY, WISHLISTS & ACCOUNT LINKING ENGAGEMENT
Wishlist GOALS on your platform | Click on link to the page via the game | 2x Uncommon+ | 1x |  |  | ALL BETA | cannot track | bar: Fri to Sun
Connect your platform | Link your account to either: Steam/Xbox/PlayStation | 1x Epic + | 1x |  |  | ALL BETA | bar: Fri to Sun
Join Discord for an award (during beta) | Click on discord link and watch for daily codes | TBD with CM | 1x | There will be a single-use code on Discord to redeem for players |  | ALL BETA | bar: Fri to Sun
BETA rewards news | Click on the News | None | None | summarize beta events timeline and most important rewards |  | ALL BETA (if we can deliver on time) | bar: Mon to Sun
Newsletter Subscribed | Subsribe to newsletter | 2x Rare+ | 1x | bar: Fri to Sun
RANKED GAMES ENGAGEMENT
Play Ranked matches x times | Play Ranked matches, amount of times: 1x, 3x, 10x, 25x, 50x | 1x: 3x Basic+ 3x: 1x Common+ 10x: 3x Common+ 25x: 3x Uncommon+ 50x: 1x Rare+, 3x Uncommon+ | 1x |  |  | ALL BETA | bar: Mon to Sun
Win Ranked matches x times | Win Ranked matches, amount of times: 1x, 5x, 10x, 25x, 50x | 1x: 3x Basic+ 5x: 3x Common+ 10x: 3x Uncommon+ 25x: 1x Rare+, 3x Uncommon+ 50x: 1x Epic, 1 x Rare | 1x |  |  | ALL BETA | bar: Mon to Sun
Score goals in Ranked matches x Times | Score goals in Ranked matches, amount of times: 1x, 5x, 25x, 50x, 100x | 1x: 5000 Character XP 5x: 15000 Character XP 25x: 70000 Character XP 50x: 125000 Character XP 100x: 200000 Character XP | 1x |  |  | ALL BETA | bar: Mon to Sun
NEW KNOCKOUT MODE ENGAGEMENT
Participate in Knockout matches x times | Play X Knockout Matches: 1x, 3x, 10x, 25x, 50x | 1x: 5x Basic+ 3x: 3x Common+ 10x: 5x Common+ 25x: 5x Uncommon+ 50x: 3x Rare+ | 1x |  |  | Fri 09:00 - Mon 09:00 CET | bar: Fri to Mon
Win in Knockout matches x times | Win X Knockout matches: 1x, 3x, 9x, 16x, 24x | 1x: 5x Basic+ 3x: 5x Common+ 9x: 5x Uncommon+ 16x: 5x Rare+, 24x: 2x Epic | 1x |  |  | Fri 09:00 - Mon 09:00 CET | bar: Fri to Mon
Score goals in Knockout matches | Score in Knockout matches amount of times: 1x, 5x, 25x, 50x, 100x | 1x: 2500 Points 5x: 5000Points 25x: 25000 Points 50x: 50000 Points 100x: 100000 Points | 1x |  |  | Fri 09:00 - Mon 09:00 CET | bar: Fri to Mon
RERUN (KNOCKOUT MODE ENGAGEMENT)
Participate in Knockout matches x times | Play X Knockout Matches: 1x, 3x, 5x, 10x, 15x, 20x | 1x: 5x Basic+ 3x: 3x Common+ 5x: 5x Common+ 10x: 5x Uncommon+ 15x: 3x Rare+ 20x: 500000 XP Points | 1x | Play 50 Knockout matches |  | Fri 09:00 - Mon 09:00 CET | bar: Fri to Mon; Fri to END
Win in Knockout matches x times | Win X Knockout matches: 1x, 3x, 5x, 10x, 15x | 1x: 5x Basic+ 3x: 5x Common+ 5x: 5x Uncommon+ 10x: 5x Rare+, 15x: 2x Epic | 1x | Win 24 Knockout matches |  | Fri 09:00 - Mon 09:00 CET | bar: Fri to Mon; Fri to END
Score goals in Knockout matches | Score in Knockout matches amount of times: 1x, 5x,10x, 15x, 25x | 1x: 50000 XP Points 5x: 100000 XP Points 10x: 200000 XP Points 20x: 300000 XP Points 30x: 500000 XP Points | 1x | Score 100 goals in Knockout matches |  | Fri 09:00 - Mon 09:00 CET | bar: Fri to Mon; Fri to END
ENGAGEMENT HOOKS
New Starter Pack | Start the game (Check Starting Pack) | 1x Rare + 1 Uncommon+ | 1x | 1 strong player (captain player) + supporting player |  | ALL BETA | bar: Mon to Sun
Introducting extra kits | Purchase in the shop | Pulse V01: Pulse V02 Pulse V03 | 1x | Purchasable in the store |  | 14.03-22.03 | bar: Sat to Sun
Weekend Exchange | Discard players, Swap Players | Sell 10 Players: 5000 Points Sell 20 Players: 10000 Points Sell 50 players: 20000 Points Swap Any 1 Swap: 5000 Points Swap Any 5 Swaps: 20000 Points Swap Any 10 Swaps: 50000 Points | Weekends (1x) | Available only during weekends |  | Weekend time | bar: Sat to Sun; Sat to Sun
National Packs | National Packs in store (5x Uncommon+, 5x Rare+, 1 per day) | National Packs in store (5x Uncommon+, 5x Rare+, 1 per day) | Daily | incentive for countries with top player count influx |  | FRI-SUN | bar: Fri to Sun; Fri to Sun
ONBOARDING ENGAGEMENT
Extra rewards for Completing Onboarding Scenario | Complete Scenario: Amateur Intermediate, Professional | Amateur: 5x Common Intermediate: 3x Uncommon Professional: 1x Rare | 1x |  |  | ALL BETA | bar: Mon to Sun
REINFORCE EVENTS VIA PUSH NOTIFICATIONS
Log in to the game od D1 | Push Notification to all on D1 (if possible) | x | 1x | Mention it's 24hrs offer and it will disappear |  | On D1 | Very time consuming at that time
Log in to the game on D7 | Push Notification to all on D7 (if possible) | x | 1x | Mention it's 24hrs offer and it will disappear |  | On D7 | Very time consuming at that time
Log in to the game od D1 | Comeback Tomorrow (D0-D1 Hook) | x | 1x | Claim your Legendary Player ⚡ Return on your second day of the beta to unlock a guaranteed Legendary player ! |  | Reminder (24hrs award / 7th day reward |  | Sat: x; Fri: 7th day reminder
Thank you for BETA | Last day of the BETA | x | 1x | Thank you for playing Beta Wishlist the game and come back on official release! |  | 22.03 | bar: Sun
Complete the team (D0-D9) Score a ranked goal every day | Complete the team (D0-D9) | x | Daily | Receive your Epic player 🔥 Score a ranked goal Today and get an Epic ... |  | 13.03-22.03 |  | Mon: 17:30; Tue: 19:00; Wed: x; Thu: x; Fri: x; Sat: x; Sun: x
New Kits purchasable | New PULSE kits available | x | 1x | New Player Kits available 👕 3 brand new PULSE player kits added to GOALS! |  | 14.03 |  | Sat: 9:00
Monday rush - 3 epic 90+ PAC | [7 empty] | Mon: 17:00
Tuesday Rush - 1,5 mln XP | [7 empty] | Tue: 17:30
Basic pack reminder | [11 empty] | 14:05 | 14:05 | 14:05 | 14:05 | 14:05 | 14:05 | 14:05 | 14:05 | 14:05 | 14:05
BETA Code on Discord | bar: Fri
Repeatable challenges (grinders)
Play the "5v5" mode | Play: 1x, 3x, 5x, 10x, 15x | 5x basic, 5 common, 5 uncommon, 3 rare, 1 epic | bar: Mon to Sun
Score Chip shot goal in a ranked game | 1x | 1x Epic ST | bar: Mon to Sun
Score 5+ goals in one match | repeatable | 5x common | bar: Mon to Sun
Score x goals in a single ranked game | 3x, 5x, 6x, 7x, 8x, 10x | 5x common, 5 uncommon, 2 rare, 1 epic, 1 legendary, 1 Mythic | bar: Mon to Sun
Provide 5 through-ball assists | repeatable | 5x basic | bar: Mon to Sun
Play 5 ranked games | repeatable | 3x uncommon | bar: Mon to Sun
Score 10 goals | repeatable | 5x basic | bar: Mon to Sun
Score from corner x5 times | repeatable | 5x common | bar: Mon to Sun
Play 10 games (any mode) | repeatable | Experience: 50.000 | bar: Mon to Sun
Assist with a goalkeeper | 1x | 1x Epic GK | bar: Mon to Sun
Score with a goalkeeper | 1x | 1x Legendary GK | bar: Mon to Sun
Win a tournament (win 4 matches) | repeatable | Points: 10.000 | bar: Mon to Sun
Rewards Summary from MAIN events:
1x Mythical+
1x Legendary+
16x Epic+
Make 1 assist with a goalkeeper in a Ranked game | [6 empty] | 19x Rare+
23x Uncommon+
From Main rewards
Expected Rewards Summary for avarage player (that spends 7 days - 50% of time)
1x Mythical+
1x Legendary+
9x Epic+
11x Rare+
12x Uncommon+

## Challenges (V)
Rookie | 1-10 Range |  |  | Basic-Common |  |  | Contender | 5-50 | (min 1 fo exceptional tasks) |  | Basic-Uncommon |  | Champion | 30-100 | (min 10 fo exceptional tasks) |  | Uncommon-Rare |  | Live
Name | Game formats | Requirement | Starts / Ends | Rewards |  | Recurring | Name | Game formats | Requirement | Starts / Ends | Rewards | Recurring | Name | Game formats | Requirement | Starts / Ends | Rewards | Recurring | Name | Game formats | Requirement | Starts / Ends | Rewards | Recurring
Play 1 match |  | Matches Played (1) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Basic+ | x | - | Play 20 matches | Any PVP | Matches Played (20) | 2026-03-9 00:00 / 2026-03-22 23:59 | 10000 Points |  | Play 100 matches | Any PVP | Matches Played (100) | 2026-03-9 00:00 / 2026-03-22 23:59 | 40000 Points |  | Win 50 matches | Any PVP | Matches Won (50) | 2026-03-13 00:00 / 2026-03-22 23:59 | 1 Epic+
Play 5 matches | Any PVP | Matches Played (5) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Basic+ | x | - | Play 50 matches | Any PVP | Matches Played (50) | 2026-03-9 00:00 / 2026-03-22 23:59 | 20000 Points |  | Win 30 matches | Any PVP | Matches Won (30) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Rare+ |  | Score 1 goal with a midfielder | Any PVP | Goals Scored (1) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Common+
Win 3 matches | Any PVP | Matches Won (3) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Common+ | x | - | Win 10 matches | Any PVP | Matches Won (10) | 2026-03-9 00:00 / 2026-03-22 23:59 | 3 Common+ |  | Score 50 goals | Any PVP | Goals Scored (50) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Rare+ |  | Score 1 penalty | Any PVP | Penalties Scored (1) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Common+
Win 2 games with bots | Bots | Matches Won Bots (2) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Basic+ | x | - | Score 10 goals | Any PVP | Goals Scored (10) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Uncommon+ |  | Score 30 headers | Any PVP | Headers Scored (30) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Rare+ Attacker |  | Provide 1 assist with a defender | Any PVP | Assists (5) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Common+
Score 5 goals with attackers | Any PVP | Goals Scored (5) | 2026-03-9 00:00 / 2026-03-22 23:59 | 2 Common+ 3000 Points | x | - | Score 20 goals with midfielders | Any PVP | Goals Scored (20) | 2026-03-9 00:00 / 2026-03-22 23:59 | 2 Uncommon + Midfielders |  | Score 10 penalties | Any PVP | Penalties Scored (10) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Rare+ Goalkeeper |  | Open 100 player packs |  | Packs Opened (100) | 2026-03-13 00:00 / 2026-03-22 23:59 | 2 Rare+
Score 10 goals in the Practice Arena | Practice Arena | Goals Scored (10) | 2026-03-9 00:00 / 2026-03-22 23:59 | 3000 Points | x | - | Score from 1 corner | Any PVP | Corners Scored (1) | 2026-03-9 00:00 / 2026-03-22 23:59 | 10 Basic+ |  | Score 10 free kicks | Any PVP | Free Kicks Scored (10) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Uncommon+ |  | Achieve a team rating (OVR) of 85 or higher |  | Squad Rating (85) | 2026-03-13 00:00 / 2026-03-22 23:59 | 2 Epic+ 20000 Points
Win 5 tackles | Any PVP | Tackles (5) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Basic+ | x | - | Score 5 volleys | Any PVP | Volleys Scored (5) | 2026-03-9 00:00 / 2026-03-22 23:59 | 3 Uncommon+ |  | Score 10 Chip Shots | Any PVP | Chip Shot Scored (10) | 2026-03-9 00:00 / 2026-03-22 23:59 | 3 Uncommon+ |  | Win 100 matches | Any PVP | Matches Won (100) | 2026-03-13 00:00 / 2026-03-22 23:59 | 1 Legendary+
Provide 5 assists | Any PVP | Assists (5) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Basic+ | x | - | Score 1 free kick | Any PVP | Free Kicks Scored (1) | 2026-03-9 00:00 / 2026-03-22 23:59 | 2 Common+ |  | Score 20 Finesse Shots | Any PVP | Finesse Shot Scored (20) | 2026-03-9 00:00 / 2026-03-22 23:59 | 3 Uncommon+
Achieve a team rating (OVR) of 60 or higher |  | Squad Rating (60) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Common+ 1000 Points | x | - | Score 5 penalties | Any PVP | Penalties Scored (5) | 2026-03-9 00:00 / 2026-03-22 23:59 | 2 Uncommon + |  | Provide 50 assists with Midfielders | Any PVP | Assists (50) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Rare+ Midfielder
Open 1 player pack |  | Packs Opened (1) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1500 Points | x | - | Provide 20 assists | Any PVP | Assists (20) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Common + |  | Win 50 tackles with Defenders | Any PVP | Tackles (50) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1 Rare+ Defender
Open 10 player packs |  | Packs Opened (10) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5000 Points | x |  | Win 25 tackles | Any PVP | Tackles (25) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Common + |  | Achieve a squad rating of 80 |  | Squad Rating (80) | 2026-03-9 00:00 / 2026-03-22 23:59 | 2 Rare + 10000 Points
Complete 1 swap |  | Completed Swaps (1) | 2026-03-9 00:00 / 2026-03-22 23:59 | 1500 Points | x |  | Achieve a team rating (OVR) of 70 or higher |  | Squad Rating (70) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Uncommon+ 5000 Points |  | Open 50 player packs |  | Packs Opened (50) | 2026-03-9 00:00 / 2026-03-22 23:59 | 2 Uncommon+
Sell 1 player |  | Characters Discarded (1) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Basic+ | x |  | Open 25 player packs |  | Packs Opened (25) | 2026-03-9 00:00 / 2026-03-22 23:59 | 2 Common+ |  | Complete 50 Swaps |  | Completed Swaps (50) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Uncommon+
[7 empty] | Complete 20 Swaps |  | Completed Swaps (20) | 2026-03-9 00:00 / 2026-03-22 23:59 | 50000 Character XP |  | Sell 30 players |  | Characters Discarded (30) | 2026-03-9 00:00 / 2026-03-22 23:59 | 5 Common+
[7 empty] | Sell 10 players |  | Characters Discarded (10) | 2026-03-9 00:00 / 2026-03-22 23:59 | 10 Basic+

## Tournaments (X)
Name | Masters Cup | Challengers Cup | Beginners Cup | Champions Cup | Contenders Cup | Rookies Cup | Staging Cup
Rules | playing eleven, max ovr: 99 playing eleven, min ovr: 80 | playing eleven, max ovr: 85playing eleven, min ovr: 70 | Playing eleven, max ovr: 79 | playing eleven | playing eleven, max ovr: 80 | playing eleven, max ovr: 75 | playing eleven, max ovr: 85
Stages | 4 | 4 | 4 | 4 | 4 | 4 | 4
Time | 2026-03-16 00:00 2026-03-22 23:59 | 2026-03-13 00:00 2026-03-22 23:59 | 2026-03-09 00:00 2026-03-22 23:59 | 2026-03-9 00:00 / 2026-03-22 00:00 | 2026-01-21 00:00 / 2026-03-05 00:00 | 2026-01-21 00:00 / 2026-03-05 00:00 | 2026-01-21 00:00 / 2026-03-05 00:00
Round 1
Reward Character XP | 10000 | 7500 | 5000
Reward Money
Points | 1000 | 750 | 500
Round 2
Reward Character XP | 15000 | 10000 | 7500
Reward Money
Points | 1500 | 1000 | 750
Round 3
Reward Character XP | 20000 | 15000 | 10000
Reward Money
Points | 2000 | 1500 | 1000
Round 4
Reward Character XP | 30000 | 20000 | 15000
Reward Money
Points | 3000 | 2000 | 1500
First win reward
Character XP | 250000 | 200000 | 150000
Money
Points | 20000 | 15000 | 10000
Reward Pack | 5 x Rare + | 5x Uncommon+ | 5x Common+
Subsequent win reward
Character XP | 100000 | 75000 | 50000
Money
Points | 8000 | 6000 | 4000
Reward Pack | 5x Uncommon + | 5x Common + | 5x Basic+

## Swaps (X - 13.03)
Swaps
Name | Requirement | Starts / Ends | Max | Reward
Clean Sheet | 10 basic players | Full BETA |  | BASIC+ GK
Basic Swap | 10 basic players | Full BETA |  | BASIC+ 2
Common Swap | 10 common players | Full BETA |  | COMMON+ 2
Uncommon Swap | 10 uncommon players | Full BETA |  | UNCOMMON+ 2
Rare Swap | 10 rare players | Full BETA |  | RARE+ 2
Epic Swap | 10 epic players | Full BETA |  | EPIC+ 2
XP SWAP | Any 10 players | From D1 | Max: 10 times | XP: 50000 | cannot have 2 different swaps
Master Cards | Any 99 players | From D1 | Max: 2 times | 1 x EPIC+ | canot swap more than 10 - replacing with 100 challenge
Coin exchange | Any 10 players from: Basic Common Uncommon Rare | Weekends | Max: 10 times | Coin: 1,000 2,500 6,500 30,000 | NOT ACTIVE

## Store (x)
[6 empty] | week 0 | [6 empty] | Week 1
Order | Name | Pack content | Supply renewal | Supply per user | Price | 9.03 | 10.03 | 11.03 | 12.03 | 13.03 | 14.03 | 15.03 | 16.03 | 17.03 | 18.03 | 19.03 | 20.03 | 21.03 | 22.03
Player Packs: | [5 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
10 | 5 Basic Pack | 5x BASIC+ | 1 day | 1 | 0 | bar: Mon to Sun
9 | Starter Pack | 1x RARE+ 1 UNCOMMON+ | none | 1 | 15000 | bar: Mon to Sun
8 | Squad Builder | 3 x UNCOMMON+ | none | 1 | 10000 | bar: Mon to Sun
7 | Going Pro | 2 x RARE+ | none | 1 | 20000 | bar: Mon to Sun
6 | 3 Basic+ | 3 x BASIC+ | unlimited | unlimited | 2500 | bar: Mon to Sun
5 | 2 Common+ | 2x COMMON+ | unlimited | unlimited | 4000 | bar: Mon to Sun
4 | 1 Uncommon+ | UNCOMMON+ | unlimited | unlimited | 6500 | bar: Mon to Sun
3 | 1 Uncommon+ Goalkeeper | UNCOMMON+ GOALKEEPER | unlimited | unlimited | 6500 | bar: Mon to Sun
2 | 1 Rare+ | RARE+ | unlimited | unlimited | 30000 | bar: Mon to Sun
1 | 1 Epic + | EPIC+ | unlimited | unlimited | 250000 | bar: Mon to Sun
1 | 1 Legendary + | LEGENDARY+ | unlimited | unlimited | 2500000 | bar: Fri to Sun
9 | Booster Pack | 5 x UNCOMMON+ | none | 3 | 25000 | bar: Fri to Sun
10 | 5 Superior Basic Pack | 10x BASIC+ | 1 day | 1 | 0 | bar: Mon to Sun
Kits:
2 | Pulse: | light01_v01 | light01_v01 kit | 1 | 41000 | bar: Sat to Sun
2 | Pulse: | light01_v02 | light01_v02 kit | 1 | 41000 | bar: Sat to Sun
1 | Pulse: | light01_v03 | light01_v03 kit | 1 | 55000 | bar: Sat to Sun
3 | Mech01 | mech_01_v01 | mech_01_v01 kit | 1 | 25000 | bar: Mon to Sun
3 | Mech01 | mech_01_v03 | mech_01_v03 kit | 1 | 25000 | bar: Mon to Sun
4 | National Pool | kit_national_de | kit_national_de kit | 1 | 16000 | bar: Mon to Sun
4 | National Pool | kit_national_pt | kit_national_pt kit | 1 | 16000 | bar: Mon to Sun
4 | National Pool | kit_national_gben | kit_national_gben kit | 1 | 16000 | bar: Mon to Sun
Celebrations:
Featured:

## Starting Pack (X)
Basic Players | Common Players | Uncommon Players | Rare Players (the hook) | [5 empty] | Age Min | Age Max
3x BASIC+ | 2x COMMON+ | 1x UNCOMMON CB 1x UNCOMMON FB | 1 EPIC STRIKER |  |  |  |  | BASIC+ | 16 | 23
[8 empty] | COMMON+ | 23 | 26
Position | Tier | Nationality | Stats guaranteed | Age | Stats | min | Max | UNCOMMON+ | 26 | 30
Goal Keeper | UNCOMMON | x |  | X | REF | 70 | 99 | RARE+ | 30 | 33
[5 empty] | DIV | 70 | 99
Position | Tier
Player 1 | RARE | x |  | 33
Player 2 | UNCOMMON | x |  | 30
Player 3 | UNCOMMON | x |  | 28
Player 4 | COMMON | x |  | 26
Player 5 | COMMON | x |  | 25
Player 6 | COMMON | x |  | 24
Player 7 | Basic | x |  | 23
Player 8 | Basic | x |  | 22
Player 9 | Basic | x |  | 21
Player 10 | Basic | x |  | 19
25.1
Average Age

## Onboarding - (X)
Amateur |  |  | Intermediate |  |  | Professional
Name | Scenario ID | Rewards | Name | Scenario ID | Rewards | Name | Scenario ID | Rewards
Power Shots | Score_Power_Shots | BASIC+ | Loaded Shot | Loaded_Shot | 3000 Points | Curved Loaded Shot | Loaded_Curved_Shot | 5000 Points
Ground Passes | Ground_Passes | 1500 Points | Chip Shots | Score_Chip_Shots | BASIC+ 2 | Manual Switching | Win_Ball_Right_Stick_Switch | BASIC+ 3
Sprinting | Sprint_And_Score_Inside_Penalty | BASIC+ | Stepovers | Stepover_And_Score | 3000 Points | Scissor & Bicycle Kicks | Score_Scissor_Or_Bicycle_Kick | 5000 Points
Stand Tackles | Win_Ball_ManualTackle | 1500 Points | Runners | Triggered_Run_Assist_And_Score | BASIC+ 2 | Dragbacks | Dragback_Through_Pass_And_Score | BASIC+ 3
Curved Shots | Score_Curved_Shots | BASIC+ | Lofted Through Passes | Lofted_Through_Pass_And_Score | 3000 Points | Secondary Player Press | Second_Player_Press | 5000 Points
Through Passes | Through_Pass_And_Score | 1500 Points | Low Curved Shots | Score_Low_Curved_Shots | BASIC+ 2 | Driven Passes | Power_Passes_Offensive_Half | BASIC+ 3
Auto Tackles | Win_Ball_Autotackle | BASIC+ | Corners | Score_From_Corner_Kick | 3000 Points | Advanced Skill Moves | Skill_Moves_And_Score | 5000 Points
Crossing | Cross_And_Score | 1500 Points | Ball Rolls | Ball_Roll_And_Score_Power_Shot | BASIC+ 2 | Decisive Tackles | Win_Ball_Tackle_And_Score | BASIC+ 3
Slide Tackles | Win_Ball_Slide_Tackle | BASIC+ | Jockeying | Win_Ball_Jockey_Autotackle | 3000 Points | Wing Play | Low_Cross_And_Score | 5000 Points
Low Shots | Score_Low_Shots | 1500 Points | Dummy | Dummy_And_Score | BASIC+ 2 | Counter-Attack | Corner_Win_Ball_And_Score | BASIC+ 3
Penalties | Score_Consecutive_Penalties | BASIC+ | Fake Shots | Fakeshot_And_Score | 3000 Points | High Pressure | HP_Win_Ball_Slide_Tackle_And_Score | 5000 Points
|  |  | Free Kicks | Score_Free_Kick | BASIC+ 2 | Long Shots | Score_Outside_Box | BASIC+ 3
[6 empty] | Late Comeback | Late_Comeback | 5000 Points
Section Rewards |  |  | Section Rewards |  |  | Section Rewards
Money | 0 |  | Money | 0 |  | Money | 0
Points | 10000 |  | Points | 10000 |  | Points | 0
Reward Pack | 0 |  | Reward Pack | 0 |  | Reward Pack | Rare+ Pack
Extra rewards for Completing Onboarding Scenario | Complete Scenario: Amateur Intermediate, Professional | Amateur: 5x Common Intermediate: 3x Uncommon Professional: 1x Rare

## Ranks rewards - (X)
Rank 1 | Rank 2 | Rank 3 | Rank 4 | Rank 5 | Rank 6 | Rank 7 | Rank 8 | Rank 9 | Rank 10
XP: 200000 | XP: 200000 | XP: 200000 | XP: 200000 | XP: 200000 | XP: 200000 | XP: 200000 | XP: 200000 | XP: 200000 | XP: 200000
Points: 10000 | Points: 9000 | Points: 8000 | Points: 7500 | Points: 7000 | Points: 6500 | Points: 6000 | Points: 5500 | Points: 5000 | Points: 5000
1 Rare+ Player | 3 Uncommon+ Players | 3 Uncommon+ Players | 2 Uncommon+ Players | 2 Uncommon+ Players | 2 Uncommon+ Players | 2 Uncommon+ Players | 2 Uncommon+ Players | 1 Uncommon+ Player | 1 Uncommon+ Player
| 3 Common+ Players | 2 Common+ Players | 2 Common+ Players | 2 Common+ Players | 1 Common+ Player | 1 Common+ Player | 3 Basic+ Players | 2 Common+ Players | 1 Common+ Player
|  |  | 5 Basic+ Players | 3 Basic+ Players | 5 Basic+ Players | 3 Basic+ Players |  | 3 Basic+ Players | 5 Basic+ Players

## Tiers & Pricing
|  |  |  | Base conversion ( 25000 points = 6 $ = 500 coins) | [5 empty] | Tier | MIN OVR | MAX OVR | Value | Discard |  | Swap
|  |  |  | Points value | Coins | USD | points / coin | points / USD | coins / USD | BASIC+ | 40 | 59 | 1000 | 100 | 10% | 2000 | 1000 | 2
|  |  |  | 25000 | 500 | 6 | 50 | 4166.6667 | 83.3333 | COMMON+ | 60 | 69 | 2500 | 350 | 14% | 5000 | 3500 | 1.4286
[10 empty] | UNCOMMON+ | 70 | 79 | 6500 | 1000 | 15.38% | 13000 | 10000 | 1.3
|  | Categories | [7 empty] | RARE+ | 80 | 84 | 30000 | 5000 | 16.67% | 60000 | 50000 | 1.2
|  | Kit | [7 empty] | EPIC+ | 85 | 89 | 250000 | 40000 | 16% | 500000 | 400000 | 1.25
|  | Pack | [7 empty] | LEGENDARY+ | 90 | 94 | 2500000 | 350000 | 14% | 5000000 | 3500000 | 1.4286
|  | Celebration | [7 empty] | MYTHIC | 95 | 99 | 20000000 | 1500000 | 7.5% | 40000000 | 15000000 | 2.6667
Original
The following amount of XP is required per tier to unlock the next upgrade:
Basic 500,000 XP
Common 1,000,000 XP
Uncommon 1,500,000 XP
Rare 2,500,000 XP
For reference only. Not used in this model | [9 empty] | Epic 4,000,000 XP
Legendary 5,500,000 XP
1st Party Store | USD | coins | coins rounded incl bonus | value | points value |  |  |  |  | Mythic 7,500,000 XP
| 3.99 | 332.5 | 500 | 150.4% | 16625
| 5.99 | 499.1667 | 500 | 100.2% | 24958.3333 |  | $5.99 →baseline. no bonus |  |  | Drop rates
| 9.99 | 832.5 | 1000 | 120.1% | 41625 |  | $9.99 → (+20%) |  |  | https://goalsgame.atlassian.net/wiki/spaces/GG/pages/1412399113/User+Facing+Drop+Rates
| 12.99 | 1082.5 | 1000 | 92.38% | 54125
| 19.99 | 1665.8333 | 2050 | 123.1% | 83291.6667 |  | $19.99 → (+25%) ← decoy
| 29.99 | 2499.1667 | 3500 | 140% | 124958.3333 |  | $29.99 → (+40%) Best value
| 49.99 | 4165.8333 | 6500 | 156% | 208291.6667 |  | $49.99 → (+50%)
| 99.99 | 8332.5 | 14500 | 174% | 416625 |  | $99.99 → (+70%) best bargain