## Project Summary
Goals Studio Pricing Engagement
Client | Goals Studio (Goals AB)
Location | Stockholm, Sweden
Primary Contact | Jonas Rundberg (CEO)
Secondary Contact | Julius (Live Ops)
NBI Team | Glen Pryer (domain + relationship), Tom Rieger (contract), Devin Rieger (research)
Contract
SOW Value | 100,000 SEK (~$10,000 USD)
Budget | ~50 billable hours over 5 working days
SOW Date | 8 April 2026
Delivery Deadline | 28 April 2026 (written summary), review call same week
Hard Deadline | Before Goals submits to PS/Xbox (~5 May for 14 May launch)
Scope
Deliverable | Written summary (12-18 pages) + remote review call (30-45 min)
Area 1 | Review competitive pricing positioning in sports/football game space
Area 2 | Price point selection, currency pack structure, conversion rate guidance
Area 3 | Regional pricing for base and regional markets (40+ countries)
Area 4 | Assessment of current pricing against market norms
Area 5 | Recommendations on adjustments and areas of risk
The Game (GOALS)
Genre | F2P football game
Launch Date | 14 May 2026
Platforms | Steam, Epic Games Store, Xbox, PlayStation
Unique Mechanic | Generated players (not licensed), RPG progression, aging/retirement
Monetisation | 80% skill / 20% purchased advantage (explicitly non-P2W)
Economy Type | Seasonless (no battle pass, no seasonal resets, no wipes)
Beta Stats | 400K total players, 50% D1 retention (PS), NPS +24.6, CPI $0.43
Key Event | World Cup June 2026 = first major monetisation peak
HC Economy | 6-tier pack ladder: $5.99-$99.99. 1 HC = 50 points = $0.012 USD
Key Questions
Jonas | "Are we pricing too low?"
Glen Principle | Launch high, patch down. Never raise prices post-launch.
Conversion Risk | 10.4% payer target vs 2-5% industry norm for month 1
Hour Budget
F1: Competitive HC Pricing Benchmark | 16h (32%)
F2: Regional Pricing Strategy | 13h (26%)
F3: Risk Assessment & Recommendations | 10h (20%)
F4: Value-Add (Conditional) | 4h (8%)
F5: Deliverable Assembly & Review | 7h (14%)
Total | 50h (100%)
Timeline
Day 1 (Tue 22 Apr) | Foundation + Competitive position (9h)
Day 2 (Wed 23 Apr) | Competitive completion + Regional start (10h)
Day 3 (Thu 24 Apr) | Regional deep-dive + Quality Gate 3 (10h)
Day 4 (Fri 25 Apr) | Synthesis + Recommendations (10h)
Day 5 (Mon 28 Apr) | Deliverable + Review (7h)
Notes
Buffer Strategy | Feature 4 is conditional - only if F1-3 complete within budget
Quality Gate 3 | End of Day 3 - Glen reviews draft recs before synthesis
Old SOW Warning | The $62K proposal (31 March) is NOT the current SOW
Documentation | 15 markdown files extracted from client PDFs/Excel/PPTX in Clients/Goals/

## Task Breakdown
ID | Type | Title | Status | Priority | Assignees | Hours Est. | Start Date | End Date | Due Date | Success Criteria | Description | Parent Path | Practice Area
PROJECT | Project | Goals Studio Pricing Engagement | In progress | High |  | 50 | 2026-04-22 | 2026-04-28 | 2026-04-28 |  | Deliver competitive pricing benchmark, regional pricing strategy, and risk assessment for GOALS F2P football game launching 14 May 2026. Budget: 100,000 SEK (~$10K USD) ¦ ~50 billable hours ¦ 5 working days Client: Goals AB (Goals Studio), Stockholm, Sweden Contacts: Jonas Rundberg (CEO), Julius (Live Ops) NBI team: Glen Pryer (relationship + domain), Tom Rieger (contract/President), Devin Rieger (research) SOW scope: - Review competitive pricing positioning in sports/football game space - Price point selection, currency pack structure, conversion rate guidance - Regional pricing for base and regional markets - Assessment of current pricing plans against market norms - Recommendations on adjustments and areas of risk - Deliverable: Written summary (12-18 pages) + remote review call The game: - F2P football game, launching 14 May 2026 on Steam/Epic/Xbox/PlayStation - Unique generated players (not licensed), RPG progression, aging/retirement - 80% skill / 20% purchased advantage (non-P2W) - No seasons, no battle pass, no wipes - 400K total beta players, 50% D1 retention on PS, NPS +24.6, CPI $0.43 - World Cup June 2026 = first major monetisation peak Architecture: Foundation (map HC economy) > Competitive benchmark > Regional analysis > Synthesis (recommendations + scenarios) > Deliverable Hard deadline: Must deliver before Goals submits pricing to PS/Xbox (9-day review needed before May 14 launch) Key question from Jonas: "Are we pricing too low?" Glen's 27-game principle: Launch high, patch down. Never raise prices post-launch. Feature 4 is CONDITIONAL - only delivered if F1-3 complete within budget. |  | gaming
F1 | Feature | F1: Competitive HC Pricing Benchmark | Not started | High |  | 16 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | Show Goals where they sit relative to the sports/football F2P market. Extend their existing competitive analysis with insights their internal position doesn't give them. What NBI adds: Independent cross-genre validation, pricing psychology assessment, conversion rate benchmarks from NBI 27-game launch history, and the confidence that an external expert agrees (or disagrees) with their conclusions. Budget: 16h (32% of total) | Goals Studio Pricing Engagement | gaming
S1.0 | Story | S1.0: Foundation - Map the HC Economy | Not started |  |  | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  | Before comparing prices, establish exactly what Goals HC buys and what the player value chain looks like. Prerequisite for everything else. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark | gaming
T1.0.1 | Task | T1.0.1: Map HC Value Chain | Not started |  | Glen Pryer | 2 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Complete HC value chain documented. Every store item category mapped to HC cost. Minimum meaningful purchase identified and costed. | Document the complete path from real money to in-game value in Goals. Key mapping: 1 HC coin = 50 points = $0.012 USD at base rate. Map what each HC tier ACTUALLY buys (380 HC/$5.99 buys 1 National kit with 60 leftover). Map all item categories: National Kits 320 HC, Mech Kits 500 HC, Pulse Kits 820-1100 HC, Celebrations ~580 HC. Identify the "minimum meaningful purchase" - cheapest satisfying thing a new player can buy. Sources: GG-Monetization, Pricing Model, player_pricing.md Done when: Complete HC value chain documented. Every store item category mapped to HC cost. "Minimum meaningful purchase" identified and costed. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark > S1.0: Foundation - Map the HC Economy | gaming
T1.0.2 | Task | T1.0.2: Establish Payer Persona Benchmarks | Not started |  | Glen Pryer | 2 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Goals payer assumptions benchmarked against industry. Clear assessment of whether conversion/ARPPU targets are realistic at launch. Implication for pricing strategy documented. | Benchmark Goals 3-persona model against industry norms. Goals targets: Persona 1 (Core FUT, 20% players, 30% pay, ARPPU $46), Persona 2 (Dedicated, 35%, 10% pay, ARPPU $15.81), Persona 3 (Casual, 45%, 2% pay, ARPPU $7.24). Overall: 10.4% payer rate, ARPU $3.38, ARPPU $32.48. Industry benchmarks: Typical F2P payer conversion 2-5% (Goals targets 10.4% - aggressive). Typical ARPPU $20-$50/month. Whale concentration: top 10% = 50-70% of revenue. Source: NBI portfolio data across 27 F2P launches. Seasonless economy implication: No resets/battle pass/FOMO wipes means HC pack ladder must do ALL conversion work. Compare with eFootball (closer non-seasonal model). Done when: Goals payer assumptions benchmarked. Clear assessment of whether conversion/ARPPU targets are realistic at launch. Implication for pricing strategy documented. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark > S1.0: Foundation - Map the HC Economy | gaming
S1.1 | Story | S1.1: Competitive Pricing Position | Not started |  |  | 7 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | Show Goals exactly where their HC pricing sits relative to market - by synthesising their existing competitive data into a clear positioning statement they can't write themselves. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark | gaming
T1.1.1 | Task | T1.1.1: Build Normalised Price Position Map | Not started |  | Glen Pryer | 2.5 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Position map complete showing Goals percentile at each tier. Clear one-line answer: "Goals is at the Xth percentile - below/at/above median." | Create position map showing Goals effective USD/HC against competitive range at each tier. At entry ($5-6): Goals = $0.01576/HC. At mid ($20): $0.01454/HC. At top ($100): $0.01290/HC. For each tier: calculate market min, median, max, and Goals percentile. Spot-check 2-3 competitor prices to confirm Goals data is current. Source: Goals Pricing Model sheet "Softhard currency comparison". Done when: Position map complete. One-line answer: "Goals is at the Xth percentile - [below/at/above] median." | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark > S1.1: Competitive Pricing Position | gaming
T1.1.2 | Task | T1.1.2: Discount Curve Comparison | Not started |  | Glen Pryer | 1.5 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Curve comparison documented. Assessment of whether Goals discount progression is appropriate for new launch. Specific recommendation if any tier discount should change. | Compare Goals bonus/discount scaling against competitors. Goals curve: Tier 1 0%, Tier 2 ~2.5%, Tier 3 ~7.7%, Tier 4 ~9.4%, Tier 5 ~15.4%, Tier 6 ~18.1%. Competitors: EA FC ~39% max, Fortnite ~24%, Apex ~13%. Goals at ~18%. Assessment: Is 18% enough to incentivise whale spending? Is the tier-to-tier jump consistent? Is there a clear "best value" tier? Key principle: New launches should be MORE conservative on discounts. Done when: Curve comparison documented. Recommendation if any tier discount should change. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark > S1.1: Competitive Pricing Position | gaming
T1.1.3 | Task | T1.1.3: SKU Structure and Entry Point Audit | Not started |  | Glen Pryer | 2 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Structure audit complete. Entry point assessment with recommendation. Whale ceiling analysis documented. Structural gaps identified with recommendation. | Assess 6-tier HC ladder: $5.99/$9.99/$19.99/$29.99/$49.99/$99.99. Entry point: Goals $5.99 vs EA FC $0.99, Apex $4.99. Does $5.99 create first-purchase friction? Structural gaps: $9.99 to $19.99 (100% jump), $49.99 to $99.99 (100% jump) - standard in industry. Whale ceiling: $99.99 cap + no purchase limits = whale-friendly without optically aggressive pricing. Counter-argument on low entry tier: $0.99 nets only $0.69 after 30% platform fee. Done when: Structure audit complete. Entry point assessment with recommendation. Whale ceiling analysis documented. Structural gaps identified with recommendation. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark > S1.1: Competitive Pricing Position | gaming
T1.1.4 | Task | T1.1.4: Platform Fee Impact and Net Revenue Table | Not started |  | Devin Rieger | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Net revenue table complete. Margin concerns flagged. Epic revenue advantage quantified. | Calculate actual net revenue per SKU per platform. Build table: SKU ¦ Gross ¦ Steam Net (30%) ¦ Epic Net (12%) ¦ PS/Xbox Net (30%) Epic advantage: Goals earns 40% more per transaction on Epic vs other platforms at same price. Verify alignment with PS wholesale rates in Goals matrix. Done when: Net revenue table complete. Margin concerns flagged. Epic advantage quantified. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark > S1.1: Competitive Pricing Position | gaming
S1.2 | Story | S1.2: Conversion Rate and Elasticity Context | Not started |  |  | 3 | 2026-04-23 | 2026-04-23 | 2026-04-23 |  | Provide conversion/revenue modelling context that turns a static price comparison into actionable strategy. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark | gaming
T1.2.1 | Task | T1.2.1: Price Elasticity Scenario Modelling | Not started |  | Glen Pryer | 3 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 4 scenarios modelled with revenue impact ranges. Clear recommendation on which scenario maximises launch revenue while preserving future flexibility. | Model 4 scenarios using Goals revenue model (805,250 MAU, 10.4% payer rate, $32.48 ARPPU = $2.72M). Scenario A: Raise all prices 10% (conversion drops 5-15%). Scenario B: Raise all prices 20% (conversion drops 10-25%). Scenario C: Raise entry tier only $5.99 to $6.99 (entry conversion drops 5-10%). Scenario D: Keep prices, steepen discount curve to 25% max. Present as impact ranges (conservative/optimistic), not point estimates. Key insight: If 10.4% conversion is optimistic for month 1, lowering prices won't help. Launch high, patch down. Done when: 4 scenarios modelled with revenue impact ranges. Clear recommendation on which scenario maximises launch revenue while preserving future flexibility. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark > S1.2: Conversion Rate and Elasticity Context | gaming
S1.3 | Story | S1.3: Promotional and First-Purchase Pricing | Not started |  |  | 2 | 2026-04-23 | 2026-04-23 | 2026-04-23 |  | Address gap in static HC pack analysis. First-purchase incentives and promotional pricing drive early conversion. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark | gaming
T1.3.1 | Task | T1.3.1: First-Purchase and Starter Pack Recommendations | Not started |  | Glen Pryer | 2 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2-3 specific first-purchase recommendations documented with rationale and expected conversion impact. Clearly framed as complementary to core pricing. | Recommend complementary offers that improve conversion on core HC ladder: 1. First Purchase Bonus: Double HC on first-ever purchase (industry standard, improves conversion from 2% to 4-6% in first 30 days). Zero revenue cost. 2. Limited Starter Pack: One-time $3.99 offer (500 HC + Rare+ player + exclusive kit). Breaks first-purchase barrier. 3. World Cup Launch Bundle: Tied to June event, limited availability, higher value/dollar. Frame as complementary to core pricing (not scope creep). Done when: 2-3 specific recommendations with rationale and expected conversion impact. | Goals Studio Pricing Engagement > F1: Competitive HC Pricing Benchmark > S1.3: Promotional and First-Purchase Pricing | gaming
F2 | Feature | F2: Regional Pricing Strategy | Not started | High |  | 13 | 2026-04-23 | 2026-04-25 | 2026-04-25 |  | Validate Goals 40+ country pricing matrix. NBI adds: competitive regional context, PPP-adjusted analysis, and platform compliance verification they can't get from their own spreadsheet. What NBI adds: Goals built their matrix using exchange rates and some PPP data. They CANNOT benchmark their regional pricing against what EA FC actually charges in Turkey or Brazil. NBI provides this. Budget: 13h (26% of total) | Goals Studio Pricing Engagement | gaming
S2.1 | Story | S2.1: Regional Deviation and Risk Identification | Not started |  |  | 6.5 | 2026-04-23 | 2026-04-24 | 2026-04-24 |  | Flag countries where Goals pricing creates material risk (too high = player backlash, too low = revenue leakage, misaligned = platform rejection). | Goals Studio Pricing Engagement > F2: Regional Pricing Strategy | gaming
T2.1.1 | Task | T2.1.1: Categorise All Countries by Risk Level | Not started |  | Devin Rieger | 3 | 2026-04-23 | 2026-04-24 | 2026-04-24 | Every country categorised (green/amber/red). Red countries have specific risk descriptions. Ranked priority list for deeper analysis. | Apply NBI risk framework to all countries in Goals matrix: Green: Deviation <15% from FX AND aligned with platform norms. Amber: Deviation 15-25% OR misaligned with one factor. Red: Deviation >25% OR multiple risk factors OR large player market with >15% over-pricing. Red candidates: Poland (+25%), Switzerland (+26%), Ukraine (-26%), Turkey, Brazil. Amber candidates: South Africa, Czech Republic, Norway, Denmark. EUR zone: Same price across all EUR countries but PPP varies significantly. Cross-reference with beta data: UK 1,274, France 1,026, Turkey 667, Brazil 495, Poland 392. Done when: Every country categorised (green/amber/red). Red countries have specific risk descriptions. Output is a ranked priority list for deeper analysis. | Goals Studio Pricing Engagement > F2: Regional Pricing Strategy > S2.1: Regional Deviation and Risk Identification | gaming
T2.1.2 | Task | T2.1.2: Competitor Regional Pricing for Red/Amber Markets | Not started |  | Devin Rieger | 3.5 | 2026-04-24 | 2026-04-24 | 2026-04-24 | Competitor pricing gathered for all red/amber countries. Goals position vs EA FC documented per market. Countries significantly above/below EA FC identified. | Research EA FC and Fortnite pricing in 5-10 red/amber countries. Sources: PS Store regional web store, SteamDB, Epic Games Store. For each market: Country ¦ Goals proposed ¦ EA FC actual ¦ Fortnite actual ¦ Market median ¦ Position. Priority markets: Brazil (large, low PPP, WC critical), Turkey (5th largest beta community, extreme PPP), Poland (large beta, +25% above FX), Russia/CIS (currency volatility). SCHEDULE RISK: May take up to 5h if stores region-locked. Fallback: SteamDB for Steam, third-party sources for PS/Xbox. Overrun absorbed from F4 budget. Done when: Competitor pricing gathered for all red/amber countries. Goals position vs EA FC documented. | Goals Studio Pricing Engagement > F2: Regional Pricing Strategy > S2.1: Regional Deviation and Risk Identification | gaming
S2.2 | Story | S2.2: Platform Compliance and Submission Guidance | Not started |  |  | 1.5 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  | Ensure Goals pricing will pass PS/Xbox review without rejection or delay. | Goals Studio Pricing Engagement > F2: Regional Pricing Strategy | gaming
T2.2.1 | Task | T2.2.1: Verify Platform Tier Compliance | Not started |  | Glen Pryer | 1.5 | 2026-04-24 | 2026-04-24 | 2026-04-24 | Platform compliance verified or issues flagged. Submission timeline documented. Blockers escalated to Julius. | Cross-reference Goals proposed prices against valid PS/Xbox tier selections. Sources: Goals "Copy of PS4_PS5 Digital" sheet, "Xbox wholesale pricing" sheet. Flag any non-standard tier prices (Sony/Xbox will reject). Submission checklist: valid tiers, all territories covered, USD fallback for unsupported currencies. Timeline: deliver by 28 April > Goals submits by 5 May > 9-day review > 14 May launch. Ask Julius: has a test pricing configuration been submitted? Done when: Platform compliance verified or issues flagged. Submission timeline documented. | Goals Studio Pricing Engagement > F2: Regional Pricing Strategy > S2.2: Platform Compliance and Submission Guidance | gaming
S2.3 | Story | S2.3: Country-Specific Recommendations | Not started |  |  | 3 | 2026-04-24 | 2026-04-25 | 2026-04-25 |  | Provide specific price adjustment recommendations for each red/amber country. | Goals Studio Pricing Engagement > F2: Regional Pricing Strategy | gaming
T2.3.1 | Task | T2.3.1: Write Country Recommendation Cards | Not started |  | Glen Pryer | 3 | 2026-04-24 | 2026-04-25 | 2026-04-25 | All red/amber countries have specific, actionable recommendation cards. Each card self-contained for Julius to implement. | For each red/amber country, write a recommendation card: Country ¦ Current proposed price ¦ Issue ¦ Recommended price ¦ Rationale ¦ Revenue impact ¦ Risk if unchanged. Prioritise by: player base size x deviation severity. Group by action: "Reduce price" / "Can increase" / "Platform tier adjustment". Expected output: 8-12 country cards. Each card must be self-contained - Julius can implement without reading the full report. Done when: All red/amber countries have specific, actionable recommendation cards. | Goals Studio Pricing Engagement > F2: Regional Pricing Strategy > S2.3: Country-Specific Recommendations | gaming
F3 | Feature | F3: Risk Assessment, Scenarios and Recommendations | Not started | High |  | 10 | 2026-04-25 | 2026-04-25 | 2026-04-25 |  | Synthesise all analysis into clear, specific, actionable guidance with modelled impact. Budget: 10h (20% of total) | Goals Studio Pricing Engagement | gaming
S3.1 | Story | S3.1: Are We Too Low? - The Central Answer | Not started |  |  | 1.5 | 2026-04-25 | 2026-04-25 | 2026-04-25 |  | Directly address Jonas's core concern with evidence. | Goals Studio Pricing Engagement > F3: Risk Assessment, Scenarios and Recommendations | gaming
T3.1.1 | Task | T3.1.1: Build the Definitive Position Statement | Not started |  | Glen Pryer | 1.5 | 2026-04-25 | 2026-04-25 | 2026-04-25 | One clear paragraph answering "are we too low?" with specific evidence and specific recommendation. No hedging. | Synthesise competitive position (T1.1.1), payer benchmarks (T1.0.2), and scenario modelling (T1.2.1) into one clear paragraph answering "are we too low?" Format: "Goals base HC pricing is at the Xth percentile... This means... Given your 80/20 positioning, this is [appropriate/low/high] because... Your payer conversion target of 10.4% is [realistic/aggressive] for month 1... Our recommendation is [specific]." Take a position. No hedging. Reference: launch high, patch down. Done when: One clear paragraph with specific evidence and specific recommendation. | Goals Studio Pricing Engagement > F3: Risk Assessment, Scenarios and Recommendations > S3.1: Are We Too Low? - The Central Answer | gaming
S3.2 | Story | S3.2: Risk Register | Not started |  |  | 2 | 2026-04-25 | 2026-04-25 | 2026-04-25 |  | Document all identified pricing risks before launch, ranked by severity. | Goals Studio Pricing Engagement > F3: Risk Assessment, Scenarios and Recommendations | gaming
T3.2.1 | Task | T3.2.1: Compile and Rank Risks | Not started |  | Glen Pryer | 2 | 2026-04-25 | 2026-04-25 | 2026-04-25 | Minimum 7 risks documented with full detail. Ranked by severity x likelihood. Top 3 have specific, actionable mitigations. | Minimum 7 risks with Description ¦ Severity ¦ Likelihood ¦ Markets Affected ¦ Mitigation: 1. P2W perception at high price points (Critical/Medium) 2. Post-launch price increase impossibility (High/Medium) 3. Over-pricing in price-sensitive markets - Turkey, Brazil, Poland (High/High) 4. Platform pricing rejection (Critical/Low) 5. Discount curve too shallow for launch (Medium/Medium) 6. Missing entry-tier conversion at $5.99 (Medium/Medium) 7. Originals/Celebrity pack pricing gap (Low/N/A) Done when: All risks documented. Ranked by severity x likelihood. Top 3 have specific mitigations. | Goals Studio Pricing Engagement > F3: Risk Assessment, Scenarios and Recommendations > S3.2: Risk Register | gaming
S3.3 | Story | S3.3: Top 5 Recommendations | Not started |  |  | 2.5 | 2026-04-25 | 2026-04-25 | 2026-04-25 |  | The five highest-impact actions Goals should take before platform submission. | Goals Studio Pricing Engagement > F3: Risk Assessment, Scenarios and Recommendations | gaming
T3.3.1 | Task | T3.3.1: Write Top 5 Recommendations | Not started |  | Glen Pryer | 2.5 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 5 recommendations in full format. No vague advice. Every number specific. Every impact range stated. | Five specific numbered recommendations. Each must include: - What to change (exact specification) - Why (evidence from analysis) - Revenue impact (conservative-to-optimistic range) - Implementation (which cells, which platform to resubmit) - Risk if skipped Expected candidates: (1) pricing position adjustment, (2) regional correction, (3) discount curve adjustment, (4) first-purchase incentive, (5) launch framing. Must pass test: would a studio economy designer respect this and act immediately? Done when: 5 recommendations in full format. No vague advice. Every number specific. | Goals Studio Pricing Engagement > F3: Risk Assessment, Scenarios and Recommendations > S3.3: Top 5 Recommendations | gaming
F4 | Feature | F4: Value-Add (Conditional - Time Permitting) | Not started | Medium |  | 4 | 2026-04-25 | 2026-04-25 | 2026-04-25 |  | Supplementary tools demonstrating NBI strategic depth and positioning Phase 2. ONLY executed if F1-3 complete within budget. Scope reduced first if any day overruns. Budget: 4h (8% of total) | Goals Studio Pricing Engagement | gaming
S4.1 | Story | S4.1: Reusable Regional Pricing Methodology | Not started |  |  | 1.5 | 2026-04-25 | 2026-04-25 | 2026-04-25 |  | One-page methodology Goals can use for any future SKU without NBI. | Goals Studio Pricing Engagement > F4: Value-Add (Conditional - Time Permitting) | gaming
T4.1.1 | Task | T4.1.1: Write How to Price a New SKU Guide | Not started |  | Glen Pryer | 1.5 | 2026-04-25 | 2026-04-25 | 2026-04-25 | One-page document Julius can follow to price any new SKU. Worked example (Celebration at $7 for Brazil) included. | 6-step methodology: 1. Set USD base price (anchor against EA FC equivalent) 2. Convert to local currencies using current FX 3. Check PPP factor (provide lookup table) 4. Compare against EA FC in that market (+/-15% acceptable) 5. Round to nearest platform tier 6. Verify discount curve is maintained Include worked example: pricing a new Celebration at $7.00 USD for Brazil. Include PPP factor table for all launch markets. Position as: "This is the manual method. Phase 2 builds a model that does this automatically." Done when: One-page document Julius can follow. Worked example included. | Goals Studio Pricing Engagement > F4: Value-Add (Conditional - Time Permitting) > S4.1: Reusable Regional Pricing Methodology | gaming
S4.2 | Story | S4.2: World Cup Pricing Opportunity Notes | Not started |  |  | 1 | 2026-04-25 | 2026-04-25 | 2026-04-25 |  | 3-5 tactical pricing observations for the June World Cup window. | Goals Studio Pricing Engagement > F4: Value-Add (Conditional - Time Permitting) | gaming
T4.2.1 | Task | T4.2.1: Write World Cup Quick-Hit Observations | Not started |  | Glen Pryer | 1 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 3-5 bullet points with specific, actionable World Cup pricing tactics. Half page max. | 3-5 tactical pricing observations for June World Cup: - National kit pricing: premium during group stage (emotional spending), discount in knockout (fire sale) - Time-limited "World Cup Coin Pack" at 10% better value than standard - drives urgency - ARPPU peak benchmarks: typical 2-3x normal during major events Keep SHORT. Half a page max. Teaser for Phase 2 live service consulting, not a full plan. Done when: 3-5 bullet points with specific, actionable World Cup pricing tactics. | Goals Studio Pricing Engagement > F4: Value-Add (Conditional - Time Permitting) > S4.2: World Cup Pricing Opportunity Notes | gaming
S4.3 | Story | S4.3: Phase 2 Positioning | Not started |  |  | 1.5 | 2026-04-25 | 2026-04-25 | 2026-04-25 |  | Brief section positioning the larger engagement. | Goals Studio Pricing Engagement > F4: Value-Add (Conditional - Time Permitting) | gaming
T4.3.1 | Task | T4.3.1: Write What Is Next Section | Not started |  | Tom Rieger | 1.5 | 2026-04-25 | 2026-04-25 | 2026-04-25 | Half-page "What's Next" section. Helpful, not salesy. Positions Phase 2 naturally. | Position Phase 2 naturally (helpful, not salesy): - Post-launch telemetry review (2-3 weeks after 14 May): real data replaces estimates - A/B test design: optimise conversion at each tier using live cohorts - Store optimisation: offer sequencing, time-limited promotion design - World Cup monetisation strategy: full tactical plan for June peak - Ongoing live service consulting: content cadence, engagement frameworks Close with: "We recommend a check-in call 2-3 weeks post-launch to review initial transaction data and scope the next phase." Do NOT include NBI internal pricing for Phase 2. Done when: Half-page "What's Next" section. Positions naturally. | Goals Studio Pricing Engagement > F4: Value-Add (Conditional - Time Permitting) > S4.3: Phase 2 Positioning | gaming
F5 | Feature | F5: Deliverable Assembly and Client Review | Not started | High |  | 7 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  | Package all analysis into the contracted deliverable: written summary + remote review call. Budget: 7h (14% of total) | Goals Studio Pricing Engagement | gaming
S5.1 | Story | S5.1: Written Summary Document | Not started |  |  | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  | Create the final client-facing document: 12-18 pages, British English, numbers-backed. | Goals Studio Pricing Engagement > F5: Deliverable Assembly and Client Review | gaming
T5.1.1 | Task | T5.1.1: Assemble the Written Summary | Not started |  | Glen Pryer | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Complete document draft. All sections populated with real findings. Internally consistent. 12-18 pages. | Final client-facing document structure: 1. Executive Summary (1 page) - headline finding, top 5 recs, immediate action 2. Your Competitive Position - where Goals sits vs market (F1) 3. Regional Pricing Assessment - country risk map + recommendation cards (F2) 4. Pricing Scenarios - what-if modelling with revenue impact (S1.2) 5. Risk Register - all risks with mitigation (S3.2) 6. Recommendations - top 5 specific changes (S3.3) 7. Pricing Framework - reusable methodology (F4, if completed) 8. World Cup Opportunities - tactical observations (F4, if completed) 9. Next Steps - Phase 2 positioning 10. Appendix - full comparison tables, country matrix, competitor data Style: British English. No em dashes. Direct, specific, numbers-backed. 12-18 pages. Written for Jonas (strategic) and Julius (practitioner) simultaneously. Done when: Complete document draft. All sections populated. Internally consistent. | Goals Studio Pricing Engagement > F5: Deliverable Assembly and Client Review > S5.1: Written Summary Document | gaming
S5.2 | Story | S5.2: Internal Review and Polish | Not started |  |  | 1.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  | Glen and Tom review before client delivery. | Goals Studio Pricing Engagement > F5: Deliverable Assembly and Client Review | gaming
T5.2.1 | Task | T5.2.1: Quality Gate - Internal Review | Not started |  | Glen Pryer, Tom Rieger | 1.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Final document approved by Glen and Tom. Sent to client 24h before review call. Call scheduled. | Glen reviews: domain accuracy, tone (expertise without condescension), completeness. Tom reviews: commercial positioning, NBI brand consistency, contractual/legal issues. Address all feedback. Produce final version. Send to Jonas/Julius 24h before review call. Done when: Final document approved by Glen and Tom. Sent to client. Call scheduled. | Goals Studio Pricing Engagement > F5: Deliverable Assembly and Client Review > S5.2: Internal Review and Polish | gaming
S5.3 | Story | S5.3: Remote Review Session | Not started |  |  | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  | 30-45 minute call walking Jonas/Julius through findings and recommendations. | Goals Studio Pricing Engagement > F5: Deliverable Assembly and Client Review | gaming
T5.3.1 | Task | T5.3.1: Conduct Client Review Call | Not started |  | Glen Pryer | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Call completed. Follow-up email sent within 24h. Phase 2 interest level documented. | Call agenda (30-45 min): - 5 min: Recap scope and methodology - 10 min: Top 5 recommendations (highest impact first) - 10 min: Regional pricing highlights (red countries, what needs to change) - 5 min: Pricing framework overview - 5 min: Next steps / Phase 2 - 10 min: Q&A Prepared answers: - "Should we delay?" > No, configuration changes not architecture. - "What if platforms reject?" > Built within tier systems. Low risk if compliance verified. - "Can we change later?" > Down only without backlash. Launch high, patch down. Follow-up within 24h: summary email, adjusted recs if needed, confirmed next steps. Done when: Call completed. Follow-up sent. Phase 2 interest level documented. | Goals Studio Pricing Engagement > F5: Deliverable Assembly and Client Review > S5.3: Remote Review Session | gaming

## Timeline
Task | Type | Assignee | Hours | Day 1 22 Apr | Day 2 23 Apr | Day 3 24 Apr | Day 4 25 Apr | Day 5 28 Apr
T1.0.1: Map HC Value Chain | Task |  | 2 | 2h
T1.0.2: Establish Payer Persona Benchmarks | Task |  | 2 | 2h
T1.1.1: Build Normalised Price Position Map | Task |  | 2.5 | 2.5h
T1.1.2: Discount Curve Comparison | Task |  | 1.5 | 1.5h
T1.1.3: SKU Structure and Entry Point Audit | Task |  | 2 |  | 2h
T1.1.4: Platform Fee Impact and Net Revenue Table | Task |  | 1 |  | 1h
T1.2.1: Price Elasticity Scenario Modelling | Task |  | 3 |  | 3h
T1.3.1: First-Purchase and Starter Pack Recommendations | Task |  | 2 |  | 2h
T2.1.1: Categorise All Countries by Risk Level | Task |  | 3 |  | 3h | 3h
T2.1.2: Competitor Regional Pricing for Red/Amber Markets | Task |  | 3.5 |  |  | 3.5h
T2.2.1: Verify Platform Tier Compliance | Task |  | 1.5 |  |  | 1.5h
T2.3.1: Write Country Recommendation Cards | Task |  | 3 |  |  | 3h | 3h
T3.1.1: Build the Definitive Position Statement | Task |  | 1.5 |  |  |  | 1.5h
T3.2.1: Compile and Rank Risks | Task |  | 2 |  |  |  | 2h
T3.3.1: Write Top 5 Recommendations | Task |  | 2.5 |  |  |  | 2.5h
T4.1.1: Write How to Price a New SKU Guide | Task |  | 1.5 |  |  |  | 1.5h
T4.2.1: Write World Cup Quick-Hit Observations | Task |  | 1 |  |  |  | 1h
T4.3.1: Write What Is Next Section | Task |  | 1.5 |  |  |  | 1.5h
T5.1.1: Assemble the Written Summary | Task |  | 3 |  |  |  |  | 3h
T5.2.1: Quality Gate - Internal Review | Task |  | 1.5 |  |  |  |  | 1.5h
T5.3.1: Conduct Client Review Call | Task |  | 2 |  |  |  |  | 2h