## Project Summary
Goals Studio Pricing Engagement
Client | Goals Studio (Goals AB), Stockholm
Primary Contact | Jonas Rundberg (CEO)
Secondary Contact | Julius (Live Ops)
NBI Team | Glen Pryer (45h), Devin Rieger (50h), Tom Rieger (20h)
Contract
SOW Value | 100,000 SEK (~10,000 USD)
Total Effort | ~116 billable hours
SOW Date | 8 April 2026
Delivery Deadline | 28 April 2026
Hour Budget
F1: Competitive HC Pricing Benchmark | 38h (33%)
F2: Regional Pricing Strategy | 34h (29%)
F3: Risk Assessment and Recommendations | 16h (14%)
F4: Value-Add (Conditional) | 8h (7%)
F5: Deliverable Assembly and Review | 18h (16%)
Total | ~116h
Blocking Questions for Julius
Q5 | Which discount curve proposal is final?
Q6 | When exactly does pricing need to be submitted to Sony/Xbox?
Q7 | Has any pricing test config been submitted previously?
Q8 | What items are in the Day 1 store specifically?

## Task Breakdown
Title | Status | Hours | Assignees | Description | Success Criteria
F1: Competitive HC Pricing Benchmark | Not started | 16 |  | Show Goals where they sit relative to the sports/football F2P market. Extend their existing competitive analysis with insights their internal position doesn't give them. What NBI adds: Independent cross-genre validation, pricing psychology assessment, conversion rate benchmarks from NBI 27-game launch history, and the confidence that an external expert agrees (or disagrees) with their conclusions. Budget: 16h (32% of total)
F2: Regional Pricing Strategy | Not started | 13 |  | Validate Goals 40+ country pricing matrix. NBI adds: competitive regional context, PPP-adjusted analysis, and platform compliance verification they can't get from their own spreadsheet. What NBI adds: Goals built their matrix using exchange rates and some PPP data. They CANNOT benchmark their regional pricing against what EA FC actually charges in Turkey or Brazil. NBI provides this. Budget: 13h (26% of total)
F3: Risk Assessment, Scenarios and Recommendations | Not started | 10 |  | Synthesise all analysis into clear, specific, actionable guidance with modelled impact. Budget: 10h (20% of total)
F4: Value-Add (Conditional - Time Permitting) | Not started | 4 |  | Supplementary tools demonstrating NBI strategic depth and positioning Phase 2. ONLY executed if F1-3 complete within budget. Scope reduced first if any day overruns. Budget: 4h (8% of total)
F5: Deliverable Assembly and Client Review | Not started | 7 |  | Package all analysis into the contracted deliverable: written summary + remote review call. Budget: 7h (14% of total)
Goals Studio Pricing Engagement | In progress | 50 |  | Deliver competitive pricing benchmark, regional pricing strategy, and risk assessment for GOALS F2P football game launching 14 May 2026. Budget: 100,000 SEK (~$10K USD) ¦ ~50 billable hours ¦ 5 working days Client: Goals AB (Goals Studio), Stockholm, Sweden Contacts: Jonas Rundberg (CEO), Julius (Live Ops) NBI team: Glen Pryer (relationship + domain), Tom Rieger (contract/President), Devin Rieger (research) SOW scope: - Review competitive pricing positioning in sports/football game space - Price point selection, currency pack structure, conversion rate guidance - Regional pricing for base and regional markets - Assessment of current pricing plans against market norms - Recommendations on adjustments and areas of risk - Deliverable: Written summary (12-18 pages) + remote review call The game: - F2P football game, launching 14 May 2026 on Steam/Epic/Xbox/PlayStation - Unique generated players (not licensed), RPG progression, aging/retirement - 80% skill / 20% purchased advantage (non-P2W) - No seasons, no battle pass, no wipes - 400K total beta players, 50% D1 retention on PS, NPS +24.6, CPI $0.43 - World Cup June 2026 = first major monetisation peak Architecture: Foundation (map HC economy) > Competitive benchmark > Regional analysis > Synthesis (recommendations + scenarios) > Deliverable Hard deadline: Must deliver before Goals submits pricing to PS/Xbox (9-day review needed before May 14 launch) Key question from Jonas: "Are we pricing too low?" Glen's 27-game principle: Launch high, patch down. Never raise prices post-launch. Feature 4 is CONDITIONAL - only delivered if F1-3 complete within budget. | Deliver the Statement of Work at a detail and fidelity level that shows differentiation from their existing estimations. If reasonable, that would be ideal. If the data comes back and it shows exactly the same, then we need to answer why and add 15% value above the base cell where possible
S1.0: Foundation - Map the HC Economy | Not started | 4 |  | Before comparing prices, establish exactly what Goals HC buys and what the player value chain looks like. Prerequisite for everything else.
S1.1: Competitive Pricing Position | Not started | 7 |  | Show Goals exactly where their HC pricing sits relative to market - by synthesising their existing competitive data into a clear positioning statement they can't write themselves.
S1.2: Conversion Rate and Elasticity Context | Not started | 3 |  | Provide conversion/revenue modelling context that turns a static price comparison into actionable strategy.
S1.3: Promotional and First-Purchase Pricing | Not started | 2 |  | Address gap in static HC pack analysis. First-purchase incentives and promotional pricing drive early conversion.
S2.1: Regional Deviation and Risk Identification | Not started | 6.5 |  | Flag countries where Goals pricing creates material risk (too high = player backlash, too low = revenue leakage, misaligned = platform rejection).
S2.2: Platform Compliance and Submission Guidance | Not started | 1.5 |  | Ensure Goals pricing will pass PS/Xbox review without rejection or delay.
S2.3: Country-Specific Recommendations | Not started | 3 |  | Provide specific price adjustment recommendations for each red/amber country.
S3.1: Are We Too Low? - The Central Answer | Not started | 1.5 |  | Directly address Jonas's core concern with evidence.
S3.2: Risk Register | Not started | 2 |  | Document all identified pricing risks before launch, ranked by severity.
S3.3: Top 5 Recommendations | Not started | 2.5 |  | The five highest-impact actions Goals should take before platform submission.
S4.1: Reusable Regional Pricing Methodology | Not started | 1.5 |  | One-page methodology Goals can use for any future SKU without NBI.
S4.2: World Cup Pricing Opportunity Notes | Not started | 1 |  | 3-5 tactical pricing observations for the June World Cup window.
S4.3: Phase 2 Positioning | Not started | 1.5 |  | Brief section positioning the larger engagement.
S5.1: Written Summary Document | Not started | 3 |  | Create the final client-facing document: 12-18 pages, British English, numbers-backed.
S5.2: Internal Review and Polish | Not started | 1.5 |  | Glen and Tom review before client delivery.
S5.3: Remote Review Session | Not started | 2 |  | 30-45 minute call walking Jonas/Julius through findings and recommendations.
T1.0.1: Map HC Value Chain | Not started | 3 | Glen Pryer | Create a one-page map showing exactly what a player gets for their money at each price point ($5.99 to $99.99). For each tier, list what items they can afford and what they cannot. Flag any gaps where Julius needs to confirm pricing. | One-page document exists showing all 6 HC tiers and what each one buys. Any unconfirmed prices are clearly flagged. Glen can explain the value chain to Jonas in plain English.
T1.0.2: Establish Payer Persona Benchmarks | Not started | 5 | Glen Pryer | Check whether Goals' revenue assumptions are realistic. They assume 10.4% of players will pay and spend $32.48 on average. Find published data from EA, Konami, or analyst reports showing what comparable games actually achieve. State clearly whether Goals' targets are aggressive, conservative, or realistic. | Written assessment with at least 2 cited sources comparing Goals' assumptions to real-world data. Clear verdict: realistic, aggressive, or fantasy. If aggressive, state what the implication is for pricing.
T1.1.1: Build Normalised Price Position Map | Not started | 8 | Glen Pryer | Build a chart showing where Goals sits vs 5-8 competitors at each price tier. For example: "At the $9.99 tier, Goals gives you X coins per dollar. The market average is Y. Goals is at the 60th percentile." Verify 2-3 competitor prices are still current by checking their stores. | Position map exists for all 6 tiers. Each tier shows: Goals price, market range (min/median/max), Goals percentile. One clear sentence summarising overall position.
T1.1.2: Discount Curve Comparison | Not started | 4 | Glen Pryer | Compare how much extra value Goals gives for buying bigger packs vs how much competitors give. Goals currently gives ~19% bonus at the top tier. EA FC gives ~40%. Fortnite gives ~24%. Assess whether Goals' bonuses are enough to motivate players to spend more. | Comparison table showing discount curves for Goals + 4 competitors. Written recommendation: keep current curve, steepen it, or flatten it. With reasoning.
T1.1.3: SKU Structure and Entry Point Audit | Not started | 5 | Glen Pryer | Review the 6-tier price structure ($5.99 to $99.99). Check: Is $5.99 too high for a first purchase? Are there gaps between tiers that need filling? Is the top tier appropriate? Compare structure to what EA FC, Fortnite, and Apex use. | Written audit covering: entry point assessment, tier gap analysis, whale ceiling analysis. Clear recommendation for each: keep, add tier, or adjust. Supported by competitor comparison.
T1.1.4: Platform Fee Impact and Net Revenue Table | Not started | 2 | Devin Rieger | Build a table showing how much Goals actually keeps after platform fees at each price point and platform. Steam takes 30%, Epic takes 12%, PlayStation and Xbox take 30%. Calculate the net for all 6 tiers on all 4 platforms. | Complete net revenue table (6 tiers x 4 platforms = 24 cells). Any concerns about margins flagged. Epic advantage quantified as a percentage.
T1.2.1: Price Elasticity Scenario Modelling | Not started | 8 | Glen Pryer | Model 4 "what if" scenarios showing what happens to revenue if prices change. Scenario A: raise everything 10%. Scenario B: raise everything 20%. Scenario C: raise only the cheapest tier. Scenario D: keep prices but give better bonuses on the biggest pack. Show revenue impact as a range (pessimistic to optimistic) for each. | 4 scenarios modelled with revenue ranges. Each shows: price change, assumed conversion impact, net revenue change. Clear recommendation on which scenario is best for launch.
T1.3.1: First-Purchase and Starter Pack Recommendations | Not started | 5 | Glen Pryer | Research what EA FC, Fortnite, Apex, and eFootball offer to first-time buyers (starter packs, first-purchase bonuses, welcome deals). Based on findings, recommend 2-3 specific offers Goals could implement to get new players to make their first purchase. | 2-3 specific first-purchase recommendations. Each includes: what it is, what it costs Goals, expected benefit. Clearly framed as additional to the core pricing, not a change to it.
T2.1.1: Categorise All Countries by Risk Level | Not started | 8 | Devin Rieger | Go through all 40+ countries in the pricing spreadsheet. Mark each one green (fine as-is), amber (needs review), or red (must change before submission). Use the FX deviation column and the existing recommendation flags. Cross-reference with how many beta players came from each country. | Every country has a colour rating. Red countries have a one-sentence explanation of the problem. Output is a ranked list with highest-risk markets at the top.
T2.1.2: Competitor Regional Pricing for Red/Amber Markets | Not started | 15 | Devin Rieger | For each red/amber country (expect 5-10), find out what EA FC and Fortnite actually charge there. Check SteamDB for Steam prices, PlayStation Store web pages for console prices. Build a comparison: what Goals charges vs what EA FC charges in each market. | Comparison table for all red/amber countries. Each row: country, Goals price, EA FC price, Fortnite price, percentage difference. Sources cited for every price.
T2.2.1: Verify Platform Tier Compliance | Not started | 3 | Glen Pryer | Check that every price in the PlayStation and Xbox columns of the pricing matrix matches a real platform tier. Sony and Xbox only allow specific price points. If any price is not a valid tier, flag it because it will be rejected during submission. | Written confirmation: all prices are valid platform tiers, OR a list of specific prices that need adjustment with the nearest valid tier for each.
T2.3.1: Write Country Recommendation Cards | Not started | 8 | Glen Pryer | For each red/amber country, write a one-page recommendation card. Each card should be completely standalone so Julius can action it without reading the full report. Include: current price, what is wrong, recommended new price, why, and what happens if we do not change it. | 8-12 country cards completed. Each is self-contained. Julius can read one card and know exactly what to change in the pricing spreadsheet for that country.
T3.1.1: Build the Definitive Position Statement | Not started | 4 | Glen Pryer | Write one paragraph that directly answers Jonas' question: "Are we pricing too low?" Use the competitive position data, the payer assumptions, and the scenario modelling to take a clear position. No hedging. Say "yes you are too low" or "no, your pricing is appropriate" and back it up with numbers. | One paragraph exists that Jonas can read and immediately know whether to raise prices or not. Contains a specific recommendation with a number.
T3.2.1: Compile and Rank Risks | Not started | 5 | Glen Pryer | List every pricing risk identified during the analysis. For each: what could go wrong, how likely is it, how bad would it be, which markets does it affect, and what should Goals do about it. Rank them from most to least dangerous. | Minimum 7 risks documented. Each has severity, likelihood, affected markets, and a mitigation action. Top 3 risks have specific, implementable steps Goals can take immediately.
T3.3.1: Write Top 5 Recommendations | Not started | 7 | Glen Pryer | Write the 5 most impactful things Goals should do before submitting prices to Sony/Xbox. Each recommendation must be specific enough that Julius can implement it without asking follow-up questions. Include the expected revenue impact of each. | 5 recommendations written. Each has: exact change to make, evidence for why, expected revenue impact (range), and what happens if they skip it. A studio economy designer would read these and act same day.
T4.1.1: Write How to Price a New SKU Guide | Not started | 3 | Glen Pryer | Write a simple step-by-step guide that Julius can follow when Goals creates a new item and needs to set prices for it. Include a worked example (e.g. pricing a new celebration for Brazil). This should be a tool that outlasts the engagement. | One-page guide exists. Julius can follow it without NBI help. Worked example included. PPP lookup table for all launch markets included.
T4.2.1: Write World Cup Quick-Hit Observations | Not started | 2 | Glen Pryer | Write 3-5 quick tactical observations about how Goals can maximise revenue during the World Cup (June 2026). Keep it short (half a page). This is a teaser showing what a full live service engagement could deliver. | 3-5 bullet points. Each is a specific, actionable pricing tactic for the World Cup window. Clearly positioned as a taste of what Phase 2 would cover in detail.
T4.3.1: Write What Is Next Section | Not started | 3 | Tom Rieger | Write a brief "what comes next" section for the deliverable. Position the logical follow-on work (post-launch data review, A/B testing, World Cup strategy) naturally. Should feel helpful, not like a sales pitch. | Half-page section written. Reads as genuine advice, not upselling. Recommends a check-in call 2-3 weeks post-launch. Does NOT include NBI pricing.
T5.1.1: Assemble the Written Summary | Not started | 10 | Glen Pryer | Assemble all findings into the final document for Jonas and Julius. 12-18 pages. Executive summary first (1 page with the headline answer and top 5 actions). Then sections covering competitive position, regional pricing, scenarios, risks, recommendations, framework, and appendix. | Complete document draft ready for internal review. All sections filled with real findings (no placeholders). Internally consistent. Written in British English, direct and numbers-backed.
T5.2.1: Quality Gate - Internal Review | Not started | 4 | Glen Pryer, Tom Rieger | Glen reviews the document for accuracy and tone. Tom reviews for commercial positioning and brand. Address all feedback and produce the final version. Send to Jonas and Julius 24 hours before the review call. | Final document approved by both Glen and Tom. Sent to client. Review call scheduled and confirmed.
T5.3.1: Conduct Client Review Call | Not started | 4 | Glen Pryer | Run a 30-45 minute remote call with Jonas and Julius. Walk them through the top 5 recommendations and regional highlights. Answer their questions. Send a follow-up email within 24 hours summarising agreed actions and next steps. | Call completed. Follow-up email sent within 24 hours. Phase 2 interest level documented. Any adjusted recommendations captured.