## Sheet1
|  | IDEATION |  |  |  |  | DEVELOPMENT | [5 empty] | RELEASE
WORK STREAMS |  | G A T E 0 | CONCEPT | G A T E 1 | FEATURE PLANNING | G A T E 2 | FIRST PRODUCTION | G A T E 3 | MID PRODUCTION | G A T E 3.5 | LATE PRODUCTION | G A T E 4 | ALPHA DEV | G A T E 4.1 | BETA DEV | G A T E 4.2 | FINALING | G A T E 5 | LAUNCH | G A T E 6
PREVIOUS TITLE INSIGHT |  |  | Document and share previous title insights (Concept) Document and share previous title insights (Y Doc / Pitch) Title Sizing |  | Document and share previous title insights (Feature Level)
COMPETITIVE ANALYSIS |  |  | Competitive Analysis (Concept) Competitive Analysis (Audience & Industry) |  | Game Health R1 |  | Game Health R2 |  | Game Health R3 |  | Game Health R4 |  | Game Health Alpha |  | Game Health Beta |  |  |  | Game Health Launch
PLAYER PROFILING |  |  | Player Profiling (R2) Player Profiling (R1) |  | Player Profiling (R3) |  | Player Profiling (R4) |  | Player Profiling (R5)
ADSE PLANNING |  |  | Create ADSE Resource Plan |  | Create GA team’s scope and roadmap |  | Headcount, scope and roadmap review R1 |  | Headcount, scope and roadmap review R2 |  | Headcount, scope and roadmap review R3 |  | Headcount, scope and roadmap review R4 |  | Headcount, scope and roadmap review R5 |  |  |  | Headcount, scope and roadmap review R6
Live Service Roadmap & Sustain Plan
|  |  | Define Broad Working Team |  | Risk and status review R1 |  | Risk and status review R2 |  | Risk and status review R3 |  | Risk and status review R4 |  | Risk and status review R5 |  | Risk and status review R6 |  |  |  | Risk and status review R7
|  |  | Create Stakeholder Matrix |  |  |  | Revise Stakeholder Matrix R1 |  |  |  | Revise Stakeholder Matrix R2 | [7 empty] | Revise Stakeholder Matrix R3
BUSINESS MODEL |  |  | Business Model Exploration R2 Business Model Exploration (R1) |  | Business Model Questions Doc |  | Business Model Analysis and Design Feedback |  | Business Model Analysis and Design Feedback |  | Business Model Analysis and Design Feedback
LIVE SERVICE |  |  |  |  | Live Service Questions Doc |  | Live Service Plan Analysis and Design Feedback R1 |  | Live Service Plan Analysis and Design Feedback R2 |  | Live Service Plan Analysis and Design Feedback R3 |  | Live Service Plan Analysis and Design Feedback R4 |  | Live Service Plan Analysis and Design Feedback R5 |  |  |  | Live Service Plan Analysis and Design Feedback R6
ECONOMY |  |  |  |  | Economy Design Feedback |  | Economy Modeling (R1) |  | Economy Modeling (R2) |  | Economy Modeling (R3) |  | Economy Validation and Design Feedback |  | Economy Validation and Design Feedback
FORECASTING |  |  | Long Range Forecast R1 |  | Long Range Forecast R2 |  | Quarterly Forecast Revisions |  | Quarterly Forecast Revisions |  | Quarterly Forecast Revisions |  | Monthly Forecast Revisions |  | Monthly Forecast Revisions |  |  |  | Monthly Forecast Revisions
|  |  | Define KPI Success Criteria |  | Revise KPI Success Criteria R1 |  | Revise KPI Success Criteria R2 |  | Revise KPI Success Criteria R3 |  | Revise KPI Success Criteria R4 |  |  |  | Revise KPI Success Criteria Beta
PSU & Play-First Trial Forecast
Q&A ASSESSMENT |  |  | Q&A Doc (Concept) Q&A Doc (Pitch) |  | Q&A Doc Drafted (2.0) |  | Q&A Doc revisions (3.0) |  | Q&A Doc revisions (3.5) |  | Q&A Doc revisions (4.0) |  | Q&A Doc revisions (4.1) |  | Q&A Doc revisions (4.2) |  |  |  | Q&A Doc revisions (6.0)
INSIGHTS | Plan | [5 empty] | Insights Plan Drafted |  | Revise Insights Plan (R1) |  | Revise Insights Plan (R2) |  | Revise Insights Plan (R3) |  | Revise Insights Plan (R4) |  |  |  | Revise Insights Plan (R5)
| Playtest | [5 empty] | Internal / UXR Playtesting enabled |  | Mid Production Playtest Insights Delivered |  | Late Production Playtest Insights Delivered
| Balance | [5 empty] | Balance Insights Plan Drafted |  | Balance Analysis |  | Balance Analysis |  |  |  | Balance Analysis |  |  |  | Balance Analysis
| Progression | [5 empty] | Progression Insights Plan Drafted |  | Progression Analysis |  | Progression Analysis |  |  |  | Progression Analysis |  |  |  | Progression Analysis
| UI/UX | [5 empty] | UIUX Insights Plan Drafted |  | UIUX Analysis |  | UIUX Analysis |  |  |  | UIUX Analysis |  |  |  | UIUX Analysis
| Product | [5 empty] | Product Insights Plan Drafted |  | Product Analysis |  | Product Analysis |  |  |  | Product Analysis |  |  |  | Product Analysis
| Economy | [5 empty] | Economy Insights Plan Drafted |  | Economy Analysis |  | Economy Analysis |  |  |  | Economy Analysis |  |  |  | Economy Analysis
| Operational Intelligence | [5 empty] | Ops Intel Insights Plan Drafted |  | Ops Intel Analysis |  | Ops Intel Analysis |  |  |  | Ops Intel Analysis |  |  |  | Ops Intel Analysis
| Social Features | [5 empty] | Social Insights Plan Drafted |  | Social Features Analysis |  | Social Features Analysis |  |  |  | Social Features Analysis |  |  |  | Social Features Analysis
| Sentiment | [5 empty] | Sentiment Insights Plan Drafted |  | Sentiment Features Analysis |  | Sentiment Analysis |  |  |  | Sentiment Analysis |  |  |  | Sentiment Analysis
METRICS |  |  |  |  | Measurement Spec (R1) |  | Measurement Spec (R2) |  | Measurement Spec (R3) |  | Measurement Spec (R4)
TELEMETRY DOCUMENTATION | [6 empty] | Write Telemetry Brief |  | Telemetry Brief updated for 3.5 scope |  | Telemetry Brief updated for 4.0 scope |  | Telemetry Brief updated for 4.1 scope |  | Telemetry Brief updated for 4.2 scope |  |  |  | Telemetry Brief updated for 6.0scope
TELEMETRY IMPLEMENTATION | [6 empty] | Critical Telemetry Implemented |  | Telemetry Implemented for 3.5 feature scope |  | Telemetry Implemented for 4.0 feature scope |  | Telemetry Implemented for 4.1 feature scope (Alpha) |  | Telemetry Implemented for 4.2 feature scope (Beta) |  |  |  | Telemetry Implemented for 6.0 feature scope (Day 0)
DATA ARCHITECTURE | [6 empty] | Schema and table design |  | Build schema / Architecture (R1) |  | Build schema / Architecture (R2) |  | Build schema / Architecture (R3) |  | Build schema / Architecture (R4)
TELEMETRY VALIDATION | [6 empty] | Telemetry Validated (3.0 scope) |  | Telemetry Validated (3.5 scope) |  | Telemetry Validated (4.0 scope) |  | Telemetry Validated (4.1 scope) |  | Telemetry Validated (4.2 scope) |  |  |  | Telemetry Validated (6.0 scope)
DASHBOARDS | [8 empty] | Commit Dashboard and Wireframe spec for launch scope |  | Revising and build Dashboard and Wireframe spec for launch scope |  | Alpha Dashboard Shipped |  | Beta Dashboard Shipped |  |  |  | Launch Dashboard Shipped
LIVE SERVICE REPORTING | [14 empty] | Alpha Reporting |  |  |  | Beta Reporting
ARCHIVING |  |  |  |  | Snapshot Game Design and Business Model docs |  | Snapshot Game Design and Business Model docs |  | Snapshot Game Design and Business Model docs |  | Snapshot Game Design and Business Model docs
[5 empty] | Snapshot Title Roadmap and Dates |  | Snapshot Title Roadmap and Dates |  | Snapshot Title Roadmap and Dates |  | Snapshot Title Roadmap and Dates
[5 empty] | Snapshot Live Service Plan |  | Snapshot Live Service Plan |  | Snapshot Live Service Plan |  | Snapshot Live Service Plan